## START_HERE
PMS-11 ¦ ENTERPRISE CONTROL MODEL
Scope | 24 WPS / 89 Rules; approved by user for this rebuild
Authority | Preserved source content is not independent regulatory verification.
Workflow | Edit blue input fields; formula fields are green. Add records inside Excel tables.
Automation | Import RedTeam.bas in Excel VBA; save as .xlsm; run RunRedTeam.
Macro status | VBA source supplied separately; not embedded and not desktop-tested.
Safety | No macros auto-run. Review VBA before enabling; no external calls or file access.
Red team | All red-team outputs start NOT RUN. Each run replaces current detail and appends summary history.
Closure | Computed checks are not authority approval; evidence location and verification are mandatory for closure.
Dates | Source TBC dates moved to MIGRATION_ISSUES and blanked in model date fields.
Cost | Estimate at Completion uses explicit Remaining Estimate, not an invented forecast.
Scope history | 16-WPS controls are legacy; original file remains the unmodified audit reference.
Limitations | Flat Excel tables and normalized link table; no Power Pivot model or critical-path scheduler.
Coverage | Primary registers plus functional activities, dependencies, resource summary, dashboard, and test controls.
Formula cache | Open in Excel and calculate before reading summaries.
Setup | See SETUP.txt for exact import and test instructions.
Relationship maintenance | Relationships is the canonical link table. Source list strings are traceability snapshots, not synchronized. Maintain normalized links when assignments change. Gap_WPS is the gap-to-WPS bridge and must be maintained for gap rollups.
Red-team coverage limit | Tests check keys, links, scope, schedule/date ranges, ownership, costs, closure metadata, dependency endpoints/self-links, and formula errors. They do not verify evidence contents, multi-step dependency cycles, or legal adequacy.
Source register anomaly | Original Source ID column is blank and other attributes appear shifted. All raw source cells are preserved in Sources under generated Source Record IDs; semantic repair requires review.

## DASHBOARD
Metric | Live value
WPS
Rules
Execution records
Open gaps
Weighted progress
Missing weight warning
Approved budget
Actual cost
EAC inputs missing
Overdue executions
Execution quality issues
Red-team state | NOT RUN — run VBA in desktop Excel

## CONFIG
Control | Value
Expected WPS | 24
Expected Rules | 89
Model Version | 1.0
Scope Basis | User-approved 24 WPS

## Rules
Rule ID | Rule Group ID | Rule Title / Requirement | Authority / Source | Source Document | Document Number | Edition / Year | Effective Date | Part | Chapter | Section | Paragraph | Requirement Text | Applicability Trigger | Applicability Status | Requirement Type | PMS-11 System | Required Evidence | Evidence Owner | Verification Method | Criticality | WPS ID | Activity ID | Deliverable ID | Gap ID | Acceptance Criteria ID | Closure Authority | Status | Source URL | Notes | Source Rule ID
R-001 | RG-01 | Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | DNV Rules for Classification | DNV Rules for Classification | TBC | RU-SHIP / non-self-propelled unit framework; exact edition/section TBC from class basis | Current DNV Certificate and Class Status; class history; complete notation/scope; DNV-RU-SHIP vs DNV-RU-OU assessment; alternative IACS class-transfer feasibility; authority dispositions. | TBC | TBC | Classification strategy must be assessed before the governing class regime is frozen. | TBC | E-001,E-094,E-095,E-096 | Current class certificate/approved class basis | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Current DNV Class Certificate + class status | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-01 | A-R-001 | D-R-001 | G-001 | AC-R-001 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-001
R-002 | RG-01 | Confirm complete class notation and qualifiers; do not infer notation from vessel description. | DNV Class Certificate | DNV Class Certificate | TBC | Notation text — exact certificate entry required | TBC | TBC | TBC | TBC | TBC | Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Current certificate | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Current DNV Class Certificate | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-01 | A-R-002 | D-R-002 | G-002 | AC-R-002 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-002
R-003 | RG-01 | Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | DNV Rules | DNV Rules | TBC | Applicable edition/history — exact edition TBC | TBC | TBC | TBC | TBC | TBC | Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Build date, class history, modifications | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Class basis + rule edition evidence | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-02 | A-R-003 | D-R-003 | G-003 | AC-R-003 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-003
R-004 | RG-02 | Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | DNV Class Status | DNV Class Status | TBC | Class status records | TBC | TBC | TBC | TBC | TBC | Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Current status | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Class Status Report + survey records | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-01 | A-R-004 | D-R-004 | G-004 | AC-R-004 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-004
R-005 | RG-02 | Identify approved drawings and documents forming the class technical basis. | DNV Class File | DNV Class File | TBC | Approved drawings/documents | TBC | TBC | TBC | TBC | TBC | Identify approved drawings and documents forming the class technical basis. | Current class file | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Approved drawings list / class file | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-01 | A-R-005 | D-R-005 | G-005 | AC-R-005 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-005
R-006 | RG-02 | Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | DNV Survey/Certification | DNV Survey/Certification | TBC | Survey status — exact survey references TBC | TBC | TBC | TBC | TBC | TBC | Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Class status | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Survey status/history | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-02 | A-R-006 | D-R-006 | G-006 | AC-R-006 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-006
R-007 | RG-03 | Assess effects of modifications, conversion, change of service or operating area on class requirements. | DNV Rules | DNV Rules | TBC | Applicable modification/conversion provisions TBC | TBC | TBC | TBC | TBC | TBC | Assess effects of modifications, conversion, change of service or operating area on class requirements. | Any modification/change of service | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Modification history + approvals | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-02 | A-R-007 | D-R-007 | G-007 | AC-R-007 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-007
R-008 | RG-03 | Establish the approved operating limits and service scope relevant to Jordan operations. | DNV Class File | DNV Class File | TBC | Operating restrictions/limitations | TBC | TBC | TBC | TBC | TBC | Establish the approved operating limits and service scope relevant to Jordan operations. | Certificate/class file | Conditional | Class / Statutory / Local / Project / OEM | DNV Class Basis | Certificate + approved operational documents | Rule/WPS owner to be assigned | DNV Class Basis | Critical | WPS-01 | A-R-008 | D-R-008 | G-008 | AC-R-008 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-008
R-009 | RG-03 | Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | SOLAS / DNV | SOLAS / DNV | TBC | SOLAS II-1/3-13; MSC.1/Circ.1663; DNV lifting guidance | TBC | TBC | TBC | TBC | TBC | Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Vessel statutory certification + appliance type | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Flag/statutory basis + appliance register | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-03 | A-R-009 | D-R-009 | G-009 | AC-R-009 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-009
R-010 | RG-04 | Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | SOLAS / DNV | SOLAS / DNV | TBC | SOLAS II-1/3-13 offshore construction exclusion; DNV lifting guidance | TBC | TBC | TBC | TBC | TBC | Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Administration acceptance + alternative standard | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Flag acceptance + technical basis | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-03 | A-R-010 | D-R-010 | G-010 | AC-R-010 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-010
R-011 | RG-04 | Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | DNV / SOLAS | DNV / SOLAS | TBC | DNV lifting-appliance requirements; exact applicable service documents TBC | TBC | TBC | TBC | TBC | TBC | Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Applicability decision | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Register + certificates + examination/load-test records | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-03 | A-R-011 | D-R-011 | G-011 | AC-R-011 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-011
R-012 | RG-04 | Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | DNV / OEM | DNV / OEM | TBC | Applicable class/OEM lifting basis TBC | TBC | TBC | TBC | TBC | TBC | Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Installed configuration | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | HMC 5500 technical/certification file | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-04 | A-R-012 | D-R-012 | G-012 | AC-R-012 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-012
R-013 | RG-05 | Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | DNV / Project | DNV / Project | TBC | Applicable class/project basis TBC | TBC | TBC | TBC | TBC | TBC | Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Operational mode | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Crane manual, load charts, limits, procedures | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-04 | A-R-013 | D-R-013 | G-013 | AC-R-013 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-013
R-014 | RG-05 | Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | OEM / DNV | OEM / DNV | TBC | OEM data + applicable offshore acceptance basis | TBC | TBC | TBC | TBC | TBC | Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Installed crawler configuration | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | OEM/configuration file | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-05 | A-R-014 | D-R-014 | G-014 | AC-R-014 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-014
R-015 | RG-05 | Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | DNV / Engineering | DNV / Engineering | TBC | Applicable engineering/class basis TBC | TBC | TBC | TBC | TBC | TBC | Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Crawler used offshore | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Engineering assessment + load chart + deck data | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-05 | A-R-015 | D-R-015 | G-015 | AC-R-015 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-015
R-016 | RG-06 | Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | DNV / OEM | DNV / OEM | TBC | Applicable winch/lifting basis TBC | TBC | TBC | TBC | TBC | TBC | Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Used as lifting/recovery appliance | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Winch certificate/test/exam/OEM file | Rule/WPS owner to be assigned | Lifting Appliances | Major | WPS-03 | A-R-016 | D-R-016 | G-016 | AC-R-016 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-016
R-017 | RG-06 | Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | DNV / OEM | DNV / OEM | TBC | Applicable winch/lifting basis TBC | TBC | TBC | TBC | TBC | TBC | Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Use in marine operations/lifting | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Tugger certificates/tests/exams | Rule/WPS owner to be assigned | Lifting Appliances | Major | WPS-03 | A-R-017 | D-R-017 | G-017 | AC-R-017 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-017
R-018 | RG-06 | Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | DNV / Statutory / OEM | DNV / Statutory / OEM | TBC | Applicable lifting/loose-gear scheme TBC | TBC | TBC | TBC | TBC | TBC | Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Equipment used for lifting | Conditional | Class / Statutory / Local / Project / OEM | Lifting Appliances | Loose-gear register + certificates/exams | Rule/WPS owner to be assigned | Lifting Appliances | Critical | WPS-03 | A-R-018 | D-R-018 | G-018 | AC-R-018 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-018
R-019 | RG-07 | Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | DNV Rules | DNV Rules | TBC | DNV-RU-SHIP Pt.5 Ch.10 Sec.4 — verify against applicable edition/class basis | TBC | TBC | TBC | TBC | TBC | Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Class regime + notation | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | Class basis + applicable rule edition | Rule/WPS owner to be assigned | Pipe Laying | Critical | WPS-06 | A-R-019 | D-R-019 | G-019 | AC-R-019 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-019
R-020 | RG-07 | Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | DNV / OEM / Project | DNV / OEM / Project | TBC | Class/project/OEM basis TBC | TBC | TBC | TBC | TBC | TBC | Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Actual spread configuration | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | CRC drawings/manuals/tests | Rule/WPS owner to be assigned | Pipe Laying | Critical | WPS-06 | A-R-020 | D-R-020 | G-020 | AC-R-020 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-020
R-021 | RG-07 | Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | OEM / DNV / Project | OEM / DNV / Project | TBC | Applicable tensioner basis TBC | TBC | TBC | TBC | TBC | TBC | Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Installed tensioner | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | Tensioner certificate/manual/test records | Rule/WPS owner to be assigned | Pipe Laying | Critical | WPS-06 | A-R-021 | D-R-021 | G-021 | AC-R-021 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-021
R-022 | RG-08 | Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | DNV / Engineering | DNV / Engineering | TBC | Applicable class/project basis TBC | TBC | TBC | TBC | TBC | TBC | Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Actual pipe-lay configuration | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | Drawings + calculations + inspection/test records | Rule/WPS owner to be assigned | Pipe Laying | Critical | WPS-06 | A-R-022 | D-R-022 | G-022 | AC-R-022 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-022
R-023 | RG-08 | Verify welding stations, coating station and related QA/QC controls. | Project / Industry | Project / Industry | TBC | Project pipeline specification; applicable welding/coating standard TBC | TBC | TBC | TBC | TBC | TBC | Verify welding stations, coating station and related QA/QC controls. | Project scope | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | Welding/coating procedures + qualifications | Rule/WPS owner to be assigned | Pipe Laying | Major | WPS-07 | A-R-023 | D-R-023 | G-023 | AC-R-023 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-023
R-024 | RG-08 | Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Statutory / Project | Statutory / Project | TBC | Applicable radiation/NDT authority and project requirements TBC | TBC | TBC | TBC | TBC | TBC | Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | X-ray/NDT performed | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | Equipment certificates + personnel qualifications + procedures | Rule/WPS owner to be assigned | Pipe Laying | Critical | WPS-07 | A-R-024 | D-R-024 | G-024 | AC-R-024 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-024
R-025 | RG-09 | Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | DNV / Project | DNV / Project | TBC | Applicable DNV/project installation basis TBC | TBC | TBC | TBC | TBC | TBC | Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Project/site data | Conditional | Class / Statutory / Local / Project / OEM | Pipe Laying | Installation analysis + operating limits + procedures | Rule/WPS owner to be assigned | Pipe Laying | Critical | WPS-07 | A-R-025 | D-R-025 | G-025 | AC-R-025 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-025
R-026 | RG-09 | Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | DNV | DNV | TBC | DNV-ST-F101 (2021-08, amended 2021-12) | TBC | TBC | TBC | TBC | TBC | Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Project pipeline specification | Conditional | Class / Statutory / Local / Project / OEM | Pipeline Engineering | Project design basis/specification | Rule/WPS owner to be assigned | Pipeline Engineering | Major | WPS-07 | A-R-026 | D-R-026 | G-026 | AC-R-026 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-026
R-027 | RG-09 | Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | DNV | DNV | TBC | DNV pipeline RP family; exact selection TBC | TBC | TBC | TBC | TBC | TBC | Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Pipeline design/installation scope | Conditional | Class / Statutory / Local / Project / OEM | Pipeline Engineering | Project specification + engineering basis | Rule/WPS owner to be assigned | Pipeline Engineering | Major | WPS-07 | A-R-027 | D-R-027 | G-027 | AC-R-027 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-027
R-028 | RG-10 | Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | DNV / Project | DNV / Project | TBC | DNV-ST-F101 + applicable RPs/project basis | TBC | TBC | TBC | TBC | TBC | Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Pipeline/site data | Conditional | Class / Statutory / Local / Project / OEM | Pipeline Engineering | Installation analysis package | Rule/WPS owner to be assigned | Pipeline Engineering | Critical | WPS-07 | A-R-028 | D-R-028 | G-028 | AC-R-028 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-028
R-029 | RG-10 | Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | DNV / IACS | DNV / IACS | TBC | Applicable DNV class basis + IACS mooring/anchoring URs as incorporated | TBC | TBC | TBC | TBC | TBC | Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Actual mooring configuration | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Mooring arrangement + equipment certificates | Rule/WPS owner to be assigned | Mooring / Anchoring | Critical | WPS-08 | A-R-029 | D-R-029 | G-029 | AC-R-029 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-029
R-030 | RG-10 | Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | DNV / OEM | DNV / OEM | TBC | Applicable class/OEM basis TBC | TBC | TBC | TBC | TBC | TBC | Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Installed mooring equipment | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Winch manuals/tests/exams | Rule/WPS owner to be assigned | Mooring / Anchoring | Critical | WPS-08 | A-R-030 | D-R-030 | G-030 | AC-R-030 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-030
R-031 | RG-11 | Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | DNV / Engineering | DNV / Engineering | TBC | DNV marine-operation/engineering basis; exact rule sections TBC | TBC | TBC | TBC | TBC | TBC | Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Site-specific analysis | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Mooring analysis + environmental design basis | Rule/WPS owner to be assigned | Mooring / Anchoring | Critical | WPS-08 | A-R-031 | D-R-031 | G-031 | AC-R-031 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-031
R-032 | RG-11 | Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | DNV / Project | DNV / Project | TBC | Site-specific engineering basis | TBC | TBC | TBC | TBC | TBC | Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Actual Jordan worksite | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Verified survey/geotech package | Rule/WPS owner to be assigned | Mooring / Anchoring | Critical | WPS-09 | A-R-032 | D-R-032 | G-032 | AC-R-032 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-032
R-033 | RG-11 | Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Project / Jordan / ASEZA | Project / Jordan / ASEZA | TBC | Site/project/authority data | TBC | TBC | TBC | TBC | TBC | Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Actual worksite | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Subsea asset register + approved site layout | Rule/WPS owner to be assigned | Mooring / Anchoring | Critical | WPS-09 | A-R-033 | D-R-033 | G-033 | AC-R-033 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-033
R-034 | RG-12 | Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | DNV / Project | DNV / Project | TBC | DNV-RP-C205 (2025-04, amended 2026-03) + project metocean basis | TBC | TBC | TBC | TBC | TBC | Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Site-specific analysis | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Metocean design basis | Rule/WPS owner to be assigned | Mooring / Anchoring | Critical | WPS-09 | A-R-034 | D-R-034 | G-034 | AC-R-034 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-034
R-035 | RG-12 | Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | DNV / Project | DNV / Project | TBC | DNV-ST-N001; MWS scope where contracted | TBC | TBC | TBC | TBC | TBC | Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Project/MWS scope | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | MWS scope + approval documents | Rule/WPS owner to be assigned | Mooring / Anchoring | Major | WPS-11 | A-R-035 | D-R-035 | G-035 | AC-R-035 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-035
R-036 | RG-12 | Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Project / Marine | Project / Marine | TBC | Project marine-operation procedure basis | TBC | TBC | TBC | TBC | TBC | Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Mooring operation | Conditional | Class / Statutory / Local / Project / OEM | Mooring / Anchoring | Approved procedures + drills/records | Rule/WPS owner to be assigned | Mooring / Anchoring | Major | WPS-08 | A-R-036 | D-R-036 | G-036 | AC-R-036 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-036
R-037 | RG-13 | Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | DNV | DNV | TBC | DNV-ST-N001 (2023-12) + applicable class/Flag requirements | TBC | TBC | TBC | TBC | TBC | Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Wet tow | Conditional | Class / Statutory / Local / Project / OEM | Wet Tow / Mobilization | Tow engineering package | Rule/WPS owner to be assigned | Wet Tow / Mobilization | Critical | WPS-10 | A-R-037 | D-R-037 | G-037 | AC-R-037 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-037
R-038 | RG-13 | Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | DNV / Engineering | DNV / Engineering | TBC | DNV-ST-N001 + class structural basis | TBC | TBC | TBC | TBC | TBC | Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Tow configuration | Conditional | Class / Statutory / Local / Project / OEM | Wet Tow / Mobilization | Structural verification | Rule/WPS owner to be assigned | Wet Tow / Mobilization | Critical | WPS-10 | A-R-038 | D-R-038 | G-038 | AC-R-038 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-038
R-039 | RG-13 | Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | DNV / Flag | DNV / Flag | TBC | Applicable tow/stability basis TBC | TBC | TBC | TBC | TBC | TBC | Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Tow condition | Conditional | Class / Statutory / Local / Project / OEM | Wet Tow / Mobilization | Stability/tow condition calculations | Rule/WPS owner to be assigned | Wet Tow / Mobilization | Critical | WPS-10 | A-R-039 | D-R-039 | G-039 | AC-R-039 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-039
R-040 | RG-14 | Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Marine / DNV / Project | Marine / DNV / Project | TBC | DNV-ST-N001 + tow plan | TBC | TBC | TBC | TBC | TBC | Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Selected tug | Conditional | Class / Statutory / Local / Project / OEM | Wet Tow / Mobilization | Tug data + tow plan | Rule/WPS owner to be assigned | Wet Tow / Mobilization | Critical | WPS-10 | A-R-040 | D-R-040 | G-040 | AC-R-040 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-040
R-041 | RG-14 | Establish route, weather criteria, forecast limits, abort criteria and emergency response. | DNV / Marine | DNV / Marine | TBC | DNV-ST-N001 + voyage/tow plan | TBC | TBC | TBC | TBC | TBC | Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Route and season | Conditional | Class / Statutory / Local / Project / OEM | Wet Tow / Mobilization | Tow route/weather/emergency plan | Rule/WPS owner to be assigned | Wet Tow / Mobilization | Critical | WPS-10 | A-R-041 | D-R-041 | G-041 | AC-R-041 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-041
R-042 | RG-14 | Define pre-tow inspection, readiness verification and required approval/statement before departure. | DNV / Flag / MWS | DNV / Flag / MWS | TBC | Applicable authority/MWS scope | TBC | TBC | TBC | TBC | TBC | Define pre-tow inspection, readiness verification and required approval/statement before departure. | Tow approval pathway | Conditional | Class / Statutory / Local / Project / OEM | Wet Tow / Mobilization | Pre-tow inspection + approval | Rule/WPS owner to be assigned | Wet Tow / Mobilization | Critical | WPS-10 | A-R-042 | D-R-042 | G-042 | AC-R-042 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-042
R-043 | RG-15 | Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | DNV / Project | DNV / Project | TBC | DNV-ST-N001; DNV-ST-N002 where applicable; DNV-SE-0080 where contracted | TBC | TBC | TBC | TBC | TBC | Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Client/MWS scope + operation type | Conditional | Class / Statutory / Local / Project / OEM | Marine Warranty | MWS scope and approvals | Rule/WPS owner to be assigned | Marine Warranty | Major | WPS-11 | A-R-043 | D-R-043 | G-043 | AC-R-043 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-043
R-044 | RG-15 | Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | IMCA | IMCA | TBC | Applicable IMCA guidance/documents — exact document set to be identified from project/IMCA inspection scope | TBC | TBC | TBC | TBC | TBC | Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | IMCA inspection/project scope | Conditional | Class / Statutory / Local / Project / OEM | Diving | IMCA inspection report + controlled diving procedures/records | Rule/WPS owner to be assigned | Diving | Critical | WPS-12 | A-R-044 | D-R-044 | G-044 | AC-R-044 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-044
R-045 | RG-15 | Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | IMCA | IMCA | TBC | Applicable IMCA guidance/inspection criteria TBC | TBC | TBC | TBC | TBC | TBC | Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Air diving operations | Conditional | Class / Statutory / Local / Project / OEM | Diving | IMCA inspection/evidence package | Rule/WPS owner to be assigned | Diving | Critical | WPS-12 | A-R-045 | D-R-045 | G-045 | AC-R-045 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-045
R-046 | RG-16 | Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | IMCA | IMCA | TBC | Applicable IMCA guidance/inspection criteria TBC | TBC | TBC | TBC | TBC | TBC | Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Saturation diving capability | Conditional | Class / Statutory / Local / Project / OEM | Diving | IMCA inspection/evidence package | Rule/WPS owner to be assigned | Diving | Critical | WPS-12 | A-R-046 | D-R-046 | G-046 | AC-R-046 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-046
R-047 | RG-16 | Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | IMCA | IMCA | TBC | Applicable IMCA competency guidance TBC | TBC | TBC | TBC | TBC | TBC | Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Diving personnel roster | Conditional | Class / Statutory / Local / Project / OEM | Diving | Competence matrix + records | Rule/WPS owner to be assigned | Diving | Critical | WPS-12 | A-R-047 | D-R-047 | G-047 | AC-R-047 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-047
R-048 | RG-16 | Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | IMCA | IMCA | TBC | Applicable IMCA inspection basis TBC | TBC | TBC | TBC | TBC | TBC | Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | IMCA inspection | Conditional | Class / Statutory / Local / Project / OEM | Diving | Maintenance/test records + IMCA acceptance | Rule/WPS owner to be assigned | Diving | Critical | WPS-12 | A-R-048 | D-R-048 | G-048 | AC-R-048 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-048
R-049 | RG-17 | Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | DNV / Flag | DNV / Flag | TBC | Applicable DNV class/statutory references TBC | TBC | TBC | TBC | TBC | TBC | Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Class/statutory scope | Conditional | Class / Statutory / Local / Project / OEM | Machinery / Electrical | Electrical single-line + tests + survey records | Rule/WPS owner to be assigned | Machinery / Electrical | Critical | WPS-13 | A-R-049 | D-R-049 | G-049 | AC-R-049 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-049
R-050 | RG-17 | Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | DNV / Flag / OEM | DNV / Flag / OEM | TBC | Applicable class/statutory/OEM basis TBC | TBC | TBC | TBC | TBC | TBC | Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Installed systems | Conditional | Class / Statutory / Local / Project / OEM | Machinery / Electrical | P&IDs + tests + maintenance records | Rule/WPS owner to be assigned | Machinery / Electrical | Critical | WPS-13 | A-R-050 | D-R-050 | G-050 | AC-R-050 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-050
R-051 | RG-17 | Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | SOLAS / Flag / DNV | SOLAS / Flag / DNV | TBC | SOLAS/FSS as applicable; exact scope TBC | TBC | TBC | TBC | TBC | TBC | Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Statutory certification scope | Conditional | Class / Statutory / Local / Project / OEM | Fire / LSA / Emergency | FSS certificates/tests + plans | Rule/WPS owner to be assigned | Fire / LSA / Emergency | Critical | WPS-14 | A-R-051 | D-R-051 | G-051 | AC-R-051 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-051
R-052 | RG-18 | Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | SOLAS / Flag / DNV | SOLAS / Flag / DNV | TBC | SOLAS/LSA as applicable; exact scope TBC | TBC | TBC | TBC | TBC | TBC | Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Statutory certification scope | Conditional | Class / Statutory / Local / Project / OEM | Fire / LSA / Emergency | LSA certificates + drill records | Rule/WPS owner to be assigned | Fire / LSA / Emergency | Critical | WPS-14 | A-R-052 | D-R-052 | G-052 | AC-R-052 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-052
R-053 | RG-18 | Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Flag / DNV / Project | Flag / DNV / Project | TBC | Applicable statutory/class/project basis TBC | TBC | TBC | TBC | TBC | TBC | Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | International tow/offshore operation | Conditional | Class / Statutory / Local / Project / OEM | Navigation / Communications | Equipment list + calibration/service records | Rule/WPS owner to be assigned | Navigation / Communications | Major | WPS-14 | A-R-053 | D-R-053 | G-053 | AC-R-053 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-053
R-054 | RG-18 | Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Jordan JMA | Jordan JMA | TBC | Entry/Departure & VTS regulation | TBC | TBC | TBC | TBC | TBC | Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Jordan territorial waters/port | Conditional | Class / Statutory / Local / Project / OEM | Navigation / Communications | JMA/VTS requirements + agent confirmation | Rule/WPS owner to be assigned | Navigation / Communications | Critical | WPS-14 | A-R-054 | D-R-054 | G-054 | AC-R-054 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-054
R-055 | RG-19 | Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | MLC / Flag / DNV | MLC / Flag / DNV | TBC | MLC 2006 as applicable + Flag/class scope | TBC | TBC | TBC | TBC | TBC | Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Crew/employment/vessel status | Conditional | Class / Statutory / Local / Project / OEM | Accommodation / Welfare | Crew profile + accommodation inspection/certification | Rule/WPS owner to be assigned | Accommodation / Welfare | Major | WPS-15 | A-R-055 | D-R-055 | G-055 | AC-R-055 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-055
R-056 | RG-19 | Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | MLC / Flag / Jordan Port Health | MLC / Flag / Jordan Port Health | TBC | MLC/Flag + Jordan health-services requirements | TBC | TBC | TBC | TBC | TBC | Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Crew onboard + Jordan entry | Conditional | Class / Statutory / Local / Project / OEM | Food / Potable Water | Health/galley/water evidence | Rule/WPS owner to be assigned | Food / Potable Water | Major | WPS-15 | A-R-056 | D-R-056 | G-056 | AC-R-056 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-056
R-057 | RG-19 | Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | STCW / Flag / Jordan | STCW / Flag / Jordan | TBC | STCW + Egyptian Flag + Jordan PSC requirements | TBC | TBC | TBC | TBC | TBC | Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Crew roster and voyage | Conditional | Class / Statutory / Local / Project / OEM | Manning / STCW | Crew certification matrix | Rule/WPS owner to be assigned | Manning / STCW | Critical | WPS-15 | A-R-057 | D-R-057 | G-057 | AC-R-057 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-057
R-058 | RG-20 | Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Flag / Project / Company | Flag / Project / Company | TBC | Applicable statutory/project/company competency requirements | TBC | TBC | TBC | TBC | TBC | Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Roles and equipment used | Conditional | Class / Statutory / Local / Project / OEM | Competence / Training | Competence matrix + training records | Rule/WPS owner to be assigned | Competence / Training | Major | WPS-15 | A-R-058 | D-R-058 | G-058 | AC-R-058 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-058
R-059 | RG-20 | Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | DNV / Flag / OEM / Project | DNV / Flag / OEM / Project | TBC | Applicable governing documents | TBC | TBC | TBC | TBC | TBC | Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Equipment/system criticality | Conditional | Class / Statutory / Local / Project / OEM | Maintenance / PMS | PMS matrix + OEM manuals + records | Rule/WPS owner to be assigned | Maintenance / PMS | Critical | WPS-13 | A-R-059 | D-R-059 | G-059 | AC-R-059 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-059
R-060 | RG-20 | Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | DNV / Flag / OEM | DNV / Flag / OEM | TBC | Applicable inspection/test/calibration basis TBC | TBC | TBC | TBC | TBC | TBC | Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Equipment criticality | Conditional | Class / Statutory / Local / Project / OEM | Maintenance / PMS | Certificates, test reports, calibration records | Rule/WPS owner to be assigned | Maintenance / PMS | Critical | WPS-13 | A-R-060 | D-R-060 | G-060 | AC-R-060 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-060
R-061 | RG-21 | Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | DNV / Flag / IMCA | DNV / Flag / IMCA | TBC | Applicable survey/inspection regimes | TBC | TBC | TBC | TBC | TBC | Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Class/statutory/IMCA scope | Conditional | Class / Statutory / Local / Project / OEM | Survey / Inspection | Survey matrix + records | Rule/WPS owner to be assigned | Survey / Inspection | Critical | WPS-16 | A-R-061 | D-R-061 | G-061 | AC-R-061 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-061
R-062 | RG-21 | Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | DNV / Flag / Project | DNV / Flag / Project | TBC | Applicable class/statutory/project documentation requirements | TBC | TBC | TBC | TBC | TBC | Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Readiness evidence | Conditional | Class / Statutory / Local / Project / OEM | Documentation | Controlled document register | Rule/WPS owner to be assigned | Documentation | Major | WPS-16 | A-R-062 | D-R-062 | G-062 | AC-R-062 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-062
R-063 | RG-21 | Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Entry/Departure & VTS regulation | TBC | TBC | TBC | TBC | TBC | Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Foreign vessel/barge in Jordanian waters | Confirmed in principle | Class / Statutory / Local / Project / OEM | Jordan Entry / Port | Agent/JMA entry requirements | Rule/WPS owner to be assigned | Jordan Entry / Port | Critical | WPS-16 | A-R-063 | D-R-063 | G-063 | AC-R-063 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-063
R-064 | RG-22 | Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | PSC Regulations 2012 | TBC | TBC | TBC | TBC | TBC | Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Foreign vessel in Jordanian waters/port | Confirmed in principle | Class / Statutory / Local / Project / OEM | Jordan PSC | PSC readiness package | Rule/WPS owner to be assigned | Jordan PSC | Critical | WPS-16 | A-R-064 | D-R-064 | G-064 | AC-R-064 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-064
R-065 | RG-22 | Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Regulations for Conducting Marine Surveys | TBC | TBC | TBC | TBC | TBC | Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Activity/port/site | Conditional | Class / Statutory / Local / Project / OEM | Jordan Marine Surveys | JMA survey requirements + reports | Rule/WPS owner to be assigned | Jordan Marine Surveys | Major | WPS-16 | A-R-065 | D-R-065 | G-065 | AC-R-065 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-065
R-066 | RG-22 | Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Regulations for Conducting Health Services for Ships | TBC | TBC | TBC | TBC | TBC | Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Arrival/port call | Conditional | Class / Statutory / Local / Project / OEM | Jordan Health | Health clearance evidence | Rule/WPS owner to be assigned | Jordan Health | Major | WPS-16 | A-R-066 | D-R-066 | G-066 | AC-R-066 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-066
R-067 | RG-23 | Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | JMC regulations/instructions for agencies/services | TBC | TBC | TBC | TBC | TBC | Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Port call and logistics | Conditional | Class / Statutory / Local / Project / OEM | Jordan Agencies / Services | Agent/service approvals | Rule/WPS owner to be assigned | Jordan Agencies / Services | Major | WPS-16 | A-R-067 | D-R-067 | G-067 | AC-R-067 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-067
R-068 | RG-23 | Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Jordan ISPS instructions/regulations | TBC | TBC | TBC | TBC | TBC | Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Ship/facility/port security scope | Conditional | Class / Statutory / Local / Project / OEM | Jordan ISPS | Security applicability/approval | Rule/WPS owner to be assigned | Jordan ISPS | Major | WPS-16 | A-R-068 | D-R-068 | G-068 | AC-R-068 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-068
R-069 | RG-23 | Determine ISM applicability and required interface; do not assume applicability. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Jordan ISM instructions/regulations | TBC | TBC | TBC | TBC | TBC | Determine ISM applicability and required interface; do not assume applicability. | Flag/statutory status + operation | Conditional | Class / Statutory / Local / Project / OEM | Jordan ISM | ISM applicability/approval | Rule/WPS owner to be assigned | Jordan ISM | Major | WPS-16 | A-R-069 | D-R-069 | G-069 | AC-R-069 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-069
R-070 | RG-24 | Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Jordan Load Lines / Tonnage instructions | TBC | TBC | TBC | TBC | TBC | Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Statutory certification scope | Conditional | Class / Statutory / Local / Project / OEM | Jordan Load Line / Tonnage | Certificates + JMA recognition | Rule/WPS owner to be assigned | Jordan Load Line / Tonnage | Major | WPS-16 | A-R-070 | D-R-070 | G-070 | AC-R-070 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-070
R-071 | RG-24 | Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Jordan BWM instructions | TBC | TBC | TBC | TBC | TBC | Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Ballast operations + statutory scope | Conditional | Class / Statutory / Local / Project / OEM | Jordan Ballast Water | BWM certificate/records where applicable | Rule/WPS owner to be assigned | Jordan Ballast Water | Major | WPS-09 | A-R-071 | D-R-071 | G-071 | AC-R-071 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-071
R-072 | RG-24 | Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Jordan FSS and Fire Test instructions | TBC | TBC | TBC | TBC | TBC | Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Statutory scope | Conditional | Class / Statutory / Local / Project / OEM | Jordan Fire / FSS | Certificates/test records | Rule/WPS owner to be assigned | Jordan Fire / FSS | Major | WPS-14 | A-R-072 | D-R-072 | G-072 | AC-R-072 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-072
R-073 | RG-25 | Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Pilot, tug master, safe navigation and VTS regulations | TBC | TBC | TBC | TBC | TBC | Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Port entry/movement | Conditional | Class / Statutory / Local / Project / OEM | Jordan Safe Navigation | Pilot/tug/VTS arrangements | Rule/WPS owner to be assigned | Jordan Safe Navigation | Critical | WPS-14 | A-R-073 | D-R-073 | G-073 | AC-R-073 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-073
R-074 | RG-25 | Establish casualty/incident reporting requirements for events in Jordanian waters. | Jordan Maritime Commission | Jordan Maritime Commission | TBC | Regulations for Investigation of Marine Casualties and Incidents | TBC | TBC | TBC | TBC | TBC | Establish casualty/incident reporting requirements for events in Jordanian waters. | Incident/casualty | Conditional | Class / Statutory / Local / Project / OEM | Jordan Casualty Reporting | Reporting procedure/contact matrix | Rule/WPS owner to be assigned | Jordan Casualty Reporting | Major | WPS-16 | A-R-074 | D-R-074 | G-074 | AC-R-074 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-074
R-075 | RG-25 | Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | ASEZA | ASEZA | TBC | Aqaba Marine Reserve Regulation No.61 of 2022 | TBC | TBC | TBC | TBC | TBC | Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Actual coordinates/activity | Conditional | Class / Statutory / Local / Project / OEM | Aqaba Marine Reserve | Official boundary + permit/control assessment | Rule/WPS owner to be assigned | Aqaba Marine Reserve | Critical | WPS-09 | A-R-075 | D-R-075 | G-075 | AC-R-075 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-075
R-076 | RG-26 | Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | ASEZA | ASEZA | TBC | Marine Environment Protection / Marine Reserve rules | TBC | TBC | TBC | TBC | TBC | Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Actual worksite/activity | Conditional | Class / Statutory / Local / Project / OEM | Aqaba Environment | ASEZA environmental requirements/permits | Rule/WPS owner to be assigned | Aqaba Environment | Critical | WPS-09 | A-R-076 | D-R-076 | G-076 | AC-R-076 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-076
R-077 | RG-26 | Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | IMO / Jordan JMA | IMO / Jordan JMA | TBC | MARPOL instructions + Jordan environmental requirements | TBC | TBC | TBC | TBC | TBC | Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Vessel/activity/waste stream | Conditional | Class / Statutory / Local / Project / OEM | Pollution / Waste | Garbage/oil/sewage/waste records | Rule/WPS owner to be assigned | Pollution / Waste | Critical | WPS-09 | A-R-077 | D-R-077 | G-077 | AC-R-077 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-077
R-078 | RG-26 | Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Jordan / Project | Jordan / Project | TBC | Jordan environmental controls + project spill plan | TBC | TBC | TBC | TBC | TBC | Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Fuel/chemicals/marine operations | Conditional | Class / Statutory / Local / Project / OEM | Spill Response | SOPEP/SMPEP as applicable + project spill plan | Rule/WPS owner to be assigned | Spill Response | Critical | WPS-09 | A-R-078 | D-R-078 | G-078 | AC-R-078 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-078
R-079 | RG-27 | Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Jordan Authorities / Agent | Jordan Authorities / Agent | TBC | Jordan port-entry process — exact authority documents TBC | TBC | TBC | TBC | TBC | TBC | Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | International arrival | Conditional | Class / Statutory / Local / Project / OEM | Customs / Immigration | Agent checklist + customs/immigration clearance | Rule/WPS owner to be assigned | Customs / Immigration | Major | WPS-16 | A-R-079 | D-R-079 | G-079 | AC-R-079 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-079
R-080 | RG-27 | Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | IACS | IACS | TBC | Unified Requirements categories A,E,F,L,M,N,P,S,W,Z; exact URs to be mapped after class basis | TBC | TBC | TBC | TBC | TBC | Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Governing DNV class basis | Conditional | Class / Statutory / Local / Project / OEM | IACS | IACS-to-DNV applicability matrix | Rule/WPS owner to be assigned | IACS | Major | WPS-01 | A-R-080 | D-R-080 | G-080 | AC-R-080 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-080
R-081 | RG-27 | Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | IACS | IACS | TBC | UR Z15 Rev.4 Jan 2025 | TBC | TBC | TBC | TBC | TBC | Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Unit type/class basis | Conditional | Class / Statutory / Local / Project / OEM | IACS | Applicability decision | Rule/WPS owner to be assigned | IACS | Major | WPS-02 | A-R-081 | D-R-081 | G-081 | AC-R-081 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-081
R-082 | RG-28 | Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | IACS | IACS | TBC | IACS UR framework | TBC | TBC | TBC | TBC | TBC | Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | DNV incorporation/ratification | Confirmed methodology | Class / Statutory / Local / Project / OEM | IACS | Rule cross-reference | Rule/WPS owner to be assigned | IACS | Major | WPS-01 | A-R-082 | D-R-082 | G-082 | AC-R-082 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-082
R-083 | RG-28 | Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Project / Industry | Project / Industry | TBC | Project specification; exact standards TBC | TBC | TBC | TBC | TBC | TBC | Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Client/project scope | Conditional | Class / Statutory / Local / Project / OEM | Industry / Project | Contract/specification | Rule/WPS owner to be assigned | Industry / Project | Major | WPS-01 | A-R-083 | D-R-083 | G-083 | AC-R-083 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-083
R-084 | RG-28 | Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | OEM | OEM | TBC | HMC 5500, LS718, CRC, CHT 50L26, winches and critical equipment | TBC | TBC | TBC | TBC | TBC | Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Equipment identity | Conditional | Class / Statutory / Local / Project / OEM | OEM | OEM manuals/records | Rule/WPS owner to be assigned | OEM | Major | WPS-13 | A-R-084 | D-R-084 | G-084 | AC-R-084 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-084
R-085 | RG-29 | Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Client / MWS | Client / MWS | TBC | Contract/SOW/MWS scope | TBC | TBC | TBC | TBC | TBC | Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Contract/MWS appointment | Conditional | Class / Statutory / Local / Project / OEM | Client / MWS | Controlled client/MWS requirement register | Rule/WPS owner to be assigned | Client / MWS | Major | WPS-11 | A-R-085 | D-R-085 | G-085 | AC-R-085 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-085
R-086 | RG-29 | Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Project / Engineering | Project / Engineering | TBC | Site-specific design basis | TBC | TBC | TBC | TBC | TBC | Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Actual site data available | Confirmed methodology | Class / Statutory / Local / Project / OEM | Site Engineering | Verified site data package | Rule/WPS owner to be assigned | Site Engineering | Critical | WPS-09 | A-R-086 | D-R-086 | G-086 | AC-R-086 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-086
R-087 | RG-29 | Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Project Governance | Project Governance | TBC | PMS-11 readiness methodology | TBC | TBC | TBC | TBC | TBC | Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Departmental verification | Confirmed methodology | Class / Statutory / Local / Project / OEM | Evidence Control | Evidence request/status record | Rule/WPS owner to be assigned | Evidence Control | Critical | WPS-16 | A-R-087 | D-R-087 | G-087 | AC-R-087 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-087
R-088 | RG-30 | Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Egyptian Flag / EAMS baseline carried from original 89-rule source set | Egyptian Flag / EAMS baseline carried from original 89-rule source set | TBC | Exact current Flag circulars/certificates/delegation basis TBC | TBC | TBC | TBC | TBC | TBC | Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Egyptian Flag status and intended Egypt-to-Jordan international operation | Conditional | Class / Statutory / Local / Project / OEM | Egyptian Flag / Statutory Basis | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements | Rule/WPS owner to be assigned | Egyptian Flag / Statutory Basis | Critical | WPS-02 | A-R-088 | D-R-088 | G-088 | AC-R-088 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-088
R-089 | RG-30 | Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set | TBC | Exact class/statutory references TBC pending current class basis and approved vessel documents | TBC | TBC | TBC | TBC | TBC | Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Current class scope, vessel condition, tow condition and offshore configuration | Conditional | Class / Statutory / Local / Project / OEM | Hull / Structural / Stability Basis | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions | Rule/WPS owner to be assigned | Hull / Structural / Stability Basis | Critical | WPS-02 | A-R-089 | D-R-089 | G-089 | AC-R-089 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Open |  | Exact reference remains TBC unless evidenced; no inference from vessel description. | R-089

## WPS
WPS ID | WPS Name | Rule Count | Verification Streams | Primary Rule Domains | Readiness Gate | Objective | Scope Included | Scope Excluded | Source Rule IDs | Governing Sources | Applicability Status | Prerequisites / Inputs | Required Activities | Required Deliverables | Predecessor WPS IDs | Successor WPS IDs | Dependency Type | Responsible Lead | Accountable Authority | Consulted Parties | Informed Parties | Criticality | WPS Acceptance Criteria ID | WPS Acceptance Evidence | WPS Status | Open Gap Count | Critical Gap Count | Closure Authority | Closure Date | Notes | Execution Count | Weighted Progress | Control Readiness
WPS-01 | Class Basis, Status, Notation & IACS Cross-Check |  | Class basis; notation/status; IACS cross-check; classification strategy / reclassification feasibility | DNV Class Basis; IACS; Industry / Project | GATE-1 | Controlled verification package for Class Basis, Status, Notation & IACS Cross-Check, including assessment of current DNV basis, DNV-RU-SHIP vs DNV-RU-OU applicability, and an alternative IACS class-transfer pathway before the governing class basis is frozen. | Current class evidence; notation/status; rule edition; IACS cross-check; DNV-RU-SHIP / DNV-RU-OU feasibility; alternative IACS class-transfer feasibility. | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-001,R-002,R-004,R-005,R-008,R-080,R-082,R-083 | DNV Class Basis; IACS; Industry / Project | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-01-001… | D-WPS-01-001… |  | WPS-02 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-01-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis |  | Existing-unit history; rule edition; Flag/statutory; hull/structural/stability | DNV Class Basis; Egyptian Flag / Statutory Basis; Hull / Structural / Stability Basis; IACS | GATE-1 | Controlled verification and readiness package for Existing Unit, Flag/Statutory & Rule-Edition Basis | Existing-unit history; rule edition; Flag/statutory; hull/structural/stability | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-003,R-006,R-007,R-081,R-088,R-089 | DNV Class Basis; Egyptian Flag / Statutory Basis; Hull / Structural / Stability Basis; IACS | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-02-001… | D-WPS-02-001… | WPS-01 | WPS-03 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-02-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-03 | Lifting Appliances & Loose Gear |  | Lifting register; recovery winch; side tugger winches; loose gear | Lifting Appliances | GATE-2 | Controlled verification and readiness package for Lifting Appliances & Loose Gear | Lifting register; recovery winch; side tugger winches; loose gear | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-009,R-010,R-011,R-016,R-017,R-018 | Lifting Appliances | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-03-001… | D-WPS-03-001… | WPS-02 | WPS-04 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-03-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-04 | HMC 5500 Derrick Crane |  | HMC 5500 identity/configuration/offshore acceptance | Lifting Appliances | GATE-2 | Controlled verification and readiness package for HMC 5500 Derrick Crane | HMC 5500 identity/configuration/offshore acceptance | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-012,R-013 | Lifting Appliances | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-04-001… | D-WPS-04-001… | WPS-03 | WPS-05 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-04-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-05 | Link-Belt LS 718 Crawler Crane |  | LS 718 identity/configuration/offshore acceptance | Lifting Appliances | GATE-2 | Controlled verification and readiness package for Link-Belt LS 718 Crawler Crane | LS 718 identity/configuration/offshore acceptance | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-014,R-015 | Lifting Appliances | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-05-001… | D-WPS-05-001… | WPS-04 | WPS-06 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-05-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-06 | Pipe-Lay Spread & Tensioner |  | CRC pipe-lay spread; CHT 50L26 tensioner; pipe handling | Pipe Laying | GATE-3 | Controlled verification and readiness package for Pipe-Lay Spread & Tensioner | CRC pipe-lay spread; CHT 50L26 tensioner; pipe handling | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-019,R-020,R-021,R-022 | Pipe Laying | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-06-001… | D-WPS-06-001… | WPS-05 | WPS-07 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Major | AC-WPS-06-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-07 | Pipeline Installation, Welding & NDT |  | Pipeline design/install analysis; welding/coating; X-ray/NDT; QA/QC | Pipe Laying; Pipeline Engineering | GATE-3 | Controlled verification and readiness package for Pipeline Installation, Welding & NDT | Pipeline design/install analysis; welding/coating; X-ray/NDT; QA/QC | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-023,R-024,R-025,R-026,R-027,R-028 | Pipe Laying; Pipeline Engineering | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-07-001… | D-WPS-07-001… | WPS-06 | WPS-08 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Major | AC-WPS-07-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-08 | Eight-Point Mooring & Anchoring |  | Mooring inventory; winches; anchor handling; analysis | Mooring / Anchoring | GATE-3 | Controlled verification and readiness package for Eight-Point Mooring & Anchoring | Mooring inventory; winches; anchor handling; analysis | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-029,R-030,R-031,R-036 | Mooring / Anchoring | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-08-001… | D-WPS-08-001… | WPS-07 | WPS-09 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-08-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-09 | Aqaba Site, Environmental & Pollution Constraints |  | Aqaba site data; seabed/metocean/subsea constraints; reserve; environmental/pollution/spill controls | Aqaba Environment; Aqaba Marine Reserve; Jordan Ballast Water; Mooring / Anchoring; Pollution / Waste; Site Engineering; Spill Response | GATE-3 | Controlled verification and readiness package for Aqaba Site, Environmental & Pollution Constraints | Aqaba site data; seabed/metocean/subsea constraints; reserve; environmental/pollution/spill controls | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-032,R-033,R-034,R-071,R-075,R-076,R-077,R-078,R-086 | Aqaba Environment; Aqaba Marine Reserve; Jordan Ballast Water; Mooring / Anchoring; Pollution / Waste; Site Engineering; Spill Response | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-09-001… | D-WPS-09-001… | WPS-08 | WPS-10 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-09-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-10 | Egypt–Aqaba Wet Tow |  | Tow configuration; tow points; tug; stability; route/weather; pre-tow readiness | Wet Tow / Mobilization | GATE-5 | Controlled verification and readiness package for Egypt–Aqaba Wet Tow | Tow configuration; tow points; tug; stability; route/weather; pre-tow readiness | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-037,R-038,R-039,R-040,R-041,R-042 | Wet Tow / Mobilization | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-10-001… | D-WPS-10-001… | WPS-09 | WPS-11 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-10-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-11 | Marine Warranty / Independent Verification |  | MWS/client/independent verification; contractual hold points | Client / MWS; Marine Warranty; Mooring / Anchoring | GATE-4 | Controlled verification and readiness package for Marine Warranty / Independent Verification | MWS/client/independent verification; contractual hold points | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-035,R-043,R-085 | Client / MWS; Marine Warranty; Mooring / Anchoring | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-11-001… | D-WPS-11-001… | WPS-10 | WPS-12 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Major | AC-WPS-11-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-12 | Diving Systems — IMCA Only |  | IMCA-only air/saturation diving plant, LARS, life support, competence and audit/examination | Diving | GATE-7 | Controlled verification and readiness package for Diving Systems — IMCA Only | IMCA-only air/saturation diving plant, LARS, life support, competence and audit/examination | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-044,R-045,R-046,R-047,R-048 | Diving | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-12-001… | D-WPS-12-001… | WPS-11 | WPS-13 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-12-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance |  | Machinery; electrical; ballast/bilge; hydraulics; compressed air; PMS; maintenance/calibration; OEM | Machinery / Electrical; Maintenance / PMS; OEM | GATE-7/8 | Controlled verification and readiness package for Machinery, Electrical, Ballast, Mechanical & Maintenance | Machinery; electrical; ballast/bilge; hydraulics; compressed air; PMS; maintenance/calibration; OEM | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-049,R-050,R-059,R-060,R-084 | Machinery / Electrical; Maintenance / PMS; OEM | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-13-001… | D-WPS-13-001… | WPS-12 | WPS-14 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Major | AC-WPS-13-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-14 | Fire, LSA, Emergency, Navigation & Communications |  | Fire/LSA/emergency; navigation/communications; Jordan safe navigation/fire interface where applicable | Fire / LSA / Emergency; Jordan Fire / FSS; Jordan Safe Navigation; Navigation / Communications | GATE-6/7 | Controlled verification and readiness package for Fire, LSA, Emergency, Navigation & Communications | Fire/LSA/emergency; navigation/communications; Jordan safe navigation/fire interface where applicable | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-051,R-052,R-053,R-054,R-072,R-073 | Fire / LSA / Emergency; Jordan Fire / FSS; Jordan Safe Navigation; Navigation / Communications | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-14-001… | D-WPS-14-001… | WPS-13 | WPS-15 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Major | AC-WPS-14-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-15 | Accommodation, Welfare, Manning & Competence |  | Accommodation/welfare; food/potable water; manning/STCW; competence/training | Accommodation / Welfare; Competence / Training; Food / Potable Water; Manning / STCW | GATE-4/7 | Controlled verification and readiness package for Accommodation, Welfare, Manning & Competence | Accommodation/welfare; food/potable water; manning/STCW; competence/training | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-055,R-056,R-057,R-058 | Accommodation / Welfare; Competence / Training; Food / Potable Water; Manning / STCW | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-15-001… | D-WPS-15-001… | WPS-14 | WPS-16 | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Major | AC-WPS-15-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance |  | Jordan port/PSC/health/agencies/customs; marine surveys; security/ISM; casualty reporting; controlled evidence | Customs / Immigration; Documentation; Evidence Control; Jordan Agencies / Services; Jordan Casualty Reporting; Jordan Entry / Port; Jordan Health; Jordan ISM; Jordan ISPS; Jordan Load Line / Tonnage; Jordan Marine Surveys; Jordan PSC; Survey / Inspection | GATE-4/6/8 | Controlled verification and readiness package for Jordan Regulatory, Port, Survey & Controlled Assurance | Jordan port/PSC/health/agencies/customs; marine surveys; security/ISM; casualty reporting; controlled evidence | Unsupported compliance declarations; unverified assumptions; authority decisions belonging to competent authorities. | R-061,R-062,R-063,R-064,R-065,R-066,R-067,R-068,R-069,R-070,R-074,R-079,R-087 | Customs / Immigration; Documentation; Evidence Control; Jordan Agencies / Services; Jordan Casualty Reporting; Jordan Entry / Port; Jordan Health; Jordan ISM; Jordan ISPS; Jordan Load Line / Tonnage; Jordan Marine Surveys; Jordan PSC; Survey / Inspection | Conditional / Information Gap | Current controlled source evidence and authority scope; no unsupported assumption. | A-WPS-16-001… | D-WPS-16-001… | WPS-15 |  | Finish-to-Start | WPS owner / lead | Competent authority per rule and evidence | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | Owner / Project Director | Critical | AC-WPS-16-001 | Controlled package, measurable criteria and accepted evidence | Open |  |  | Relevant competent authority / accepting party |  | Canonical 16-WPS register from user-provided Drive workbook; legacy coverage retained by crosswalks.
WPS-17 | DNV Class Recovery / Reinstatement |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | DNV Class Recovery / Reinstatement | GATE-1 | Recover suspended DNV class through verified cause, survey scope, repairs, tests and formal reinstatement decision. | Class suspension evidence; DNV survey scope; repair/tests; reinstatement decision. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-01,WPS-02 | WPS-03,WPS-10,WPS-13,WPS-14,WPS-16 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Critical | AC-WPS-17 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-18 | Alternative IACS Reclassification / Transfer Feasibility |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Alternative IACS Reclassification / Transfer Feasibility | GATE-1 | Evaluate and, only if approved, execute transfer or reassignment to an alternative IACS member without presuming acceptance. | Transfer-of-class prerequisites; records; surveys; gap/cost/schedule comparison; authority decision. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-01,WPS-02 | WPS-03,WPS-10,WPS-13,WPS-14,WPS-16 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Critical | AC-WPS-18 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-19 | Helideck & Aviation Interface Readiness |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Helideck & Aviation Interface Readiness | GATE-7 | Determine applicability and secure the competent aviation and marine approvals for helideck design, equipment, procedures and flight interface. | Helideck technical file; operating manual; obstacles; lighting/marking; rescue/firefighting; Jordan airspace interface. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-14,WPS-16 | WPS-24 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Critical | AC-WPS-19 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-20 | Fuel, Emissions, Water & Waste Operational Control |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Fuel, Emissions, Water & Waste Operational Control | GATE-7/8 | Control fuel quality documentation, emissions applicability, sludge, sewage, potable water, garbage and spill interfaces. | BDN/fuel records; applicability assessment; tanks; STP/RO; waste plan; disposal records. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-09,WPS-13,WPS-16 | WPS-24 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Major | AC-WPS-20 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-21 | Digital PMS / CMMS, Spares & Materials Readiness |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Digital PMS / CMMS, Spares & Materials Readiness | GATE-7 | Verify maintenance database integrity, critical-equipment jobs, defects, spares, materials and procurement readiness. | Asset hierarchy; job plans; backlog; critical spares; stock verification; procurement. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-13 | WPS-17,WPS-18,WPS-22,WPS-24 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Critical | AC-WPS-21 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-22 | Anchor Handling, Control Room & Position Monitoring Operations |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Anchor Handling, Control Room & Position Monitoring Operations | GATE-3 | Develop and verify executable anchor-handling, control-room, communication, monitoring and emergency-release arrangements. | Anchor sequence; control-room procedures; APMS/DGPS; winch tests; tug matrix; drills. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-08,WPS-09,WPS-13,WPS-14 | WPS-24 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Critical | AC-WPS-22 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-23 | Crew Mobilization, Medical & Behavioral Safety |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Crew Mobilization, Medical & Behavioral Safety | GATE-4/7 | Plan department staffing, competence, medical facility, fatigue, drug/alcohol policy and Egypt-Jordan crew logistics. | Crew matrix; clinic/pharmacy; licenses; rest-hour controls; policy; visas/travel/repatriation. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-15,WPS-16 | WPS-24 | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Major | AC-WPS-23 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.
WPS-24 | Integrated Operational & Emergency Readiness |  | Supplemental operational assurance controls integrated into the same execution/evidence/acceptance chain | Integrated Operational & Emergency Readiness | GATE-8 | Integrate marine, aviation, diving, environmental and shore-response arrangements and verify through scenario-based drills. | IERP; interface matrix; drills; communications; medevac; no-go criteria; closeout. | Unverified authority decisions; classified site data; unsupported fixed thresholds. | SUPPLEMENTAL CONTROL — not a canonical Rule | Source-grounded operational control / applicability determination / competent authority as applicable | Conditional / Information Gap | Verified source evidence and responsible-authority scope | See 30_EXECUTION_CONTROL | See 30_EXECUTION_CONTROL | WPS-09,WPS-10,WPS-12,WPS-14,WPS-17,WPS-18,WPS-19,WPS-20,WPS-21,WPS-22,WPS-23 |  | Logical network; relationship set at activity level | To be assigned by PMO | Competent authority per activity | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / aviation authority / competent person | Owner / Project Director | Critical | AC-WPS-24 | Accepted deliverables and closed blocker/critical gaps | Planned |  |  | Relevant competent authority / accepting party |  | V7 supplemental WPS; does not alter the 89 canonical rule universe.

## Activities
Activity ID | WPS ID | Activity Group ID | Activity Title | Activity Description | Activity Type | Source Rule IDs | Applicability Status | Trigger | Required Inputs | Activity Owner | Accountable Authority | Consulted Parties | Predecessor Activity IDs | Dependency Type | Successor Activity IDs | Planned Start | Planned Finish | Duration | Actual Start | Actual Finish | Status | Priority | Critical Path | Related Deliverable IDs | Related Acceptance Criteria IDs | Related Gap IDs | Evidence Required | Verification Method | Closure Authority | Closure Date | Source Activity ID | Notes
A-R-001 | WPS-01 | AG-01 | Verify and close: Determine the governing classification regime and assess DNV-RU-SHIP / DNV-RU-OU / alternative IACS class-transfer pathways before freezing the PMS-11 class basis. | Obtain and authenticate current class certificate/status and class history; extract notation/scope/restrictions; assess DNV-RU-SHIP versus DNV-RU-OU applicability; assess feasibility prerequisites for an alternative IACS class transfer without naming or assuming an unsupported society; record competent-authority decision, conditions and limits. | Document Review / Applicability Determination | R-001 | Conditional | Current class certificate/approved class basis | Current DNV Class Certificate + class status; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | GATE-0 | Finish-to-Start | A-R-002 | [5 empty] | Open | Critical | To Be Determined | D-R-001 | AC-R-001 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Current DNV Class Certificate + class status; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-001 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-002 | WPS-01 | AG-02 | Verify and close: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Document Review / Applicability Determination | R-002 | Conditional | Current certificate | Current DNV Class Certificate; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-001 | Finish-to-Start | A-R-003 | [5 empty] | Open | Critical | To Be Determined | D-R-002 | AC-R-002 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Current DNV Class Certificate; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-002 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-003 | WPS-02 | AG-03 | Verify and close: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Document Review / Applicability Determination | R-003 | Conditional | Build date, class history, modifications | Class basis + rule edition evidence; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-002 | Finish-to-Start | A-R-004 | [5 empty] | Open | Critical | To Be Determined | D-R-003 | AC-R-003 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Class basis + rule edition evidence; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-003 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-004 | WPS-01 | AG-04 | Verify and close: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Document Review / Applicability Determination | R-004 | Conditional | Current status | Class Status Report + survey records; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-003 | Finish-to-Start | A-R-005 | [5 empty] | Open | Critical | To Be Determined | D-R-004 | AC-R-004 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Class Status Report + survey records; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-004 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-005 | WPS-01 | AG-05 | Verify and close: Identify approved drawings and documents forming the class technical basis. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Identify approved drawings and documents forming the class technical basis. | Document Review / Applicability Determination | R-005 | Conditional | Current class file | Approved drawings list / class file; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-004 | Finish-to-Start | A-R-006 | [5 empty] | Open | Critical | To Be Determined | D-R-005 | AC-R-005 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify approved drawings and documents forming the class technical basis. | Approved drawings list / class file; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-005 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-006 | WPS-02 | AG-06 | Verify and close: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Document Review / Applicability Determination | R-006 | Conditional | Class status | Survey status/history; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-005 | Finish-to-Start | A-R-007 | [5 empty] | Open | Critical | To Be Determined | D-R-006 | AC-R-006 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Survey status/history; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-006 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-007 | WPS-02 | AG-07 | Verify and close: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Document Review / Applicability Determination | R-007 | Conditional | Any modification/change of service | Modification history + approvals; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-006 | Finish-to-Start | A-R-008 | [5 empty] | Open | Critical | To Be Determined | D-R-007 | AC-R-007 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Modification history + approvals; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-007 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-008 | WPS-01 | AG-08 | Verify and close: Establish the approved operating limits and service scope relevant to Jordan operations. | Obtain and authenticate the governing class evidence; extract exact applicability, scope, restrictions, survey status and governing reference, then reconcile it to PMS-11. Record applicability, discrepancies, limitations and acceptance authority for: Establish the approved operating limits and service scope relevant to Jordan operations. | Document Review / Applicability Determination | R-008 | Conditional | Certificate/class file | Certificate + approved operational documents; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-007 | Finish-to-Start | A-R-009 | [5 empty] | Open | Critical | To Be Determined | D-R-008 | AC-R-008 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the approved operating limits and service scope relevant to Jordan operations. | Certificate + approved operational documents; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | DNV Class Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-008 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-009 | WPS-03 | AG-09 | Verify and close: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Document Review / Applicability Determination | R-009 | Conditional | Vessel statutory certification + appliance type | Flag/statutory basis + appliance register; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-008 | Finish-to-Start | A-R-010 | [5 empty] | Open | Critical | To Be Determined | D-R-009 | AC-R-009 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Flag/statutory basis + appliance register; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-009 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-010 | WPS-03 | AG-10 | Verify and close: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Document Review / Applicability Determination | R-010 | Conditional | Administration acceptance + alternative standard | Flag acceptance + technical basis; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-009 | Finish-to-Start | A-R-011 | [5 empty] | Open | Critical | To Be Determined | D-R-010 | AC-R-010 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Flag acceptance + technical basis; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-010 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-011 | WPS-03 | AG-11 | Verify and close: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Document Review / Applicability Determination | R-011 | Conditional | Applicability decision | Register + certificates + examination/load-test records; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-010 | Finish-to-Start | A-R-012 | [5 empty] | Open | Critical | To Be Determined | D-R-011 | AC-R-011 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Register + certificates + examination/load-test records; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-011 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-012 | WPS-04 | AG-12 | Verify and close: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Document Review / Applicability Determination | R-012 | Conditional | Installed configuration | HMC 5500 technical/certification file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-011 | Finish-to-Start | A-R-013 | [5 empty] | Open | Critical | To Be Determined | D-R-012 | AC-R-012 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | HMC 5500 technical/certification file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-012 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-013 | WPS-04 | AG-13 | Verify and close: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Document Review / Applicability Determination | R-013 | Conditional | Operational mode | Crane manual, load charts, limits, procedures; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-012 | Finish-to-Start | A-R-014 | [5 empty] | Open | Critical | To Be Determined | D-R-013 | AC-R-013 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Crane manual, load charts, limits, procedures; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-013 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-014 | WPS-05 | AG-14 | Verify and close: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Document Review / Applicability Determination | R-014 | Conditional | Installed crawler configuration | OEM/configuration file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-013 | Finish-to-Start | A-R-015 | [5 empty] | Open | Critical | To Be Determined | D-R-014 | AC-R-014 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | OEM/configuration file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-014 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-015 | WPS-05 | AG-15 | Verify and close: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Document Review / Applicability Determination | R-015 | Conditional | Crawler used offshore | Engineering assessment + load chart + deck data; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-014 | Finish-to-Start | A-R-016 | [5 empty] | Open | Critical | To Be Determined | D-R-015 | AC-R-015 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Engineering assessment + load chart + deck data; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-015 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-016 | WPS-03 | AG-01 | Verify and close: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Document Review / Applicability Determination | R-016 | Conditional | Used as lifting/recovery appliance | Winch certificate/test/exam/OEM file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-015 | Finish-to-Start | A-R-017 | [5 empty] | Open | Major | To Be Determined | D-R-016 | AC-R-016 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Winch certificate/test/exam/OEM file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-016 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-017 | WPS-03 | AG-02 | Verify and close: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Document Review / Applicability Determination | R-017 | Conditional | Use in marine operations/lifting | Tugger certificates/tests/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-016 | Finish-to-Start | A-R-018 | [5 empty] | Open | Major | To Be Determined | D-R-017 | AC-R-017 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Tugger certificates/tests/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-017 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-018 | WPS-03 | AG-03 | Verify and close: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Identify the equipment item(s); reconcile physical identity/configuration and certificate/OEM data; verify rating, examination/testing, structural interface and operating limits. Record applicability, discrepancies, limitations and acceptance authority for: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Document Review / Applicability Determination | R-018 | Conditional | Equipment used for lifting | Loose-gear register + certificates/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-017 | Finish-to-Start | A-R-019 | [5 empty] | Open | Critical | To Be Determined | D-R-018 | AC-R-018 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Loose-gear register + certificates/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Lifting Appliances | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-018 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-019 | WPS-06 | AG-04 | Verify and close: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Document Review / Applicability Determination | R-019 | Conditional | Class regime + notation | Class basis + applicable rule edition; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-018 | Finish-to-Start | A-R-020 | [5 empty] | Open | Critical | To Be Determined | D-R-019 | AC-R-019 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Class basis + applicable rule edition; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-019 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-020 | WPS-06 | AG-05 | Verify and close: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Document Review / Applicability Determination | R-020 | Conditional | Actual spread configuration | CRC drawings/manuals/tests; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-019 | Finish-to-Start | A-R-021 | [5 empty] | Open | Critical | To Be Determined | D-R-020 | AC-R-020 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | CRC drawings/manuals/tests; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-020 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-021 | WPS-06 | AG-06 | Verify and close: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Document Review / Applicability Determination | R-021 | Conditional | Installed tensioner | Tensioner certificate/manual/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-020 | Finish-to-Start | A-R-022 | [5 empty] | Open | Critical | To Be Determined | D-R-021 | AC-R-021 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Tensioner certificate/manual/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-021 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-022 | WPS-06 | AG-07 | Verify and close: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Document Review / Applicability Determination | R-022 | Conditional | Actual pipe-lay configuration | Drawings + calculations + inspection/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-021 | Finish-to-Start | A-R-023 | [5 empty] | Open | Critical | To Be Determined | D-R-022 | AC-R-022 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Drawings + calculations + inspection/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-022 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-023 | WPS-07 | AG-08 | Verify and close: Verify welding stations, coating station and related QA/QC controls. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Verify welding stations, coating station and related QA/QC controls. | Document Review / Applicability Determination | R-023 | Conditional | Project scope | Welding/coating procedures + qualifications; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-022 | Finish-to-Start | A-R-024 | [5 empty] | Open | Major | To Be Determined | D-R-023 | AC-R-023 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify welding stations, coating station and related QA/QC controls. | Welding/coating procedures + qualifications; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-023 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-024 | WPS-07 | AG-09 | Verify and close: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Document Review / Applicability Determination | R-024 | Conditional | X-ray/NDT performed | Equipment certificates + personnel qualifications + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-023 | Finish-to-Start | A-R-025 | [5 empty] | Open | Critical | To Be Determined | D-R-024 | AC-R-024 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Equipment certificates + personnel qualifications + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-024 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-025 | WPS-07 | AG-10 | Verify and close: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Document Review / Applicability Determination | R-025 | Conditional | Project/site data | Installation analysis + operating limits + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-024 | Finish-to-Start | A-R-026 | [5 empty] | Open | Critical | To Be Determined | D-R-025 | AC-R-025 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Installation analysis + operating limits + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipe Laying | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-025 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-026 | WPS-07 | AG-11 | Verify and close: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Document Review / Applicability Determination | R-026 | Conditional | Project pipeline specification | Project design basis/specification; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-025 | Finish-to-Start | A-R-027 | [5 empty] | Open | Major | To Be Determined | D-R-026 | AC-R-026 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Project design basis/specification; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipeline Engineering | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-026 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-027 | WPS-07 | AG-12 | Verify and close: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Document Review / Applicability Determination | R-027 | Conditional | Pipeline design/installation scope | Project specification + engineering basis; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-026 | Finish-to-Start | A-R-028 | [5 empty] | Open | Major | To Be Determined | D-R-027 | AC-R-027 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Project specification + engineering basis; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipeline Engineering | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-027 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-028 | WPS-07 | AG-13 | Verify and close: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Review the installed pipe-lay/welding/NDT arrangement against controlled drawings, equipment records and project design basis; verify configuration, capacity/limits, tests and interfaces. Record applicability, discrepancies, limitations and acceptance authority for: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Document Review / Applicability Determination | R-028 | Conditional | Pipeline/site data | Installation analysis package; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-027 | Finish-to-Start | A-R-029 | [5 empty] | Open | Critical | To Be Determined | D-R-028 | AC-R-028 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Installation analysis package; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Pipeline Engineering | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-028 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-029 | WPS-08 | AG-14 | Verify and close: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Document Review / Applicability Determination | R-029 | Conditional | Actual mooring configuration | Mooring arrangement + equipment certificates; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-028 | Finish-to-Start | A-R-030 | [5 empty] | Open | Critical | To Be Determined | D-R-029 | AC-R-029 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Mooring arrangement + equipment certificates; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-029 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-030 | WPS-08 | AG-15 | Verify and close: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Document Review / Applicability Determination | R-030 | Conditional | Installed mooring equipment | Winch manuals/tests/exams; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-029 | Finish-to-Start | A-R-031 | [5 empty] | Open | Critical | To Be Determined | D-R-030 | AC-R-030 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Winch manuals/tests/exams; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-030 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-031 | WPS-08 | AG-01 | Verify and close: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Document Review / Applicability Determination | R-031 | Conditional | Site-specific analysis | Mooring analysis + environmental design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-030 | Finish-to-Start | A-R-032 | [5 empty] | Open | Critical | To Be Determined | D-R-031 | AC-R-031 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Mooring analysis + environmental design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-031 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-032 | WPS-09 | AG-02 | Verify and close: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Document Review / Applicability Determination | R-032 | Conditional | Actual Jordan worksite | Verified survey/geotech package; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-031 | Finish-to-Start | A-R-033 | [5 empty] | Open | Critical | To Be Determined | D-R-032 | AC-R-032 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Verified survey/geotech package; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-032 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-033 | WPS-09 | AG-03 | Verify and close: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Document Review / Applicability Determination | R-033 | Conditional | Actual worksite | Subsea asset register + approved site layout; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-032 | Finish-to-Start | A-R-034 | [5 empty] | Open | Critical | To Be Determined | D-R-033 | AC-R-033 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Subsea asset register + approved site layout; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-033 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-034 | WPS-09 | AG-04 | Verify and close: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Document Review / Applicability Determination | R-034 | Conditional | Site-specific analysis | Metocean design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-033 | Finish-to-Start | A-R-035 | [5 empty] | Open | Critical | To Be Determined | D-R-034 | AC-R-034 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Metocean design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-034 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-035 | WPS-11 | AG-05 | Verify and close: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Document Review / Applicability Determination | R-035 | Conditional | Project/MWS scope | MWS scope + approval documents; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-034 | Finish-to-Start | A-R-036 | [5 empty] | Open | Major | To Be Determined | D-R-035 | AC-R-035 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | MWS scope + approval documents; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-035 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-036 | WPS-08 | AG-06 | Verify and close: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Verify the complete mooring/anchoring inventory and certificates, then reconcile the engineering basis with actual site data, operating configuration, failure cases and clearances. Record applicability, discrepancies, limitations and acceptance authority for: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Document Review / Applicability Determination | R-036 | Conditional | Mooring operation | Approved procedures + drills/records; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-035 | Finish-to-Start | A-R-037 | [5 empty] | Open | Major | To Be Determined | D-R-036 | AC-R-036 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Approved procedures + drills/records; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Mooring / Anchoring | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-036 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-037 | WPS-10 | AG-07 | Verify and close: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Review the controlled tow verification pack; reconcile tow configuration, structure, stability, tug capability, route/weather/emergency criteria and approvals. Record applicability, discrepancies, limitations and acceptance authority for: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Document Review / Applicability Determination | R-037 | Conditional | Wet tow | Tow engineering package; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-036 | Finish-to-Start | A-R-038 | [5 empty] | Open | Critical | To Be Determined | D-R-037 | AC-R-037 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Tow engineering package; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Wet Tow / Mobilization | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-037 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-038 | WPS-10 | AG-08 | Verify and close: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Review the controlled tow verification pack; reconcile tow configuration, structure, stability, tug capability, route/weather/emergency criteria and approvals. Record applicability, discrepancies, limitations and acceptance authority for: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Document Review / Applicability Determination | R-038 | Conditional | Tow configuration | Structural verification; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-037 | Finish-to-Start | A-R-039 | [5 empty] | Open | Critical | To Be Determined | D-R-038 | AC-R-038 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Structural verification; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Wet Tow / Mobilization | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-038 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-039 | WPS-10 | AG-09 | Verify and close: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Review the controlled tow verification pack; reconcile tow configuration, structure, stability, tug capability, route/weather/emergency criteria and approvals. Record applicability, discrepancies, limitations and acceptance authority for: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Document Review / Applicability Determination | R-039 | Conditional | Tow condition | Stability/tow condition calculations; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-038 | Finish-to-Start | A-R-040 | [5 empty] | Open | Critical | To Be Determined | D-R-039 | AC-R-039 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Stability/tow condition calculations; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Wet Tow / Mobilization | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-039 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-040 | WPS-10 | AG-10 | Verify and close: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Review the controlled tow verification pack; reconcile tow configuration, structure, stability, tug capability, route/weather/emergency criteria and approvals. Record applicability, discrepancies, limitations and acceptance authority for: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Document Review / Applicability Determination | R-040 | Conditional | Selected tug | Tug data + tow plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-039 | Finish-to-Start | A-R-041 | [5 empty] | Open | Critical | To Be Determined | D-R-040 | AC-R-040 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Tug data + tow plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Wet Tow / Mobilization | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-040 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-041 | WPS-10 | AG-11 | Verify and close: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Review the controlled tow verification pack; reconcile tow configuration, structure, stability, tug capability, route/weather/emergency criteria and approvals. Record applicability, discrepancies, limitations and acceptance authority for: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Document Review / Applicability Determination | R-041 | Conditional | Route and season | Tow route/weather/emergency plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-040 | Finish-to-Start | A-R-042 | [5 empty] | Open | Critical | To Be Determined | D-R-041 | AC-R-041 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Tow route/weather/emergency plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Wet Tow / Mobilization | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-041 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-042 | WPS-10 | AG-12 | Verify and close: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Review the controlled tow verification pack; reconcile tow configuration, structure, stability, tug capability, route/weather/emergency criteria and approvals. Record applicability, discrepancies, limitations and acceptance authority for: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Document Review / Applicability Determination | R-042 | Conditional | Tow approval pathway | Pre-tow inspection + approval; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-041 | Finish-to-Start | A-R-043 | [5 empty] | Open | Critical | To Be Determined | D-R-042 | AC-R-042 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Pre-tow inspection + approval; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Wet Tow / Mobilization | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-042 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-043 | WPS-11 | AG-13 | Verify and close: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Obtain the controlled contractual/MWS requirement set, identify hold points and approval roles, and map each to an acceptance record. Record applicability, discrepancies, limitations and acceptance authority for: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Document Review / Applicability Determination | R-043 | Conditional | Client/MWS scope + operation type | MWS scope and approvals; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-042 | Finish-to-Start | A-R-044 | [5 empty] | Open | Major | To Be Determined | D-R-043 | AC-R-043 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | MWS scope and approvals; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Marine Warranty | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-043 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-044 | WPS-12 | AG-14 | Verify and close: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Apply the project IMCA-only verification path: identify scope, inspect plant/system records, verify tests/maintenance/emergency arrangements and competence. Record applicability, discrepancies, limitations and acceptance authority for: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Document Review / Applicability Determination | R-044 | Conditional | IMCA inspection/project scope | IMCA inspection report + controlled diving procedures/records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-043 | Finish-to-Start | A-R-045 | [5 empty] | Open | Critical | To Be Determined | D-R-044 | AC-R-044 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | IMCA inspection report + controlled diving procedures/records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Diving | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-044 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-045 | WPS-12 | AG-15 | Verify and close: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Apply the project IMCA-only verification path: identify scope, inspect plant/system records, verify tests/maintenance/emergency arrangements and competence. Record applicability, discrepancies, limitations and acceptance authority for: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Document Review / Applicability Determination | R-045 | Conditional | Air diving operations | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-044 | Finish-to-Start | A-R-046 | [5 empty] | Open | Critical | To Be Determined | D-R-045 | AC-R-045 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Diving | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-045 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-046 | WPS-12 | AG-01 | Verify and close: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Apply the project IMCA-only verification path: identify scope, inspect plant/system records, verify tests/maintenance/emergency arrangements and competence. Record applicability, discrepancies, limitations and acceptance authority for: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Document Review / Applicability Determination | R-046 | Conditional | Saturation diving capability | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-045 | Finish-to-Start | A-R-047 | [5 empty] | Open | Critical | To Be Determined | D-R-046 | AC-R-046 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Diving | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-046 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-047 | WPS-12 | AG-02 | Verify and close: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Apply the project IMCA-only verification path: identify scope, inspect plant/system records, verify tests/maintenance/emergency arrangements and competence. Record applicability, discrepancies, limitations and acceptance authority for: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Document Review / Applicability Determination | R-047 | Conditional | Diving personnel roster | Competence matrix + records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-046 | Finish-to-Start | A-R-048 | [5 empty] | Open | Critical | To Be Determined | D-R-047 | AC-R-047 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Competence matrix + records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Diving | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-047 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-048 | WPS-12 | AG-03 | Verify and close: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Apply the project IMCA-only verification path: identify scope, inspect plant/system records, verify tests/maintenance/emergency arrangements and competence. Record applicability, discrepancies, limitations and acceptance authority for: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Document Review / Applicability Determination | R-048 | Conditional | IMCA inspection | Maintenance/test records + IMCA acceptance; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-047 | Finish-to-Start | A-R-049 | [5 empty] | Open | Critical | To Be Determined | D-R-048 | AC-R-048 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Maintenance/test records + IMCA acceptance; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Diving | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-048 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-049 | WPS-13 | AG-04 | Verify and close: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Verify the named system/equipment using controlled drawings, tests, calibration, PMS/OEM records and survey status; record outstanding restrictions. Record applicability, discrepancies, limitations and acceptance authority for: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Document Review / Applicability Determination | R-049 | Conditional | Class/statutory scope | Electrical single-line + tests + survey records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-048 | Finish-to-Start | A-R-050 | [5 empty] | Open | Critical | To Be Determined | D-R-049 | AC-R-049 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Electrical single-line + tests + survey records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Machinery / Electrical | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-049 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-050 | WPS-13 | AG-05 | Verify and close: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Verify the named system/equipment using controlled drawings, tests, calibration, PMS/OEM records and survey status; record outstanding restrictions. Record applicability, discrepancies, limitations and acceptance authority for: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Document Review / Applicability Determination | R-050 | Conditional | Installed systems | P&IDs + tests + maintenance records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-049 | Finish-to-Start | A-R-051 | [5 empty] | Open | Critical | To Be Determined | D-R-050 | AC-R-050 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | P&IDs + tests + maintenance records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Machinery / Electrical | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-050 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-051 | WPS-14 | AG-06 | Verify and close: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Verify current equipment/service/test/drill evidence and reconcile navigation, communications, fire/LSA or emergency requirements to the actual operating scenario. Record applicability, discrepancies, limitations and acceptance authority for: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Document Review / Applicability Determination | R-051 | Conditional | Statutory certification scope | FSS certificates/tests + plans; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-050 | Finish-to-Start | A-R-052 | [5 empty] | Open | Critical | To Be Determined | D-R-051 | AC-R-051 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | FSS certificates/tests + plans; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Fire / LSA / Emergency | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-051 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-052 | WPS-14 | AG-07 | Verify and close: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Verify current equipment/service/test/drill evidence and reconcile navigation, communications, fire/LSA or emergency requirements to the actual operating scenario. Record applicability, discrepancies, limitations and acceptance authority for: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Document Review / Applicability Determination | R-052 | Conditional | Statutory certification scope | LSA certificates + drill records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-051 | Finish-to-Start | A-R-053 | [5 empty] | Open | Critical | To Be Determined | D-R-052 | AC-R-052 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | LSA certificates + drill records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Fire / LSA / Emergency | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-052 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-053 | WPS-14 | AG-08 | Verify and close: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Verify current equipment/service/test/drill evidence and reconcile navigation, communications, fire/LSA or emergency requirements to the actual operating scenario. Record applicability, discrepancies, limitations and acceptance authority for: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Document Review / Applicability Determination | R-053 | Conditional | International tow/offshore operation | Equipment list + calibration/service records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-052 | Finish-to-Start | A-R-054 | [5 empty] | Open | Major | To Be Determined | D-R-053 | AC-R-053 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Equipment list + calibration/service records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Navigation / Communications | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-053 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-054 | WPS-14 | AG-09 | Verify and close: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Verify current equipment/service/test/drill evidence and reconcile navigation, communications, fire/LSA or emergency requirements to the actual operating scenario. Record applicability, discrepancies, limitations and acceptance authority for: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Document Review / Applicability Determination | R-054 | Conditional | Jordan territorial waters/port | JMA/VTS requirements + agent confirmation; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-053 | Finish-to-Start | A-R-055 | [5 empty] | Open | Critical | To Be Determined | D-R-054 | AC-R-054 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | JMA/VTS requirements + agent confirmation; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Navigation / Communications | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-054 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-055 | WPS-15 | AG-10 | Verify and close: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Verify the actual crew/role matrix and current certificates, medicals, training, competence, accommodation and welfare evidence as applicable. Record applicability, discrepancies, limitations and acceptance authority for: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Document Review / Applicability Determination | R-055 | Conditional | Crew/employment/vessel status | Crew profile + accommodation inspection/certification; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-054 | Finish-to-Start | A-R-056 | [5 empty] | Open | Major | To Be Determined | D-R-055 | AC-R-055 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Crew profile + accommodation inspection/certification; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Accommodation / Welfare | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-055 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-056 | WPS-15 | AG-11 | Verify and close: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Verify the actual crew/role matrix and current certificates, medicals, training, competence, accommodation and welfare evidence as applicable. Record applicability, discrepancies, limitations and acceptance authority for: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Document Review / Applicability Determination | R-056 | Conditional | Crew onboard + Jordan entry | Health/galley/water evidence; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-055 | Finish-to-Start | A-R-057 | [5 empty] | Open | Major | To Be Determined | D-R-056 | AC-R-056 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Health/galley/water evidence; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Food / Potable Water | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-056 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-057 | WPS-15 | AG-12 | Verify and close: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Verify the actual crew/role matrix and current certificates, medicals, training, competence, accommodation and welfare evidence as applicable. Record applicability, discrepancies, limitations and acceptance authority for: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Document Review / Applicability Determination | R-057 | Conditional | Crew roster and voyage | Crew certification matrix; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-056 | Finish-to-Start | A-R-058 | [5 empty] | Open | Critical | To Be Determined | D-R-057 | AC-R-057 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Crew certification matrix; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Manning / STCW | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-057 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-058 | WPS-15 | AG-13 | Verify and close: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Verify the actual crew/role matrix and current certificates, medicals, training, competence, accommodation and welfare evidence as applicable. Record applicability, discrepancies, limitations and acceptance authority for: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Document Review / Applicability Determination | R-058 | Conditional | Roles and equipment used | Competence matrix + training records; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-057 | Finish-to-Start | A-R-059 | [5 empty] | Open | Major | To Be Determined | D-R-058 | AC-R-058 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Competence matrix + training records; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Competence / Training | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-058 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-059 | WPS-13 | AG-14 | Verify and close: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Verify the named system/equipment using controlled drawings, tests, calibration, PMS/OEM records and survey status; record outstanding restrictions. Record applicability, discrepancies, limitations and acceptance authority for: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Document Review / Applicability Determination | R-059 | Conditional | Equipment/system criticality | PMS matrix + OEM manuals + records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-058 | Finish-to-Start | A-R-060 | [5 empty] | Open | Critical | To Be Determined | D-R-059 | AC-R-059 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | PMS matrix + OEM manuals + records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Maintenance / PMS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-059 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-060 | WPS-13 | AG-15 | Verify and close: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Verify the named system/equipment using controlled drawings, tests, calibration, PMS/OEM records and survey status; record outstanding restrictions. Record applicability, discrepancies, limitations and acceptance authority for: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Document Review / Applicability Determination | R-060 | Conditional | Equipment criticality | Certificates, test reports, calibration records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-059 | Finish-to-Start | A-R-061 | [5 empty] | Open | Critical | To Be Determined | D-R-060 | AC-R-060 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Certificates, test reports, calibration records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Maintenance / PMS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-060 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-061 | WPS-16 | AG-01 | Verify and close: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Reconcile the current survey/examination matrix to the equipment/system register and verify completion evidence for due items. Record applicability, discrepancies, limitations and acceptance authority for: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Document Review / Applicability Determination | R-061 | Conditional | Class/statutory/IMCA scope | Survey matrix + records; survey/examination matrix by equipment/system, due date, completion date, certificate/report, findings and restrictions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-060 | Finish-to-Start | A-R-062 | [5 empty] | Open | Critical | To Be Determined | D-R-061 | AC-R-061 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Survey matrix + records; survey/examination matrix by equipment/system, due date, completion date, certificate/report, findings and restrictions. | Survey / Inspection | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-061 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-062 | WPS-16 | AG-02 | Verify and close: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Trace the required source document/evidence from owner to controlled repository; verify revision/date/validity and link it to the requirement. Record applicability, discrepancies, limitations and acceptance authority for: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Document Review / Applicability Determination | R-062 | Conditional | Readiness evidence | Controlled document register; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-061 | Finish-to-Start | A-R-063 | [5 empty] | Open | Major | To Be Determined | D-R-062 | AC-R-062 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Controlled document register; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Documentation | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-062 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-063 | WPS-16 | AG-03 | Verify and close: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Document Review / Applicability Determination | R-063 | Confirmed in principle | Foreign vessel/barge in Jordanian waters | Agent/JMA entry requirements; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-062 | Finish-to-Start | A-R-064 | [5 empty] | Open | Critical | To Be Determined | D-R-063 | AC-R-063 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Agent/JMA entry requirements; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Entry / Port | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-063 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-064 | WPS-16 | AG-04 | Verify and close: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Document Review / Applicability Determination | R-064 | Confirmed in principle | Foreign vessel in Jordanian waters/port | PSC readiness package; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-063 | Finish-to-Start | A-R-065 | [5 empty] | Open | Critical | To Be Determined | D-R-064 | AC-R-064 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | PSC readiness package; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan PSC | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-064 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-065 | WPS-16 | AG-05 | Verify and close: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Document Review / Applicability Determination | R-065 | Conditional | Activity/port/site | JMA survey requirements + reports; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-064 | Finish-to-Start | A-R-066 | [5 empty] | Open | Major | To Be Determined | D-R-065 | AC-R-065 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | JMA survey requirements + reports; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Marine Surveys | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-065 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-066 | WPS-16 | AG-06 | Verify and close: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Document Review / Applicability Determination | R-066 | Conditional | Arrival/port call | Health clearance evidence; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-065 | Finish-to-Start | A-R-067 | [5 empty] | Open | Major | To Be Determined | D-R-066 | AC-R-066 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Health clearance evidence; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Health | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-066 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-067 | WPS-16 | AG-07 | Verify and close: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Document Review / Applicability Determination | R-067 | Conditional | Port call and logistics | Agent/service approvals; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-066 | Finish-to-Start | A-R-068 | [5 empty] | Open | Major | To Be Determined | D-R-067 | AC-R-067 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Agent/service approvals; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Agencies / Services | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-067 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-068 | WPS-16 | AG-08 | Verify and close: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Document Review / Applicability Determination | R-068 | Conditional | Ship/facility/port security scope | Security applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-067 | Finish-to-Start | A-R-069 | [5 empty] | Open | Major | To Be Determined | D-R-068 | AC-R-068 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Security applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan ISPS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-068 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-069 | WPS-16 | AG-09 | Verify and close: Determine ISM applicability and required interface; do not assume applicability. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine ISM applicability and required interface; do not assume applicability. | Document Review / Applicability Determination | R-069 | Conditional | Flag/statutory status + operation | ISM applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-068 | Finish-to-Start | A-R-070 | [5 empty] | Open | Major | To Be Determined | D-R-069 | AC-R-069 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISM applicability and required interface; do not assume applicability. | ISM applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan ISM | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-069 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-070 | WPS-16 | AG-10 | Verify and close: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Document Review / Applicability Determination | R-070 | Conditional | Statutory certification scope | Certificates + JMA recognition; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-069 | Finish-to-Start | A-R-071 | [5 empty] | Open | Major | To Be Determined | D-R-070 | AC-R-070 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Certificates + JMA recognition; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Load Line / Tonnage | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-070 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-071 | WPS-09 | AG-11 | Verify and close: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Document Review / Applicability Determination | R-071 | Conditional | Ballast operations + statutory scope | BWM certificate/records where applicable; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-070 | Finish-to-Start | A-R-072 | [5 empty] | Open | Major | To Be Determined | D-R-071 | AC-R-071 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | BWM certificate/records where applicable; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Ballast Water | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-071 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-072 | WPS-14 | AG-12 | Verify and close: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Verify current equipment/service/test/drill evidence and reconcile navigation, communications, fire/LSA or emergency requirements to the actual operating scenario. Record applicability, discrepancies, limitations and acceptance authority for: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Document Review / Applicability Determination | R-072 | Conditional | Statutory scope | Certificates/test records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-071 | Finish-to-Start | A-R-073 | [5 empty] | Open | Major | To Be Determined | D-R-072 | AC-R-072 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Certificates/test records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Jordan Fire / FSS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-072 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-073 | WPS-14 | AG-13 | Verify and close: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Verify current equipment/service/test/drill evidence and reconcile navigation, communications, fire/LSA or emergency requirements to the actual operating scenario. Record applicability, discrepancies, limitations and acceptance authority for: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Document Review / Applicability Determination | R-073 | Conditional | Port entry/movement | Pilot/tug/VTS arrangements; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-072 | Finish-to-Start | A-R-074 | [5 empty] | Open | Critical | To Be Determined | D-R-073 | AC-R-073 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Pilot/tug/VTS arrangements; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Jordan Safe Navigation | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-073 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-074 | WPS-16 | AG-14 | Verify and close: Establish casualty/incident reporting requirements for events in Jordanian waters. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Establish casualty/incident reporting requirements for events in Jordanian waters. | Document Review / Applicability Determination | R-074 | Conditional | Incident/casualty | Reporting procedure/contact matrix; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-073 | Finish-to-Start | A-R-075 | [5 empty] | Open | Major | To Be Determined | D-R-074 | AC-R-074 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish casualty/incident reporting requirements for events in Jordanian waters. | Reporting procedure/contact matrix; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Jordan Casualty Reporting | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-074 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-075 | WPS-09 | AG-15 | Verify and close: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Verify the actual Aqaba/site/environmental basis from authorized data and permits; reconcile boundaries, controls, waste/pollution and emergency arrangements. Record applicability, discrepancies, limitations and acceptance authority for: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Document Review / Applicability Determination | R-075 | Conditional | Actual coordinates/activity | Official boundary + permit/control assessment; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-074 | Finish-to-Start | A-R-076 | [5 empty] | Open | Critical | To Be Determined | D-R-075 | AC-R-075 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Official boundary + permit/control assessment; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Aqaba Marine Reserve | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-075 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-076 | WPS-09 | AG-01 | Verify and close: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Verify the actual Aqaba/site/environmental basis from authorized data and permits; reconcile boundaries, controls, waste/pollution and emergency arrangements. Record applicability, discrepancies, limitations and acceptance authority for: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Document Review / Applicability Determination | R-076 | Conditional | Actual worksite/activity | ASEZA environmental requirements/permits; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-075 | Finish-to-Start | A-R-077 | [5 empty] | Open | Critical | To Be Determined | D-R-076 | AC-R-076 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | ASEZA environmental requirements/permits; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Aqaba Environment | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-076 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-077 | WPS-09 | AG-02 | Verify and close: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Verify the actual Aqaba/site/environmental basis from authorized data and permits; reconcile boundaries, controls, waste/pollution and emergency arrangements. Record applicability, discrepancies, limitations and acceptance authority for: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Document Review / Applicability Determination | R-077 | Conditional | Vessel/activity/waste stream | Garbage/oil/sewage/waste records; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-076 | Finish-to-Start | A-R-078 | [5 empty] | Open | Critical | To Be Determined | D-R-077 | AC-R-077 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Garbage/oil/sewage/waste records; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Pollution / Waste | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-077 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-078 | WPS-09 | AG-03 | Verify and close: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Verify the actual Aqaba/site/environmental basis from authorized data and permits; reconcile boundaries, controls, waste/pollution and emergency arrangements. Record applicability, discrepancies, limitations and acceptance authority for: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Document Review / Applicability Determination | R-078 | Conditional | Fuel/chemicals/marine operations | SOPEP/SMPEP as applicable + project spill plan; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-077 | Finish-to-Start | A-R-079 | [5 empty] | Open | Critical | To Be Determined | D-R-078 | AC-R-078 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | SOPEP/SMPEP as applicable + project spill plan; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Spill Response | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-078 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-079 | WPS-16 | AG-04 | Verify and close: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Obtain written confirmation from the competent Jordanian authority or authorized agent, reconcile it to PMS-11 status, and record permits/certificates/conditions. Record applicability, discrepancies, limitations and acceptance authority for: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Document Review / Applicability Determination | R-079 | Conditional | International arrival | Agent checklist + customs/immigration clearance; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-078 | Finish-to-Start | A-R-080 | [5 empty] | Open | Major | To Be Determined | D-R-079 | AC-R-079 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Agent checklist + customs/immigration clearance; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Customs / Immigration | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-079 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-080 | WPS-01 | AG-05 | Verify and close: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Cross-check the requirement against the confirmed DNV/class basis and record whether it is incorporated, conditional or not applicable. Record applicability, discrepancies, limitations and acceptance authority for: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Document Review / Applicability Determination | R-080 | Conditional | Governing DNV class basis | IACS-to-DNV applicability matrix; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-079 | Finish-to-Start | A-R-081 | [5 empty] | Open | Major | To Be Determined | D-R-080 | AC-R-080 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | IACS-to-DNV applicability matrix; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | IACS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-080 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-081 | WPS-02 | AG-06 | Verify and close: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Cross-check the requirement against the confirmed DNV/class basis and record whether it is incorporated, conditional or not applicable. Record applicability, discrepancies, limitations and acceptance authority for: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Document Review / Applicability Determination | R-081 | Conditional | Unit type/class basis | Applicability decision; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-080 | Finish-to-Start | A-R-082 | [5 empty] | Open | Major | To Be Determined | D-R-081 | AC-R-081 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Applicability decision; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | IACS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-081 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-082 | WPS-01 | AG-07 | Verify and close: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Cross-check the requirement against the confirmed DNV/class basis and record whether it is incorporated, conditional or not applicable. Record applicability, discrepancies, limitations and acceptance authority for: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Document Review / Applicability Determination | R-082 | Confirmed methodology | DNV incorporation/ratification | Rule cross-reference; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-081 | Finish-to-Start | A-R-083 | [5 empty] | Open | Major | To Be Determined | D-R-082 | AC-R-082 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Rule cross-reference; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | IACS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-082 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-083 | WPS-01 | AG-08 | Verify and close: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Identify the project/contractual standard actually required, confirm revision/applicability and verify the project evidence. Record applicability, discrepancies, limitations and acceptance authority for: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Document Review / Applicability Determination | R-083 | Conditional | Client/project scope | Contract/specification; project/contract specification, applicable standard list/revision, required clause/section, applicability decision and client/MWS acceptance. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-082 | Finish-to-Start | A-R-084 | [5 empty] | Open | Major | To Be Determined | D-R-083 | AC-R-083 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Contract/specification; project/contract specification, applicable standard list/revision, required clause/section, applicability decision and client/MWS acceptance. | Industry / Project | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-083 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-084 | WPS-13 | AG-09 | Verify and close: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Obtain OEM-controlled technical basis and reconcile serial/configuration, limits, maintenance and test requirements to installed equipment. Record applicability, discrepancies, limitations and acceptance authority for: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Document Review / Applicability Determination | R-084 | Conditional | Equipment identity | OEM manuals/records; OEM manual, serial/configuration confirmation, mandatory limits, maintenance/test instructions and technical bulletins. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-083 | Finish-to-Start | A-R-085 | [5 empty] | Open | Major | To Be Determined | D-R-084 | AC-R-084 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | OEM manuals/records; OEM manual, serial/configuration confirmation, mandatory limits, maintenance/test instructions and technical bulletins. | OEM | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-084 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-085 | WPS-11 | AG-10 | Verify and close: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Obtain the controlled contractual/MWS requirement set, identify hold points and approval roles, and map each to an acceptance record. Record applicability, discrepancies, limitations and acceptance authority for: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Document Review / Applicability Determination | R-085 | Conditional | Contract/MWS appointment | Controlled client/MWS requirement register; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-084 | Finish-to-Start | A-R-086 | [5 empty] | Open | Major | To Be Determined | D-R-085 | AC-R-085 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Controlled client/MWS requirement register; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Client / MWS | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-085 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-086 | WPS-09 | AG-11 | Verify and close: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Verify the actual Aqaba/site/environmental basis from authorized data and permits; reconcile boundaries, controls, waste/pollution and emergency arrangements. Record applicability, discrepancies, limitations and acceptance authority for: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Document Review / Applicability Determination | R-086 | Confirmed methodology | Actual site data available | Verified site data package; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-085 | Finish-to-Start | A-R-087 | [5 empty] | Open | Critical | To Be Determined | D-R-086 | AC-R-086 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Verified site data package; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Site Engineering | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-086 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-087 | WPS-16 | AG-12 | Verify and close: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Trace the required source document/evidence from owner to controlled repository; verify revision/date/validity and link it to the requirement. Record applicability, discrepancies, limitations and acceptance authority for: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Document Review / Applicability Determination | R-087 | Confirmed methodology | Departmental verification | Evidence request/status record; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-086 | Finish-to-Start | A-R-088 | [5 empty] | Open | Critical | To Be Determined | D-R-087 | AC-R-087 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Evidence request/status record; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Evidence Control | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-087 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-088 | WPS-02 | AG-13 | Verify and close: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Obtain and reconcile the current Egyptian Flag/EAMS statutory basis, certificates, delegation and international-operation requirements to the actual PMS-11 scenario. Record applicability, discrepancies, limitations and acceptance authority for: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Document Review / Applicability Determination | R-088 | Conditional | Egyptian Flag status and intended Egypt-to-Jordan international operation | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; certificate validity, Flag delegation/RO basis, exemptions/dispensations, survey status, manning/safety/pollution certificates and foreign-port requirements. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-087 | Finish-to-Start | A-R-089 | [5 empty] | Open | Critical | To Be Determined | D-R-088 | AC-R-088 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; certificate validity, Flag delegation/RO basis, exemptions/dispensations, survey status, manning/safety/pollution certificates and foreign-port requirements. | Egyptian Flag / Statutory Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-088 | One activity per validated rule; do not close without evidence and authority disposition.
A-R-089 | WPS-02 | AG-14 | Verify and close: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Review approved structural/stability documentation and current condition/survey evidence; reconcile the technical basis to PMS-11 and intended operating/tow conditions. Record applicability, discrepancies, limitations and acceptance authority for: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Document Review / Applicability Determination | R-089 | Conditional | Current class scope, vessel condition, tow condition and offshore configuration | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; approved GA/structural drawings, stability booklet, loading manual, load-line evidence where applicable, thickness/condition records and operating restrictions. | Rule/WPS owner to be assigned | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / JMA / ASEZA / Client / MWS / OEM / competent person | A-R-088 | Finish-to-Start | GATE-8 | [5 empty] | Open | Critical | To Be Determined | D-R-089 | AC-R-089 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; approved GA/structural drawings, stability booklet, loading manual, load-line evidence where applicable, thickness/condition records and operating restrictions. | Hull / Structural / Stability Basis | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable |  | ACT-089 | One activity per validated rule; do not close without evidence and authority disposition.
A-S-17-01 | WPS-17 | SG-17 | Obtain formal DNV suspension notice, class status and violation summary | Execute and close the supplemental operational control: Obtain formal DNV suspension notice, class status and violation summary. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-17-01 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Class Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-01,WPS-02 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-17-01 | AC-S-17-01 | G-S-17-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-17-01 | Supplemental control SC-17-01; no canonical Rule is claimed.
A-S-17-02 | WPS-17 | SG-17 | Agree DNV reinstatement survey scope and attendance plan | Execute and close the supplemental operational control: Agree DNV reinstatement survey scope and attendance plan. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-17-02 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Class Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-17-01 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-17-02 | AC-S-17-02 | G-S-17-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-17-02 | Supplemental control SC-17-02; no canonical Rule is claimed.
A-S-17-03 | WPS-17 | SG-17 | Complete hull, machinery, electrical and statutory condition assessment | Execute and close the supplemental operational control: Complete hull, machinery, electrical and statutory condition assessment. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-17-03 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Technical Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-17-02 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-17-03 | AC-S-17-03 | G-S-17-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-17-03 | Supplemental control SC-17-03; no canonical Rule is claimed.
A-S-17-04 | WPS-17 | SG-17 | Execute repairs, tests and survey closeout | Execute and close the supplemental operational control: Execute repairs, tests and survey closeout. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-17-04 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Project Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-17-03 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-17-04 | AC-S-17-04 | G-S-17-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-17-04 | Supplemental control SC-17-04; no canonical Rule is claimed.
A-S-17-05 | WPS-17 | SG-17 | Receive formal DNV reinstatement decision and updated class status | Execute and close the supplemental operational control: Receive formal DNV reinstatement decision and updated class status. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-17-05 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Class Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-17-04 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-17-05 | AC-S-17-05 | G-S-17-05 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-17-05 | Supplemental control SC-17-05; no canonical Rule is claimed.
A-S-18-01 | WPS-18 | SG-18 | Issue neutral request for information to candidate IACS societies | Execute and close the supplemental operational control: Issue neutral request for information to candidate IACS societies. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-18-01 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Class Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-01,WPS-02 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-18-01 | AC-S-18-01 | G-S-18-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-18-01 | Supplemental control SC-18-01; no canonical Rule is claimed.
A-S-18-02 | WPS-18 | SG-18 | Prepare transfer technical dossier and disclosure register | Execute and close the supplemental operational control: Prepare transfer technical dossier and disclosure register. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-18-02 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Class Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-18-01 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-18-02 | AC-S-18-02 | G-S-18-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-18-02 | Supplemental control SC-18-02; no canonical Rule is claimed.
A-S-18-03 | WPS-18 | SG-18 | Perform comparative gap, cost and schedule assessment | Execute and close the supplemental operational control: Perform comparative gap, cost and schedule assessment. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-18-03 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Project Controls Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-18-02,WPS-17-02 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-18-03 | AC-S-18-03 | G-S-18-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-18-03 | Supplemental control SC-18-03; no canonical Rule is claimed.
A-S-18-04 | WPS-18 | SG-18 | Record management and authority path decision | Execute and close the supplemental operational control: Record management and authority path decision. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-18-04 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Project Director | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-18-03 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-18-04 | AC-S-18-04 | G-S-18-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-18-04 | Supplemental control SC-18-04; no canonical Rule is claimed.
A-S-18-05 | WPS-18 | SG-18 | If selected, complete transfer surveys and obtain certificate | Execute and close the supplemental operational control: If selected, complete transfer surveys and obtain certificate. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-18-05 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Class Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-18-04 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-18-05 | AC-S-18-05 | G-S-18-05 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-18-05 | Supplemental control SC-18-05; no canonical Rule is claimed.
A-S-19-01 | WPS-19 | SG-19 | Confirm helideck status, intended aircraft and authority jurisdiction | Execute and close the supplemental operational control: Confirm helideck status, intended aircraft and authority jurisdiction. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-19-01 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Aviation Coordinator | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-14,WPS-16 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-19-01 | AC-S-19-01 | G-S-19-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-19-01 | Supplemental control SC-19-01; no canonical Rule is claimed.
A-S-19-02 | WPS-19 | SG-19 | Review helideck structural, obstacle, marking, lighting and access basis | Execute and close the supplemental operational control: Review helideck structural, obstacle, marking, lighting and access basis. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-19-02 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Aviation Coordinator | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-19-01 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-19-02 | AC-S-19-02 | G-S-19-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-19-02 | Supplemental control SC-19-02; no canonical Rule is claimed.
A-S-19-03 | WPS-19 | SG-19 | Review flight operations and marine-aviation interface manual | Execute and close the supplemental operational control: Review flight operations and marine-aviation interface manual. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-19-03 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Aviation Coordinator | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-19-01 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-19-03 | AC-S-19-03 | G-S-19-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-19-03 | Supplemental control SC-19-03; no canonical Rule is claimed.
A-S-19-04 | WPS-19 | SG-19 | Verify helideck firefighting, rescue, PPE and trained team | Execute and close the supplemental operational control: Verify helideck firefighting, rescue, PPE and trained team. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-19-04 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | HSE Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-19-02,WPS-14 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-19-04 | AC-S-19-04 | G-S-19-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-19-04 | Supplemental control SC-19-04; no canonical Rule is claimed.
A-S-19-05 | WPS-19 | SG-19 | Secure required operational permissions and acceptance evidence | Execute and close the supplemental operational control: Secure required operational permissions and acceptance evidence. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-19-05 | Conditional | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Aviation Coordinator | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-19-02,WPS-19-03,WPS-19-04 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-19-05 | AC-S-19-05 | G-S-19-05 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-19-05 | Supplemental control SC-19-05; no canonical Rule is claimed.
A-S-20-01 | WPS-20 | SG-20 | Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Execute and close the supplemental operational control: Determine applicable fuel sulphur and emissions requirements for route and Aqaba. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-20-01 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Environmental Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-09,WPS-16 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-20-01 | AC-S-20-01 | G-S-20-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-20-01 | Supplemental control SC-20-01; no canonical Rule is claimed.
A-S-20-02 | WPS-20 | SG-20 | Verify BDN, fuel samples, changeover procedures and consumption plan | Execute and close the supplemental operational control: Verify BDN, fuel samples, changeover procedures and consumption plan. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-20-02 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Chief Engineer | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-20-01 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-20-02 | AC-S-20-02 | G-S-20-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-20-02 | Supplemental control SC-20-02; no canonical Rule is claimed.
A-S-20-03 | WPS-20 | SG-20 | Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Execute and close the supplemental operational control: Verify sludge, oily water, sewage and garbage capacity/disposal arrangements. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-20-03 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Chief Engineer | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-09,WPS-13,WPS-20-01 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-20-03 | AC-S-20-03 | G-S-20-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-20-03 | Supplemental control SC-20-03; no canonical Rule is claimed.
A-S-20-04 | WPS-20 | SG-20 | Commission potable-water and RO systems and obtain laboratory results | Execute and close the supplemental operational control: Commission potable-water and RO systems and obtain laboratory results. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-20-04 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Chief Engineer | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-13 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-20-04 | AC-S-20-04 | G-S-20-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-20-04 | Supplemental control SC-20-04; no canonical Rule is claimed.
A-S-20-05 | WPS-20 | SG-20 | Close spill prevention and waste contractor interfaces | Execute and close the supplemental operational control: Close spill prevention and waste contractor interfaces. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-20-05 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Environmental Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-20-02,WPS-20-03 | Finish-to-Start | [6 empty] | Not Started | Major | Yes | D-S-20-05 | AC-S-20-05 | G-S-20-05 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-20-05 | Supplemental control SC-20-05; no canonical Rule is claimed.
A-S-21-01 | WPS-21 | SG-21 | Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Execute and close the supplemental operational control: Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-21-01 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Maintenance Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-13 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-21-01 | AC-S-21-01 | G-S-21-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-21-01 | Supplemental control SC-21-01; no canonical Rule is claimed.
A-S-21-02 | WPS-21 | SG-21 | Generate critical defect and overdue-maintenance backlog | Execute and close the supplemental operational control: Generate critical defect and overdue-maintenance backlog. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-21-02 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Maintenance Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-21-01 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-21-02 | AC-S-21-02 | G-S-21-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-21-02 | Supplemental control SC-21-02; no canonical Rule is claimed.
A-S-21-03 | WPS-21 | SG-21 | Map critical spares/materials to equipment and physically verify stock | Execute and close the supplemental operational control: Map critical spares/materials to equipment and physically verify stock. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-21-03 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Stores Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-21-01 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-21-03 | AC-S-21-03 | G-S-21-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-21-03 | Supplemental control SC-21-03; no canonical Rule is claimed.
A-S-21-04 | WPS-21 | SG-21 | Issue procurement plan for shortages and long-lead items | Execute and close the supplemental operational control: Issue procurement plan for shortages and long-lead items. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-21-04 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Procurement Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-21-02,WPS-21-03 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-21-04 | AC-S-21-04 | G-S-21-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-21-04 | Supplemental control SC-21-04; no canonical Rule is claimed.
A-S-21-05 | WPS-21 | SG-21 | Back up CMMS database and approve mobilization maintenance baseline | Execute and close the supplemental operational control: Back up CMMS database and approve mobilization maintenance baseline. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-21-05 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Maintenance Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-21-02,WPS-21-03,WPS-21-04 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-21-05 | AC-S-21-05 | G-S-21-05 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-21-05 | Supplemental control SC-21-05; no canonical Rule is claimed.
A-S-22-01 | WPS-22 | SG-22 | Develop approved anchor pattern, deployment sequence and exclusion controls | Execute and close the supplemental operational control: Develop approved anchor pattern, deployment sequence and exclusion controls. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-22-01 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Marine Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-08,WPS-09 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-22-01 | AC-S-22-01 | G-S-22-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-22-01 | Supplemental control SC-22-01; no canonical Rule is claimed.
A-S-22-02 | WPS-22 | SG-22 | Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Execute and close the supplemental operational control: Verify control-room/APMS/DGPS/gyro displays, alarms and calibration. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-22-02 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Survey Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-14,WPS-22-01 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-22-02 | AC-S-22-02 | G-S-22-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-22-02 | Supplemental control SC-22-02; no canonical Rule is claimed.
A-S-22-03 | WPS-22 | SG-22 | Test winches, brakes, controls, communications and emergency release | Execute and close the supplemental operational control: Test winches, brakes, controls, communications and emergency release. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-22-03 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Marine Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-08,WPS-13,WPS-22-02 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-22-03 | AC-S-22-03 | G-S-22-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-22-03 | Supplemental control SC-22-03; no canonical Rule is claimed.
A-S-22-04 | WPS-22 | SG-22 | Approve tug assignment, command hierarchy and standard communications | Execute and close the supplemental operational control: Approve tug assignment, command hierarchy and standard communications. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-22-04 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Marine Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-22-01,WPS-22-03 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-22-04 | AC-S-22-04 | G-S-22-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-22-04 | Supplemental control SC-22-04; no canonical Rule is claimed.
A-S-22-05 | WPS-22 | SG-22 | Conduct anchor-handling tabletop and operational drill | Execute and close the supplemental operational control: Conduct anchor-handling tabletop and operational drill. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-22-05 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Marine Superintendent | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-22-02,WPS-22-03,WPS-22-04 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-22-05 | AC-S-22-05 | G-S-22-05 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-22-05 | Supplemental control SC-22-05; no canonical Rule is claimed.
A-S-23-01 | WPS-23 | SG-23 | Approve departmental manpower, competency and rotation matrix | Execute and close the supplemental operational control: Approve departmental manpower, competency and rotation matrix. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-23-01 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | HR Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-15 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-23-01 | AC-S-23-01 | G-S-23-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-23-01 | Supplemental control SC-23-01; no canonical Rule is claimed.
A-S-23-02 | WPS-23 | SG-23 | Verify clinic equipment, medicines, licenses and medevac interface | Execute and close the supplemental operational control: Verify clinic equipment, medicines, licenses and medevac interface. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-23-02 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Medical Coordinator | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-23-01,WPS-19-03 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-23-02 | AC-S-23-02 | G-S-23-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-23-02 | Supplemental control SC-23-02; no canonical Rule is claimed.
A-S-23-03 | WPS-23 | SG-23 | Implement fatigue, rest-hour and drug/alcohol policy controls | Execute and close the supplemental operational control: Implement fatigue, rest-hour and drug/alcohol policy controls. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-23-03 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | HSE Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-23-01 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-23-03 | AC-S-23-03 | G-S-23-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-23-03 | Supplemental control SC-23-03; no canonical Rule is claimed.
A-S-23-04 | WPS-23 | SG-23 | Complete visas, travel, repatriation and crew-change logistics | Execute and close the supplemental operational control: Complete visas, travel, repatriation and crew-change logistics. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-23-04 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | HR Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-16,WPS-23-01 | Finish-to-Start | [6 empty] | Not Started | High | No | D-S-23-04 | AC-S-23-04 | G-S-23-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-23-04 | Supplemental control SC-23-04; no canonical Rule is claimed.
A-S-24-01 | WPS-24 | SG-24 | Issue integrated emergency response and shore-interface matrix | Execute and close the supplemental operational control: Issue integrated emergency response and shore-interface matrix. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-24-01 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | HSE Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-09,WPS-10,WPS-12,WPS-14,WPS-19,WPS-20,WPS-22,WPS-23 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-24-01 | AC-S-24-01 | G-S-24-01 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-24-01 | Supplemental control SC-24-01; no canonical Rule is claimed.
A-S-24-02 | WPS-24 | SG-24 | Define scenario drill programme and measurable acceptance criteria | Execute and close the supplemental operational control: Define scenario drill programme and measurable acceptance criteria. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-24-02 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | HSE Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-24-01 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-24-02 | AC-S-24-02 | G-S-24-02 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-24-02 | Supplemental control SC-24-02; no canonical Rule is claimed.
A-S-24-03 | WPS-24 | SG-24 | Conduct marine, aviation, diving, pollution and medevac interface drills | Execute and close the supplemental operational control: Conduct marine, aviation, diving, pollution and medevac interface drills. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-24-03 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Project Manager | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-24-02,WPS-19-04,WPS-22-05,WPS-23-02 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-24-03 | AC-S-24-03 | G-S-24-03 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-24-03 | Supplemental control SC-24-03; no canonical Rule is claimed.
A-S-24-04 | WPS-24 | SG-24 | Close drill findings and issue final operational readiness recommendation | Execute and close the supplemental operational control: Close drill findings and issue final operational readiness recommendation. Maintain applicability status, controlled inputs, verification results, evidence, acceptance decision and limitations; do not convert unsupported assumptions into mandatory criteria. | Supplemental Operational Control | SC-24-04 | Confirmed | Current approved execution basis / applicable authority decision | Controlled source basis; approved procedure/design; equipment/system records; authority requirements as applicable | Project Director | Relevant competent authority / Project Director as applicable | Technical / HSE / QAQC / Marine / Regulatory as applicable | WPS-24-03,WPS-17-05,WPS-18-04,WPS-20-05,WPS-21-05 | Finish-to-Start | [6 empty] | Not Started | Critical | Yes | D-S-24-04 | AC-S-24-04 | G-S-24-04 | Yes | Document review / inspection / test / drill / authority review as applicable | Relevant competent authority / Project Director as applicable |  | WPS-24-04 | Supplemental control SC-24-04; no canonical Rule is claimed.

## Deliverables
Deliverable ID | WPS ID | Activity ID | Deliverable Name | Deliverable Type | Description | Source Rule IDs | Required Format | Prepared By | Reviewed By | Approved By | Required Before | Acceptance Criteria ID | Evidence Location | Revision | Date | Status | Rejected Reason | Superseded By | Notes
D-R-001 | WPS-01 | A-R-001 | Controlled verification / decision record for Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-001 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-001 | E-R-001 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-002 | WPS-01 | A-R-002 | Controlled verification / decision record for Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-002 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-002 | E-R-002 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-003 | WPS-02 | A-R-003 | Controlled verification / decision record for Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-003 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-003 | E-R-003 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-004 | WPS-01 | A-R-004 | Controlled verification / decision record for Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-004 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-004 | E-R-004 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-005 | WPS-01 | A-R-005 | Controlled verification / decision record for Identify approved drawings and documents forming the class technical basis. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-005 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-005 | E-R-005 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-006 | WPS-02 | A-R-006 | Controlled verification / decision record for Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-006 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-006 | E-R-006 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-007 | WPS-02 | A-R-007 | Controlled verification / decision record for Assess effects of modifications, conversion, change of service or operating area on class requirements. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-007 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-007 | E-R-007 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-008 | WPS-01 | A-R-008 | Controlled verification / decision record for Establish the approved operating limits and service scope relevant to Jordan operations. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-008 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-008 | E-R-008 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-009 | WPS-03 | A-R-009 | Controlled verification / decision record for Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-009 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-009 | E-R-009 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-010 | WPS-03 | A-R-010 | Controlled verification / decision record for Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-010 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-010 | E-R-010 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-011 | WPS-03 | A-R-011 | Controlled verification / decision record for Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-011 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-011 | E-R-011 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-012 | WPS-04 | A-R-012 | Controlled verification / decision record for Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-012 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-012 | E-R-012 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-013 | WPS-04 | A-R-013 | Controlled verification / decision record for Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-013 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-013 | E-R-013 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-014 | WPS-05 | A-R-014 | Controlled verification / decision record for Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-014 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-014 | E-R-014 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-015 | WPS-05 | A-R-015 | Controlled verification / decision record for Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-015 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-015 | E-R-015 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-016 | WPS-03 | A-R-016 | Controlled verification / decision record for Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-016 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-016 | E-R-016 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-017 | WPS-03 | A-R-017 | Controlled verification / decision record for Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-017 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-017 | E-R-017 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-018 | WPS-03 | A-R-018 | Controlled verification / decision record for Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-018 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-018 | E-R-018 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-019 | WPS-06 | A-R-019 | Controlled verification / decision record for Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-019 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-019 | E-R-019 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-020 | WPS-06 | A-R-020 | Controlled verification / decision record for Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-020 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-020 | E-R-020 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-021 | WPS-06 | A-R-021 | Controlled verification / decision record for Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-021 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-021 | E-R-021 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-022 | WPS-06 | A-R-022 | Controlled verification / decision record for Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-022 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-022 | E-R-022 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-023 | WPS-07 | A-R-023 | Controlled verification / decision record for Verify welding stations, coating station and related QA/QC controls. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-023 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-023 | E-R-023 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-024 | WPS-07 | A-R-024 | Controlled verification / decision record for Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-024 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-024 | E-R-024 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-025 | WPS-07 | A-R-025 | Controlled verification / decision record for Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-025 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-025 | E-R-025 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-026 | WPS-07 | A-R-026 | Controlled verification / decision record for Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-026 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-026 | E-R-026 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-027 | WPS-07 | A-R-027 | Controlled verification / decision record for Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-027 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-027 | E-R-027 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-028 | WPS-07 | A-R-028 | Controlled verification / decision record for Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-028 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-028 | E-R-028 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-029 | WPS-08 | A-R-029 | Controlled verification / decision record for Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-029 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-029 | E-R-029 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-030 | WPS-08 | A-R-030 | Controlled verification / decision record for Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-030 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-030 | E-R-030 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-031 | WPS-08 | A-R-031 | Controlled verification / decision record for Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-031 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-031 | E-R-031 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-032 | WPS-09 | A-R-032 | Controlled verification / decision record for Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-032 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-032 | E-R-032 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-033 | WPS-09 | A-R-033 | Controlled verification / decision record for Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-033 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-033 | E-R-033 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-034 | WPS-09 | A-R-034 | Controlled verification / decision record for Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-034 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-034 | E-R-034 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-035 | WPS-11 | A-R-035 | Controlled verification / decision record for Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-035 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-035 | E-R-035 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-036 | WPS-08 | A-R-036 | Controlled verification / decision record for Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-036 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-036 | E-R-036 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-037 | WPS-10 | A-R-037 | Controlled verification / decision record for Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-037 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-037 | E-R-037 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-038 | WPS-10 | A-R-038 | Controlled verification / decision record for Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-038 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-038 | E-R-038 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-039 | WPS-10 | A-R-039 | Controlled verification / decision record for Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-039 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-039 | E-R-039 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-040 | WPS-10 | A-R-040 | Controlled verification / decision record for Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-040 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-040 | E-R-040 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-041 | WPS-10 | A-R-041 | Controlled verification / decision record for Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-041 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-041 | E-R-041 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-042 | WPS-10 | A-R-042 | Controlled verification / decision record for Define pre-tow inspection, readiness verification and required approval/statement before departure. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-042 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-042 | E-R-042 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-043 | WPS-11 | A-R-043 | Controlled verification / decision record for Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Verification Record | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | R-043 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-043 | E-R-043 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-044 | WPS-12 | A-R-044 | Controlled verification / decision record for Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Verification Record | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | R-044 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-044 | E-R-044 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-045 | WPS-12 | A-R-045 | Controlled verification / decision record for Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Verification Record | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | R-045 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-045 | E-R-045 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-046 | WPS-12 | A-R-046 | Controlled verification / decision record for Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Verification Record | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | R-046 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-046 | E-R-046 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-047 | WPS-12 | A-R-047 | Controlled verification / decision record for Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Verification Record | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | R-047 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-047 | E-R-047 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-048 | WPS-12 | A-R-048 | Controlled verification / decision record for Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Verification Record | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | R-048 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-048 | E-R-048 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-049 | WPS-13 | A-R-049 | Controlled verification / decision record for Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-049 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-049 | E-R-049 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-050 | WPS-13 | A-R-050 | Controlled verification / decision record for Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-050 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-050 | E-R-050 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-051 | WPS-14 | A-R-051 | Controlled verification / decision record for Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-051 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-051 | E-R-051 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-052 | WPS-14 | A-R-052 | Controlled verification / decision record for Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-052 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-052 | E-R-052 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-053 | WPS-14 | A-R-053 | Controlled verification / decision record for Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-053 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-053 | E-R-053 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-054 | WPS-14 | A-R-054 | Controlled verification / decision record for Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-054 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-054 | E-R-054 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-055 | WPS-15 | A-R-055 | Controlled verification / decision record for Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Verification Record | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | R-055 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-055 | E-R-055 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-056 | WPS-15 | A-R-056 | Controlled verification / decision record for Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Verification Record | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | R-056 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-056 | E-R-056 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-057 | WPS-15 | A-R-057 | Controlled verification / decision record for Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Verification Record | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | R-057 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-057 | E-R-057 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-058 | WPS-15 | A-R-058 | Controlled verification / decision record for Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Verification Record | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | R-058 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-058 | E-R-058 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-059 | WPS-13 | A-R-059 | Controlled verification / decision record for Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-059 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-059 | E-R-059 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-060 | WPS-13 | A-R-060 | Controlled verification / decision record for Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-060 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-060 | E-R-060 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-061 | WPS-16 | A-R-061 | Controlled verification / decision record for Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-061 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-061 | E-R-061 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-062 | WPS-16 | A-R-062 | Controlled verification / decision record for Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-062 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-062 | E-R-062 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-063 | WPS-16 | A-R-063 | Controlled verification / decision record for Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-063 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-063 | E-R-063 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-064 | WPS-16 | A-R-064 | Controlled verification / decision record for Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-064 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-064 | E-R-064 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-065 | WPS-16 | A-R-065 | Controlled verification / decision record for Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-065 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-065 | E-R-065 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-066 | WPS-16 | A-R-066 | Controlled verification / decision record for Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-066 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-066 | E-R-066 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-067 | WPS-16 | A-R-067 | Controlled verification / decision record for Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-067 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-067 | E-R-067 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-068 | WPS-16 | A-R-068 | Controlled verification / decision record for Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-068 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-068 | E-R-068 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-069 | WPS-16 | A-R-069 | Controlled verification / decision record for Determine ISM applicability and required interface; do not assume applicability. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-069 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-069 | E-R-069 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-070 | WPS-16 | A-R-070 | Controlled verification / decision record for Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-070 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-070 | E-R-070 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-071 | WPS-09 | A-R-071 | Controlled verification / decision record for Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-071 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-071 | E-R-071 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-072 | WPS-14 | A-R-072 | Controlled verification / decision record for Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-072 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-072 | E-R-072 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-073 | WPS-14 | A-R-073 | Controlled verification / decision record for Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-073 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-073 | E-R-073 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-074 | WPS-16 | A-R-074 | Controlled verification / decision record for Establish casualty/incident reporting requirements for events in Jordanian waters. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-074 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-074 | E-R-074 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-075 | WPS-09 | A-R-075 | Controlled verification / decision record for Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Verification Record | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | R-075 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-075 | E-R-075 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-076 | WPS-09 | A-R-076 | Controlled verification / decision record for Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Verification Record | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | R-076 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-076 | E-R-076 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-077 | WPS-09 | A-R-077 | Controlled verification / decision record for Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Verification Record | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | R-077 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-077 | E-R-077 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-078 | WPS-09 | A-R-078 | Controlled verification / decision record for Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Verification Record | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | R-078 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-078 | E-R-078 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-079 | WPS-16 | A-R-079 | Controlled verification / decision record for Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Verification Record | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | R-079 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-079 | E-R-079 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-080 | WPS-01 | A-R-080 | Controlled verification / decision record for Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Verification Record | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | R-080 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-080 | E-R-080 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-081 | WPS-02 | A-R-081 | Controlled verification / decision record for Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Verification Record | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | R-081 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-081 | E-R-081 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-082 | WPS-01 | A-R-082 | Controlled verification / decision record for Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Verification Record | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | R-082 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-082 | E-R-082 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-083 | WPS-01 | A-R-083 | Controlled verification / decision record for Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-083 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-083 | E-R-083 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-084 | WPS-13 | A-R-084 | Controlled verification / decision record for Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-084 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-084 | E-R-084 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-085 | WPS-11 | A-R-085 | Controlled verification / decision record for Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Verification Record | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | R-085 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-085 | E-R-085 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-086 | WPS-09 | A-R-086 | Controlled verification / decision record for Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Verification Record | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | R-086 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-086 | E-R-086 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-087 | WPS-16 | A-R-087 | Controlled verification / decision record for Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Verification Record | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | R-087 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-087 | E-R-087 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-088 | WPS-02 | A-R-088 | Controlled verification / decision record for Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Verification Record | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | R-088 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-088 | E-R-088 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-R-089 | WPS-02 | A-R-089 | Controlled verification / decision record for Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Verification Record | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | R-089 | Controlled PDF/XLSX/letter or report | Rule/WPS owner | Technical Manager / QAQC | Relevant competent authority | Applicable gate | AC-R-089 | E-R-089 | Rev0 |  | Open |  |  | Every Activity produces or updates a controlled deliverable; exact format follows the authority and source.
D-S-17-01 | WPS-17 | A-S-17-01 | Controlled closure package — Obtain formal DNV suspension notice, class status and violation summary | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Obtain formal DNV suspension notice, class status and violation summary. | SC-17-01 | Controlled PDF/XLSX/report/letter as applicable | Class Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-17-01 | E-S-17-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-17-02 | WPS-17 | A-S-17-02 | Controlled closure package — Agree DNV reinstatement survey scope and attendance plan | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Agree DNV reinstatement survey scope and attendance plan. | SC-17-02 | Controlled PDF/XLSX/report/letter as applicable | Class Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-17-02 | E-S-17-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-17-03 | WPS-17 | A-S-17-03 | Controlled closure package — Complete hull, machinery, electrical and statutory condition assessment | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Complete hull, machinery, electrical and statutory condition assessment. | SC-17-03 | Controlled PDF/XLSX/report/letter as applicable | Technical Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-17-03 | E-S-17-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-17-04 | WPS-17 | A-S-17-04 | Controlled closure package — Execute repairs, tests and survey closeout | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Execute repairs, tests and survey closeout. | SC-17-04 | Controlled PDF/XLSX/report/letter as applicable | Project Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-17-04 | E-S-17-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-17-05 | WPS-17 | A-S-17-05 | Controlled closure package — Receive formal DNV reinstatement decision and updated class status | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Receive formal DNV reinstatement decision and updated class status. | SC-17-05 | Controlled PDF/XLSX/report/letter as applicable | Class Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-17-05 | E-S-17-05 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-18-01 | WPS-18 | A-S-18-01 | Controlled closure package — Issue neutral request for information to candidate IACS societies | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Issue neutral request for information to candidate IACS societies. | SC-18-01 | Controlled PDF/XLSX/report/letter as applicable | Class Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-18-01 | E-S-18-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-18-02 | WPS-18 | A-S-18-02 | Controlled closure package — Prepare transfer technical dossier and disclosure register | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Prepare transfer technical dossier and disclosure register. | SC-18-02 | Controlled PDF/XLSX/report/letter as applicable | Class Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-18-02 | E-S-18-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-18-03 | WPS-18 | A-S-18-03 | Controlled closure package — Perform comparative gap, cost and schedule assessment | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Perform comparative gap, cost and schedule assessment. | SC-18-03 | Controlled PDF/XLSX/report/letter as applicable | Project Controls Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-18-03 | E-S-18-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-18-04 | WPS-18 | A-S-18-04 | Controlled closure package — Record management and authority path decision | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Record management and authority path decision. | SC-18-04 | Controlled PDF/XLSX/report/letter as applicable | Project Director | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-18-04 | E-S-18-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-18-05 | WPS-18 | A-S-18-05 | Controlled closure package — If selected, complete transfer surveys and obtain certificate | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for If selected, complete transfer surveys and obtain certificate. | SC-18-05 | Controlled PDF/XLSX/report/letter as applicable | Class Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-1 | AC-S-18-05 | E-S-18-05 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-19-01 | WPS-19 | A-S-19-01 | Controlled closure package — Confirm helideck status, intended aircraft and authority jurisdiction | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Confirm helideck status, intended aircraft and authority jurisdiction. | SC-19-01 | Controlled PDF/XLSX/report/letter as applicable | Aviation Coordinator | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-19-01 | E-S-19-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-19-02 | WPS-19 | A-S-19-02 | Controlled closure package — Review helideck structural, obstacle, marking, lighting and access basis | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Review helideck structural, obstacle, marking, lighting and access basis. | SC-19-02 | Controlled PDF/XLSX/report/letter as applicable | Aviation Coordinator | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-19-02 | E-S-19-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-19-03 | WPS-19 | A-S-19-03 | Controlled closure package — Review flight operations and marine-aviation interface manual | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Review flight operations and marine-aviation interface manual. | SC-19-03 | Controlled PDF/XLSX/report/letter as applicable | Aviation Coordinator | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-19-03 | E-S-19-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-19-04 | WPS-19 | A-S-19-04 | Controlled closure package — Verify helideck firefighting, rescue, PPE and trained team | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Verify helideck firefighting, rescue, PPE and trained team. | SC-19-04 | Controlled PDF/XLSX/report/letter as applicable | HSE Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-19-04 | E-S-19-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-19-05 | WPS-19 | A-S-19-05 | Controlled closure package — Secure required operational permissions and acceptance evidence | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Secure required operational permissions and acceptance evidence. | SC-19-05 | Controlled PDF/XLSX/report/letter as applicable | Aviation Coordinator | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-19-05 | E-S-19-05 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-20-01 | WPS-20 | A-S-20-01 | Controlled closure package — Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Determine applicable fuel sulphur and emissions requirements for route and Aqaba. | SC-20-01 | Controlled PDF/XLSX/report/letter as applicable | Environmental Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7/8 | AC-S-20-01 | E-S-20-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-20-02 | WPS-20 | A-S-20-02 | Controlled closure package — Verify BDN, fuel samples, changeover procedures and consumption plan | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Verify BDN, fuel samples, changeover procedures and consumption plan. | SC-20-02 | Controlled PDF/XLSX/report/letter as applicable | Chief Engineer | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7/8 | AC-S-20-02 | E-S-20-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-20-03 | WPS-20 | A-S-20-03 | Controlled closure package — Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Verify sludge, oily water, sewage and garbage capacity/disposal arrangements. | SC-20-03 | Controlled PDF/XLSX/report/letter as applicable | Chief Engineer | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7/8 | AC-S-20-03 | E-S-20-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-20-04 | WPS-20 | A-S-20-04 | Controlled closure package — Commission potable-water and RO systems and obtain laboratory results | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Commission potable-water and RO systems and obtain laboratory results. | SC-20-04 | Controlled PDF/XLSX/report/letter as applicable | Chief Engineer | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7/8 | AC-S-20-04 | E-S-20-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-20-05 | WPS-20 | A-S-20-05 | Controlled closure package — Close spill prevention and waste contractor interfaces | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Close spill prevention and waste contractor interfaces. | SC-20-05 | Controlled PDF/XLSX/report/letter as applicable | Environmental Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7/8 | AC-S-20-05 | E-S-20-05 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-21-01 | WPS-21 | A-S-21-01 | Controlled closure package — Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity. | SC-21-01 | Controlled PDF/XLSX/report/letter as applicable | Maintenance Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-21-01 | E-S-21-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-21-02 | WPS-21 | A-S-21-02 | Controlled closure package — Generate critical defect and overdue-maintenance backlog | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Generate critical defect and overdue-maintenance backlog. | SC-21-02 | Controlled PDF/XLSX/report/letter as applicable | Maintenance Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-21-02 | E-S-21-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-21-03 | WPS-21 | A-S-21-03 | Controlled closure package — Map critical spares/materials to equipment and physically verify stock | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Map critical spares/materials to equipment and physically verify stock. | SC-21-03 | Controlled PDF/XLSX/report/letter as applicable | Stores Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-21-03 | E-S-21-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-21-04 | WPS-21 | A-S-21-04 | Controlled closure package — Issue procurement plan for shortages and long-lead items | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Issue procurement plan for shortages and long-lead items. | SC-21-04 | Controlled PDF/XLSX/report/letter as applicable | Procurement Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-21-04 | E-S-21-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-21-05 | WPS-21 | A-S-21-05 | Controlled closure package — Back up CMMS database and approve mobilization maintenance baseline | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Back up CMMS database and approve mobilization maintenance baseline. | SC-21-05 | Controlled PDF/XLSX/report/letter as applicable | Maintenance Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-7 | AC-S-21-05 | E-S-21-05 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-22-01 | WPS-22 | A-S-22-01 | Controlled closure package — Develop approved anchor pattern, deployment sequence and exclusion controls | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Develop approved anchor pattern, deployment sequence and exclusion controls. | SC-22-01 | Controlled PDF/XLSX/report/letter as applicable | Marine Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-3 | AC-S-22-01 | E-S-22-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-22-02 | WPS-22 | A-S-22-02 | Controlled closure package — Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Verify control-room/APMS/DGPS/gyro displays, alarms and calibration. | SC-22-02 | Controlled PDF/XLSX/report/letter as applicable | Survey Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-3 | AC-S-22-02 | E-S-22-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-22-03 | WPS-22 | A-S-22-03 | Controlled closure package — Test winches, brakes, controls, communications and emergency release | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Test winches, brakes, controls, communications and emergency release. | SC-22-03 | Controlled PDF/XLSX/report/letter as applicable | Marine Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-3 | AC-S-22-03 | E-S-22-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-22-04 | WPS-22 | A-S-22-04 | Controlled closure package — Approve tug assignment, command hierarchy and standard communications | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Approve tug assignment, command hierarchy and standard communications. | SC-22-04 | Controlled PDF/XLSX/report/letter as applicable | Marine Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-3 | AC-S-22-04 | E-S-22-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-22-05 | WPS-22 | A-S-22-05 | Controlled closure package — Conduct anchor-handling tabletop and operational drill | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Conduct anchor-handling tabletop and operational drill. | SC-22-05 | Controlled PDF/XLSX/report/letter as applicable | Marine Superintendent | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-3 | AC-S-22-05 | E-S-22-05 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-23-01 | WPS-23 | A-S-23-01 | Controlled closure package — Approve departmental manpower, competency and rotation matrix | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Approve departmental manpower, competency and rotation matrix. | SC-23-01 | Controlled PDF/XLSX/report/letter as applicable | HR Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-4/7 | AC-S-23-01 | E-S-23-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-23-02 | WPS-23 | A-S-23-02 | Controlled closure package — Verify clinic equipment, medicines, licenses and medevac interface | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Verify clinic equipment, medicines, licenses and medevac interface. | SC-23-02 | Controlled PDF/XLSX/report/letter as applicable | Medical Coordinator | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-4/7 | AC-S-23-02 | E-S-23-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-23-03 | WPS-23 | A-S-23-03 | Controlled closure package — Implement fatigue, rest-hour and drug/alcohol policy controls | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Implement fatigue, rest-hour and drug/alcohol policy controls. | SC-23-03 | Controlled PDF/XLSX/report/letter as applicable | HSE Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-4/7 | AC-S-23-03 | E-S-23-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-23-04 | WPS-23 | A-S-23-04 | Controlled closure package — Complete visas, travel, repatriation and crew-change logistics | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Complete visas, travel, repatriation and crew-change logistics. | SC-23-04 | Controlled PDF/XLSX/report/letter as applicable | HR Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-4/7 | AC-S-23-04 | E-S-23-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-24-01 | WPS-24 | A-S-24-01 | Controlled closure package — Issue integrated emergency response and shore-interface matrix | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Issue integrated emergency response and shore-interface matrix. | SC-24-01 | Controlled PDF/XLSX/report/letter as applicable | HSE Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-8 | AC-S-24-01 | E-S-24-01 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-24-02 | WPS-24 | A-S-24-02 | Controlled closure package — Define scenario drill programme and measurable acceptance criteria | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Define scenario drill programme and measurable acceptance criteria. | SC-24-02 | Controlled PDF/XLSX/report/letter as applicable | HSE Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-8 | AC-S-24-02 | E-S-24-02 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-24-03 | WPS-24 | A-S-24-03 | Controlled closure package — Conduct marine, aviation, diving, pollution and medevac interface drills | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Conduct marine, aviation, diving, pollution and medevac interface drills. | SC-24-03 | Controlled PDF/XLSX/report/letter as applicable | Project Manager | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-8 | AC-S-24-03 | E-S-24-03 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.
D-S-24-04 | WPS-24 | A-S-24-04 | Controlled closure package — Close drill findings and issue final operational readiness recommendation | Supplemental Control Deliverable | Controlled output demonstrating execution, verification, limitations and acceptance for Close drill findings and issue final operational readiness recommendation. | SC-24-04 | Controlled PDF/XLSX/report/letter as applicable | Project Director | QA/QC / Technical Manager | Relevant competent authority / Project Director | GATE-8 | AC-S-24-04 | E-S-24-04 | Rev0 |  | Not Started |  |  | Supplemental control; no unsupported legal or numerical threshold added.

## Tasks
Task ID | Activity ID | WPS ID | Task Title | Task Description | Task Sequence | Task Owner | Required Input | Expected Output | Predecessor Task IDs | Dependency Type | Successor Task IDs | Planned Start | Planned Finish | Duration | Actual Start | Actual Finish | Status | Related Deliverable ID | Related Gap ID | Acceptance Criteria ID | Completion Evidence | Completion Authority | Notes
T-R-001-01 | A-R-001 | WPS-01 | Obtain and control current DNV Class Certificate, Class Status Report, complete notation/scope, class history and records needed to evaluate DNV-RU-SHIP, DNV-RU-OU and alternative IACS class-transfer pathways. | Record document identity, revision/date, issuing authority, class status, notation, scope, restrictions and class-history availability. | 01 | Rule/WPS owner to be assigned | Current DNV Certificate + Class Status Report; complete notation/scope; class history; DNV-RU-SHIP/RU-OU applicability evidence; alternative IACS class-transfer feasibility records. | Classification regime/strategy is explicitly determined or formally left unresolved by the competent authority; all alternatives considered are traceable; no unsupported class assumption remains. | GATE-0 | Finish-to-Start | T-R-001-02 | [5 empty] | Not Started | D-R-001 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | AC-R-001 | E-R-001 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-001-02 | A-R-001 | WPS-01 | Verify applicability and technical sufficiency: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Current DNV Class Certificate + class status; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-001-01 | Finish-to-Start | T-R-001-03 | [5 empty] | Not Started | D-R-001 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | AC-R-001 | E-R-001 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-001-03 | A-R-001 | WPS-01 | Issue acceptance or escalation record: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Current DNV Class Certificate + class status; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-001-02 | Finish-to-Start | T-R-002-01 | [5 empty] | Not Started | D-R-001 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | AC-R-001 | E-R-001 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-002-01 | A-R-002 | WPS-01 | Obtain and control source evidence: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Current DNV Class Certificate; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-001-03 | Finish-to-Start | T-R-002-02 | [5 empty] | Not Started | D-R-002 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | AC-R-002 | E-R-002 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-002-02 | A-R-002 | WPS-01 | Verify applicability and technical sufficiency: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Current DNV Class Certificate; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-002-01 | Finish-to-Start | T-R-002-03 | [5 empty] | Not Started | D-R-002 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | AC-R-002 | E-R-002 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-002-03 | A-R-002 | WPS-01 | Issue acceptance or escalation record: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Current DNV Class Certificate; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-002-02 | Finish-to-Start | T-R-003-01 | [5 empty] | Not Started | D-R-002 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | AC-R-002 | E-R-002 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-003-01 | A-R-003 | WPS-02 | Obtain and control source evidence: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Class basis + rule edition evidence; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-002-03 | Finish-to-Start | T-R-003-02 | [5 empty] | Not Started | D-R-003 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | AC-R-003 | E-R-003 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-003-02 | A-R-003 | WPS-02 | Verify applicability and technical sufficiency: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Class basis + rule edition evidence; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-003-01 | Finish-to-Start | T-R-003-03 | [5 empty] | Not Started | D-R-003 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | AC-R-003 | E-R-003 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-003-03 | A-R-003 | WPS-02 | Issue acceptance or escalation record: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Class basis + rule edition evidence; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-003-02 | Finish-to-Start | T-R-004-01 | [5 empty] | Not Started | D-R-003 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | AC-R-003 | E-R-003 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-004-01 | A-R-004 | WPS-01 | Obtain and control source evidence: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Class Status Report + survey records; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-003-03 | Finish-to-Start | T-R-004-02 | [5 empty] | Not Started | D-R-004 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | AC-R-004 | E-R-004 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-004-02 | A-R-004 | WPS-01 | Verify applicability and technical sufficiency: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Class Status Report + survey records; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-004-01 | Finish-to-Start | T-R-004-03 | [5 empty] | Not Started | D-R-004 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | AC-R-004 | E-R-004 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-004-03 | A-R-004 | WPS-01 | Issue acceptance or escalation record: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Class Status Report + survey records; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-004-02 | Finish-to-Start | T-R-005-01 | [5 empty] | Not Started | D-R-004 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | AC-R-004 | E-R-004 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-005-01 | A-R-005 | WPS-01 | Obtain and control source evidence: Identify approved drawings and documents forming the class technical basis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Approved drawings list / class file; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-004-03 | Finish-to-Start | T-R-005-02 | [5 empty] | Not Started | D-R-005 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify approved drawings and documents forming the class technical basis. | AC-R-005 | E-R-005 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-005-02 | A-R-005 | WPS-01 | Verify applicability and technical sufficiency: Identify approved drawings and documents forming the class technical basis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Approved drawings list / class file; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-005-01 | Finish-to-Start | T-R-005-03 | [5 empty] | Not Started | D-R-005 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify approved drawings and documents forming the class technical basis. | AC-R-005 | E-R-005 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-005-03 | A-R-005 | WPS-01 | Issue acceptance or escalation record: Identify approved drawings and documents forming the class technical basis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Approved drawings list / class file; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-005-02 | Finish-to-Start | T-R-006-01 | [5 empty] | Not Started | D-R-005 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify approved drawings and documents forming the class technical basis. | AC-R-005 | E-R-005 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-006-01 | A-R-006 | WPS-02 | Obtain and control source evidence: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Survey status/history; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-005-03 | Finish-to-Start | T-R-006-02 | [5 empty] | Not Started | D-R-006 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | AC-R-006 | E-R-006 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-006-02 | A-R-006 | WPS-02 | Verify applicability and technical sufficiency: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Survey status/history; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-006-01 | Finish-to-Start | T-R-006-03 | [5 empty] | Not Started | D-R-006 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | AC-R-006 | E-R-006 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-006-03 | A-R-006 | WPS-02 | Issue acceptance or escalation record: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Survey status/history; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-006-02 | Finish-to-Start | T-R-007-01 | [5 empty] | Not Started | D-R-006 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | AC-R-006 | E-R-006 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-007-01 | A-R-007 | WPS-02 | Obtain and control source evidence: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Modification history + approvals; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-006-03 | Finish-to-Start | T-R-007-02 | [5 empty] | Not Started | D-R-007 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Assess effects of modifications, conversion, change of service or operating area on class requirements. | AC-R-007 | E-R-007 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-007-02 | A-R-007 | WPS-02 | Verify applicability and technical sufficiency: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Modification history + approvals; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-007-01 | Finish-to-Start | T-R-007-03 | [5 empty] | Not Started | D-R-007 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Assess effects of modifications, conversion, change of service or operating area on class requirements. | AC-R-007 | E-R-007 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-007-03 | A-R-007 | WPS-02 | Issue acceptance or escalation record: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Modification history + approvals; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-007-02 | Finish-to-Start | T-R-008-01 | [5 empty] | Not Started | D-R-007 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Assess effects of modifications, conversion, change of service or operating area on class requirements. | AC-R-007 | E-R-007 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-008-01 | A-R-008 | WPS-01 | Obtain and control source evidence: Establish the approved operating limits and service scope relevant to Jordan operations. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Certificate + approved operational documents; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-007-03 | Finish-to-Start | T-R-008-02 | [5 empty] | Not Started | D-R-008 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the approved operating limits and service scope relevant to Jordan operations. | AC-R-008 | E-R-008 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-008-02 | A-R-008 | WPS-01 | Verify applicability and technical sufficiency: Establish the approved operating limits and service scope relevant to Jordan operations. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Certificate + approved operational documents; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-008-01 | Finish-to-Start | T-R-008-03 | [5 empty] | Not Started | D-R-008 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the approved operating limits and service scope relevant to Jordan operations. | AC-R-008 | E-R-008 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-008-03 | A-R-008 | WPS-01 | Issue acceptance or escalation record: Establish the approved operating limits and service scope relevant to Jordan operations. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Certificate + approved operational documents; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-008-02 | Finish-to-Start | T-R-009-01 | [5 empty] | Not Started | D-R-008 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the approved operating limits and service scope relevant to Jordan operations. | AC-R-008 | E-R-008 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-009-01 | A-R-009 | WPS-03 | Obtain and control source evidence: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Flag/statutory basis + appliance register; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-008-03 | Finish-to-Start | T-R-009-02 | [5 empty] | Not Started | D-R-009 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | AC-R-009 | E-R-009 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-009-02 | A-R-009 | WPS-03 | Verify applicability and technical sufficiency: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Flag/statutory basis + appliance register; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-009-01 | Finish-to-Start | T-R-009-03 | [5 empty] | Not Started | D-R-009 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | AC-R-009 | E-R-009 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-009-03 | A-R-009 | WPS-03 | Issue acceptance or escalation record: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Flag/statutory basis + appliance register; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-009-02 | Finish-to-Start | T-R-010-01 | [5 empty] | Not Started | D-R-009 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | AC-R-009 | E-R-009 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-010-01 | A-R-010 | WPS-03 | Obtain and control source evidence: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Flag acceptance + technical basis; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-009-03 | Finish-to-Start | T-R-010-02 | [5 empty] | Not Started | D-R-010 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | AC-R-010 | E-R-010 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-010-02 | A-R-010 | WPS-03 | Verify applicability and technical sufficiency: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Flag acceptance + technical basis; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-010-01 | Finish-to-Start | T-R-010-03 | [5 empty] | Not Started | D-R-010 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | AC-R-010 | E-R-010 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-010-03 | A-R-010 | WPS-03 | Issue acceptance or escalation record: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Flag acceptance + technical basis; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-010-02 | Finish-to-Start | T-R-011-01 | [5 empty] | Not Started | D-R-010 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | AC-R-010 | E-R-010 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-011-01 | A-R-011 | WPS-03 | Obtain and control source evidence: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Register + certificates + examination/load-test records; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-010-03 | Finish-to-Start | T-R-011-02 | [5 empty] | Not Started | D-R-011 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | AC-R-011 | E-R-011 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-011-02 | A-R-011 | WPS-03 | Verify applicability and technical sufficiency: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Register + certificates + examination/load-test records; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-011-01 | Finish-to-Start | T-R-011-03 | [5 empty] | Not Started | D-R-011 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | AC-R-011 | E-R-011 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-011-03 | A-R-011 | WPS-03 | Issue acceptance or escalation record: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Register + certificates + examination/load-test records; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-011-02 | Finish-to-Start | T-R-012-01 | [5 empty] | Not Started | D-R-011 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | AC-R-011 | E-R-011 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-012-01 | A-R-012 | WPS-04 | Obtain and control source evidence: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | HMC 5500 technical/certification file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-011-03 | Finish-to-Start | T-R-012-02 | [5 empty] | Not Started | D-R-012 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | AC-R-012 | E-R-012 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-012-02 | A-R-012 | WPS-04 | Verify applicability and technical sufficiency: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | HMC 5500 technical/certification file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-012-01 | Finish-to-Start | T-R-012-03 | [5 empty] | Not Started | D-R-012 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | AC-R-012 | E-R-012 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-012-03 | A-R-012 | WPS-04 | Issue acceptance or escalation record: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | HMC 5500 technical/certification file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-012-02 | Finish-to-Start | T-R-013-01 | [5 empty] | Not Started | D-R-012 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | AC-R-012 | E-R-012 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-013-01 | A-R-013 | WPS-04 | Obtain and control source evidence: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Crane manual, load charts, limits, procedures; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-012-03 | Finish-to-Start | T-R-013-02 | [5 empty] | Not Started | D-R-013 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | AC-R-013 | E-R-013 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-013-02 | A-R-013 | WPS-04 | Verify applicability and technical sufficiency: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Crane manual, load charts, limits, procedures; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-013-01 | Finish-to-Start | T-R-013-03 | [5 empty] | Not Started | D-R-013 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | AC-R-013 | E-R-013 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-013-03 | A-R-013 | WPS-04 | Issue acceptance or escalation record: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Crane manual, load charts, limits, procedures; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-013-02 | Finish-to-Start | T-R-014-01 | [5 empty] | Not Started | D-R-013 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | AC-R-013 | E-R-013 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-014-01 | A-R-014 | WPS-05 | Obtain and control source evidence: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | OEM/configuration file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-013-03 | Finish-to-Start | T-R-014-02 | [5 empty] | Not Started | D-R-014 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | AC-R-014 | E-R-014 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-014-02 | A-R-014 | WPS-05 | Verify applicability and technical sufficiency: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | OEM/configuration file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-014-01 | Finish-to-Start | T-R-014-03 | [5 empty] | Not Started | D-R-014 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | AC-R-014 | E-R-014 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-014-03 | A-R-014 | WPS-05 | Issue acceptance or escalation record: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | OEM/configuration file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-014-02 | Finish-to-Start | T-R-015-01 | [5 empty] | Not Started | D-R-014 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | AC-R-014 | E-R-014 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-015-01 | A-R-015 | WPS-05 | Obtain and control source evidence: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Engineering assessment + load chart + deck data; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-014-03 | Finish-to-Start | T-R-015-02 | [5 empty] | Not Started | D-R-015 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | AC-R-015 | E-R-015 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-015-02 | A-R-015 | WPS-05 | Verify applicability and technical sufficiency: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Engineering assessment + load chart + deck data; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-015-01 | Finish-to-Start | T-R-015-03 | [5 empty] | Not Started | D-R-015 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | AC-R-015 | E-R-015 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-015-03 | A-R-015 | WPS-05 | Issue acceptance or escalation record: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Engineering assessment + load chart + deck data; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-015-02 | Finish-to-Start | T-R-016-01 | [5 empty] | Not Started | D-R-015 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | AC-R-015 | E-R-015 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-016-01 | A-R-016 | WPS-03 | Obtain and control source evidence: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Winch certificate/test/exam/OEM file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-015-03 | Finish-to-Start | T-R-016-02 | [5 empty] | Not Started | D-R-016 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | AC-R-016 | E-R-016 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-016-02 | A-R-016 | WPS-03 | Verify applicability and technical sufficiency: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Winch certificate/test/exam/OEM file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-016-01 | Finish-to-Start | T-R-016-03 | [5 empty] | Not Started | D-R-016 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | AC-R-016 | E-R-016 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-016-03 | A-R-016 | WPS-03 | Issue acceptance or escalation record: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Winch certificate/test/exam/OEM file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-016-02 | Finish-to-Start | T-R-017-01 | [5 empty] | Not Started | D-R-016 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | AC-R-016 | E-R-016 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-017-01 | A-R-017 | WPS-03 | Obtain and control source evidence: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Tugger certificates/tests/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-016-03 | Finish-to-Start | T-R-017-02 | [5 empty] | Not Started | D-R-017 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | AC-R-017 | E-R-017 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-017-02 | A-R-017 | WPS-03 | Verify applicability and technical sufficiency: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Tugger certificates/tests/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-017-01 | Finish-to-Start | T-R-017-03 | [5 empty] | Not Started | D-R-017 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | AC-R-017 | E-R-017 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-017-03 | A-R-017 | WPS-03 | Issue acceptance or escalation record: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Tugger certificates/tests/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-017-02 | Finish-to-Start | T-R-018-01 | [5 empty] | Not Started | D-R-017 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | AC-R-017 | E-R-017 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-018-01 | A-R-018 | WPS-03 | Obtain and control source evidence: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Loose-gear register + certificates/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-017-03 | Finish-to-Start | T-R-018-02 | [5 empty] | Not Started | D-R-018 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | AC-R-018 | E-R-018 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-018-02 | A-R-018 | WPS-03 | Verify applicability and technical sufficiency: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Loose-gear register + certificates/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-018-01 | Finish-to-Start | T-R-018-03 | [5 empty] | Not Started | D-R-018 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | AC-R-018 | E-R-018 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-018-03 | A-R-018 | WPS-03 | Issue acceptance or escalation record: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Loose-gear register + certificates/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-018-02 | Finish-to-Start | T-R-019-01 | [5 empty] | Not Started | D-R-018 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | AC-R-018 | E-R-018 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-019-01 | A-R-019 | WPS-06 | Obtain and control source evidence: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Class basis + applicable rule edition; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-018-03 | Finish-to-Start | T-R-019-02 | [5 empty] | Not Started | D-R-019 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | AC-R-019 | E-R-019 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-019-02 | A-R-019 | WPS-06 | Verify applicability and technical sufficiency: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Class basis + applicable rule edition; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-019-01 | Finish-to-Start | T-R-019-03 | [5 empty] | Not Started | D-R-019 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | AC-R-019 | E-R-019 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-019-03 | A-R-019 | WPS-06 | Issue acceptance or escalation record: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Class basis + applicable rule edition; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-019-02 | Finish-to-Start | T-R-020-01 | [5 empty] | Not Started | D-R-019 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | AC-R-019 | E-R-019 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-020-01 | A-R-020 | WPS-06 | Obtain and control source evidence: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | CRC drawings/manuals/tests; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-019-03 | Finish-to-Start | T-R-020-02 | [5 empty] | Not Started | D-R-020 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | AC-R-020 | E-R-020 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-020-02 | A-R-020 | WPS-06 | Verify applicability and technical sufficiency: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | CRC drawings/manuals/tests; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-020-01 | Finish-to-Start | T-R-020-03 | [5 empty] | Not Started | D-R-020 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | AC-R-020 | E-R-020 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-020-03 | A-R-020 | WPS-06 | Issue acceptance or escalation record: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | CRC drawings/manuals/tests; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-020-02 | Finish-to-Start | T-R-021-01 | [5 empty] | Not Started | D-R-020 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | AC-R-020 | E-R-020 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-021-01 | A-R-021 | WPS-06 | Obtain and control source evidence: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Tensioner certificate/manual/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-020-03 | Finish-to-Start | T-R-021-02 | [5 empty] | Not Started | D-R-021 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | AC-R-021 | E-R-021 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-021-02 | A-R-021 | WPS-06 | Verify applicability and technical sufficiency: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Tensioner certificate/manual/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-021-01 | Finish-to-Start | T-R-021-03 | [5 empty] | Not Started | D-R-021 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | AC-R-021 | E-R-021 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-021-03 | A-R-021 | WPS-06 | Issue acceptance or escalation record: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Tensioner certificate/manual/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-021-02 | Finish-to-Start | T-R-022-01 | [5 empty] | Not Started | D-R-021 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | AC-R-021 | E-R-021 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-022-01 | A-R-022 | WPS-06 | Obtain and control source evidence: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Drawings + calculations + inspection/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-021-03 | Finish-to-Start | T-R-022-02 | [5 empty] | Not Started | D-R-022 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | AC-R-022 | E-R-022 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-022-02 | A-R-022 | WPS-06 | Verify applicability and technical sufficiency: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Drawings + calculations + inspection/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-022-01 | Finish-to-Start | T-R-022-03 | [5 empty] | Not Started | D-R-022 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | AC-R-022 | E-R-022 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-022-03 | A-R-022 | WPS-06 | Issue acceptance or escalation record: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Drawings + calculations + inspection/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-022-02 | Finish-to-Start | T-R-023-01 | [5 empty] | Not Started | D-R-022 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | AC-R-022 | E-R-022 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-023-01 | A-R-023 | WPS-07 | Obtain and control source evidence: Verify welding stations, coating station and related QA/QC controls. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Welding/coating procedures + qualifications; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-022-03 | Finish-to-Start | T-R-023-02 | [5 empty] | Not Started | D-R-023 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify welding stations, coating station and related QA/QC controls. | AC-R-023 | E-R-023 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-023-02 | A-R-023 | WPS-07 | Verify applicability and technical sufficiency: Verify welding stations, coating station and related QA/QC controls. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Welding/coating procedures + qualifications; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-023-01 | Finish-to-Start | T-R-023-03 | [5 empty] | Not Started | D-R-023 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify welding stations, coating station and related QA/QC controls. | AC-R-023 | E-R-023 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-023-03 | A-R-023 | WPS-07 | Issue acceptance or escalation record: Verify welding stations, coating station and related QA/QC controls. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Welding/coating procedures + qualifications; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-023-02 | Finish-to-Start | T-R-024-01 | [5 empty] | Not Started | D-R-023 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify welding stations, coating station and related QA/QC controls. | AC-R-023 | E-R-023 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-024-01 | A-R-024 | WPS-07 | Obtain and control source evidence: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Equipment certificates + personnel qualifications + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-023-03 | Finish-to-Start | T-R-024-02 | [5 empty] | Not Started | D-R-024 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | AC-R-024 | E-R-024 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-024-02 | A-R-024 | WPS-07 | Verify applicability and technical sufficiency: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Equipment certificates + personnel qualifications + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-024-01 | Finish-to-Start | T-R-024-03 | [5 empty] | Not Started | D-R-024 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | AC-R-024 | E-R-024 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-024-03 | A-R-024 | WPS-07 | Issue acceptance or escalation record: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Equipment certificates + personnel qualifications + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-024-02 | Finish-to-Start | T-R-025-01 | [5 empty] | Not Started | D-R-024 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | AC-R-024 | E-R-024 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-025-01 | A-R-025 | WPS-07 | Obtain and control source evidence: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Installation analysis + operating limits + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-024-03 | Finish-to-Start | T-R-025-02 | [5 empty] | Not Started | D-R-025 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | AC-R-025 | E-R-025 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-025-02 | A-R-025 | WPS-07 | Verify applicability and technical sufficiency: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Installation analysis + operating limits + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-025-01 | Finish-to-Start | T-R-025-03 | [5 empty] | Not Started | D-R-025 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | AC-R-025 | E-R-025 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-025-03 | A-R-025 | WPS-07 | Issue acceptance or escalation record: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Installation analysis + operating limits + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-025-02 | Finish-to-Start | T-R-026-01 | [5 empty] | Not Started | D-R-025 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | AC-R-025 | E-R-025 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-026-01 | A-R-026 | WPS-07 | Obtain and control source evidence: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Project design basis/specification; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-025-03 | Finish-to-Start | T-R-026-02 | [5 empty] | Not Started | D-R-026 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | AC-R-026 | E-R-026 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-026-02 | A-R-026 | WPS-07 | Verify applicability and technical sufficiency: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Project design basis/specification; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-026-01 | Finish-to-Start | T-R-026-03 | [5 empty] | Not Started | D-R-026 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | AC-R-026 | E-R-026 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-026-03 | A-R-026 | WPS-07 | Issue acceptance or escalation record: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Project design basis/specification; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-026-02 | Finish-to-Start | T-R-027-01 | [5 empty] | Not Started | D-R-026 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | AC-R-026 | E-R-026 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-027-01 | A-R-027 | WPS-07 | Obtain and control source evidence: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Project specification + engineering basis; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-026-03 | Finish-to-Start | T-R-027-02 | [5 empty] | Not Started | D-R-027 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | AC-R-027 | E-R-027 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-027-02 | A-R-027 | WPS-07 | Verify applicability and technical sufficiency: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Project specification + engineering basis; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-027-01 | Finish-to-Start | T-R-027-03 | [5 empty] | Not Started | D-R-027 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | AC-R-027 | E-R-027 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-027-03 | A-R-027 | WPS-07 | Issue acceptance or escalation record: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Project specification + engineering basis; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-027-02 | Finish-to-Start | T-R-028-01 | [5 empty] | Not Started | D-R-027 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | AC-R-027 | E-R-027 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-028-01 | A-R-028 | WPS-07 | Obtain and control source evidence: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Installation analysis package; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-027-03 | Finish-to-Start | T-R-028-02 | [5 empty] | Not Started | D-R-028 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | AC-R-028 | E-R-028 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-028-02 | A-R-028 | WPS-07 | Verify applicability and technical sufficiency: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Installation analysis package; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-028-01 | Finish-to-Start | T-R-028-03 | [5 empty] | Not Started | D-R-028 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | AC-R-028 | E-R-028 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-028-03 | A-R-028 | WPS-07 | Issue acceptance or escalation record: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Installation analysis package; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-028-02 | Finish-to-Start | T-R-029-01 | [5 empty] | Not Started | D-R-028 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | AC-R-028 | E-R-028 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-029-01 | A-R-029 | WPS-08 | Obtain and control source evidence: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Mooring arrangement + equipment certificates; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-028-03 | Finish-to-Start | T-R-029-02 | [5 empty] | Not Started | D-R-029 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | AC-R-029 | E-R-029 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-029-02 | A-R-029 | WPS-08 | Verify applicability and technical sufficiency: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Mooring arrangement + equipment certificates; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-029-01 | Finish-to-Start | T-R-029-03 | [5 empty] | Not Started | D-R-029 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | AC-R-029 | E-R-029 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-029-03 | A-R-029 | WPS-08 | Issue acceptance or escalation record: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Mooring arrangement + equipment certificates; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-029-02 | Finish-to-Start | T-R-030-01 | [5 empty] | Not Started | D-R-029 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | AC-R-029 | E-R-029 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-030-01 | A-R-030 | WPS-08 | Obtain and control source evidence: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Winch manuals/tests/exams; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-029-03 | Finish-to-Start | T-R-030-02 | [5 empty] | Not Started | D-R-030 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | AC-R-030 | E-R-030 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-030-02 | A-R-030 | WPS-08 | Verify applicability and technical sufficiency: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Winch manuals/tests/exams; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-030-01 | Finish-to-Start | T-R-030-03 | [5 empty] | Not Started | D-R-030 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | AC-R-030 | E-R-030 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-030-03 | A-R-030 | WPS-08 | Issue acceptance or escalation record: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Winch manuals/tests/exams; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-030-02 | Finish-to-Start | T-R-031-01 | [5 empty] | Not Started | D-R-030 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | AC-R-030 | E-R-030 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-031-01 | A-R-031 | WPS-08 | Obtain and control source evidence: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Mooring analysis + environmental design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-030-03 | Finish-to-Start | T-R-031-02 | [5 empty] | Not Started | D-R-031 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | AC-R-031 | E-R-031 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-031-02 | A-R-031 | WPS-08 | Verify applicability and technical sufficiency: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Mooring analysis + environmental design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-031-01 | Finish-to-Start | T-R-031-03 | [5 empty] | Not Started | D-R-031 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | AC-R-031 | E-R-031 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-031-03 | A-R-031 | WPS-08 | Issue acceptance or escalation record: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Mooring analysis + environmental design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-031-02 | Finish-to-Start | T-R-032-01 | [5 empty] | Not Started | D-R-031 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | AC-R-031 | E-R-031 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-032-01 | A-R-032 | WPS-09 | Obtain and control source evidence: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Verified survey/geotech package; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-031-03 | Finish-to-Start | T-R-032-02 | [5 empty] | Not Started | D-R-032 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | AC-R-032 | E-R-032 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-032-02 | A-R-032 | WPS-09 | Verify applicability and technical sufficiency: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Verified survey/geotech package; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-032-01 | Finish-to-Start | T-R-032-03 | [5 empty] | Not Started | D-R-032 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | AC-R-032 | E-R-032 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-032-03 | A-R-032 | WPS-09 | Issue acceptance or escalation record: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Verified survey/geotech package; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-032-02 | Finish-to-Start | T-R-033-01 | [5 empty] | Not Started | D-R-032 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | AC-R-032 | E-R-032 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-033-01 | A-R-033 | WPS-09 | Obtain and control source evidence: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Subsea asset register + approved site layout; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-032-03 | Finish-to-Start | T-R-033-02 | [5 empty] | Not Started | D-R-033 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | AC-R-033 | E-R-033 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-033-02 | A-R-033 | WPS-09 | Verify applicability and technical sufficiency: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Subsea asset register + approved site layout; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-033-01 | Finish-to-Start | T-R-033-03 | [5 empty] | Not Started | D-R-033 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | AC-R-033 | E-R-033 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-033-03 | A-R-033 | WPS-09 | Issue acceptance or escalation record: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Subsea asset register + approved site layout; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-033-02 | Finish-to-Start | T-R-034-01 | [5 empty] | Not Started | D-R-033 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | AC-R-033 | E-R-033 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-034-01 | A-R-034 | WPS-09 | Obtain and control source evidence: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Metocean design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-033-03 | Finish-to-Start | T-R-034-02 | [5 empty] | Not Started | D-R-034 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | AC-R-034 | E-R-034 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-034-02 | A-R-034 | WPS-09 | Verify applicability and technical sufficiency: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Metocean design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-034-01 | Finish-to-Start | T-R-034-03 | [5 empty] | Not Started | D-R-034 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | AC-R-034 | E-R-034 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-034-03 | A-R-034 | WPS-09 | Issue acceptance or escalation record: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Metocean design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-034-02 | Finish-to-Start | T-R-035-01 | [5 empty] | Not Started | D-R-034 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | AC-R-034 | E-R-034 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-035-01 | A-R-035 | WPS-11 | Obtain and control source evidence: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | MWS scope + approval documents; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-034-03 | Finish-to-Start | T-R-035-02 | [5 empty] | Not Started | D-R-035 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | AC-R-035 | E-R-035 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-035-02 | A-R-035 | WPS-11 | Verify applicability and technical sufficiency: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | MWS scope + approval documents; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-035-01 | Finish-to-Start | T-R-035-03 | [5 empty] | Not Started | D-R-035 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | AC-R-035 | E-R-035 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-035-03 | A-R-035 | WPS-11 | Issue acceptance or escalation record: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | MWS scope + approval documents; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-035-02 | Finish-to-Start | T-R-036-01 | [5 empty] | Not Started | D-R-035 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | AC-R-035 | E-R-035 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-036-01 | A-R-036 | WPS-08 | Obtain and control source evidence: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Approved procedures + drills/records; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-035-03 | Finish-to-Start | T-R-036-02 | [5 empty] | Not Started | D-R-036 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | AC-R-036 | E-R-036 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-036-02 | A-R-036 | WPS-08 | Verify applicability and technical sufficiency: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Approved procedures + drills/records; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-036-01 | Finish-to-Start | T-R-036-03 | [5 empty] | Not Started | D-R-036 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | AC-R-036 | E-R-036 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-036-03 | A-R-036 | WPS-08 | Issue acceptance or escalation record: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Approved procedures + drills/records; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-036-02 | Finish-to-Start | T-R-037-01 | [5 empty] | Not Started | D-R-036 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | AC-R-036 | E-R-036 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-037-01 | A-R-037 | WPS-10 | Obtain and control source evidence: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Tow engineering package; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-036-03 | Finish-to-Start | T-R-037-02 | [5 empty] | Not Started | D-R-037 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | AC-R-037 | E-R-037 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-037-02 | A-R-037 | WPS-10 | Verify applicability and technical sufficiency: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Tow engineering package; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-037-01 | Finish-to-Start | T-R-037-03 | [5 empty] | Not Started | D-R-037 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | AC-R-037 | E-R-037 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-037-03 | A-R-037 | WPS-10 | Issue acceptance or escalation record: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Tow engineering package; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-037-02 | Finish-to-Start | T-R-038-01 | [5 empty] | Not Started | D-R-037 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | AC-R-037 | E-R-037 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-038-01 | A-R-038 | WPS-10 | Obtain and control source evidence: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Structural verification; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-037-03 | Finish-to-Start | T-R-038-02 | [5 empty] | Not Started | D-R-038 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | AC-R-038 | E-R-038 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-038-02 | A-R-038 | WPS-10 | Verify applicability and technical sufficiency: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Structural verification; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-038-01 | Finish-to-Start | T-R-038-03 | [5 empty] | Not Started | D-R-038 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | AC-R-038 | E-R-038 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-038-03 | A-R-038 | WPS-10 | Issue acceptance or escalation record: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Structural verification; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-038-02 | Finish-to-Start | T-R-039-01 | [5 empty] | Not Started | D-R-038 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | AC-R-038 | E-R-038 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-039-01 | A-R-039 | WPS-10 | Obtain and control source evidence: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Stability/tow condition calculations; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-038-03 | Finish-to-Start | T-R-039-02 | [5 empty] | Not Started | D-R-039 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | AC-R-039 | E-R-039 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-039-02 | A-R-039 | WPS-10 | Verify applicability and technical sufficiency: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Stability/tow condition calculations; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-039-01 | Finish-to-Start | T-R-039-03 | [5 empty] | Not Started | D-R-039 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | AC-R-039 | E-R-039 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-039-03 | A-R-039 | WPS-10 | Issue acceptance or escalation record: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Stability/tow condition calculations; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-039-02 | Finish-to-Start | T-R-040-01 | [5 empty] | Not Started | D-R-039 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | AC-R-039 | E-R-039 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-040-01 | A-R-040 | WPS-10 | Obtain and control source evidence: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Tug data + tow plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-039-03 | Finish-to-Start | T-R-040-02 | [5 empty] | Not Started | D-R-040 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | AC-R-040 | E-R-040 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-040-02 | A-R-040 | WPS-10 | Verify applicability and technical sufficiency: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Tug data + tow plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-040-01 | Finish-to-Start | T-R-040-03 | [5 empty] | Not Started | D-R-040 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | AC-R-040 | E-R-040 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-040-03 | A-R-040 | WPS-10 | Issue acceptance or escalation record: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Tug data + tow plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-040-02 | Finish-to-Start | T-R-041-01 | [5 empty] | Not Started | D-R-040 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | AC-R-040 | E-R-040 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-041-01 | A-R-041 | WPS-10 | Obtain and control source evidence: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Tow route/weather/emergency plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-040-03 | Finish-to-Start | T-R-041-02 | [5 empty] | Not Started | D-R-041 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | AC-R-041 | E-R-041 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-041-02 | A-R-041 | WPS-10 | Verify applicability and technical sufficiency: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Tow route/weather/emergency plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-041-01 | Finish-to-Start | T-R-041-03 | [5 empty] | Not Started | D-R-041 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | AC-R-041 | E-R-041 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-041-03 | A-R-041 | WPS-10 | Issue acceptance or escalation record: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Tow route/weather/emergency plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-041-02 | Finish-to-Start | T-R-042-01 | [5 empty] | Not Started | D-R-041 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | AC-R-041 | E-R-041 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-042-01 | A-R-042 | WPS-10 | Obtain and control source evidence: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Pre-tow inspection + approval; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-041-03 | Finish-to-Start | T-R-042-02 | [5 empty] | Not Started | D-R-042 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Define pre-tow inspection, readiness verification and required approval/statement before departure. | AC-R-042 | E-R-042 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-042-02 | A-R-042 | WPS-10 | Verify applicability and technical sufficiency: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Pre-tow inspection + approval; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-042-01 | Finish-to-Start | T-R-042-03 | [5 empty] | Not Started | D-R-042 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Define pre-tow inspection, readiness verification and required approval/statement before departure. | AC-R-042 | E-R-042 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-042-03 | A-R-042 | WPS-10 | Issue acceptance or escalation record: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Pre-tow inspection + approval; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-042-02 | Finish-to-Start | T-R-043-01 | [5 empty] | Not Started | D-R-042 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Define pre-tow inspection, readiness verification and required approval/statement before departure. | AC-R-042 | E-R-042 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-043-01 | A-R-043 | WPS-11 | Obtain and control source evidence: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | MWS scope and approvals; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | T-R-042-03 | Finish-to-Start | T-R-043-02 | [5 empty] | Not Started | D-R-043 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | AC-R-043 | E-R-043 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-043-02 | A-R-043 | WPS-11 | Verify applicability and technical sufficiency: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | MWS scope and approvals; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | T-R-043-01 | Finish-to-Start | T-R-043-03 | [5 empty] | Not Started | D-R-043 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | AC-R-043 | E-R-043 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-043-03 | A-R-043 | WPS-11 | Issue acceptance or escalation record: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | MWS scope and approvals; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | T-R-043-02 | Finish-to-Start | T-R-044-01 | [5 empty] | Not Started | D-R-043 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | AC-R-043 | E-R-043 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-044-01 | A-R-044 | WPS-12 | Obtain and control source evidence: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | IMCA inspection report + controlled diving procedures/records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-043-03 | Finish-to-Start | T-R-044-02 | [5 empty] | Not Started | D-R-044 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | AC-R-044 | E-R-044 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-044-02 | A-R-044 | WPS-12 | Verify applicability and technical sufficiency: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | IMCA inspection report + controlled diving procedures/records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-044-01 | Finish-to-Start | T-R-044-03 | [5 empty] | Not Started | D-R-044 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | AC-R-044 | E-R-044 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-044-03 | A-R-044 | WPS-12 | Issue acceptance or escalation record: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | IMCA inspection report + controlled diving procedures/records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-044-02 | Finish-to-Start | T-R-045-01 | [5 empty] | Not Started | D-R-044 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | AC-R-044 | E-R-044 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-045-01 | A-R-045 | WPS-12 | Obtain and control source evidence: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-044-03 | Finish-to-Start | T-R-045-02 | [5 empty] | Not Started | D-R-045 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | AC-R-045 | E-R-045 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-045-02 | A-R-045 | WPS-12 | Verify applicability and technical sufficiency: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-045-01 | Finish-to-Start | T-R-045-03 | [5 empty] | Not Started | D-R-045 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | AC-R-045 | E-R-045 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-045-03 | A-R-045 | WPS-12 | Issue acceptance or escalation record: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-045-02 | Finish-to-Start | T-R-046-01 | [5 empty] | Not Started | D-R-045 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | AC-R-045 | E-R-045 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-046-01 | A-R-046 | WPS-12 | Obtain and control source evidence: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-045-03 | Finish-to-Start | T-R-046-02 | [5 empty] | Not Started | D-R-046 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | AC-R-046 | E-R-046 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-046-02 | A-R-046 | WPS-12 | Verify applicability and technical sufficiency: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-046-01 | Finish-to-Start | T-R-046-03 | [5 empty] | Not Started | D-R-046 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | AC-R-046 | E-R-046 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-046-03 | A-R-046 | WPS-12 | Issue acceptance or escalation record: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-046-02 | Finish-to-Start | T-R-047-01 | [5 empty] | Not Started | D-R-046 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | AC-R-046 | E-R-046 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-047-01 | A-R-047 | WPS-12 | Obtain and control source evidence: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Competence matrix + records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-046-03 | Finish-to-Start | T-R-047-02 | [5 empty] | Not Started | D-R-047 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | AC-R-047 | E-R-047 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-047-02 | A-R-047 | WPS-12 | Verify applicability and technical sufficiency: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Competence matrix + records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-047-01 | Finish-to-Start | T-R-047-03 | [5 empty] | Not Started | D-R-047 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | AC-R-047 | E-R-047 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-047-03 | A-R-047 | WPS-12 | Issue acceptance or escalation record: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Competence matrix + records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-047-02 | Finish-to-Start | T-R-048-01 | [5 empty] | Not Started | D-R-047 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | AC-R-047 | E-R-047 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-048-01 | A-R-048 | WPS-12 | Obtain and control source evidence: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Maintenance/test records + IMCA acceptance; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-047-03 | Finish-to-Start | T-R-048-02 | [5 empty] | Not Started | D-R-048 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | AC-R-048 | E-R-048 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-048-02 | A-R-048 | WPS-12 | Verify applicability and technical sufficiency: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Maintenance/test records + IMCA acceptance; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-048-01 | Finish-to-Start | T-R-048-03 | [5 empty] | Not Started | D-R-048 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | AC-R-048 | E-R-048 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-048-03 | A-R-048 | WPS-12 | Issue acceptance or escalation record: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Maintenance/test records + IMCA acceptance; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Applicable IMCA scope is explicitly identified; relevant plant/system examinations, tests, maintenance, emergency arrangements and personnel competence are current and traceable; limitations are documented and accepted. No IMO Diving Code or unsupported DNV/Flag diving baseline is used. | T-R-048-02 | Finish-to-Start | T-R-049-01 | [5 empty] | Not Started | D-R-048 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | AC-R-048 | E-R-048 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-049-01 | A-R-049 | WPS-13 | Obtain and control source evidence: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Electrical single-line + tests + survey records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-048-03 | Finish-to-Start | T-R-049-02 | [5 empty] | Not Started | D-R-049 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | AC-R-049 | E-R-049 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-049-02 | A-R-049 | WPS-13 | Verify applicability and technical sufficiency: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Electrical single-line + tests + survey records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-049-01 | Finish-to-Start | T-R-049-03 | [5 empty] | Not Started | D-R-049 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | AC-R-049 | E-R-049 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-049-03 | A-R-049 | WPS-13 | Issue acceptance or escalation record: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Electrical single-line + tests + survey records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-049-02 | Finish-to-Start | T-R-050-01 | [5 empty] | Not Started | D-R-049 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | AC-R-049 | E-R-049 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-050-01 | A-R-050 | WPS-13 | Obtain and control source evidence: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | P&IDs + tests + maintenance records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-049-03 | Finish-to-Start | T-R-050-02 | [5 empty] | Not Started | D-R-050 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | AC-R-050 | E-R-050 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-050-02 | A-R-050 | WPS-13 | Verify applicability and technical sufficiency: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | P&IDs + tests + maintenance records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-050-01 | Finish-to-Start | T-R-050-03 | [5 empty] | Not Started | D-R-050 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | AC-R-050 | E-R-050 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-050-03 | A-R-050 | WPS-13 | Issue acceptance or escalation record: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | P&IDs + tests + maintenance records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-050-02 | Finish-to-Start | T-R-051-01 | [5 empty] | Not Started | D-R-050 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | AC-R-050 | E-R-050 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-051-01 | A-R-051 | WPS-14 | Obtain and control source evidence: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | FSS certificates/tests + plans; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-050-03 | Finish-to-Start | T-R-051-02 | [5 empty] | Not Started | D-R-051 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | AC-R-051 | E-R-051 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-051-02 | A-R-051 | WPS-14 | Verify applicability and technical sufficiency: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | FSS certificates/tests + plans; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-051-01 | Finish-to-Start | T-R-051-03 | [5 empty] | Not Started | D-R-051 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | AC-R-051 | E-R-051 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-051-03 | A-R-051 | WPS-14 | Issue acceptance or escalation record: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | FSS certificates/tests + plans; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-051-02 | Finish-to-Start | T-R-052-01 | [5 empty] | Not Started | D-R-051 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | AC-R-051 | E-R-051 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-052-01 | A-R-052 | WPS-14 | Obtain and control source evidence: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | LSA certificates + drill records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-051-03 | Finish-to-Start | T-R-052-02 | [5 empty] | Not Started | D-R-052 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | AC-R-052 | E-R-052 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-052-02 | A-R-052 | WPS-14 | Verify applicability and technical sufficiency: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | LSA certificates + drill records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-052-01 | Finish-to-Start | T-R-052-03 | [5 empty] | Not Started | D-R-052 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | AC-R-052 | E-R-052 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-052-03 | A-R-052 | WPS-14 | Issue acceptance or escalation record: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | LSA certificates + drill records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-052-02 | Finish-to-Start | T-R-053-01 | [5 empty] | Not Started | D-R-052 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | AC-R-052 | E-R-052 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-053-01 | A-R-053 | WPS-14 | Obtain and control source evidence: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Equipment list + calibration/service records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-052-03 | Finish-to-Start | T-R-053-02 | [5 empty] | Not Started | D-R-053 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | AC-R-053 | E-R-053 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-053-02 | A-R-053 | WPS-14 | Verify applicability and technical sufficiency: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Equipment list + calibration/service records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-053-01 | Finish-to-Start | T-R-053-03 | [5 empty] | Not Started | D-R-053 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | AC-R-053 | E-R-053 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-053-03 | A-R-053 | WPS-14 | Issue acceptance or escalation record: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Equipment list + calibration/service records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-053-02 | Finish-to-Start | T-R-054-01 | [5 empty] | Not Started | D-R-053 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | AC-R-053 | E-R-053 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-054-01 | A-R-054 | WPS-14 | Obtain and control source evidence: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | JMA/VTS requirements + agent confirmation; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-053-03 | Finish-to-Start | T-R-054-02 | [5 empty] | Not Started | D-R-054 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | AC-R-054 | E-R-054 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-054-02 | A-R-054 | WPS-14 | Verify applicability and technical sufficiency: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | JMA/VTS requirements + agent confirmation; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-054-01 | Finish-to-Start | T-R-054-03 | [5 empty] | Not Started | D-R-054 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | AC-R-054 | E-R-054 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-054-03 | A-R-054 | WPS-14 | Issue acceptance or escalation record: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | JMA/VTS requirements + agent confirmation; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-054-02 | Finish-to-Start | T-R-055-01 | [5 empty] | Not Started | D-R-054 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | AC-R-054 | E-R-054 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-055-01 | A-R-055 | WPS-15 | Obtain and control source evidence: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Crew profile + accommodation inspection/certification; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-054-03 | Finish-to-Start | T-R-055-02 | [5 empty] | Not Started | D-R-055 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | AC-R-055 | E-R-055 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-055-02 | A-R-055 | WPS-15 | Verify applicability and technical sufficiency: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Crew profile + accommodation inspection/certification; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-055-01 | Finish-to-Start | T-R-055-03 | [5 empty] | Not Started | D-R-055 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | AC-R-055 | E-R-055 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-055-03 | A-R-055 | WPS-15 | Issue acceptance or escalation record: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Crew profile + accommodation inspection/certification; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-055-02 | Finish-to-Start | T-R-056-01 | [5 empty] | Not Started | D-R-055 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | AC-R-055 | E-R-055 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-056-01 | A-R-056 | WPS-15 | Obtain and control source evidence: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Health/galley/water evidence; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-055-03 | Finish-to-Start | T-R-056-02 | [5 empty] | Not Started | D-R-056 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | AC-R-056 | E-R-056 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-056-02 | A-R-056 | WPS-15 | Verify applicability and technical sufficiency: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Health/galley/water evidence; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-056-01 | Finish-to-Start | T-R-056-03 | [5 empty] | Not Started | D-R-056 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | AC-R-056 | E-R-056 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-056-03 | A-R-056 | WPS-15 | Issue acceptance or escalation record: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Health/galley/water evidence; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-056-02 | Finish-to-Start | T-R-057-01 | [5 empty] | Not Started | D-R-056 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | AC-R-056 | E-R-056 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-057-01 | A-R-057 | WPS-15 | Obtain and control source evidence: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Crew certification matrix; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-056-03 | Finish-to-Start | T-R-057-02 | [5 empty] | Not Started | D-R-057 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | AC-R-057 | E-R-057 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-057-02 | A-R-057 | WPS-15 | Verify applicability and technical sufficiency: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Crew certification matrix; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-057-01 | Finish-to-Start | T-R-057-03 | [5 empty] | Not Started | D-R-057 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | AC-R-057 | E-R-057 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-057-03 | A-R-057 | WPS-15 | Issue acceptance or escalation record: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Crew certification matrix; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-057-02 | Finish-to-Start | T-R-058-01 | [5 empty] | Not Started | D-R-057 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | AC-R-057 | E-R-057 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-058-01 | A-R-058 | WPS-15 | Obtain and control source evidence: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Competence matrix + training records; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-057-03 | Finish-to-Start | T-R-058-02 | [5 empty] | Not Started | D-R-058 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | AC-R-058 | E-R-058 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-058-02 | A-R-058 | WPS-15 | Verify applicability and technical sufficiency: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Competence matrix + training records; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-058-01 | Finish-to-Start | T-R-058-03 | [5 empty] | Not Started | D-R-058 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | AC-R-058 | E-R-058 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-058-03 | A-R-058 | WPS-15 | Issue acceptance or escalation record: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Competence matrix + training records; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Applicability is documented; assigned personnel/welfare arrangements meet the criterion and certificates/medical/training/inspection evidence is current and traceable. | T-R-058-02 | Finish-to-Start | T-R-059-01 | [5 empty] | Not Started | D-R-058 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | AC-R-058 | E-R-058 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-059-01 | A-R-059 | WPS-13 | Obtain and control source evidence: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | PMS matrix + OEM manuals + records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-058-03 | Finish-to-Start | T-R-059-02 | [5 empty] | Not Started | D-R-059 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | AC-R-059 | E-R-059 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-059-02 | A-R-059 | WPS-13 | Verify applicability and technical sufficiency: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | PMS matrix + OEM manuals + records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-059-01 | Finish-to-Start | T-R-059-03 | [5 empty] | Not Started | D-R-059 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | AC-R-059 | E-R-059 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-059-03 | A-R-059 | WPS-13 | Issue acceptance or escalation record: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | PMS matrix + OEM manuals + records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-059-02 | Finish-to-Start | T-R-060-01 | [5 empty] | Not Started | D-R-059 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | AC-R-059 | E-R-059 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-060-01 | A-R-060 | WPS-13 | Obtain and control source evidence: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Certificates, test reports, calibration records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-059-03 | Finish-to-Start | T-R-060-02 | [5 empty] | Not Started | D-R-060 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | AC-R-060 | E-R-060 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-060-02 | A-R-060 | WPS-13 | Verify applicability and technical sufficiency: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Certificates, test reports, calibration records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-060-01 | Finish-to-Start | T-R-060-03 | [5 empty] | Not Started | D-R-060 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | AC-R-060 | E-R-060 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-060-03 | A-R-060 | WPS-13 | Issue acceptance or escalation record: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Certificates, test reports, calibration records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-060-02 | Finish-to-Start | T-R-061-01 | [5 empty] | Not Started | D-R-060 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | AC-R-060 | E-R-060 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-061-01 | A-R-061 | WPS-16 | Obtain and control source evidence: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Survey matrix + records; survey/examination matrix by equipment/system, due date, completion date, certificate/report, findings and restrictions. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-060-03 | Finish-to-Start | T-R-061-02 | [5 empty] | Not Started | D-R-061 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | AC-R-061 | E-R-061 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-061-02 | A-R-061 | WPS-16 | Verify applicability and technical sufficiency: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Survey matrix + records; survey/examination matrix by equipment/system, due date, completion date, certificate/report, findings and restrictions. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-061-01 | Finish-to-Start | T-R-061-03 | [5 empty] | Not Started | D-R-061 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | AC-R-061 | E-R-061 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-061-03 | A-R-061 | WPS-16 | Issue acceptance or escalation record: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Survey matrix + records; survey/examination matrix by equipment/system, due date, completion date, certificate/report, findings and restrictions. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-061-02 | Finish-to-Start | T-R-062-01 | [5 empty] | Not Started | D-R-061 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | AC-R-061 | E-R-061 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-062-01 | A-R-062 | WPS-16 | Obtain and control source evidence: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Controlled document register; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-061-03 | Finish-to-Start | T-R-062-02 | [5 empty] | Not Started | D-R-062 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | AC-R-062 | E-R-062 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-062-02 | A-R-062 | WPS-16 | Verify applicability and technical sufficiency: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Controlled document register; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-062-01 | Finish-to-Start | T-R-062-03 | [5 empty] | Not Started | D-R-062 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | AC-R-062 | E-R-062 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-062-03 | A-R-062 | WPS-16 | Issue acceptance or escalation record: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Controlled document register; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-062-02 | Finish-to-Start | T-R-063-01 | [5 empty] | Not Started | D-R-062 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | AC-R-062 | E-R-062 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-063-01 | A-R-063 | WPS-16 | Obtain and control source evidence: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Agent/JMA entry requirements; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-062-03 | Finish-to-Start | T-R-063-02 | [5 empty] | Not Started | D-R-063 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | AC-R-063 | E-R-063 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-063-02 | A-R-063 | WPS-16 | Verify applicability and technical sufficiency: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Agent/JMA entry requirements; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-063-01 | Finish-to-Start | T-R-063-03 | [5 empty] | Not Started | D-R-063 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | AC-R-063 | E-R-063 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-063-03 | A-R-063 | WPS-16 | Issue acceptance or escalation record: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Agent/JMA entry requirements; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-063-02 | Finish-to-Start | T-R-064-01 | [5 empty] | Not Started | D-R-063 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | AC-R-063 | E-R-063 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-064-01 | A-R-064 | WPS-16 | Obtain and control source evidence: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | PSC readiness package; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-063-03 | Finish-to-Start | T-R-064-02 | [5 empty] | Not Started | D-R-064 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | AC-R-064 | E-R-064 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-064-02 | A-R-064 | WPS-16 | Verify applicability and technical sufficiency: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | PSC readiness package; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-064-01 | Finish-to-Start | T-R-064-03 | [5 empty] | Not Started | D-R-064 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | AC-R-064 | E-R-064 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-064-03 | A-R-064 | WPS-16 | Issue acceptance or escalation record: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | PSC readiness package; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-064-02 | Finish-to-Start | T-R-065-01 | [5 empty] | Not Started | D-R-064 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | AC-R-064 | E-R-064 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-065-01 | A-R-065 | WPS-16 | Obtain and control source evidence: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | JMA survey requirements + reports; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-064-03 | Finish-to-Start | T-R-065-02 | [5 empty] | Not Started | D-R-065 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | AC-R-065 | E-R-065 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-065-02 | A-R-065 | WPS-16 | Verify applicability and technical sufficiency: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | JMA survey requirements + reports; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-065-01 | Finish-to-Start | T-R-065-03 | [5 empty] | Not Started | D-R-065 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | AC-R-065 | E-R-065 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-065-03 | A-R-065 | WPS-16 | Issue acceptance or escalation record: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | JMA survey requirements + reports; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-065-02 | Finish-to-Start | T-R-066-01 | [5 empty] | Not Started | D-R-065 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | AC-R-065 | E-R-065 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-066-01 | A-R-066 | WPS-16 | Obtain and control source evidence: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Health clearance evidence; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-065-03 | Finish-to-Start | T-R-066-02 | [5 empty] | Not Started | D-R-066 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | AC-R-066 | E-R-066 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-066-02 | A-R-066 | WPS-16 | Verify applicability and technical sufficiency: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Health clearance evidence; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-066-01 | Finish-to-Start | T-R-066-03 | [5 empty] | Not Started | D-R-066 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | AC-R-066 | E-R-066 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-066-03 | A-R-066 | WPS-16 | Issue acceptance or escalation record: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Health clearance evidence; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-066-02 | Finish-to-Start | T-R-067-01 | [5 empty] | Not Started | D-R-066 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | AC-R-066 | E-R-066 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-067-01 | A-R-067 | WPS-16 | Obtain and control source evidence: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Agent/service approvals; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-066-03 | Finish-to-Start | T-R-067-02 | [5 empty] | Not Started | D-R-067 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | AC-R-067 | E-R-067 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-067-02 | A-R-067 | WPS-16 | Verify applicability and technical sufficiency: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Agent/service approvals; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-067-01 | Finish-to-Start | T-R-067-03 | [5 empty] | Not Started | D-R-067 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | AC-R-067 | E-R-067 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-067-03 | A-R-067 | WPS-16 | Issue acceptance or escalation record: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Agent/service approvals; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-067-02 | Finish-to-Start | T-R-068-01 | [5 empty] | Not Started | D-R-067 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | AC-R-067 | E-R-067 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-068-01 | A-R-068 | WPS-16 | Obtain and control source evidence: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Security applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-067-03 | Finish-to-Start | T-R-068-02 | [5 empty] | Not Started | D-R-068 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | AC-R-068 | E-R-068 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-068-02 | A-R-068 | WPS-16 | Verify applicability and technical sufficiency: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Security applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-068-01 | Finish-to-Start | T-R-068-03 | [5 empty] | Not Started | D-R-068 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | AC-R-068 | E-R-068 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-068-03 | A-R-068 | WPS-16 | Issue acceptance or escalation record: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Security applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-068-02 | Finish-to-Start | T-R-069-01 | [5 empty] | Not Started | D-R-068 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | AC-R-068 | E-R-068 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-069-01 | A-R-069 | WPS-16 | Obtain and control source evidence: Determine ISM applicability and required interface; do not assume applicability. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | ISM applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-068-03 | Finish-to-Start | T-R-069-02 | [5 empty] | Not Started | D-R-069 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISM applicability and required interface; do not assume applicability. | AC-R-069 | E-R-069 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-069-02 | A-R-069 | WPS-16 | Verify applicability and technical sufficiency: Determine ISM applicability and required interface; do not assume applicability. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | ISM applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-069-01 | Finish-to-Start | T-R-069-03 | [5 empty] | Not Started | D-R-069 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISM applicability and required interface; do not assume applicability. | AC-R-069 | E-R-069 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-069-03 | A-R-069 | WPS-16 | Issue acceptance or escalation record: Determine ISM applicability and required interface; do not assume applicability. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | ISM applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-069-02 | Finish-to-Start | T-R-070-01 | [5 empty] | Not Started | D-R-069 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISM applicability and required interface; do not assume applicability. | AC-R-069 | E-R-069 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-070-01 | A-R-070 | WPS-16 | Obtain and control source evidence: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Certificates + JMA recognition; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-069-03 | Finish-to-Start | T-R-070-02 | [5 empty] | Not Started | D-R-070 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | AC-R-070 | E-R-070 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-070-02 | A-R-070 | WPS-16 | Verify applicability and technical sufficiency: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Certificates + JMA recognition; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-070-01 | Finish-to-Start | T-R-070-03 | [5 empty] | Not Started | D-R-070 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | AC-R-070 | E-R-070 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-070-03 | A-R-070 | WPS-16 | Issue acceptance or escalation record: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Certificates + JMA recognition; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-070-02 | Finish-to-Start | T-R-071-01 | [5 empty] | Not Started | D-R-070 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | AC-R-070 | E-R-070 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-071-01 | A-R-071 | WPS-09 | Obtain and control source evidence: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | BWM certificate/records where applicable; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-070-03 | Finish-to-Start | T-R-071-02 | [5 empty] | Not Started | D-R-071 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | AC-R-071 | E-R-071 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-071-02 | A-R-071 | WPS-09 | Verify applicability and technical sufficiency: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | BWM certificate/records where applicable; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-071-01 | Finish-to-Start | T-R-071-03 | [5 empty] | Not Started | D-R-071 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | AC-R-071 | E-R-071 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-071-03 | A-R-071 | WPS-09 | Issue acceptance or escalation record: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | BWM certificate/records where applicable; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-071-02 | Finish-to-Start | T-R-072-01 | [5 empty] | Not Started | D-R-071 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | AC-R-071 | E-R-071 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-072-01 | A-R-072 | WPS-14 | Obtain and control source evidence: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Certificates/test records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-071-03 | Finish-to-Start | T-R-072-02 | [5 empty] | Not Started | D-R-072 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | AC-R-072 | E-R-072 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-072-02 | A-R-072 | WPS-14 | Verify applicability and technical sufficiency: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Certificates/test records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-072-01 | Finish-to-Start | T-R-072-03 | [5 empty] | Not Started | D-R-072 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | AC-R-072 | E-R-072 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-072-03 | A-R-072 | WPS-14 | Issue acceptance or escalation record: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Certificates/test records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-072-02 | Finish-to-Start | T-R-073-01 | [5 empty] | Not Started | D-R-072 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | AC-R-072 | E-R-072 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-073-01 | A-R-073 | WPS-14 | Obtain and control source evidence: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Pilot/tug/VTS arrangements; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-072-03 | Finish-to-Start | T-R-073-02 | [5 empty] | Not Started | D-R-073 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | AC-R-073 | E-R-073 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-073-02 | A-R-073 | WPS-14 | Verify applicability and technical sufficiency: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Pilot/tug/VTS arrangements; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-073-01 | Finish-to-Start | T-R-073-03 | [5 empty] | Not Started | D-R-073 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | AC-R-073 | E-R-073 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-073-03 | A-R-073 | WPS-14 | Issue acceptance or escalation record: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Pilot/tug/VTS arrangements; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-073-02 | Finish-to-Start | T-R-074-01 | [5 empty] | Not Started | D-R-073 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | AC-R-073 | E-R-073 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-074-01 | A-R-074 | WPS-16 | Obtain and control source evidence: Establish casualty/incident reporting requirements for events in Jordanian waters. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Reporting procedure/contact matrix; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-073-03 | Finish-to-Start | T-R-074-02 | [5 empty] | Not Started | D-R-074 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish casualty/incident reporting requirements for events in Jordanian waters. | AC-R-074 | E-R-074 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-074-02 | A-R-074 | WPS-16 | Verify applicability and technical sufficiency: Establish casualty/incident reporting requirements for events in Jordanian waters. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Reporting procedure/contact matrix; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-074-01 | Finish-to-Start | T-R-074-03 | [5 empty] | Not Started | D-R-074 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish casualty/incident reporting requirements for events in Jordanian waters. | AC-R-074 | E-R-074 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-074-03 | A-R-074 | WPS-16 | Issue acceptance or escalation record: Establish casualty/incident reporting requirements for events in Jordanian waters. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Reporting procedure/contact matrix; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-074-02 | Finish-to-Start | T-R-075-01 | [5 empty] | Not Started | D-R-074 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish casualty/incident reporting requirements for events in Jordanian waters. | AC-R-074 | E-R-074 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-075-01 | A-R-075 | WPS-09 | Obtain and control source evidence: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Official boundary + permit/control assessment; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-074-03 | Finish-to-Start | T-R-075-02 | [5 empty] | Not Started | D-R-075 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | AC-R-075 | E-R-075 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-075-02 | A-R-075 | WPS-09 | Verify applicability and technical sufficiency: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Official boundary + permit/control assessment; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-075-01 | Finish-to-Start | T-R-075-03 | [5 empty] | Not Started | D-R-075 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | AC-R-075 | E-R-075 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-075-03 | A-R-075 | WPS-09 | Issue acceptance or escalation record: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Official boundary + permit/control assessment; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-075-02 | Finish-to-Start | T-R-076-01 | [5 empty] | Not Started | D-R-075 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | AC-R-075 | E-R-075 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-076-01 | A-R-076 | WPS-09 | Obtain and control source evidence: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | ASEZA environmental requirements/permits; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-075-03 | Finish-to-Start | T-R-076-02 | [5 empty] | Not Started | D-R-076 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | AC-R-076 | E-R-076 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-076-02 | A-R-076 | WPS-09 | Verify applicability and technical sufficiency: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | ASEZA environmental requirements/permits; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-076-01 | Finish-to-Start | T-R-076-03 | [5 empty] | Not Started | D-R-076 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | AC-R-076 | E-R-076 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-076-03 | A-R-076 | WPS-09 | Issue acceptance or escalation record: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | ASEZA environmental requirements/permits; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-076-02 | Finish-to-Start | T-R-077-01 | [5 empty] | Not Started | D-R-076 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | AC-R-076 | E-R-076 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-077-01 | A-R-077 | WPS-09 | Obtain and control source evidence: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Garbage/oil/sewage/waste records; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-076-03 | Finish-to-Start | T-R-077-02 | [5 empty] | Not Started | D-R-077 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | AC-R-077 | E-R-077 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-077-02 | A-R-077 | WPS-09 | Verify applicability and technical sufficiency: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Garbage/oil/sewage/waste records; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-077-01 | Finish-to-Start | T-R-077-03 | [5 empty] | Not Started | D-R-077 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | AC-R-077 | E-R-077 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-077-03 | A-R-077 | WPS-09 | Issue acceptance or escalation record: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Garbage/oil/sewage/waste records; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-077-02 | Finish-to-Start | T-R-078-01 | [5 empty] | Not Started | D-R-077 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | AC-R-077 | E-R-077 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-078-01 | A-R-078 | WPS-09 | Obtain and control source evidence: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | SOPEP/SMPEP as applicable + project spill plan; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-077-03 | Finish-to-Start | T-R-078-02 | [5 empty] | Not Started | D-R-078 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | AC-R-078 | E-R-078 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-078-02 | A-R-078 | WPS-09 | Verify applicability and technical sufficiency: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | SOPEP/SMPEP as applicable + project spill plan; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-078-01 | Finish-to-Start | T-R-078-03 | [5 empty] | Not Started | D-R-078 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | AC-R-078 | E-R-078 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-078-03 | A-R-078 | WPS-09 | Issue acceptance or escalation record: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | SOPEP/SMPEP as applicable + project spill plan; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-078-02 | Finish-to-Start | T-R-079-01 | [5 empty] | Not Started | D-R-078 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | AC-R-078 | E-R-078 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-079-01 | A-R-079 | WPS-16 | Obtain and control source evidence: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Agent checklist + customs/immigration clearance; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-078-03 | Finish-to-Start | T-R-079-02 | [5 empty] | Not Started | D-R-079 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | AC-R-079 | E-R-079 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-079-02 | A-R-079 | WPS-16 | Verify applicability and technical sufficiency: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Agent checklist + customs/immigration clearance; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-079-01 | Finish-to-Start | T-R-079-03 | [5 empty] | Not Started | D-R-079 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | AC-R-079 | E-R-079 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-079-03 | A-R-079 | WPS-16 | Issue acceptance or escalation record: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Agent checklist + customs/immigration clearance; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Written authority/agent evidence identifies the applicable requirement, approval/permit/certificate, validity and outstanding conditions; no acceptance is inferred from generic/public information. | T-R-079-02 | Finish-to-Start | T-R-080-01 | [5 empty] | Not Started | D-R-079 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | AC-R-079 | E-R-079 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-080-01 | A-R-080 | WPS-01 | Obtain and control source evidence: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | IACS-to-DNV applicability matrix; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-079-03 | Finish-to-Start | T-R-080-02 | [5 empty] | Not Started | D-R-080 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | AC-R-080 | E-R-080 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-080-02 | A-R-080 | WPS-01 | Verify applicability and technical sufficiency: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | IACS-to-DNV applicability matrix; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-080-01 | Finish-to-Start | T-R-080-03 | [5 empty] | Not Started | D-R-080 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | AC-R-080 | E-R-080 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-080-03 | A-R-080 | WPS-01 | Issue acceptance or escalation record: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | IACS-to-DNV applicability matrix; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-080-02 | Finish-to-Start | T-R-081-01 | [5 empty] | Not Started | D-R-080 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | AC-R-080 | E-R-080 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-081-01 | A-R-081 | WPS-02 | Obtain and control source evidence: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Applicability decision; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-080-03 | Finish-to-Start | T-R-081-02 | [5 empty] | Not Started | D-R-081 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | AC-R-081 | E-R-081 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-081-02 | A-R-081 | WPS-02 | Verify applicability and technical sufficiency: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Applicability decision; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-081-01 | Finish-to-Start | T-R-081-03 | [5 empty] | Not Started | D-R-081 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | AC-R-081 | E-R-081 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-081-03 | A-R-081 | WPS-02 | Issue acceptance or escalation record: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Applicability decision; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-081-02 | Finish-to-Start | T-R-082-01 | [5 empty] | Not Started | D-R-081 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | AC-R-081 | E-R-081 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-082-01 | A-R-082 | WPS-01 | Obtain and control source evidence: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Rule cross-reference; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-081-03 | Finish-to-Start | T-R-082-02 | [5 empty] | Not Started | D-R-082 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | AC-R-082 | E-R-082 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-082-02 | A-R-082 | WPS-01 | Verify applicability and technical sufficiency: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Rule cross-reference; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-082-01 | Finish-to-Start | T-R-082-03 | [5 empty] | Not Started | D-R-082 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | AC-R-082 | E-R-082 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-082-03 | A-R-082 | WPS-01 | Issue acceptance or escalation record: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Rule cross-reference; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Applicable IACS material is mapped to the governing DNV/class or project basis with a documented disposition; no IACS item is treated as independent statutory authority. | T-R-082-02 | Finish-to-Start | T-R-083-01 | [5 empty] | Not Started | D-R-082 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | AC-R-082 | E-R-082 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-083-01 | A-R-083 | WPS-01 | Obtain and control source evidence: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Contract/specification; project/contract specification, applicable standard list/revision, required clause/section, applicability decision and client/MWS acceptance. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-082-03 | Finish-to-Start | T-R-083-02 | [5 empty] | Not Started | D-R-083 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | AC-R-083 | E-R-083 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-083-02 | A-R-083 | WPS-01 | Verify applicability and technical sufficiency: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Contract/specification; project/contract specification, applicable standard list/revision, required clause/section, applicability decision and client/MWS acceptance. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-083-01 | Finish-to-Start | T-R-083-03 | [5 empty] | Not Started | D-R-083 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | AC-R-083 | E-R-083 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-083-03 | A-R-083 | WPS-01 | Issue acceptance or escalation record: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Contract/specification; project/contract specification, applicable standard list/revision, required clause/section, applicability decision and client/MWS acceptance. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-083-02 | Finish-to-Start | T-R-084-01 | [5 empty] | Not Started | D-R-083 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | AC-R-083 | E-R-083 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-084-01 | A-R-084 | WPS-13 | Obtain and control source evidence: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | OEM manuals/records; OEM manual, serial/configuration confirmation, mandatory limits, maintenance/test instructions and technical bulletins. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-083-03 | Finish-to-Start | T-R-084-02 | [5 empty] | Not Started | D-R-084 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | AC-R-084 | E-R-084 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-084-02 | A-R-084 | WPS-13 | Verify applicability and technical sufficiency: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | OEM manuals/records; OEM manual, serial/configuration confirmation, mandatory limits, maintenance/test instructions and technical bulletins. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-084-01 | Finish-to-Start | T-R-084-03 | [5 empty] | Not Started | D-R-084 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | AC-R-084 | E-R-084 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-084-03 | A-R-084 | WPS-13 | Issue acceptance or escalation record: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | OEM manuals/records; OEM manual, serial/configuration confirmation, mandatory limits, maintenance/test instructions and technical bulletins. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-084-02 | Finish-to-Start | T-R-085-01 | [5 empty] | Not Started | D-R-084 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | AC-R-084 | E-R-084 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-085-01 | A-R-085 | WPS-11 | Obtain and control source evidence: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Controlled client/MWS requirement register; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | T-R-084-03 | Finish-to-Start | T-R-085-02 | [5 empty] | Not Started | D-R-085 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | AC-R-085 | E-R-085 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-085-02 | A-R-085 | WPS-11 | Verify applicability and technical sufficiency: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Controlled client/MWS requirement register; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | T-R-085-01 | Finish-to-Start | T-R-085-03 | [5 empty] | Not Started | D-R-085 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | AC-R-085 | E-R-085 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-085-03 | A-R-085 | WPS-11 | Issue acceptance or escalation record: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Controlled client/MWS requirement register; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Contract/MWS/client requirements are controlled, each hold point has a named authority, and signed/traceable acceptance records exist. | T-R-085-02 | Finish-to-Start | T-R-086-01 | [5 empty] | Not Started | D-R-085 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | AC-R-085 | E-R-085 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-086-01 | A-R-086 | WPS-09 | Obtain and control source evidence: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Verified site data package; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-085-03 | Finish-to-Start | T-R-086-02 | [5 empty] | Not Started | D-R-086 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | AC-R-086 | E-R-086 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-086-02 | A-R-086 | WPS-09 | Verify applicability and technical sufficiency: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Verified site data package; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-086-01 | Finish-to-Start | T-R-086-03 | [5 empty] | Not Started | D-R-086 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | AC-R-086 | E-R-086 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-086-03 | A-R-086 | WPS-09 | Issue acceptance or escalation record: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Verified site data package; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Authorized site/environmental basis and applicable permits/controls are documented; boundaries/restrictions, pollution controls and emergency/reporting interfaces are defined. | T-R-086-02 | Finish-to-Start | T-R-087-01 | [5 empty] | Not Started | D-R-086 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | AC-R-086 | E-R-086 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-087-01 | A-R-087 | WPS-16 | Obtain and control source evidence: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Evidence request/status record; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-086-03 | Finish-to-Start | T-R-087-02 | [5 empty] | Not Started | D-R-087 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | AC-R-087 | E-R-087 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-087-02 | A-R-087 | WPS-16 | Verify applicability and technical sufficiency: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Evidence request/status record; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-087-01 | Finish-to-Start | T-R-087-03 | [5 empty] | Not Started | D-R-087 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | AC-R-087 | E-R-087 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-087-03 | A-R-087 | WPS-16 | Issue acceptance or escalation record: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Evidence request/status record; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Requested record is identified by owner/source, revision/date and validity; verification result and reviewer are recorded and any exception has a documented disposition. | T-R-087-02 | Finish-to-Start | T-R-088-01 | [5 empty] | Not Started | D-R-087 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | AC-R-087 | E-R-087 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-088-01 | A-R-088 | WPS-02 | Obtain and control source evidence: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; certificate validity, Flag delegation/RO basis, exemptions/dispensations, survey status, manning/safety/pollution certificates and foreign-port requirements. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-087-03 | Finish-to-Start | T-R-088-02 | [5 empty] | Not Started | D-R-088 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | AC-R-088 | E-R-088 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-088-02 | A-R-088 | WPS-02 | Verify applicability and technical sufficiency: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; certificate validity, Flag delegation/RO basis, exemptions/dispensations, survey status, manning/safety/pollution certificates and foreign-port requirements. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-088-01 | Finish-to-Start | T-R-088-03 | [5 empty] | Not Started | D-R-088 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | AC-R-088 | E-R-088 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-088-03 | A-R-088 | WPS-02 | Issue acceptance or escalation record: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; certificate validity, Flag delegation/RO basis, exemptions/dispensations, survey status, manning/safety/pollution certificates and foreign-port requirements. | PMS-11 identity, applicability, authority, exact reference/edition where available, certificate/status, restrictions and unresolved conditions are explicitly recorded and traceable to the competent authority decision. | T-R-088-02 | Finish-to-Start | T-R-089-01 | [5 empty] | Not Started | D-R-088 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | AC-R-088 | E-R-088 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-089-01 | A-R-089 | WPS-02 | Obtain and control source evidence: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Obtain the identified source evidence, record revision/date/owner and place it under document control. | 01 | Rule/WPS owner to be assigned | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; approved GA/structural drawings, stability booklet, loading manual, load-line evidence where applicable, thickness/condition records and operating restrictions. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-088-03 | Finish-to-Start | T-R-089-02 | [5 empty] | Not Started | D-R-089 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | AC-R-089 | E-R-089 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-089-02 | A-R-089 | WPS-02 | Verify applicability and technical sufficiency: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Review identity, scope, applicability, limitations and exact reference; record unresolved matters as information gaps. | 02 | Rule/WPS owner to be assigned | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; approved GA/structural drawings, stability booklet, loading manual, load-line evidence where applicable, thickness/condition records and operating restrictions. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-089-01 | Finish-to-Start | T-R-089-03 | [5 empty] | Not Started | D-R-089 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | AC-R-089 | E-R-089 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-R-089-03 | A-R-089 | WPS-02 | Issue acceptance or escalation record: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Issue the acceptance, rejection, conditional acceptance or escalation record with authority, restrictions and evidence links. | 03 | Rule/WPS owner to be assigned | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; approved GA/structural drawings, stability booklet, loading manual, load-line evidence where applicable, thickness/condition records and operating restrictions. | Identity/configuration matches controlled records; required certificates/tests/analysis are current or formally dispositioned; operating limits are documented; material discrepancies are closed or accepted by the competent authority. | T-R-089-02 | Finish-to-Start | GATE-8 | [5 empty] | Not Started | D-R-089 | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | AC-R-089 | E-R-089 | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | No actual dates assigned. Evidence-dependent closure only.
T-S-17-01-01 | A-S-17-01 | WPS-17 | Prepare / obtain inputs — Obtain formal DNV suspension notice, class status and violation summary | Collect, authenticate and control the inputs required to execute Obtain formal DNV suspension notice, class status and violation summary; identify applicability and unresolved authority questions. | 01 | Class Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Obtain formal DNV suspension notice, class status and violation summary |  | Finish-to-Start | T-S-17-01-02 | [5 empty] | Not Started | D-S-17-01 | G-S-17-01 | AC-S-17-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-17-01-02 | A-S-17-01 | WPS-17 | Verify / close — Obtain formal DNV suspension notice, class status and violation summary | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Class Manager | Inputs and deliverable for Obtain formal DNV suspension notice, class status and violation summary | Verified and dispositioned Obtain formal DNV suspension notice, class status and violation summary | T-S-17-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-17-01 | G-S-17-01 | AC-S-17-01 | E-S-17-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-17-02-01 | A-S-17-02 | WPS-17 | Prepare / obtain inputs — Agree DNV reinstatement survey scope and attendance plan | Collect, authenticate and control the inputs required to execute Agree DNV reinstatement survey scope and attendance plan; identify applicability and unresolved authority questions. | 01 | Class Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Agree DNV reinstatement survey scope and attendance plan |  | Finish-to-Start | T-S-17-02-02 | [5 empty] | Not Started | D-S-17-02 | G-S-17-02 | AC-S-17-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-17-02-02 | A-S-17-02 | WPS-17 | Verify / close — Agree DNV reinstatement survey scope and attendance plan | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Class Manager | Inputs and deliverable for Agree DNV reinstatement survey scope and attendance plan | Verified and dispositioned Agree DNV reinstatement survey scope and attendance plan | T-S-17-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-17-02 | G-S-17-02 | AC-S-17-02 | E-S-17-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-17-03-01 | A-S-17-03 | WPS-17 | Prepare / obtain inputs — Complete hull, machinery, electrical and statutory condition assessment | Collect, authenticate and control the inputs required to execute Complete hull, machinery, electrical and statutory condition assessment; identify applicability and unresolved authority questions. | 01 | Technical Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Complete hull, machinery, electrical and statutory condition assessment |  | Finish-to-Start | T-S-17-03-02 | [5 empty] | Not Started | D-S-17-03 | G-S-17-03 | AC-S-17-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-17-03-02 | A-S-17-03 | WPS-17 | Verify / close — Complete hull, machinery, electrical and statutory condition assessment | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Technical Superintendent | Inputs and deliverable for Complete hull, machinery, electrical and statutory condition assessment | Verified and dispositioned Complete hull, machinery, electrical and statutory condition assessment | T-S-17-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-17-03 | G-S-17-03 | AC-S-17-03 | E-S-17-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-17-04-01 | A-S-17-04 | WPS-17 | Prepare / obtain inputs — Execute repairs, tests and survey closeout | Collect, authenticate and control the inputs required to execute Execute repairs, tests and survey closeout; identify applicability and unresolved authority questions. | 01 | Project Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Execute repairs, tests and survey closeout |  | Finish-to-Start | T-S-17-04-02 | [5 empty] | Not Started | D-S-17-04 | G-S-17-04 | AC-S-17-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-17-04-02 | A-S-17-04 | WPS-17 | Verify / close — Execute repairs, tests and survey closeout | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Project Manager | Inputs and deliverable for Execute repairs, tests and survey closeout | Verified and dispositioned Execute repairs, tests and survey closeout | T-S-17-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-17-04 | G-S-17-04 | AC-S-17-04 | E-S-17-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-17-05-01 | A-S-17-05 | WPS-17 | Prepare / obtain inputs — Receive formal DNV reinstatement decision and updated class status | Collect, authenticate and control the inputs required to execute Receive formal DNV reinstatement decision and updated class status; identify applicability and unresolved authority questions. | 01 | Class Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Receive formal DNV reinstatement decision and updated class status |  | Finish-to-Start | T-S-17-05-02 | [5 empty] | Not Started | D-S-17-05 | G-S-17-05 | AC-S-17-05 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-17-05-02 | A-S-17-05 | WPS-17 | Verify / close — Receive formal DNV reinstatement decision and updated class status | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Class Manager | Inputs and deliverable for Receive formal DNV reinstatement decision and updated class status | Verified and dispositioned Receive formal DNV reinstatement decision and updated class status | T-S-17-05-01 | Finish-to-Start | [6 empty] | Not Started | D-S-17-05 | G-S-17-05 | AC-S-17-05 | E-S-17-05 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-18-01-01 | A-S-18-01 | WPS-18 | Prepare / obtain inputs — Issue neutral request for information to candidate IACS societies | Collect, authenticate and control the inputs required to execute Issue neutral request for information to candidate IACS societies; identify applicability and unresolved authority questions. | 01 | Class Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Issue neutral request for information to candidate IACS societies |  | Finish-to-Start | T-S-18-01-02 | [5 empty] | Not Started | D-S-18-01 | G-S-18-01 | AC-S-18-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-18-01-02 | A-S-18-01 | WPS-18 | Verify / close — Issue neutral request for information to candidate IACS societies | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Class Manager | Inputs and deliverable for Issue neutral request for information to candidate IACS societies | Verified and dispositioned Issue neutral request for information to candidate IACS societies | T-S-18-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-18-01 | G-S-18-01 | AC-S-18-01 | E-S-18-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-18-02-01 | A-S-18-02 | WPS-18 | Prepare / obtain inputs — Prepare transfer technical dossier and disclosure register | Collect, authenticate and control the inputs required to execute Prepare transfer technical dossier and disclosure register; identify applicability and unresolved authority questions. | 01 | Class Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Prepare transfer technical dossier and disclosure register |  | Finish-to-Start | T-S-18-02-02 | [5 empty] | Not Started | D-S-18-02 | G-S-18-02 | AC-S-18-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-18-02-02 | A-S-18-02 | WPS-18 | Verify / close — Prepare transfer technical dossier and disclosure register | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Class Manager | Inputs and deliverable for Prepare transfer technical dossier and disclosure register | Verified and dispositioned Prepare transfer technical dossier and disclosure register | T-S-18-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-18-02 | G-S-18-02 | AC-S-18-02 | E-S-18-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-18-03-01 | A-S-18-03 | WPS-18 | Prepare / obtain inputs — Perform comparative gap, cost and schedule assessment | Collect, authenticate and control the inputs required to execute Perform comparative gap, cost and schedule assessment; identify applicability and unresolved authority questions. | 01 | Project Controls Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Perform comparative gap, cost and schedule assessment |  | Finish-to-Start | T-S-18-03-02 | [5 empty] | Not Started | D-S-18-03 | G-S-18-03 | AC-S-18-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-18-03-02 | A-S-18-03 | WPS-18 | Verify / close — Perform comparative gap, cost and schedule assessment | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Project Controls Manager | Inputs and deliverable for Perform comparative gap, cost and schedule assessment | Verified and dispositioned Perform comparative gap, cost and schedule assessment | T-S-18-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-18-03 | G-S-18-03 | AC-S-18-03 | E-S-18-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-18-04-01 | A-S-18-04 | WPS-18 | Prepare / obtain inputs — Record management and authority path decision | Collect, authenticate and control the inputs required to execute Record management and authority path decision; identify applicability and unresolved authority questions. | 01 | Project Director | Controlled source documents / equipment records / approved basis | Controlled input pack for Record management and authority path decision |  | Finish-to-Start | T-S-18-04-02 | [5 empty] | Not Started | D-S-18-04 | G-S-18-04 | AC-S-18-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-18-04-02 | A-S-18-04 | WPS-18 | Verify / close — Record management and authority path decision | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Project Director | Inputs and deliverable for Record management and authority path decision | Verified and dispositioned Record management and authority path decision | T-S-18-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-18-04 | G-S-18-04 | AC-S-18-04 | E-S-18-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-18-05-01 | A-S-18-05 | WPS-18 | Prepare / obtain inputs — If selected, complete transfer surveys and obtain certificate | Collect, authenticate and control the inputs required to execute If selected, complete transfer surveys and obtain certificate; identify applicability and unresolved authority questions. | 01 | Class Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for If selected, complete transfer surveys and obtain certificate |  | Finish-to-Start | T-S-18-05-02 | [5 empty] | Not Started | D-S-18-05 | G-S-18-05 | AC-S-18-05 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-18-05-02 | A-S-18-05 | WPS-18 | Verify / close — If selected, complete transfer surveys and obtain certificate | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Class Manager | Inputs and deliverable for If selected, complete transfer surveys and obtain certificate | Verified and dispositioned If selected, complete transfer surveys and obtain certificate | T-S-18-05-01 | Finish-to-Start | [6 empty] | Not Started | D-S-18-05 | G-S-18-05 | AC-S-18-05 | E-S-18-05 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-19-01-01 | A-S-19-01 | WPS-19 | Prepare / obtain inputs — Confirm helideck status, intended aircraft and authority jurisdiction | Collect, authenticate and control the inputs required to execute Confirm helideck status, intended aircraft and authority jurisdiction; identify applicability and unresolved authority questions. | 01 | Aviation Coordinator | Controlled source documents / equipment records / approved basis | Controlled input pack for Confirm helideck status, intended aircraft and authority jurisdiction |  | Finish-to-Start | T-S-19-01-02 | [5 empty] | Not Started | D-S-19-01 | G-S-19-01 | AC-S-19-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-19-01-02 | A-S-19-01 | WPS-19 | Verify / close — Confirm helideck status, intended aircraft and authority jurisdiction | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Aviation Coordinator | Inputs and deliverable for Confirm helideck status, intended aircraft and authority jurisdiction | Verified and dispositioned Confirm helideck status, intended aircraft and authority jurisdiction | T-S-19-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-19-01 | G-S-19-01 | AC-S-19-01 | E-S-19-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-19-02-01 | A-S-19-02 | WPS-19 | Prepare / obtain inputs — Review helideck structural, obstacle, marking, lighting and access basis | Collect, authenticate and control the inputs required to execute Review helideck structural, obstacle, marking, lighting and access basis; identify applicability and unresolved authority questions. | 01 | Aviation Coordinator | Controlled source documents / equipment records / approved basis | Controlled input pack for Review helideck structural, obstacle, marking, lighting and access basis |  | Finish-to-Start | T-S-19-02-02 | [5 empty] | Not Started | D-S-19-02 | G-S-19-02 | AC-S-19-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-19-02-02 | A-S-19-02 | WPS-19 | Verify / close — Review helideck structural, obstacle, marking, lighting and access basis | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Aviation Coordinator | Inputs and deliverable for Review helideck structural, obstacle, marking, lighting and access basis | Verified and dispositioned Review helideck structural, obstacle, marking, lighting and access basis | T-S-19-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-19-02 | G-S-19-02 | AC-S-19-02 | E-S-19-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-19-03-01 | A-S-19-03 | WPS-19 | Prepare / obtain inputs — Review flight operations and marine-aviation interface manual | Collect, authenticate and control the inputs required to execute Review flight operations and marine-aviation interface manual; identify applicability and unresolved authority questions. | 01 | Aviation Coordinator | Controlled source documents / equipment records / approved basis | Controlled input pack for Review flight operations and marine-aviation interface manual |  | Finish-to-Start | T-S-19-03-02 | [5 empty] | Not Started | D-S-19-03 | G-S-19-03 | AC-S-19-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-19-03-02 | A-S-19-03 | WPS-19 | Verify / close — Review flight operations and marine-aviation interface manual | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Aviation Coordinator | Inputs and deliverable for Review flight operations and marine-aviation interface manual | Verified and dispositioned Review flight operations and marine-aviation interface manual | T-S-19-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-19-03 | G-S-19-03 | AC-S-19-03 | E-S-19-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-19-04-01 | A-S-19-04 | WPS-19 | Prepare / obtain inputs — Verify helideck firefighting, rescue, PPE and trained team | Collect, authenticate and control the inputs required to execute Verify helideck firefighting, rescue, PPE and trained team; identify applicability and unresolved authority questions. | 01 | HSE Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Verify helideck firefighting, rescue, PPE and trained team |  | Finish-to-Start | T-S-19-04-02 | [5 empty] | Not Started | D-S-19-04 | G-S-19-04 | AC-S-19-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-19-04-02 | A-S-19-04 | WPS-19 | Verify / close — Verify helideck firefighting, rescue, PPE and trained team | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | HSE Manager | Inputs and deliverable for Verify helideck firefighting, rescue, PPE and trained team | Verified and dispositioned Verify helideck firefighting, rescue, PPE and trained team | T-S-19-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-19-04 | G-S-19-04 | AC-S-19-04 | E-S-19-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-19-05-01 | A-S-19-05 | WPS-19 | Prepare / obtain inputs — Secure required operational permissions and acceptance evidence | Collect, authenticate and control the inputs required to execute Secure required operational permissions and acceptance evidence; identify applicability and unresolved authority questions. | 01 | Aviation Coordinator | Controlled source documents / equipment records / approved basis | Controlled input pack for Secure required operational permissions and acceptance evidence |  | Finish-to-Start | T-S-19-05-02 | [5 empty] | Not Started | D-S-19-05 | G-S-19-05 | AC-S-19-05 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-19-05-02 | A-S-19-05 | WPS-19 | Verify / close — Secure required operational permissions and acceptance evidence | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Aviation Coordinator | Inputs and deliverable for Secure required operational permissions and acceptance evidence | Verified and dispositioned Secure required operational permissions and acceptance evidence | T-S-19-05-01 | Finish-to-Start | [6 empty] | Not Started | D-S-19-05 | G-S-19-05 | AC-S-19-05 | E-S-19-05 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-20-01-01 | A-S-20-01 | WPS-20 | Prepare / obtain inputs — Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Collect, authenticate and control the inputs required to execute Determine applicable fuel sulphur and emissions requirements for route and Aqaba; identify applicability and unresolved authority questions. | 01 | Environmental Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Determine applicable fuel sulphur and emissions requirements for route and Aqaba |  | Finish-to-Start | T-S-20-01-02 | [5 empty] | Not Started | D-S-20-01 | G-S-20-01 | AC-S-20-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-20-01-02 | A-S-20-01 | WPS-20 | Verify / close — Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Environmental Manager | Inputs and deliverable for Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Verified and dispositioned Determine applicable fuel sulphur and emissions requirements for route and Aqaba | T-S-20-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-20-01 | G-S-20-01 | AC-S-20-01 | E-S-20-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-20-02-01 | A-S-20-02 | WPS-20 | Prepare / obtain inputs — Verify BDN, fuel samples, changeover procedures and consumption plan | Collect, authenticate and control the inputs required to execute Verify BDN, fuel samples, changeover procedures and consumption plan; identify applicability and unresolved authority questions. | 01 | Chief Engineer | Controlled source documents / equipment records / approved basis | Controlled input pack for Verify BDN, fuel samples, changeover procedures and consumption plan |  | Finish-to-Start | T-S-20-02-02 | [5 empty] | Not Started | D-S-20-02 | G-S-20-02 | AC-S-20-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-20-02-02 | A-S-20-02 | WPS-20 | Verify / close — Verify BDN, fuel samples, changeover procedures and consumption plan | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Chief Engineer | Inputs and deliverable for Verify BDN, fuel samples, changeover procedures and consumption plan | Verified and dispositioned Verify BDN, fuel samples, changeover procedures and consumption plan | T-S-20-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-20-02 | G-S-20-02 | AC-S-20-02 | E-S-20-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-20-03-01 | A-S-20-03 | WPS-20 | Prepare / obtain inputs — Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Collect, authenticate and control the inputs required to execute Verify sludge, oily water, sewage and garbage capacity/disposal arrangements; identify applicability and unresolved authority questions. | 01 | Chief Engineer | Controlled source documents / equipment records / approved basis | Controlled input pack for Verify sludge, oily water, sewage and garbage capacity/disposal arrangements |  | Finish-to-Start | T-S-20-03-02 | [5 empty] | Not Started | D-S-20-03 | G-S-20-03 | AC-S-20-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-20-03-02 | A-S-20-03 | WPS-20 | Verify / close — Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Chief Engineer | Inputs and deliverable for Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Verified and dispositioned Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | T-S-20-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-20-03 | G-S-20-03 | AC-S-20-03 | E-S-20-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-20-04-01 | A-S-20-04 | WPS-20 | Prepare / obtain inputs — Commission potable-water and RO systems and obtain laboratory results | Collect, authenticate and control the inputs required to execute Commission potable-water and RO systems and obtain laboratory results; identify applicability and unresolved authority questions. | 01 | Chief Engineer | Controlled source documents / equipment records / approved basis | Controlled input pack for Commission potable-water and RO systems and obtain laboratory results |  | Finish-to-Start | T-S-20-04-02 | [5 empty] | Not Started | D-S-20-04 | G-S-20-04 | AC-S-20-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-20-04-02 | A-S-20-04 | WPS-20 | Verify / close — Commission potable-water and RO systems and obtain laboratory results | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Chief Engineer | Inputs and deliverable for Commission potable-water and RO systems and obtain laboratory results | Verified and dispositioned Commission potable-water and RO systems and obtain laboratory results | T-S-20-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-20-04 | G-S-20-04 | AC-S-20-04 | E-S-20-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-20-05-01 | A-S-20-05 | WPS-20 | Prepare / obtain inputs — Close spill prevention and waste contractor interfaces | Collect, authenticate and control the inputs required to execute Close spill prevention and waste contractor interfaces; identify applicability and unresolved authority questions. | 01 | Environmental Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Close spill prevention and waste contractor interfaces |  | Finish-to-Start | T-S-20-05-02 | [5 empty] | Not Started | D-S-20-05 | G-S-20-05 | AC-S-20-05 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-20-05-02 | A-S-20-05 | WPS-20 | Verify / close — Close spill prevention and waste contractor interfaces | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Environmental Manager | Inputs and deliverable for Close spill prevention and waste contractor interfaces | Verified and dispositioned Close spill prevention and waste contractor interfaces | T-S-20-05-01 | Finish-to-Start | [6 empty] | Not Started | D-S-20-05 | G-S-20-05 | AC-S-20-05 | E-S-20-05 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-21-01-01 | A-S-21-01 | WPS-21 | Prepare / obtain inputs — Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Collect, authenticate and control the inputs required to execute Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity; identify applicability and unresolved authority questions. | 01 | Maintenance Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity |  | Finish-to-Start | T-S-21-01-02 | [5 empty] | Not Started | D-S-21-01 | G-S-21-01 | AC-S-21-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-21-01-02 | A-S-21-01 | WPS-21 | Verify / close — Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Maintenance Superintendent | Inputs and deliverable for Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Verified and dispositioned Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | T-S-21-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-21-01 | G-S-21-01 | AC-S-21-01 | E-S-21-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-21-02-01 | A-S-21-02 | WPS-21 | Prepare / obtain inputs — Generate critical defect and overdue-maintenance backlog | Collect, authenticate and control the inputs required to execute Generate critical defect and overdue-maintenance backlog; identify applicability and unresolved authority questions. | 01 | Maintenance Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Generate critical defect and overdue-maintenance backlog |  | Finish-to-Start | T-S-21-02-02 | [5 empty] | Not Started | D-S-21-02 | G-S-21-02 | AC-S-21-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-21-02-02 | A-S-21-02 | WPS-21 | Verify / close — Generate critical defect and overdue-maintenance backlog | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Maintenance Superintendent | Inputs and deliverable for Generate critical defect and overdue-maintenance backlog | Verified and dispositioned Generate critical defect and overdue-maintenance backlog | T-S-21-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-21-02 | G-S-21-02 | AC-S-21-02 | E-S-21-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-21-03-01 | A-S-21-03 | WPS-21 | Prepare / obtain inputs — Map critical spares/materials to equipment and physically verify stock | Collect, authenticate and control the inputs required to execute Map critical spares/materials to equipment and physically verify stock; identify applicability and unresolved authority questions. | 01 | Stores Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Map critical spares/materials to equipment and physically verify stock |  | Finish-to-Start | T-S-21-03-02 | [5 empty] | Not Started | D-S-21-03 | G-S-21-03 | AC-S-21-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-21-03-02 | A-S-21-03 | WPS-21 | Verify / close — Map critical spares/materials to equipment and physically verify stock | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Stores Manager | Inputs and deliverable for Map critical spares/materials to equipment and physically verify stock | Verified and dispositioned Map critical spares/materials to equipment and physically verify stock | T-S-21-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-21-03 | G-S-21-03 | AC-S-21-03 | E-S-21-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-21-04-01 | A-S-21-04 | WPS-21 | Prepare / obtain inputs — Issue procurement plan for shortages and long-lead items | Collect, authenticate and control the inputs required to execute Issue procurement plan for shortages and long-lead items; identify applicability and unresolved authority questions. | 01 | Procurement Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Issue procurement plan for shortages and long-lead items |  | Finish-to-Start | T-S-21-04-02 | [5 empty] | Not Started | D-S-21-04 | G-S-21-04 | AC-S-21-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-21-04-02 | A-S-21-04 | WPS-21 | Verify / close — Issue procurement plan for shortages and long-lead items | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Procurement Manager | Inputs and deliverable for Issue procurement plan for shortages and long-lead items | Verified and dispositioned Issue procurement plan for shortages and long-lead items | T-S-21-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-21-04 | G-S-21-04 | AC-S-21-04 | E-S-21-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-21-05-01 | A-S-21-05 | WPS-21 | Prepare / obtain inputs — Back up CMMS database and approve mobilization maintenance baseline | Collect, authenticate and control the inputs required to execute Back up CMMS database and approve mobilization maintenance baseline; identify applicability and unresolved authority questions. | 01 | Maintenance Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Back up CMMS database and approve mobilization maintenance baseline |  | Finish-to-Start | T-S-21-05-02 | [5 empty] | Not Started | D-S-21-05 | G-S-21-05 | AC-S-21-05 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-21-05-02 | A-S-21-05 | WPS-21 | Verify / close — Back up CMMS database and approve mobilization maintenance baseline | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Maintenance Superintendent | Inputs and deliverable for Back up CMMS database and approve mobilization maintenance baseline | Verified and dispositioned Back up CMMS database and approve mobilization maintenance baseline | T-S-21-05-01 | Finish-to-Start | [6 empty] | Not Started | D-S-21-05 | G-S-21-05 | AC-S-21-05 | E-S-21-05 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-22-01-01 | A-S-22-01 | WPS-22 | Prepare / obtain inputs — Develop approved anchor pattern, deployment sequence and exclusion controls | Collect, authenticate and control the inputs required to execute Develop approved anchor pattern, deployment sequence and exclusion controls; identify applicability and unresolved authority questions. | 01 | Marine Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Develop approved anchor pattern, deployment sequence and exclusion controls |  | Finish-to-Start | T-S-22-01-02 | [5 empty] | Not Started | D-S-22-01 | G-S-22-01 | AC-S-22-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-22-01-02 | A-S-22-01 | WPS-22 | Verify / close — Develop approved anchor pattern, deployment sequence and exclusion controls | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Marine Superintendent | Inputs and deliverable for Develop approved anchor pattern, deployment sequence and exclusion controls | Verified and dispositioned Develop approved anchor pattern, deployment sequence and exclusion controls | T-S-22-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-22-01 | G-S-22-01 | AC-S-22-01 | E-S-22-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-22-02-01 | A-S-22-02 | WPS-22 | Prepare / obtain inputs — Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Collect, authenticate and control the inputs required to execute Verify control-room/APMS/DGPS/gyro displays, alarms and calibration; identify applicability and unresolved authority questions. | 01 | Survey Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Verify control-room/APMS/DGPS/gyro displays, alarms and calibration |  | Finish-to-Start | T-S-22-02-02 | [5 empty] | Not Started | D-S-22-02 | G-S-22-02 | AC-S-22-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-22-02-02 | A-S-22-02 | WPS-22 | Verify / close — Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Survey Manager | Inputs and deliverable for Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Verified and dispositioned Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | T-S-22-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-22-02 | G-S-22-02 | AC-S-22-02 | E-S-22-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-22-03-01 | A-S-22-03 | WPS-22 | Prepare / obtain inputs — Test winches, brakes, controls, communications and emergency release | Collect, authenticate and control the inputs required to execute Test winches, brakes, controls, communications and emergency release; identify applicability and unresolved authority questions. | 01 | Marine Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Test winches, brakes, controls, communications and emergency release |  | Finish-to-Start | T-S-22-03-02 | [5 empty] | Not Started | D-S-22-03 | G-S-22-03 | AC-S-22-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-22-03-02 | A-S-22-03 | WPS-22 | Verify / close — Test winches, brakes, controls, communications and emergency release | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Marine Superintendent | Inputs and deliverable for Test winches, brakes, controls, communications and emergency release | Verified and dispositioned Test winches, brakes, controls, communications and emergency release | T-S-22-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-22-03 | G-S-22-03 | AC-S-22-03 | E-S-22-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-22-04-01 | A-S-22-04 | WPS-22 | Prepare / obtain inputs — Approve tug assignment, command hierarchy and standard communications | Collect, authenticate and control the inputs required to execute Approve tug assignment, command hierarchy and standard communications; identify applicability and unresolved authority questions. | 01 | Marine Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Approve tug assignment, command hierarchy and standard communications |  | Finish-to-Start | T-S-22-04-02 | [5 empty] | Not Started | D-S-22-04 | G-S-22-04 | AC-S-22-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-22-04-02 | A-S-22-04 | WPS-22 | Verify / close — Approve tug assignment, command hierarchy and standard communications | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Marine Superintendent | Inputs and deliverable for Approve tug assignment, command hierarchy and standard communications | Verified and dispositioned Approve tug assignment, command hierarchy and standard communications | T-S-22-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-22-04 | G-S-22-04 | AC-S-22-04 | E-S-22-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-22-05-01 | A-S-22-05 | WPS-22 | Prepare / obtain inputs — Conduct anchor-handling tabletop and operational drill | Collect, authenticate and control the inputs required to execute Conduct anchor-handling tabletop and operational drill; identify applicability and unresolved authority questions. | 01 | Marine Superintendent | Controlled source documents / equipment records / approved basis | Controlled input pack for Conduct anchor-handling tabletop and operational drill |  | Finish-to-Start | T-S-22-05-02 | [5 empty] | Not Started | D-S-22-05 | G-S-22-05 | AC-S-22-05 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-22-05-02 | A-S-22-05 | WPS-22 | Verify / close — Conduct anchor-handling tabletop and operational drill | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Marine Superintendent | Inputs and deliverable for Conduct anchor-handling tabletop and operational drill | Verified and dispositioned Conduct anchor-handling tabletop and operational drill | T-S-22-05-01 | Finish-to-Start | [6 empty] | Not Started | D-S-22-05 | G-S-22-05 | AC-S-22-05 | E-S-22-05 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-23-01-01 | A-S-23-01 | WPS-23 | Prepare / obtain inputs — Approve departmental manpower, competency and rotation matrix | Collect, authenticate and control the inputs required to execute Approve departmental manpower, competency and rotation matrix; identify applicability and unresolved authority questions. | 01 | HR Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Approve departmental manpower, competency and rotation matrix |  | Finish-to-Start | T-S-23-01-02 | [5 empty] | Not Started | D-S-23-01 | G-S-23-01 | AC-S-23-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-23-01-02 | A-S-23-01 | WPS-23 | Verify / close — Approve departmental manpower, competency and rotation matrix | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | HR Manager | Inputs and deliverable for Approve departmental manpower, competency and rotation matrix | Verified and dispositioned Approve departmental manpower, competency and rotation matrix | T-S-23-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-23-01 | G-S-23-01 | AC-S-23-01 | E-S-23-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-23-02-01 | A-S-23-02 | WPS-23 | Prepare / obtain inputs — Verify clinic equipment, medicines, licenses and medevac interface | Collect, authenticate and control the inputs required to execute Verify clinic equipment, medicines, licenses and medevac interface; identify applicability and unresolved authority questions. | 01 | Medical Coordinator | Controlled source documents / equipment records / approved basis | Controlled input pack for Verify clinic equipment, medicines, licenses and medevac interface |  | Finish-to-Start | T-S-23-02-02 | [5 empty] | Not Started | D-S-23-02 | G-S-23-02 | AC-S-23-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-23-02-02 | A-S-23-02 | WPS-23 | Verify / close — Verify clinic equipment, medicines, licenses and medevac interface | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Medical Coordinator | Inputs and deliverable for Verify clinic equipment, medicines, licenses and medevac interface | Verified and dispositioned Verify clinic equipment, medicines, licenses and medevac interface | T-S-23-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-23-02 | G-S-23-02 | AC-S-23-02 | E-S-23-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-23-03-01 | A-S-23-03 | WPS-23 | Prepare / obtain inputs — Implement fatigue, rest-hour and drug/alcohol policy controls | Collect, authenticate and control the inputs required to execute Implement fatigue, rest-hour and drug/alcohol policy controls; identify applicability and unresolved authority questions. | 01 | HSE Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Implement fatigue, rest-hour and drug/alcohol policy controls |  | Finish-to-Start | T-S-23-03-02 | [5 empty] | Not Started | D-S-23-03 | G-S-23-03 | AC-S-23-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-23-03-02 | A-S-23-03 | WPS-23 | Verify / close — Implement fatigue, rest-hour and drug/alcohol policy controls | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | HSE Manager | Inputs and deliverable for Implement fatigue, rest-hour and drug/alcohol policy controls | Verified and dispositioned Implement fatigue, rest-hour and drug/alcohol policy controls | T-S-23-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-23-03 | G-S-23-03 | AC-S-23-03 | E-S-23-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-23-04-01 | A-S-23-04 | WPS-23 | Prepare / obtain inputs — Complete visas, travel, repatriation and crew-change logistics | Collect, authenticate and control the inputs required to execute Complete visas, travel, repatriation and crew-change logistics; identify applicability and unresolved authority questions. | 01 | HR Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Complete visas, travel, repatriation and crew-change logistics |  | Finish-to-Start | T-S-23-04-02 | [5 empty] | Not Started | D-S-23-04 | G-S-23-04 | AC-S-23-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-23-04-02 | A-S-23-04 | WPS-23 | Verify / close — Complete visas, travel, repatriation and crew-change logistics | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | HR Manager | Inputs and deliverable for Complete visas, travel, repatriation and crew-change logistics | Verified and dispositioned Complete visas, travel, repatriation and crew-change logistics | T-S-23-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-23-04 | G-S-23-04 | AC-S-23-04 | E-S-23-04 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-24-01-01 | A-S-24-01 | WPS-24 | Prepare / obtain inputs — Issue integrated emergency response and shore-interface matrix | Collect, authenticate and control the inputs required to execute Issue integrated emergency response and shore-interface matrix; identify applicability and unresolved authority questions. | 01 | HSE Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Issue integrated emergency response and shore-interface matrix |  | Finish-to-Start | T-S-24-01-02 | [5 empty] | Not Started | D-S-24-01 | G-S-24-01 | AC-S-24-01 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-24-01-02 | A-S-24-01 | WPS-24 | Verify / close — Issue integrated emergency response and shore-interface matrix | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | HSE Manager | Inputs and deliverable for Issue integrated emergency response and shore-interface matrix | Verified and dispositioned Issue integrated emergency response and shore-interface matrix | T-S-24-01-01 | Finish-to-Start | [6 empty] | Not Started | D-S-24-01 | G-S-24-01 | AC-S-24-01 | E-S-24-01 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-24-02-01 | A-S-24-02 | WPS-24 | Prepare / obtain inputs — Define scenario drill programme and measurable acceptance criteria | Collect, authenticate and control the inputs required to execute Define scenario drill programme and measurable acceptance criteria; identify applicability and unresolved authority questions. | 01 | HSE Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Define scenario drill programme and measurable acceptance criteria |  | Finish-to-Start | T-S-24-02-02 | [5 empty] | Not Started | D-S-24-02 | G-S-24-02 | AC-S-24-02 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-24-02-02 | A-S-24-02 | WPS-24 | Verify / close — Define scenario drill programme and measurable acceptance criteria | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | HSE Manager | Inputs and deliverable for Define scenario drill programme and measurable acceptance criteria | Verified and dispositioned Define scenario drill programme and measurable acceptance criteria | T-S-24-02-01 | Finish-to-Start | [6 empty] | Not Started | D-S-24-02 | G-S-24-02 | AC-S-24-02 | E-S-24-02 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-24-03-01 | A-S-24-03 | WPS-24 | Prepare / obtain inputs — Conduct marine, aviation, diving, pollution and medevac interface drills | Collect, authenticate and control the inputs required to execute Conduct marine, aviation, diving, pollution and medevac interface drills; identify applicability and unresolved authority questions. | 01 | Project Manager | Controlled source documents / equipment records / approved basis | Controlled input pack for Conduct marine, aviation, diving, pollution and medevac interface drills |  | Finish-to-Start | T-S-24-03-02 | [5 empty] | Not Started | D-S-24-03 | G-S-24-03 | AC-S-24-03 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-24-03-02 | A-S-24-03 | WPS-24 | Verify / close — Conduct marine, aviation, diving, pollution and medevac interface drills | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Project Manager | Inputs and deliverable for Conduct marine, aviation, diving, pollution and medevac interface drills | Verified and dispositioned Conduct marine, aviation, diving, pollution and medevac interface drills | T-S-24-03-01 | Finish-to-Start | [6 empty] | Not Started | D-S-24-03 | G-S-24-03 | AC-S-24-03 | E-S-24-03 | Relevant competent authority / Project Director | Supplemental control closure task
T-S-24-04-01 | A-S-24-04 | WPS-24 | Prepare / obtain inputs — Close drill findings and issue final operational readiness recommendation | Collect, authenticate and control the inputs required to execute Close drill findings and issue final operational readiness recommendation; identify applicability and unresolved authority questions. | 01 | Project Director | Controlled source documents / equipment records / approved basis | Controlled input pack for Close drill findings and issue final operational readiness recommendation |  | Finish-to-Start | T-S-24-04-02 | [5 empty] | Not Started | D-S-24-04 | G-S-24-04 | AC-S-24-04 |  | Relevant competent authority / Project Director | Supplemental control task
T-S-24-04-02 | A-S-24-04 | WPS-24 | Verify / close — Close drill findings and issue final operational readiness recommendation | Perform the required review, inspection, test, drill or authority confirmation; record findings, evidence, limitations and acceptance decision. | 02 | Project Director | Inputs and deliverable for Close drill findings and issue final operational readiness recommendation | Verified and dispositioned Close drill findings and issue final operational readiness recommendation | T-S-24-04-01 | Finish-to-Start | [6 empty] | Not Started | D-S-24-04 | G-S-24-04 | AC-S-24-04 | E-S-24-04 | Relevant competent authority / Project Director | Supplemental control closure task

## Gaps
Gap ID | Gap Title | Gap Category | Detailed Description | Source Rule IDs | Related WPS IDs | Related Activity IDs | Related Deliverable IDs | Why It Matters | Consequence | Criticality | Risk Rating | Required Closure Action | Required Evidence | Gap Owner | Closure Authority | Blocked Gate | Due Date | Status | Residual Risk | Risk Acceptance Authority | Closure Evidence | Closure Date | Notes
G-001 | Classification regime / reclassification strategy unresolved | Missing Document / Verification | Current class evidence is insufficient to freeze the governing classification basis, or DNV-RU-SHIP / DNV-RU-OU / alternative IACS class-transfer paths have not been adequately assessed. | R-001 | WPS-01 | A-R-001 | D-R-001 | Prevents a defensible classification and downstream applicability decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain current class/status/history; perform classification-strategy assessment; obtain competent-authority disposition and record conditions/limitations. | E-001,E-094,E-095,E-096 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-002 | Evidence-dependent gap: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | R-002 | WPS-01 | A-R-002 | D-R-002 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-002 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-003 | Evidence-dependent gap: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | R-003 | WPS-02 | A-R-003 | D-R-003 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-003 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-004 | Evidence-dependent gap: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | R-004 | WPS-01 | A-R-004 | D-R-004 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-004 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-005 | Evidence-dependent gap: Identify approved drawings and documents forming the class technical basis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify approved drawings and documents forming the class technical basis. | R-005 | WPS-01 | A-R-005 | D-R-005 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-005 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-006 | Evidence-dependent gap: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | R-006 | WPS-02 | A-R-006 | D-R-006 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-006 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-007 | Evidence-dependent gap: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Assess effects of modifications, conversion, change of service or operating area on class requirements. | R-007 | WPS-02 | A-R-007 | D-R-007 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-007 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-008 | Evidence-dependent gap: Establish the approved operating limits and service scope relevant to Jordan operations. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the approved operating limits and service scope relevant to Jordan operations. | R-008 | WPS-01 | A-R-008 | D-R-008 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-008 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-009 | Evidence-dependent gap: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | R-009 | WPS-03 | A-R-009 | D-R-009 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-009 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-010 | Evidence-dependent gap: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | R-010 | WPS-03 | A-R-010 | D-R-010 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-010 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-011 | Evidence-dependent gap: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | R-011 | WPS-03 | A-R-011 | D-R-011 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-011 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-012 | Evidence-dependent gap: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | R-012 | WPS-04 | A-R-012 | D-R-012 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-012 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-013 | Evidence-dependent gap: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | R-013 | WPS-04 | A-R-013 | D-R-013 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-013 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-014 | Evidence-dependent gap: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | R-014 | WPS-05 | A-R-014 | D-R-014 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-014 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-015 | Evidence-dependent gap: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | R-015 | WPS-05 | A-R-015 | D-R-015 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-015 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-016 | Evidence-dependent gap: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | R-016 | WPS-03 | A-R-016 | D-R-016 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-016 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-017 | Evidence-dependent gap: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | R-017 | WPS-03 | A-R-017 | D-R-017 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-017 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-018 | Evidence-dependent gap: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | R-018 | WPS-03 | A-R-018 | D-R-018 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-018 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-2 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-019 | Evidence-dependent gap: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | R-019 | WPS-06 | A-R-019 | D-R-019 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-019 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-020 | Evidence-dependent gap: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | R-020 | WPS-06 | A-R-020 | D-R-020 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-020 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-021 | Evidence-dependent gap: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | R-021 | WPS-06 | A-R-021 | D-R-021 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-021 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-022 | Evidence-dependent gap: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | R-022 | WPS-06 | A-R-022 | D-R-022 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-022 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-023 | Evidence-dependent gap: Verify welding stations, coating station and related QA/QC controls. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify welding stations, coating station and related QA/QC controls. | R-023 | WPS-07 | A-R-023 | D-R-023 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-023 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-024 | Evidence-dependent gap: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | R-024 | WPS-07 | A-R-024 | D-R-024 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-024 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-025 | Evidence-dependent gap: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | R-025 | WPS-07 | A-R-025 | D-R-025 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-025 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-026 | Evidence-dependent gap: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | R-026 | WPS-07 | A-R-026 | D-R-026 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-026 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-027 | Evidence-dependent gap: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | R-027 | WPS-07 | A-R-027 | D-R-027 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-027 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-028 | Evidence-dependent gap: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | R-028 | WPS-07 | A-R-028 | D-R-028 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-028 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-029 | Evidence-dependent gap: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | R-029 | WPS-08 | A-R-029 | D-R-029 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-029 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-030 | Evidence-dependent gap: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | R-030 | WPS-08 | A-R-030 | D-R-030 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-030 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-031 | Evidence-dependent gap: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | R-031 | WPS-08 | A-R-031 | D-R-031 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-031 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-032 | Evidence-dependent gap: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | R-032 | WPS-09 | A-R-032 | D-R-032 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-032 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-033 | Evidence-dependent gap: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | R-033 | WPS-09 | A-R-033 | D-R-033 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-033 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-034 | Evidence-dependent gap: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | R-034 | WPS-09 | A-R-034 | D-R-034 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-034 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-035 | Evidence-dependent gap: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | R-035 | WPS-11 | A-R-035 | D-R-035 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-035 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-036 | Evidence-dependent gap: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | R-036 | WPS-08 | A-R-036 | D-R-036 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-036 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-037 | Evidence-dependent gap: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | R-037 | WPS-10 | A-R-037 | D-R-037 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-037 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-5 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-038 | Evidence-dependent gap: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | R-038 | WPS-10 | A-R-038 | D-R-038 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-038 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-5 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-039 | Evidence-dependent gap: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | R-039 | WPS-10 | A-R-039 | D-R-039 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-039 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-5 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-040 | Evidence-dependent gap: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | R-040 | WPS-10 | A-R-040 | D-R-040 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-040 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-5 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-041 | Evidence-dependent gap: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | R-041 | WPS-10 | A-R-041 | D-R-041 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-041 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-5 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-042 | Evidence-dependent gap: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Define pre-tow inspection, readiness verification and required approval/statement before departure. | R-042 | WPS-10 | A-R-042 | D-R-042 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-042 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-5 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-043 | Evidence-dependent gap: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | R-043 | WPS-11 | A-R-043 | D-R-043 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-043 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-044 | Evidence-dependent gap: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | R-044 | WPS-12 | A-R-044 | D-R-044 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-044 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-045 | Evidence-dependent gap: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | R-045 | WPS-12 | A-R-045 | D-R-045 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-045 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-046 | Evidence-dependent gap: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | R-046 | WPS-12 | A-R-046 | D-R-046 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-046 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-047 | Evidence-dependent gap: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | R-047 | WPS-12 | A-R-047 | D-R-047 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-047 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-048 | Evidence-dependent gap: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | R-048 | WPS-12 | A-R-048 | D-R-048 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-048 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-049 | Evidence-dependent gap: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | R-049 | WPS-13 | A-R-049 | D-R-049 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-049 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-050 | Evidence-dependent gap: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | R-050 | WPS-13 | A-R-050 | D-R-050 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-050 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-051 | Evidence-dependent gap: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | R-051 | WPS-14 | A-R-051 | D-R-051 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-051 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-6/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-052 | Evidence-dependent gap: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | R-052 | WPS-14 | A-R-052 | D-R-052 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-052 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-6/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-053 | Evidence-dependent gap: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | R-053 | WPS-14 | A-R-053 | D-R-053 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-053 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-6/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-054 | Evidence-dependent gap: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | R-054 | WPS-14 | A-R-054 | D-R-054 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-054 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-6/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-055 | Evidence-dependent gap: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | R-055 | WPS-15 | A-R-055 | D-R-055 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-055 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-056 | Evidence-dependent gap: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | R-056 | WPS-15 | A-R-056 | D-R-056 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-056 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-057 | Evidence-dependent gap: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | R-057 | WPS-15 | A-R-057 | D-R-057 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-057 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-058 | Evidence-dependent gap: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | R-058 | WPS-15 | A-R-058 | D-R-058 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-058 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-059 | Evidence-dependent gap: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | R-059 | WPS-13 | A-R-059 | D-R-059 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-059 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-060 | Evidence-dependent gap: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | R-060 | WPS-13 | A-R-060 | D-R-060 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-060 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-061 | Evidence-dependent gap: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | R-061 | WPS-16 | A-R-061 | D-R-061 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-061 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-062 | Evidence-dependent gap: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | R-062 | WPS-16 | A-R-062 | D-R-062 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-062 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-063 | Evidence-dependent gap: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | R-063 | WPS-16 | A-R-063 | D-R-063 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-063 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-064 | Evidence-dependent gap: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | R-064 | WPS-16 | A-R-064 | D-R-064 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-064 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-065 | Evidence-dependent gap: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | R-065 | WPS-16 | A-R-065 | D-R-065 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-065 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-066 | Evidence-dependent gap: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | R-066 | WPS-16 | A-R-066 | D-R-066 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-066 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-067 | Evidence-dependent gap: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | R-067 | WPS-16 | A-R-067 | D-R-067 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-067 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-068 | Evidence-dependent gap: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | R-068 | WPS-16 | A-R-068 | D-R-068 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-068 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-069 | Evidence-dependent gap: Determine ISM applicability and required interface; do not assume applicability. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ISM applicability and required interface; do not assume applicability. | R-069 | WPS-16 | A-R-069 | D-R-069 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-069 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-070 | Evidence-dependent gap: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | R-070 | WPS-16 | A-R-070 | D-R-070 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-070 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-071 | Evidence-dependent gap: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | R-071 | WPS-09 | A-R-071 | D-R-071 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-071 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-072 | Evidence-dependent gap: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | R-072 | WPS-14 | A-R-072 | D-R-072 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-072 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-6/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-073 | Evidence-dependent gap: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | R-073 | WPS-14 | A-R-073 | D-R-073 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-073 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-6/7 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-074 | Evidence-dependent gap: Establish casualty/incident reporting requirements for events in Jordanian waters. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish casualty/incident reporting requirements for events in Jordanian waters. | R-074 | WPS-16 | A-R-074 | D-R-074 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-074 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-075 | Evidence-dependent gap: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | R-075 | WPS-09 | A-R-075 | D-R-075 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-075 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-076 | Evidence-dependent gap: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | R-076 | WPS-09 | A-R-076 | D-R-076 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-076 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-077 | Evidence-dependent gap: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | R-077 | WPS-09 | A-R-077 | D-R-077 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-077 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-078 | Evidence-dependent gap: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | R-078 | WPS-09 | A-R-078 | D-R-078 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-078 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-079 | Evidence-dependent gap: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | R-079 | WPS-16 | A-R-079 | D-R-079 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-079 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-080 | Evidence-dependent gap: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | R-080 | WPS-01 | A-R-080 | D-R-080 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-080 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-081 | Evidence-dependent gap: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | R-081 | WPS-02 | A-R-081 | D-R-081 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-081 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-082 | Evidence-dependent gap: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | R-082 | WPS-01 | A-R-082 | D-R-082 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-082 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-083 | Evidence-dependent gap: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | R-083 | WPS-01 | A-R-083 | D-R-083 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-083 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-084 | Evidence-dependent gap: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | R-084 | WPS-13 | A-R-084 | D-R-084 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-084 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-7/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-085 | Evidence-dependent gap: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | R-085 | WPS-11 | A-R-085 | D-R-085 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Major | Medium | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-085 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-086 | Evidence-dependent gap: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | R-086 | WPS-09 | A-R-086 | D-R-086 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-086 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-3 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-087 | Evidence-dependent gap: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | R-087 | WPS-16 | A-R-087 | D-R-087 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-087 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-4/6/8 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-088 | Evidence-dependent gap: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | R-088 | WPS-02 | A-R-088 | D-R-088 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-088 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-089 | Evidence-dependent gap: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Missing Document / Verification | Open only after responsible-owner verification confirms the acceptance criterion cannot be demonstrated because evidence is missing, invalid, expired, mismatched, incomplete, technically inadequate or not formally accepted. Trigger: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | R-089 | WPS-02 | A-R-089 | D-R-089 | Prevents a defensible technical, regulatory or operational decision. | No closure or gate approval without controlled evidence and competent-authority disposition. | Critical | High | Obtain, verify, inspect, test, analyze or obtain formal authority decision as applicable. | E-R-089 | Rule/WPS owner to be assigned | Relevant competent authority / accepting party | GATE-1 |  | Not Opened | TBC | TBC | TBC |  | Gap opens only after verification failure is confirmed; no automatic closure.
G-S-17-01 | Execution/evidence gap — Obtain formal DNV suspension notice, class status and violation summary | Supplemental Operational Control | Required execution, evidence or acceptance for Obtain formal DNV suspension notice, class status and violation summary has not yet been demonstrated or formally dispositioned. | SC-17-01 | WPS-17 | A-S-17-01 | D-S-17-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Obtain formal DNV suspension notice, class status and violation summary. | E-S-17-01 | Class Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-17-02 | Execution/evidence gap — Agree DNV reinstatement survey scope and attendance plan | Supplemental Operational Control | Required execution, evidence or acceptance for Agree DNV reinstatement survey scope and attendance plan has not yet been demonstrated or formally dispositioned. | SC-17-02 | WPS-17 | A-S-17-02 | D-S-17-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Agree DNV reinstatement survey scope and attendance plan. | E-S-17-02 | Class Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-17-03 | Execution/evidence gap — Complete hull, machinery, electrical and statutory condition assessment | Supplemental Operational Control | Required execution, evidence or acceptance for Complete hull, machinery, electrical and statutory condition assessment has not yet been demonstrated or formally dispositioned. | SC-17-03 | WPS-17 | A-S-17-03 | D-S-17-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Complete hull, machinery, electrical and statutory condition assessment. | E-S-17-03 | Technical Superintendent | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-17-04 | Execution/evidence gap — Execute repairs, tests and survey closeout | Supplemental Operational Control | Required execution, evidence or acceptance for Execute repairs, tests and survey closeout has not yet been demonstrated or formally dispositioned. | SC-17-04 | WPS-17 | A-S-17-04 | D-S-17-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Execute repairs, tests and survey closeout. | E-S-17-04 | Project Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-17-05 | Execution/evidence gap — Receive formal DNV reinstatement decision and updated class status | Supplemental Operational Control | Required execution, evidence or acceptance for Receive formal DNV reinstatement decision and updated class status has not yet been demonstrated or formally dispositioned. | SC-17-05 | WPS-17 | A-S-17-05 | D-S-17-05 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Receive formal DNV reinstatement decision and updated class status. | E-S-17-05 | Class Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-18-01 | Execution/evidence gap — Issue neutral request for information to candidate IACS societies | Supplemental Operational Control | Required execution, evidence or acceptance for Issue neutral request for information to candidate IACS societies has not yet been demonstrated or formally dispositioned. | SC-18-01 | WPS-18 | A-S-18-01 | D-S-18-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Issue neutral request for information to candidate IACS societies. | E-S-18-01 | Class Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-18-02 | Execution/evidence gap — Prepare transfer technical dossier and disclosure register | Supplemental Operational Control | Required execution, evidence or acceptance for Prepare transfer technical dossier and disclosure register has not yet been demonstrated or formally dispositioned. | SC-18-02 | WPS-18 | A-S-18-02 | D-S-18-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Prepare transfer technical dossier and disclosure register. | E-S-18-02 | Class Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-18-03 | Execution/evidence gap — Perform comparative gap, cost and schedule assessment | Supplemental Operational Control | Required execution, evidence or acceptance for Perform comparative gap, cost and schedule assessment has not yet been demonstrated or formally dispositioned. | SC-18-03 | WPS-18 | A-S-18-03 | D-S-18-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Perform comparative gap, cost and schedule assessment. | E-S-18-03 | Project Controls Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-18-04 | Execution/evidence gap — Record management and authority path decision | Supplemental Operational Control | Required execution, evidence or acceptance for Record management and authority path decision has not yet been demonstrated or formally dispositioned. | SC-18-04 | WPS-18 | A-S-18-04 | D-S-18-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Record management and authority path decision. | E-S-18-04 | Project Director | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-18-05 | Execution/evidence gap — If selected, complete transfer surveys and obtain certificate | Supplemental Operational Control | Required execution, evidence or acceptance for If selected, complete transfer surveys and obtain certificate has not yet been demonstrated or formally dispositioned. | SC-18-05 | WPS-18 | A-S-18-05 | D-S-18-05 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for If selected, complete transfer surveys and obtain certificate. | E-S-18-05 | Class Manager | Relevant competent authority / Project Director | GATE-1 |  | Open
G-S-19-01 | Execution/evidence gap — Confirm helideck status, intended aircraft and authority jurisdiction | Supplemental Operational Control | Required execution, evidence or acceptance for Confirm helideck status, intended aircraft and authority jurisdiction has not yet been demonstrated or formally dispositioned. | SC-19-01 | WPS-19 | A-S-19-01 | D-S-19-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Confirm helideck status, intended aircraft and authority jurisdiction. | E-S-19-01 | Aviation Coordinator | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-19-02 | Execution/evidence gap — Review helideck structural, obstacle, marking, lighting and access basis | Supplemental Operational Control | Required execution, evidence or acceptance for Review helideck structural, obstacle, marking, lighting and access basis has not yet been demonstrated or formally dispositioned. | SC-19-02 | WPS-19 | A-S-19-02 | D-S-19-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Review helideck structural, obstacle, marking, lighting and access basis. | E-S-19-02 | Aviation Coordinator | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-19-03 | Execution/evidence gap — Review flight operations and marine-aviation interface manual | Supplemental Operational Control | Required execution, evidence or acceptance for Review flight operations and marine-aviation interface manual has not yet been demonstrated or formally dispositioned. | SC-19-03 | WPS-19 | A-S-19-03 | D-S-19-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Review flight operations and marine-aviation interface manual. | E-S-19-03 | Aviation Coordinator | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-19-04 | Execution/evidence gap — Verify helideck firefighting, rescue, PPE and trained team | Supplemental Operational Control | Required execution, evidence or acceptance for Verify helideck firefighting, rescue, PPE and trained team has not yet been demonstrated or formally dispositioned. | SC-19-04 | WPS-19 | A-S-19-04 | D-S-19-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Verify helideck firefighting, rescue, PPE and trained team. | E-S-19-04 | HSE Manager | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-19-05 | Execution/evidence gap — Secure required operational permissions and acceptance evidence | Supplemental Operational Control | Required execution, evidence or acceptance for Secure required operational permissions and acceptance evidence has not yet been demonstrated or formally dispositioned. | SC-19-05 | WPS-19 | A-S-19-05 | D-S-19-05 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Secure required operational permissions and acceptance evidence. | E-S-19-05 | Aviation Coordinator | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-20-01 | Execution/evidence gap — Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Supplemental Operational Control | Required execution, evidence or acceptance for Determine applicable fuel sulphur and emissions requirements for route and Aqaba has not yet been demonstrated or formally dispositioned. | SC-20-01 | WPS-20 | A-S-20-01 | D-S-20-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Determine applicable fuel sulphur and emissions requirements for route and Aqaba. | E-S-20-01 | Environmental Manager | Relevant competent authority / Project Director | GATE-7/8 |  | Open
G-S-20-02 | Execution/evidence gap — Verify BDN, fuel samples, changeover procedures and consumption plan | Supplemental Operational Control | Required execution, evidence or acceptance for Verify BDN, fuel samples, changeover procedures and consumption plan has not yet been demonstrated or formally dispositioned. | SC-20-02 | WPS-20 | A-S-20-02 | D-S-20-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Verify BDN, fuel samples, changeover procedures and consumption plan. | E-S-20-02 | Chief Engineer | Relevant competent authority / Project Director | GATE-7/8 |  | Open
G-S-20-03 | Execution/evidence gap — Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Supplemental Operational Control | Required execution, evidence or acceptance for Verify sludge, oily water, sewage and garbage capacity/disposal arrangements has not yet been demonstrated or formally dispositioned. | SC-20-03 | WPS-20 | A-S-20-03 | D-S-20-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Verify sludge, oily water, sewage and garbage capacity/disposal arrangements. | E-S-20-03 | Chief Engineer | Relevant competent authority / Project Director | GATE-7/8 |  | Open
G-S-20-04 | Execution/evidence gap — Commission potable-water and RO systems and obtain laboratory results | Supplemental Operational Control | Required execution, evidence or acceptance for Commission potable-water and RO systems and obtain laboratory results has not yet been demonstrated or formally dispositioned. | SC-20-04 | WPS-20 | A-S-20-04 | D-S-20-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Commission potable-water and RO systems and obtain laboratory results. | E-S-20-04 | Chief Engineer | Relevant competent authority / Project Director | GATE-7/8 |  | Open
G-S-20-05 | Execution/evidence gap — Close spill prevention and waste contractor interfaces | Supplemental Operational Control | Required execution, evidence or acceptance for Close spill prevention and waste contractor interfaces has not yet been demonstrated or formally dispositioned. | SC-20-05 | WPS-20 | A-S-20-05 | D-S-20-05 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Major | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Close spill prevention and waste contractor interfaces. | E-S-20-05 | Environmental Manager | Relevant competent authority / Project Director | GATE-7/8 |  | Open
G-S-21-01 | Execution/evidence gap — Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Supplemental Operational Control | Required execution, evidence or acceptance for Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity has not yet been demonstrated or formally dispositioned. | SC-21-01 | WPS-21 | A-S-21-01 | D-S-21-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity. | E-S-21-01 | Maintenance Superintendent | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-21-02 | Execution/evidence gap — Generate critical defect and overdue-maintenance backlog | Supplemental Operational Control | Required execution, evidence or acceptance for Generate critical defect and overdue-maintenance backlog has not yet been demonstrated or formally dispositioned. | SC-21-02 | WPS-21 | A-S-21-02 | D-S-21-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Generate critical defect and overdue-maintenance backlog. | E-S-21-02 | Maintenance Superintendent | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-21-03 | Execution/evidence gap — Map critical spares/materials to equipment and physically verify stock | Supplemental Operational Control | Required execution, evidence or acceptance for Map critical spares/materials to equipment and physically verify stock has not yet been demonstrated or formally dispositioned. | SC-21-03 | WPS-21 | A-S-21-03 | D-S-21-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Map critical spares/materials to equipment and physically verify stock. | E-S-21-03 | Stores Manager | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-21-04 | Execution/evidence gap — Issue procurement plan for shortages and long-lead items | Supplemental Operational Control | Required execution, evidence or acceptance for Issue procurement plan for shortages and long-lead items has not yet been demonstrated or formally dispositioned. | SC-21-04 | WPS-21 | A-S-21-04 | D-S-21-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Issue procurement plan for shortages and long-lead items. | E-S-21-04 | Procurement Manager | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-21-05 | Execution/evidence gap — Back up CMMS database and approve mobilization maintenance baseline | Supplemental Operational Control | Required execution, evidence or acceptance for Back up CMMS database and approve mobilization maintenance baseline has not yet been demonstrated or formally dispositioned. | SC-21-05 | WPS-21 | A-S-21-05 | D-S-21-05 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Back up CMMS database and approve mobilization maintenance baseline. | E-S-21-05 | Maintenance Superintendent | Relevant competent authority / Project Director | GATE-7 |  | Open
G-S-22-01 | Execution/evidence gap — Develop approved anchor pattern, deployment sequence and exclusion controls | Supplemental Operational Control | Required execution, evidence or acceptance for Develop approved anchor pattern, deployment sequence and exclusion controls has not yet been demonstrated or formally dispositioned. | SC-22-01 | WPS-22 | A-S-22-01 | D-S-22-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Develop approved anchor pattern, deployment sequence and exclusion controls. | E-S-22-01 | Marine Superintendent | Relevant competent authority / Project Director | GATE-3 |  | Open
G-S-22-02 | Execution/evidence gap — Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Supplemental Operational Control | Required execution, evidence or acceptance for Verify control-room/APMS/DGPS/gyro displays, alarms and calibration has not yet been demonstrated or formally dispositioned. | SC-22-02 | WPS-22 | A-S-22-02 | D-S-22-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Verify control-room/APMS/DGPS/gyro displays, alarms and calibration. | E-S-22-02 | Survey Manager | Relevant competent authority / Project Director | GATE-3 |  | Open
G-S-22-03 | Execution/evidence gap — Test winches, brakes, controls, communications and emergency release | Supplemental Operational Control | Required execution, evidence or acceptance for Test winches, brakes, controls, communications and emergency release has not yet been demonstrated or formally dispositioned. | SC-22-03 | WPS-22 | A-S-22-03 | D-S-22-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Test winches, brakes, controls, communications and emergency release. | E-S-22-03 | Marine Superintendent | Relevant competent authority / Project Director | GATE-3 |  | Open
G-S-22-04 | Execution/evidence gap — Approve tug assignment, command hierarchy and standard communications | Supplemental Operational Control | Required execution, evidence or acceptance for Approve tug assignment, command hierarchy and standard communications has not yet been demonstrated or formally dispositioned. | SC-22-04 | WPS-22 | A-S-22-04 | D-S-22-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Approve tug assignment, command hierarchy and standard communications. | E-S-22-04 | Marine Superintendent | Relevant competent authority / Project Director | GATE-3 |  | Open
G-S-22-05 | Execution/evidence gap — Conduct anchor-handling tabletop and operational drill | Supplemental Operational Control | Required execution, evidence or acceptance for Conduct anchor-handling tabletop and operational drill has not yet been demonstrated or formally dispositioned. | SC-22-05 | WPS-22 | A-S-22-05 | D-S-22-05 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Conduct anchor-handling tabletop and operational drill. | E-S-22-05 | Marine Superintendent | Relevant competent authority / Project Director | GATE-3 |  | Open
G-S-23-01 | Execution/evidence gap — Approve departmental manpower, competency and rotation matrix | Supplemental Operational Control | Required execution, evidence or acceptance for Approve departmental manpower, competency and rotation matrix has not yet been demonstrated or formally dispositioned. | SC-23-01 | WPS-23 | A-S-23-01 | D-S-23-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Approve departmental manpower, competency and rotation matrix. | E-S-23-01 | HR Manager | Relevant competent authority / Project Director | GATE-4/7 |  | Open
G-S-23-02 | Execution/evidence gap — Verify clinic equipment, medicines, licenses and medevac interface | Supplemental Operational Control | Required execution, evidence or acceptance for Verify clinic equipment, medicines, licenses and medevac interface has not yet been demonstrated or formally dispositioned. | SC-23-02 | WPS-23 | A-S-23-02 | D-S-23-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Verify clinic equipment, medicines, licenses and medevac interface. | E-S-23-02 | Medical Coordinator | Relevant competent authority / Project Director | GATE-4/7 |  | Open
G-S-23-03 | Execution/evidence gap — Implement fatigue, rest-hour and drug/alcohol policy controls | Supplemental Operational Control | Required execution, evidence or acceptance for Implement fatigue, rest-hour and drug/alcohol policy controls has not yet been demonstrated or formally dispositioned. | SC-23-03 | WPS-23 | A-S-23-03 | D-S-23-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Implement fatigue, rest-hour and drug/alcohol policy controls. | E-S-23-03 | HSE Manager | Relevant competent authority / Project Director | GATE-4/7 |  | Open
G-S-23-04 | Execution/evidence gap — Complete visas, travel, repatriation and crew-change logistics | Supplemental Operational Control | Required execution, evidence or acceptance for Complete visas, travel, repatriation and crew-change logistics has not yet been demonstrated or formally dispositioned. | SC-23-04 | WPS-23 | A-S-23-04 | D-S-23-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | High | Medium | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Complete visas, travel, repatriation and crew-change logistics. | E-S-23-04 | HR Manager | Relevant competent authority / Project Director | GATE-4/7 |  | Open
G-S-24-01 | Execution/evidence gap — Issue integrated emergency response and shore-interface matrix | Supplemental Operational Control | Required execution, evidence or acceptance for Issue integrated emergency response and shore-interface matrix has not yet been demonstrated or formally dispositioned. | SC-24-01 | WPS-24 | A-S-24-01 | D-S-24-01 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Issue integrated emergency response and shore-interface matrix. | E-S-24-01 | HSE Manager | Relevant competent authority / Project Director | GATE-8 |  | Open
G-S-24-02 | Execution/evidence gap — Define scenario drill programme and measurable acceptance criteria | Supplemental Operational Control | Required execution, evidence or acceptance for Define scenario drill programme and measurable acceptance criteria has not yet been demonstrated or formally dispositioned. | SC-24-02 | WPS-24 | A-S-24-02 | D-S-24-02 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Define scenario drill programme and measurable acceptance criteria. | E-S-24-02 | HSE Manager | Relevant competent authority / Project Director | GATE-8 |  | Open
G-S-24-03 | Execution/evidence gap — Conduct marine, aviation, diving, pollution and medevac interface drills | Supplemental Operational Control | Required execution, evidence or acceptance for Conduct marine, aviation, diving, pollution and medevac interface drills has not yet been demonstrated or formally dispositioned. | SC-24-03 | WPS-24 | A-S-24-03 | D-S-24-03 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Conduct marine, aviation, diving, pollution and medevac interface drills. | E-S-24-03 | Project Manager | Relevant competent authority / Project Director | GATE-8 |  | Open
G-S-24-04 | Execution/evidence gap — Close drill findings and issue final operational readiness recommendation | Supplemental Operational Control | Required execution, evidence or acceptance for Close drill findings and issue final operational readiness recommendation has not yet been demonstrated or formally dispositioned. | SC-24-04 | WPS-24 | A-S-24-04 | D-S-24-04 | Without controlled closure, the supplemental operational control cannot support the relevant gate decision. | No gate closure or operational authorization based on incomplete or unaccepted control evidence. | Critical | High | Complete the control, obtain required evidence, perform verification and record acceptance/limitations for Close drill findings and issue final operational readiness recommendation. | E-S-24-04 | Project Director | Relevant competent authority / Project Director | GATE-8 |  | Open

## Acceptance
Acceptance Criteria ID | Applies To Type | Applies To ID | Rule ID | WPS ID | Activity ID | Task ID | Criteria Statement | Verification Method | Measurement / Threshold | Required Evidence | Acceptance Authority | Rejection Condition | Escalation Condition | Status | Evidence ID | Date Verified | Reviewer | Comments
AC-R-001 | Rule | R-001 | R-001 | WPS-01 | A-R-001 | T-R-001-03 | The governing classification basis is explicitly determined from controlled evidence OR formally left unresolved by the competent authority; DNV-RU-SHIP and DNV-RU-OU applicability is assessed where relevant; an alternative IACS class-transfer pathway is considered without assuming a named society; notation/scope/restrictions and next actions are recorded. | Document review / inspection / test / engineering analysis / authority review as applicable | All classification-strategy decision inputs present; no unsupported class assumption; authority disposition recorded. | E-001,E-094,E-095,E-096 | Relevant competent authority | Class regime inferred from vessel description; alternative path ignored; or authority disposition absent. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-001 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-002 | Rule | R-002 | R-002 | WPS-01 | A-R-002 | T-R-002-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-002 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-002 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-003 | Rule | R-003 | R-003 | WPS-02 | A-R-003 | T-R-003-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-003 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-003 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-004 | Rule | R-004 | R-004 | WPS-01 | A-R-004 | T-R-004-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-004 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-004 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-005 | Rule | R-005 | R-005 | WPS-01 | A-R-005 | T-R-005-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-005 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-005 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-006 | Rule | R-006 | R-006 | WPS-02 | A-R-006 | T-R-006-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-006 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-006 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-007 | Rule | R-007 | R-007 | WPS-02 | A-R-007 | T-R-007-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-007 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-007 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-008 | Rule | R-008 | R-008 | WPS-01 | A-R-008 | T-R-008-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-008 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-008 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-009 | Rule | R-009 | R-009 | WPS-03 | A-R-009 | T-R-009-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-009 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-009 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-010 | Rule | R-010 | R-010 | WPS-03 | A-R-010 | T-R-010-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-010 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-010 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-011 | Rule | R-011 | R-011 | WPS-03 | A-R-011 | T-R-011-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-011 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-011 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-012 | Rule | R-012 | R-012 | WPS-04 | A-R-012 | T-R-012-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-012 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-012 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-013 | Rule | R-013 | R-013 | WPS-04 | A-R-013 | T-R-013-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-013 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-013 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-014 | Rule | R-014 | R-014 | WPS-05 | A-R-014 | T-R-014-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-014 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-014 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-015 | Rule | R-015 | R-015 | WPS-05 | A-R-015 | T-R-015-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-015 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-015 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-016 | Rule | R-016 | R-016 | WPS-03 | A-R-016 | T-R-016-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-016 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-016 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-017 | Rule | R-017 | R-017 | WPS-03 | A-R-017 | T-R-017-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-017 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-017 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-018 | Rule | R-018 | R-018 | WPS-03 | A-R-018 | T-R-018-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-018 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-018 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-019 | Rule | R-019 | R-019 | WPS-06 | A-R-019 | T-R-019-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-019 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-019 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-020 | Rule | R-020 | R-020 | WPS-06 | A-R-020 | T-R-020-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-020 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-020 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-021 | Rule | R-021 | R-021 | WPS-06 | A-R-021 | T-R-021-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-021 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-021 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-022 | Rule | R-022 | R-022 | WPS-06 | A-R-022 | T-R-022-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-022 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-022 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-023 | Rule | R-023 | R-023 | WPS-07 | A-R-023 | T-R-023-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-023 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-023 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-024 | Rule | R-024 | R-024 | WPS-07 | A-R-024 | T-R-024-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-024 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-024 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-025 | Rule | R-025 | R-025 | WPS-07 | A-R-025 | T-R-025-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-025 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-025 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-026 | Rule | R-026 | R-026 | WPS-07 | A-R-026 | T-R-026-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-026 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-026 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-027 | Rule | R-027 | R-027 | WPS-07 | A-R-027 | T-R-027-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-027 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-027 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-028 | Rule | R-028 | R-028 | WPS-07 | A-R-028 | T-R-028-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-028 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-028 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-029 | Rule | R-029 | R-029 | WPS-08 | A-R-029 | T-R-029-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-029 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-029 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-030 | Rule | R-030 | R-030 | WPS-08 | A-R-030 | T-R-030-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-030 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-030 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-031 | Rule | R-031 | R-031 | WPS-08 | A-R-031 | T-R-031-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-031 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-031 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-032 | Rule | R-032 | R-032 | WPS-09 | A-R-032 | T-R-032-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-032 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-032 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-033 | Rule | R-033 | R-033 | WPS-09 | A-R-033 | T-R-033-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-033 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-033 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-034 | Rule | R-034 | R-034 | WPS-09 | A-R-034 | T-R-034-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-034 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-034 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-035 | Rule | R-035 | R-035 | WPS-11 | A-R-035 | T-R-035-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-035 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-035 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-036 | Rule | R-036 | R-036 | WPS-08 | A-R-036 | T-R-036-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-036 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-036 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-037 | Rule | R-037 | R-037 | WPS-10 | A-R-037 | T-R-037-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-037 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-037 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-038 | Rule | R-038 | R-038 | WPS-10 | A-R-038 | T-R-038-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-038 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-038 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-039 | Rule | R-039 | R-039 | WPS-10 | A-R-039 | T-R-039-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-039 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-039 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-040 | Rule | R-040 | R-040 | WPS-10 | A-R-040 | T-R-040-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-040 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-040 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-041 | Rule | R-041 | R-041 | WPS-10 | A-R-041 | T-R-041-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-041 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-041 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-042 | Rule | R-042 | R-042 | WPS-10 | A-R-042 | T-R-042-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-042 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-042 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-043 | Rule | R-043 | R-043 | WPS-11 | A-R-043 | T-R-043-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-043 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-043 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-044 | Rule | R-044 | R-044 | WPS-12 | A-R-044 | T-R-044-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-044 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-044 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-045 | Rule | R-045 | R-045 | WPS-12 | A-R-045 | T-R-045-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-045 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-045 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-046 | Rule | R-046 | R-046 | WPS-12 | A-R-046 | T-R-046-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-046 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-046 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-047 | Rule | R-047 | R-047 | WPS-12 | A-R-047 | T-R-047-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-047 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-047 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-048 | Rule | R-048 | R-048 | WPS-12 | A-R-048 | T-R-048-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-048 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-048 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-049 | Rule | R-049 | R-049 | WPS-13 | A-R-049 | T-R-049-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-049 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-049 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-050 | Rule | R-050 | R-050 | WPS-13 | A-R-050 | T-R-050-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-050 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-050 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-051 | Rule | R-051 | R-051 | WPS-14 | A-R-051 | T-R-051-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-051 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-051 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-052 | Rule | R-052 | R-052 | WPS-14 | A-R-052 | T-R-052-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-052 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-052 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-053 | Rule | R-053 | R-053 | WPS-14 | A-R-053 | T-R-053-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-053 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-053 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-054 | Rule | R-054 | R-054 | WPS-14 | A-R-054 | T-R-054-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-054 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-054 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-055 | Rule | R-055 | R-055 | WPS-15 | A-R-055 | T-R-055-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-055 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-055 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-056 | Rule | R-056 | R-056 | WPS-15 | A-R-056 | T-R-056-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-056 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-056 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-057 | Rule | R-057 | R-057 | WPS-15 | A-R-057 | T-R-057-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-057 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-057 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-058 | Rule | R-058 | R-058 | WPS-15 | A-R-058 | T-R-058-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-058 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-058 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-059 | Rule | R-059 | R-059 | WPS-13 | A-R-059 | T-R-059-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-059 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-059 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-060 | Rule | R-060 | R-060 | WPS-13 | A-R-060 | T-R-060-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-060 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-060 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-061 | Rule | R-061 | R-061 | WPS-16 | A-R-061 | T-R-061-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-061 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-061 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-062 | Rule | R-062 | R-062 | WPS-16 | A-R-062 | T-R-062-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-062 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-062 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-063 | Rule | R-063 | R-063 | WPS-16 | A-R-063 | T-R-063-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-063 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-063 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-064 | Rule | R-064 | R-064 | WPS-16 | A-R-064 | T-R-064-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-064 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-064 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-065 | Rule | R-065 | R-065 | WPS-16 | A-R-065 | T-R-065-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-065 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-065 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-066 | Rule | R-066 | R-066 | WPS-16 | A-R-066 | T-R-066-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-066 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-066 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-067 | Rule | R-067 | R-067 | WPS-16 | A-R-067 | T-R-067-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-067 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-067 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-068 | Rule | R-068 | R-068 | WPS-16 | A-R-068 | T-R-068-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-068 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-068 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-069 | Rule | R-069 | R-069 | WPS-16 | A-R-069 | T-R-069-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-069 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-069 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-070 | Rule | R-070 | R-070 | WPS-16 | A-R-070 | T-R-070-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-070 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-070 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-071 | Rule | R-071 | R-071 | WPS-09 | A-R-071 | T-R-071-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-071 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-071 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-072 | Rule | R-072 | R-072 | WPS-14 | A-R-072 | T-R-072-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-072 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-072 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-073 | Rule | R-073 | R-073 | WPS-14 | A-R-073 | T-R-073-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-073 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-073 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-074 | Rule | R-074 | R-074 | WPS-16 | A-R-074 | T-R-074-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-074 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-074 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-075 | Rule | R-075 | R-075 | WPS-09 | A-R-075 | T-R-075-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-075 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-075 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-076 | Rule | R-076 | R-076 | WPS-09 | A-R-076 | T-R-076-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-076 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-076 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-077 | Rule | R-077 | R-077 | WPS-09 | A-R-077 | T-R-077-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-077 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-077 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-078 | Rule | R-078 | R-078 | WPS-09 | A-R-078 | T-R-078-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-078 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-078 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-079 | Rule | R-079 | R-079 | WPS-16 | A-R-079 | T-R-079-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-079 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-079 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-080 | Rule | R-080 | R-080 | WPS-01 | A-R-080 | T-R-080-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-080 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-080 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-081 | Rule | R-081 | R-081 | WPS-02 | A-R-081 | T-R-081-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-081 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-081 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-082 | Rule | R-082 | R-082 | WPS-01 | A-R-082 | T-R-082-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-082 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-082 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-083 | Rule | R-083 | R-083 | WPS-01 | A-R-083 | T-R-083-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-083 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-083 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-084 | Rule | R-084 | R-084 | WPS-13 | A-R-084 | T-R-084-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-084 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-084 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-085 | Rule | R-085 | R-085 | WPS-11 | A-R-085 | T-R-085-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-085 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-085 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-086 | Rule | R-086 | R-086 | WPS-09 | A-R-086 | T-R-086-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-086 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-086 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-087 | Rule | R-087 | R-087 | WPS-16 | A-R-087 | T-R-087-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-087 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-087 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-088 | Rule | R-088 | R-088 | WPS-02 | A-R-088 | T-R-088-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-088 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-088 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-R-089 | Rule | R-089 | R-089 | WPS-02 | A-R-089 | T-R-089-03 | The requirement is applicable or formally dispositioned; the PMS-11/equipment/system identity, source authority, exact reference where available, required evidence, limitations and acceptance authority are recorded; evidence is controlled and sufficient for the intended decision. | Document review / inspection / test / engineering analysis / authority review as applicable | All mandatory fields completed; no unsupported compliance statement; evidence accepted or formal disposition recorded. | E-R-089 | Relevant competent authority | Missing, expired, mismatched, uncontrolled or technically insufficient evidence. | Escalate to DNV / Flag / Jordan / MWS / Client / OEM / competent person as applicable. | Not Started | E-089 |  | TBC | Rule-level measurable acceptance; WPS closure also requires all critical criteria and deliverables.
AC-WPS-01-001 | WPS | WPS-01 |  | WPS-01 |  |  | The Class Basis, Status, Notation & IACS Cross-Check package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-02-001 | WPS | WPS-02 |  | WPS-02 |  |  | The Existing Unit, Flag/Statutory & Rule-Edition Basis package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-03-001 | WPS | WPS-03 |  | WPS-03 |  |  | The Lifting Appliances & Loose Gear package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-04-001 | WPS | WPS-04 |  | WPS-04 |  |  | The HMC 5500 Derrick Crane package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-05-001 | WPS | WPS-05 |  | WPS-05 |  |  | The Link-Belt LS 718 Crawler Crane package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-06-001 | WPS | WPS-06 |  | WPS-06 |  |  | The Pipe-Lay Spread & Tensioner package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-07-001 | WPS | WPS-07 |  | WPS-07 |  |  | The Pipeline Installation, Welding & NDT package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-08-001 | WPS | WPS-08 |  | WPS-08 |  |  | The Eight-Point Mooring & Anchoring package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-09-001 | WPS | WPS-09 |  | WPS-09 |  |  | The Aqaba Site, Environmental & Pollution Constraints package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-10-001 | WPS | WPS-10 |  | WPS-10 |  |  | The Egypt–Aqaba Wet Tow package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-11-001 | WPS | WPS-11 |  | WPS-11 |  |  | The Marine Warranty / Independent Verification package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-12-001 | WPS | WPS-12 |  | WPS-12 |  |  | The Diving Systems — IMCA Only package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-13-001 | WPS | WPS-13 |  | WPS-13 |  |  | The Machinery, Electrical, Ballast, Mechanical & Maintenance package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-14-001 | WPS | WPS-14 |  | WPS-14 |  |  | The Fire, LSA, Emergency, Navigation & Communications package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-15-001 | WPS | WPS-15 |  | WPS-15 |  |  | The Accommodation, Welfare, Manning & Competence package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-WPS-16-001 | WPS | WPS-16 |  | WPS-16 |  |  | The Jordan Regulatory, Port, Survey & Controlled Assurance package has all required activities and deliverables complete; applicability is recorded; no Critical gap remains open without formal acceptance; operational limits and authority decision are documented. | Review of WPS, activity, deliverable, evidence and gap registers | 100% of required deliverables/evidence mapped; all Critical gaps closed or formally accepted. | Controlled WPS dossier | Relevant competent authority / accepting party | Any missing critical evidence or unsupported conclusion. | Formal gate escalation and no-go until resolved or accepted. | Not Started |  |  | TBC | WPS-level closure criterion.
AC-S-17-01 | Supplemental Activity | A-S-17-01 | SC-17-01 | WPS-17 | A-S-17-01 | T-S-17-01-02 | Obtain formal DNV suspension notice, class status and violation summary is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-17-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-17-01 |  |  | Supplemental control acceptance criterion.
AC-S-17-02 | Supplemental Activity | A-S-17-02 | SC-17-02 | WPS-17 | A-S-17-02 | T-S-17-02-02 | Agree DNV reinstatement survey scope and attendance plan is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-17-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-17-02 |  |  | Supplemental control acceptance criterion.
AC-S-17-03 | Supplemental Activity | A-S-17-03 | SC-17-03 | WPS-17 | A-S-17-03 | T-S-17-03-02 | Complete hull, machinery, electrical and statutory condition assessment is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-17-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-17-03 |  |  | Supplemental control acceptance criterion.
AC-S-17-04 | Supplemental Activity | A-S-17-04 | SC-17-04 | WPS-17 | A-S-17-04 | T-S-17-04-02 | Execute repairs, tests and survey closeout is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-17-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-17-04 |  |  | Supplemental control acceptance criterion.
AC-S-17-05 | Supplemental Activity | A-S-17-05 | SC-17-05 | WPS-17 | A-S-17-05 | T-S-17-05-02 | Receive formal DNV reinstatement decision and updated class status is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-17-05 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-17-05 |  |  | Supplemental control acceptance criterion.
AC-S-18-01 | Supplemental Activity | A-S-18-01 | SC-18-01 | WPS-18 | A-S-18-01 | T-S-18-01-02 | Issue neutral request for information to candidate IACS societies is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-18-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-18-01 |  |  | Supplemental control acceptance criterion.
AC-S-18-02 | Supplemental Activity | A-S-18-02 | SC-18-02 | WPS-18 | A-S-18-02 | T-S-18-02-02 | Prepare transfer technical dossier and disclosure register is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-18-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-18-02 |  |  | Supplemental control acceptance criterion.
AC-S-18-03 | Supplemental Activity | A-S-18-03 | SC-18-03 | WPS-18 | A-S-18-03 | T-S-18-03-02 | Perform comparative gap, cost and schedule assessment is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-18-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-18-03 |  |  | Supplemental control acceptance criterion.
AC-S-18-04 | Supplemental Activity | A-S-18-04 | SC-18-04 | WPS-18 | A-S-18-04 | T-S-18-04-02 | Record management and authority path decision is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-18-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-18-04 |  |  | Supplemental control acceptance criterion.
AC-S-18-05 | Supplemental Activity | A-S-18-05 | SC-18-05 | WPS-18 | A-S-18-05 | T-S-18-05-02 | If selected, complete transfer surveys and obtain certificate is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-18-05 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-18-05 |  |  | Supplemental control acceptance criterion.
AC-S-19-01 | Supplemental Activity | A-S-19-01 | SC-19-01 | WPS-19 | A-S-19-01 | T-S-19-01-02 | Confirm helideck status, intended aircraft and authority jurisdiction is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-19-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-19-01 |  |  | Supplemental control acceptance criterion.
AC-S-19-02 | Supplemental Activity | A-S-19-02 | SC-19-02 | WPS-19 | A-S-19-02 | T-S-19-02-02 | Review helideck structural, obstacle, marking, lighting and access basis is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-19-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-19-02 |  |  | Supplemental control acceptance criterion.
AC-S-19-03 | Supplemental Activity | A-S-19-03 | SC-19-03 | WPS-19 | A-S-19-03 | T-S-19-03-02 | Review flight operations and marine-aviation interface manual is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-19-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-19-03 |  |  | Supplemental control acceptance criterion.
AC-S-19-04 | Supplemental Activity | A-S-19-04 | SC-19-04 | WPS-19 | A-S-19-04 | T-S-19-04-02 | Verify helideck firefighting, rescue, PPE and trained team is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-19-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-19-04 |  |  | Supplemental control acceptance criterion.
AC-S-19-05 | Supplemental Activity | A-S-19-05 | SC-19-05 | WPS-19 | A-S-19-05 | T-S-19-05-02 | Secure required operational permissions and acceptance evidence is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-19-05 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-19-05 |  |  | Supplemental control acceptance criterion.
AC-S-20-01 | Supplemental Activity | A-S-20-01 | SC-20-01 | WPS-20 | A-S-20-01 | T-S-20-01-02 | Determine applicable fuel sulphur and emissions requirements for route and Aqaba is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-20-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-20-01 |  |  | Supplemental control acceptance criterion.
AC-S-20-02 | Supplemental Activity | A-S-20-02 | SC-20-02 | WPS-20 | A-S-20-02 | T-S-20-02-02 | Verify BDN, fuel samples, changeover procedures and consumption plan is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-20-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-20-02 |  |  | Supplemental control acceptance criterion.
AC-S-20-03 | Supplemental Activity | A-S-20-03 | SC-20-03 | WPS-20 | A-S-20-03 | T-S-20-03-02 | Verify sludge, oily water, sewage and garbage capacity/disposal arrangements is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-20-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-20-03 |  |  | Supplemental control acceptance criterion.
AC-S-20-04 | Supplemental Activity | A-S-20-04 | SC-20-04 | WPS-20 | A-S-20-04 | T-S-20-04-02 | Commission potable-water and RO systems and obtain laboratory results is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-20-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-20-04 |  |  | Supplemental control acceptance criterion.
AC-S-20-05 | Supplemental Activity | A-S-20-05 | SC-20-05 | WPS-20 | A-S-20-05 | T-S-20-05-02 | Close spill prevention and waste contractor interfaces is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-20-05 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-20-05 |  |  | Supplemental control acceptance criterion.
AC-S-21-01 | Supplemental Activity | A-S-21-01 | SC-21-01 | WPS-21 | A-S-21-01 | T-S-21-01-02 | Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-21-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-21-01 |  |  | Supplemental control acceptance criterion.
AC-S-21-02 | Supplemental Activity | A-S-21-02 | SC-21-02 | WPS-21 | A-S-21-02 | T-S-21-02-02 | Generate critical defect and overdue-maintenance backlog is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-21-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-21-02 |  |  | Supplemental control acceptance criterion.
AC-S-21-03 | Supplemental Activity | A-S-21-03 | SC-21-03 | WPS-21 | A-S-21-03 | T-S-21-03-02 | Map critical spares/materials to equipment and physically verify stock is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-21-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-21-03 |  |  | Supplemental control acceptance criterion.
AC-S-21-04 | Supplemental Activity | A-S-21-04 | SC-21-04 | WPS-21 | A-S-21-04 | T-S-21-04-02 | Issue procurement plan for shortages and long-lead items is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-21-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-21-04 |  |  | Supplemental control acceptance criterion.
AC-S-21-05 | Supplemental Activity | A-S-21-05 | SC-21-05 | WPS-21 | A-S-21-05 | T-S-21-05-02 | Back up CMMS database and approve mobilization maintenance baseline is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-21-05 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-21-05 |  |  | Supplemental control acceptance criterion.
AC-S-22-01 | Supplemental Activity | A-S-22-01 | SC-22-01 | WPS-22 | A-S-22-01 | T-S-22-01-02 | Develop approved anchor pattern, deployment sequence and exclusion controls is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-22-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-22-01 |  |  | Supplemental control acceptance criterion.
AC-S-22-02 | Supplemental Activity | A-S-22-02 | SC-22-02 | WPS-22 | A-S-22-02 | T-S-22-02-02 | Verify control-room/APMS/DGPS/gyro displays, alarms and calibration is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-22-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-22-02 |  |  | Supplemental control acceptance criterion.
AC-S-22-03 | Supplemental Activity | A-S-22-03 | SC-22-03 | WPS-22 | A-S-22-03 | T-S-22-03-02 | Test winches, brakes, controls, communications and emergency release is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-22-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-22-03 |  |  | Supplemental control acceptance criterion.
AC-S-22-04 | Supplemental Activity | A-S-22-04 | SC-22-04 | WPS-22 | A-S-22-04 | T-S-22-04-02 | Approve tug assignment, command hierarchy and standard communications is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-22-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-22-04 |  |  | Supplemental control acceptance criterion.
AC-S-22-05 | Supplemental Activity | A-S-22-05 | SC-22-05 | WPS-22 | A-S-22-05 | T-S-22-05-02 | Conduct anchor-handling tabletop and operational drill is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-22-05 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-22-05 |  |  | Supplemental control acceptance criterion.
AC-S-23-01 | Supplemental Activity | A-S-23-01 | SC-23-01 | WPS-23 | A-S-23-01 | T-S-23-01-02 | Approve departmental manpower, competency and rotation matrix is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-23-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-23-01 |  |  | Supplemental control acceptance criterion.
AC-S-23-02 | Supplemental Activity | A-S-23-02 | SC-23-02 | WPS-23 | A-S-23-02 | T-S-23-02-02 | Verify clinic equipment, medicines, licenses and medevac interface is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-23-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-23-02 |  |  | Supplemental control acceptance criterion.
AC-S-23-03 | Supplemental Activity | A-S-23-03 | SC-23-03 | WPS-23 | A-S-23-03 | T-S-23-03-02 | Implement fatigue, rest-hour and drug/alcohol policy controls is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-23-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-23-03 |  |  | Supplemental control acceptance criterion.
AC-S-23-04 | Supplemental Activity | A-S-23-04 | SC-23-04 | WPS-23 | A-S-23-04 | T-S-23-04-02 | Complete visas, travel, repatriation and crew-change logistics is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-23-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-23-04 |  |  | Supplemental control acceptance criterion.
AC-S-24-01 | Supplemental Activity | A-S-24-01 | SC-24-01 | WPS-24 | A-S-24-01 | T-S-24-01-02 | Issue integrated emergency response and shore-interface matrix is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-24-01 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-24-01 |  |  | Supplemental control acceptance criterion.
AC-S-24-02 | Supplemental Activity | A-S-24-02 | SC-24-02 | WPS-24 | A-S-24-02 | T-S-24-02-02 | Define scenario drill programme and measurable acceptance criteria is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-24-02 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-24-02 |  |  | Supplemental control acceptance criterion.
AC-S-24-03 | Supplemental Activity | A-S-24-03 | SC-24-03 | WPS-24 | A-S-24-03 | T-S-24-03-02 | Conduct marine, aviation, diving, pollution and medevac interface drills is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-24-03 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-24-03 |  |  | Supplemental control acceptance criterion.
AC-S-24-04 | Supplemental Activity | A-S-24-04 | SC-24-04 | WPS-24 | A-S-24-04 | T-S-24-04-02 | Close drill findings and issue final operational readiness recommendation is completed against the applicable approved basis; required evidence is controlled and sufficient; verification findings are recorded; limitations/conditions are documented; and the responsible acceptance authority formally accepts or dispositions the control before the applicable gate decision. | Document review / inspection / test / drill / authority review as applicable | No unsupported fixed numerical threshold; applicable source/authority criteria and approved engineering basis control. | E-S-24-04 | Relevant competent authority / Project Director as applicable | Missing, uncontrolled, rejected, expired or technically insufficient evidence; or authority disposition absent. | Escalate to applicable authority / DNV / Flag / Jordan / MWS / Client / OEM as applicable. | Not Started | E-S-24-04 |  |  | Supplemental control acceptance criterion.

## Evidence
Evidence ID | Document Title / Request | Document Type | Document Number | Revision | Date | Expiry Date | Issuing Authority | Vessel/System/Equipment | Rule IDs | WPS IDs | Activity IDs | Task IDs | Gap IDs | Acceptance Criteria IDs | Custodian | File Location | Status | Verified By | Verification Date | Approved By | Comments
E-001 | Current DNV Class Certificate + class status; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Rules for Classification | PMS-11 / applicable system | R-001 | WPS-01 | A-R-001 | T-R-001-01,T-R-001-02,T-R-001-03 | TBC | AC-R-001 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-002 | Current DNV Class Certificate; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Class Certificate | PMS-11 / applicable system | R-002 | WPS-01 | A-R-002 | T-R-002-01,T-R-002-02,T-R-002-03 | TBC | AC-R-002 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-003 | Class basis + rule edition evidence; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Rules | PMS-11 / applicable system | R-003 | WPS-02 | A-R-003 | T-R-003-01,T-R-003-02,T-R-003-03 | TBC | AC-R-003 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-004 | Class Status Report + survey records; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Class Status | PMS-11 / applicable system | R-004 | WPS-01 | A-R-004 | T-R-004-01,T-R-004-02,T-R-004-03 | TBC | AC-R-004 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-005 | Approved drawings list / class file; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Class File | PMS-11 / applicable system | R-005 | WPS-01 | A-R-005 | T-R-005-01,T-R-005-02,T-R-005-03 | TBC | AC-R-005 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-006 | Survey status/history; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Survey/Certification | PMS-11 / applicable system | R-006 | WPS-02 | A-R-006 | T-R-006-01,T-R-006-02,T-R-006-03 | TBC | AC-R-006 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-007 | Modification history + approvals; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Rules | PMS-11 / applicable system | R-007 | WPS-02 | A-R-007 | T-R-007-01,T-R-007-02,T-R-007-03 | TBC | AC-R-007 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-008 | Certificate + approved operational documents; document revision/date, PMS-11 identity, notation/scope, Conditions of Class/Recommendations/Memoranda, survey due list and exact governing edition/paragraph. | Document / Certificate | TBC | TBC |  |  | DNV Class File | PMS-11 / applicable system | R-008 | WPS-01 | A-R-008 | T-R-008-01,T-R-008-02,T-R-008-03 | TBC | AC-R-008 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-009 | Flag/statutory basis + appliance register; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | SOLAS / DNV | PMS-11 / applicable system | R-009 | WPS-03 | A-R-009 | T-R-009-01,T-R-009-02,T-R-009-03 | TBC | AC-R-009 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-010 | Flag acceptance + technical basis; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | SOLAS / DNV | PMS-11 / applicable system | R-010 | WPS-03 | A-R-010 | T-R-010-01,T-R-010-02,T-R-010-03 | TBC | AC-R-010 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-011 | Register + certificates + examination/load-test records; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / SOLAS | PMS-11 / applicable system | R-011 | WPS-03 | A-R-011 | T-R-011-01,T-R-011-02,T-R-011-03 | TBC | AC-R-011 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-012 | HMC 5500 technical/certification file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / OEM | PMS-11 / applicable system | R-012 | WPS-04 | A-R-012 | T-R-012-01,T-R-012-02,T-R-012-03 | TBC | AC-R-012 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-013 | Crane manual, load charts, limits, procedures; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-013 | WPS-04 | A-R-013 | T-R-013-01,T-R-013-02,T-R-013-03 | TBC | AC-R-013 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-014 | OEM/configuration file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | OEM / DNV | PMS-11 / applicable system | R-014 | WPS-05 | A-R-014 | T-R-014-01,T-R-014-02,T-R-014-03 | TBC | AC-R-014 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-015 | Engineering assessment + load chart + deck data; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / Engineering | PMS-11 / applicable system | R-015 | WPS-05 | A-R-015 | T-R-015-01,T-R-015-02,T-R-015-03 | TBC | AC-R-015 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-016 | Winch certificate/test/exam/OEM file; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / OEM | PMS-11 / applicable system | R-016 | WPS-03 | A-R-016 | T-R-016-01,T-R-016-02,T-R-016-03 | TBC | AC-R-016 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-017 | Tugger certificates/tests/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / OEM | PMS-11 / applicable system | R-017 | WPS-03 | A-R-017 | T-R-017-01,T-R-017-02,T-R-017-03 | TBC | AC-R-017 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-018 | Loose-gear register + certificates/exams; equipment ID/serial, installed configuration, OEM data, SWL/WLL/load chart, deck/foundation interface, structural/stability assessment, examination/load-test records and limits. | Document / Certificate | TBC | TBC |  |  | DNV / Statutory / OEM | PMS-11 / applicable system | R-018 | WPS-03 | A-R-018 | T-R-018-01,T-R-018-02,T-R-018-03 | TBC | AC-R-018 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-019 | Class basis + applicable rule edition; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV Rules | PMS-11 / applicable system | R-019 | WPS-06 | A-R-019 | T-R-019-01,T-R-019-02,T-R-019-03 | TBC | AC-R-019 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-020 | CRC drawings/manuals/tests; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV / OEM / Project | PMS-11 / applicable system | R-020 | WPS-06 | A-R-020 | T-R-020-01,T-R-020-02,T-R-020-03 | TBC | AC-R-020 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-021 | Tensioner certificate/manual/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | OEM / DNV / Project | PMS-11 / applicable system | R-021 | WPS-06 | A-R-021 | T-R-021-01,T-R-021-02,T-R-021-03 | TBC | AC-R-021 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-022 | Drawings + calculations + inspection/test records; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV / Engineering | PMS-11 / applicable system | R-022 | WPS-06 | A-R-022 | T-R-022-01,T-R-022-02,T-R-022-03 | TBC | AC-R-022 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-023 | Welding/coating procedures + qualifications; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | Project / Industry | PMS-11 / applicable system | R-023 | WPS-07 | A-R-023 | T-R-023-01,T-R-023-02,T-R-023-03 | TBC | AC-R-023 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-024 | Equipment certificates + personnel qualifications + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | Statutory / Project | PMS-11 / applicable system | R-024 | WPS-07 | A-R-024 | T-R-024-01,T-R-024-02,T-R-024-03 | TBC | AC-R-024 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-025 | Installation analysis + operating limits + procedures; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-025 | WPS-07 | A-R-025 | T-R-025-01,T-R-025-02,T-R-025-03 | TBC | AC-R-025 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-026 | Project design basis/specification; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV | PMS-11 / applicable system | R-026 | WPS-07 | A-R-026 | T-R-026-01,T-R-026-02,T-R-026-03 | TBC | AC-R-026 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-027 | Project specification + engineering basis; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV | PMS-11 / applicable system | R-027 | WPS-07 | A-R-027 | T-R-027-01,T-R-027-02,T-R-027-03 | TBC | AC-R-027 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-028 | Installation analysis package; as-built arrangement, equipment IDs/serials, rated capacity/tension, controls, rollers/track/stinger/lowering arrangement, structural interfaces, welding/NDT/coating procedures and installation analysis. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-028 | WPS-07 | A-R-028 | T-R-028-01,T-R-028-02,T-R-028-03 | TBC | AC-R-028 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-029 | Mooring arrangement + equipment certificates; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | DNV / IACS | PMS-11 / applicable system | R-029 | WPS-08 | A-R-029 | T-R-029-01,T-R-029-02,T-R-029-03 | TBC | AC-R-029 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-030 | Winch manuals/tests/exams; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | DNV / OEM | PMS-11 / applicable system | R-030 | WPS-08 | A-R-030 | T-R-030-01,T-R-030-02,T-R-030-03 | TBC | AC-R-030 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-031 | Mooring analysis + environmental design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | DNV / Engineering | PMS-11 / applicable system | R-031 | WPS-08 | A-R-031 | T-R-031-01,T-R-031-02,T-R-031-03 | TBC | AC-R-031 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-032 | Verified survey/geotech package; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-032 | WPS-09 | A-R-032 | T-R-032-01,T-R-032-02,T-R-032-03 | TBC | AC-R-032 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-033 | Subsea asset register + approved site layout; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | Project / Jordan / ASEZA | PMS-11 / applicable system | R-033 | WPS-09 | A-R-033 | T-R-033-01,T-R-033-02,T-R-033-03 | TBC | AC-R-033 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-034 | Metocean design basis; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-034 | WPS-09 | A-R-034 | T-R-034-01,T-R-034-02,T-R-034-03 | TBC | AC-R-034 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-035 | MWS scope + approval documents; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-035 | WPS-11 | A-R-035 | T-R-035-01,T-R-035-02,T-R-035-03 | TBC | AC-R-035 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-036 | Approved procedures + drills/records; mooring arrangement, anchor/wire/chain/termination/fairlead inventory, certificates, brake/line tests, coordinates, bathymetry/geotechnical/metocean data, analysis, failure cases and clearances. | Document / Certificate | TBC | TBC |  |  | Project / Marine | PMS-11 / applicable system | R-036 | WPS-08 | A-R-036 | T-R-036-01,T-R-036-02,T-R-036-03 | TBC | AC-R-036 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-037 | Tow engineering package; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Document / Certificate | TBC | TBC |  |  | DNV | PMS-11 / applicable system | R-037 | WPS-10 | A-R-037 | T-R-037-01,T-R-037-02,T-R-037-03 | TBC | AC-R-037 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-038 | Structural verification; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Document / Certificate | TBC | TBC |  |  | DNV / Engineering | PMS-11 / applicable system | R-038 | WPS-10 | A-R-038 | T-R-038-01,T-R-038-02,T-R-038-03 | TBC | AC-R-038 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-039 | Stability/tow condition calculations; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Document / Certificate | TBC | TBC |  |  | DNV / Flag | PMS-11 / applicable system | R-039 | WPS-10 | A-R-039 | T-R-039-01,T-R-039-02,T-R-039-03 | TBC | AC-R-039 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-040 | Tug data + tow plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Document / Certificate | TBC | TBC |  |  | Marine / DNV / Project | PMS-11 / applicable system | R-040 | WPS-10 | A-R-040 | T-R-040-01,T-R-040-02,T-R-040-03 | TBC | AC-R-040 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-041 | Tow route/weather/emergency plan; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Document / Certificate | TBC | TBC |  |  | DNV / Marine | PMS-11 / applicable system | R-041 | WPS-10 | A-R-041 | T-R-041-01,T-R-041-02,T-R-041-03 | TBC | AC-R-041 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-042 | Pre-tow inspection + approval; tow configuration, tow-point structural evidence, bridle/towline certificates, tug particulars/bollard pull, stability/freeboard, route/weather criteria, abort/emergency plan and approvals. | Document / Certificate | TBC | TBC |  |  | DNV / Flag / MWS | PMS-11 / applicable system | R-042 | WPS-10 | A-R-042 | T-R-042-01,T-R-042-02,T-R-042-03 | TBC | AC-R-042 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-043 | MWS scope and approvals; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Document / Certificate | TBC | TBC |  |  | DNV / Project | PMS-11 / applicable system | R-043 | WPS-11 | A-R-043 | T-R-043-01,T-R-043-02,T-R-043-03 | TBC | AC-R-043 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-044 | IMCA inspection report + controlled diving procedures/records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Document / Certificate | TBC | TBC |  |  | IMCA | PMS-11 / applicable system | R-044 | WPS-12 | A-R-044 | T-R-044-01,T-R-044-02,T-R-044-03 | TBC | AC-R-044 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-045 | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Document / Certificate | TBC | TBC |  |  | IMCA | PMS-11 / applicable system | R-045 | WPS-12 | A-R-045 | T-R-045-01,T-R-045-02,T-R-045-03 | TBC | AC-R-045 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-046 | IMCA inspection/evidence package; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Document / Certificate | TBC | TBC |  |  | IMCA | PMS-11 / applicable system | R-046 | WPS-12 | A-R-046 | T-R-046-01,T-R-046-02,T-R-046-03 | TBC | AC-R-046 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-047 | Competence matrix + records; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Document / Certificate | TBC | TBC |  |  | IMCA | PMS-11 / applicable system | R-047 | WPS-12 | A-R-047 | T-R-047-01,T-R-047-02,T-R-047-03 | TBC | AC-R-047 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-048 | Maintenance/test records + IMCA acceptance; IMCA scope, plant inventory, chamber/bell/LARS/life-support records, examination/test records, maintenance logs, emergency/recovery arrangements and personnel competence. No IMO Diving Code or unsupported DNV/Flag diving baseline.. | Document / Certificate | TBC | TBC |  |  | IMCA | PMS-11 / applicable system | R-048 | WPS-12 | A-R-048 | T-R-048-01,T-R-048-02,T-R-048-03 | TBC | AC-R-048 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-049 | Electrical single-line + tests + survey records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Document / Certificate | TBC | TBC |  |  | DNV / Flag | PMS-11 / applicable system | R-049 | WPS-13 | A-R-049 | T-R-049-01,T-R-049-02,T-R-049-03 | TBC | AC-R-049 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-050 | P&IDs + tests + maintenance records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Document / Certificate | TBC | TBC |  |  | DNV / Flag / OEM | PMS-11 / applicable system | R-050 | WPS-13 | A-R-050 | T-R-050-01,T-R-050-02,T-R-050-03 | TBC | AC-R-050 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-051 | FSS certificates/tests + plans; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Document / Certificate | TBC | TBC |  |  | SOLAS / Flag / DNV | PMS-11 / applicable system | R-051 | WPS-14 | A-R-051 | T-R-051-01,T-R-051-02,T-R-051-03 | TBC | AC-R-051 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-052 | LSA certificates + drill records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Document / Certificate | TBC | TBC |  |  | SOLAS / Flag / DNV | PMS-11 / applicable system | R-052 | WPS-14 | A-R-052 | T-R-052-01,T-R-052-02,T-R-052-03 | TBC | AC-R-052 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-053 | Equipment list + calibration/service records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Document / Certificate | TBC | TBC |  |  | Flag / DNV / Project | PMS-11 / applicable system | R-053 | WPS-14 | A-R-053 | T-R-053-01,T-R-053-02,T-R-053-03 | TBC | AC-R-053 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-054 | JMA/VTS requirements + agent confirmation; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Document / Certificate | TBC | TBC |  |  | Jordan JMA | PMS-11 / applicable system | R-054 | WPS-14 | A-R-054 | T-R-054-01,T-R-054-02,T-R-054-03 | TBC | AC-R-054 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-055 | Crew profile + accommodation inspection/certification; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Document / Certificate | TBC | TBC |  |  | MLC / Flag / DNV | PMS-11 / applicable system | R-055 | WPS-15 | A-R-055 | T-R-055-01,T-R-055-02,T-R-055-03 | TBC | AC-R-055 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-056 | Health/galley/water evidence; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Document / Certificate | TBC | TBC |  |  | MLC / Flag / Jordan Port Health | PMS-11 / applicable system | R-056 | WPS-15 | A-R-056 | T-R-056-01,T-R-056-02,T-R-056-03 | TBC | AC-R-056 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-057 | Crew certification matrix; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Document / Certificate | TBC | TBC |  |  | STCW / Flag / Jordan | PMS-11 / applicable system | R-057 | WPS-15 | A-R-057 | T-R-057-01,T-R-057-02,T-R-057-03 | TBC | AC-R-057 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-058 | Competence matrix + training records; crew/role matrix, certificates/endorsements/medical fitness, training/familiarization, competence assessments, accommodation/welfare inspection and water/food hygiene records. | Document / Certificate | TBC | TBC |  |  | Flag / Project / Company | PMS-11 / applicable system | R-058 | WPS-15 | A-R-058 | T-R-058-01,T-R-058-02,T-R-058-03 | TBC | AC-R-058 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-059 | PMS matrix + OEM manuals + records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Document / Certificate | TBC | TBC |  |  | DNV / Flag / OEM / Project | PMS-11 / applicable system | R-059 | WPS-13 | A-R-059 | T-R-059-01,T-R-059-02,T-R-059-03 | TBC | AC-R-059 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-060 | Certificates, test reports, calibration records; system register, drawings/P&IDs/single-line diagrams, test/calibration records, alarms/shutdown tests, PMS linkage, OEM requirements, critical spares and survey/class items. | Document / Certificate | TBC | TBC |  |  | DNV / Flag / OEM | PMS-11 / applicable system | R-060 | WPS-13 | A-R-060 | T-R-060-01,T-R-060-02,T-R-060-03 | TBC | AC-R-060 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-061 | Survey matrix + records; survey/examination matrix by equipment/system, due date, completion date, certificate/report, findings and restrictions. | Document / Certificate | TBC | TBC |  |  | DNV / Flag / IMCA | PMS-11 / applicable system | R-061 | WPS-16 | A-R-061 | T-R-061-01,T-R-061-02,T-R-061-03 | TBC | AC-R-061 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-062 | Controlled document register; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Document / Certificate | TBC | TBC |  |  | DNV / Flag / Project | PMS-11 / applicable system | R-062 | WPS-16 | A-R-062 | T-R-062-01,T-R-062-02,T-R-062-03 | TBC | AC-R-062 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-063 | Agent/JMA entry requirements; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-063 | WPS-16 | A-R-063 | T-R-063-01,T-R-063-02,T-R-063-03 | TBC | AC-R-063 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-064 | PSC readiness package; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-064 | WPS-16 | A-R-064 | T-R-064-01,T-R-064-02,T-R-064-03 | TBC | AC-R-064 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-065 | JMA survey requirements + reports; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-065 | WPS-16 | A-R-065 | T-R-065-01,T-R-065-02,T-R-065-03 | TBC | AC-R-065 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-066 | Health clearance evidence; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-066 | WPS-16 | A-R-066 | T-R-066-01,T-R-066-02,T-R-066-03 | TBC | AC-R-066 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-067 | Agent/service approvals; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-067 | WPS-16 | A-R-067 | T-R-067-01,T-R-067-02,T-R-067-03 | TBC | AC-R-067 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-068 | Security applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-068 | WPS-16 | A-R-068 | T-R-068-01,T-R-068-02,T-R-068-03 | TBC | AC-R-068 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-069 | ISM applicability/approval; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-069 | WPS-16 | A-R-069 | T-R-069-01,T-R-069-02,T-R-069-03 | TBC | AC-R-069 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-070 | Certificates + JMA recognition; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-070 | WPS-16 | A-R-070 | T-R-070-01,T-R-070-02,T-R-070-03 | TBC | AC-R-070 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-071 | BWM certificate/records where applicable; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-071 | WPS-09 | A-R-071 | T-R-071-01,T-R-071-02,T-R-071-03 | TBC | AC-R-071 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-072 | Certificates/test records; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-072 | WPS-14 | A-R-072 | T-R-072-01,T-R-072-02,T-R-072-03 | TBC | AC-R-072 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-073 | Pilot/tug/VTS arrangements; equipment inventory, service/certification records, test/drill reports, emergency procedures, calibration/service dates and Flag/authority confirmation. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-073 | WPS-14 | A-R-073 | T-R-073-01,T-R-073-02,T-R-073-03 | TBC | AC-R-073 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-074 | Reporting procedure/contact matrix; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Maritime Commission | PMS-11 / applicable system | R-074 | WPS-16 | A-R-074 | T-R-074-01,T-R-074-02,T-R-074-03 | TBC | AC-R-074 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-075 | Official boundary + permit/control assessment; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Document / Certificate | TBC | TBC |  |  | ASEZA | PMS-11 / applicable system | R-075 | WPS-09 | A-R-075 | T-R-075-01,T-R-075-02,T-R-075-03 | TBC | AC-R-075 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-076 | ASEZA environmental requirements/permits; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Document / Certificate | TBC | TBC |  |  | ASEZA | PMS-11 / applicable system | R-076 | WPS-09 | A-R-076 | T-R-076-01,T-R-076-02,T-R-076-03 | TBC | AC-R-076 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-077 | Garbage/oil/sewage/waste records; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Document / Certificate | TBC | TBC |  |  | IMO / Jordan JMA | PMS-11 / applicable system | R-077 | WPS-09 | A-R-077 | T-R-077-01,T-R-077-02,T-R-077-03 | TBC | AC-R-077 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-078 | SOPEP/SMPEP as applicable + project spill plan; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Document / Certificate | TBC | TBC |  |  | Jordan / Project | PMS-11 / applicable system | R-078 | WPS-09 | A-R-078 | T-R-078-01,T-R-078-02,T-R-078-03 | TBC | AC-R-078 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-079 | Agent checklist + customs/immigration clearance; written JMA/JMC/ASEZA/Harbor Master/agent/PSC/health/customs confirmation identifying requirement, permit/certificate, validity and outstanding conditions. | Document / Certificate | TBC | TBC |  |  | Jordan Authorities / Agent | PMS-11 / applicable system | R-079 | WPS-16 | A-R-079 | T-R-079-01,T-R-079-02,T-R-079-03 | TBC | AC-R-079 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-080 | IACS-to-DNV applicability matrix; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Document / Certificate | TBC | TBC |  |  | IACS | PMS-11 / applicable system | R-080 | WPS-01 | A-R-080 | T-R-080-01,T-R-080-02,T-R-080-03 | TBC | AC-R-080 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-081 | Applicability decision; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Document / Certificate | TBC | TBC |  |  | IACS | PMS-11 / applicable system | R-081 | WPS-02 | A-R-081 | T-R-081-01,T-R-081-02,T-R-081-03 | TBC | AC-R-081 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-082 | Rule cross-reference; applicability matrix mapping each IACS item to DNV/class or project basis; exact incorporation path; no standalone statutory treatment. | Document / Certificate | TBC | TBC |  |  | IACS | PMS-11 / applicable system | R-082 | WPS-01 | A-R-082 | T-R-082-01,T-R-082-02,T-R-082-03 | TBC | AC-R-082 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-083 | Contract/specification; project/contract specification, applicable standard list/revision, required clause/section, applicability decision and client/MWS acceptance. | Document / Certificate | TBC | TBC |  |  | Project / Industry | PMS-11 / applicable system | R-083 | WPS-01 | A-R-083 | T-R-083-01,T-R-083-02,T-R-083-03 | TBC | AC-R-083 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-084 | OEM manuals/records; OEM manual, serial/configuration confirmation, mandatory limits, maintenance/test instructions and technical bulletins. | Document / Certificate | TBC | TBC |  |  | OEM | PMS-11 / applicable system | R-084 | WPS-13 | A-R-084 | T-R-084-01,T-R-084-02,T-R-084-03 | TBC | AC-R-084 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-085 | Controlled client/MWS requirement register; controlled contract/SOW, MWS scope, client hold points, insurer/lender conditions if supplied, approval matrix and signed acceptance records. | Document / Certificate | TBC | TBC |  |  | Client / MWS | PMS-11 / applicable system | R-085 | WPS-11 | A-R-085 | T-R-085-01,T-R-085-02,T-R-085-03 | TBC | AC-R-085 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-086 | Verified site data package; authorized site/permit sources, reserve/buffer boundaries, environmental approvals, waste records, pollution controls, spill plan/equipment, reporting contacts and current site data. | Document / Certificate | TBC | TBC |  |  | Project / Engineering | PMS-11 / applicable system | R-086 | WPS-09 | A-R-086 | T-R-086-01,T-R-086-02,T-R-086-03 | TBC | AC-R-086 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-087 | Evidence request/status record; source owner, revision/date, validity/expiry, controlled location, verification result, reviewer and closure reference. | Document / Certificate | TBC | TBC |  |  | Project Governance | PMS-11 / applicable system | R-087 | WPS-16 | A-R-087 | T-R-087-01,T-R-087-02,T-R-087-03 | TBC | AC-R-087 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-088 | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; certificate validity, Flag delegation/RO basis, exemptions/dispensations, survey status, manning/safety/pollution certificates and foreign-port requirements. | Document / Certificate | TBC | TBC |  |  | Egyptian Flag / EAMS baseline carried from original 89-rule source set | PMS-11 / applicable system | R-088 | WPS-02 | A-R-088 | T-R-088-01,T-R-088-02,T-R-088-03 | TBC | AC-R-088 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-089 | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; approved GA/structural drawings, stability booklet, loading manual, load-line evidence where applicable, thickness/condition records and operating restrictions. | Document / Certificate | TBC | TBC |  |  | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set | PMS-11 / applicable system | R-089 | WPS-02 | A-R-089 | T-R-089-01,T-R-089-02,T-R-089-03 | TBC | AC-R-089 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Owner/source; title; revision/date; validity/expiry; PMS-11/equipment identity; applicability; verification result; reviewer; controlled location; closure reference.
E-090 | Current Egyptian Flag certificates, exemptions, dispensations and delegation basis | Statutory | TBC | TBC |  |  | Relevant authority / client / MWS | PMS-11 | R-026:R-050 | WPS-16,WPS-22 | A-R-026… | TBC | G-018,G-019,G-024 | AC-WPS-16-001,AC-WPS-22-001 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Added from user-provided creation instructions and source comparison.
E-091 | Jordan permits, port/VTS/Harbor Master/pilotage and marine survey requirements | Permit / Authority | TBC | TBC |  |  | Relevant authority / client / MWS | PMS-11 | R-026:R-050 | WPS-16,WPS-22 | A-R-026… | TBC | G-018,G-019,G-024 | AC-WPS-16-001,AC-WPS-22-001 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Added from user-provided creation instructions and source comparison.
E-092 | Client/MWS/insurer/lender assurance scope and hold points | Assurance | TBC | TBC |  |  | Relevant authority / client / MWS | PMS-11 | R-026:R-050 | WPS-16,WPS-22 | A-R-026… | TBC | G-018,G-019,G-024 | AC-WPS-16-001,AC-WPS-22-001 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Added from user-provided creation instructions and source comparison.
E-093 | Controlled final readiness dossier, gate decisions and residual-risk acceptances | Decision Record | TBC | TBC |  |  | Relevant authority / client / MWS | PMS-11 | R-026:R-050 | WPS-16,WPS-22 | A-R-026… | TBC | G-018,G-019,G-024 | AC-WPS-16-001,AC-WPS-22-001 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Added from user-provided creation instructions and source comparison.
E-094 | PMS-11 class history / transfer / reclassification history and prior class-entry records | Class History | TBC | TBC |  |  | Current / previous class society as applicable | PMS-11 | R-001 | WPS-01 | A-R-001 | T-R-001-01,T-R-001-02 | G-001 | AC-R-001 | Owner / Document Control | TBC | Missing / To Verify | TBC |  | TBC | Required to assess legacy basis and transfer feasibility.
E-095 | DNV-RU-SHIP versus DNV-RU-OU classification applicability assessment, including exact current DNV rule basis and authority comments | Classification Strategy Assessment | TBC | TBC |  |  | DNV / Owner / Technical Manager | PMS-11 | R-001 | WPS-01 | A-R-001 | T-R-001-02 | G-001 | AC-R-001 | Owner / Technical | TBC | Missing / To Verify | TBC |  | TBC | RU-OU is not assumed from offshore use alone.
E-096 | Alternative IACS class-transfer feasibility package: records availability, survey/reclassification scope, structural/class interfaces, Flag recognition and proposed notation pathway | Class Transfer Feasibility | TBC | TBC |  |  | Proposed Class Society / Egyptian Flag / Owner | PMS-11 | R-001 | WPS-01 | A-R-001 | T-R-001-02,T-R-001-03 | G-001 | AC-R-001 | Owner / Technical | TBC | Missing / To Verify | TBC |  | TBC | No alternative society is selected until a formal feasibility assessment is completed.
E-S-17-01 | Evidence package — Obtain formal DNV suspension notice, class status and violation summary | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | DNV Class Recovery / Reinstatement | SC-17-01 | WPS-17 | A-S-17-01 | T-S-17-01-01,T-S-17-01-02 | G-S-17-01 | AC-S-17-01 | Class Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-17-02 | Evidence package — Agree DNV reinstatement survey scope and attendance plan | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | DNV Class Recovery / Reinstatement | SC-17-02 | WPS-17 | A-S-17-02 | T-S-17-02-01,T-S-17-02-02 | G-S-17-02 | AC-S-17-02 | Class Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-17-03 | Evidence package — Complete hull, machinery, electrical and statutory condition assessment | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | DNV Class Recovery / Reinstatement | SC-17-03 | WPS-17 | A-S-17-03 | T-S-17-03-01,T-S-17-03-02 | G-S-17-03 | AC-S-17-03 | Technical Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-17-04 | Evidence package — Execute repairs, tests and survey closeout | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | DNV Class Recovery / Reinstatement | SC-17-04 | WPS-17 | A-S-17-04 | T-S-17-04-01,T-S-17-04-02 | G-S-17-04 | AC-S-17-04 | Project Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-17-05 | Evidence package — Receive formal DNV reinstatement decision and updated class status | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | DNV Class Recovery / Reinstatement | SC-17-05 | WPS-17 | A-S-17-05 | T-S-17-05-01,T-S-17-05-02 | G-S-17-05 | AC-S-17-05 | Class Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-18-01 | Evidence package — Issue neutral request for information to candidate IACS societies | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Alternative IACS Reclassification / Transfer Feasibility | SC-18-01 | WPS-18 | A-S-18-01 | T-S-18-01-01,T-S-18-01-02 | G-S-18-01 | AC-S-18-01 | Class Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-18-02 | Evidence package — Prepare transfer technical dossier and disclosure register | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Alternative IACS Reclassification / Transfer Feasibility | SC-18-02 | WPS-18 | A-S-18-02 | T-S-18-02-01,T-S-18-02-02 | G-S-18-02 | AC-S-18-02 | Class Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-18-03 | Evidence package — Perform comparative gap, cost and schedule assessment | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Alternative IACS Reclassification / Transfer Feasibility | SC-18-03 | WPS-18 | A-S-18-03 | T-S-18-03-01,T-S-18-03-02 | G-S-18-03 | AC-S-18-03 | Project Controls Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-18-04 | Evidence package — Record management and authority path decision | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Alternative IACS Reclassification / Transfer Feasibility | SC-18-04 | WPS-18 | A-S-18-04 | T-S-18-04-01,T-S-18-04-02 | G-S-18-04 | AC-S-18-04 | Project Director | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-18-05 | Evidence package — If selected, complete transfer surveys and obtain certificate | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Alternative IACS Reclassification / Transfer Feasibility | SC-18-05 | WPS-18 | A-S-18-05 | T-S-18-05-01,T-S-18-05-02 | G-S-18-05 | AC-S-18-05 | Class Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-19-01 | Evidence package — Confirm helideck status, intended aircraft and authority jurisdiction | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Helideck & Aviation Interface Readiness | SC-19-01 | WPS-19 | A-S-19-01 | T-S-19-01-01,T-S-19-01-02 | G-S-19-01 | AC-S-19-01 | Aviation Coordinator | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-19-02 | Evidence package — Review helideck structural, obstacle, marking, lighting and access basis | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Helideck & Aviation Interface Readiness | SC-19-02 | WPS-19 | A-S-19-02 | T-S-19-02-01,T-S-19-02-02 | G-S-19-02 | AC-S-19-02 | Aviation Coordinator | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-19-03 | Evidence package — Review flight operations and marine-aviation interface manual | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Helideck & Aviation Interface Readiness | SC-19-03 | WPS-19 | A-S-19-03 | T-S-19-03-01,T-S-19-03-02 | G-S-19-03 | AC-S-19-03 | Aviation Coordinator | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-19-04 | Evidence package — Verify helideck firefighting, rescue, PPE and trained team | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Helideck & Aviation Interface Readiness | SC-19-04 | WPS-19 | A-S-19-04 | T-S-19-04-01,T-S-19-04-02 | G-S-19-04 | AC-S-19-04 | HSE Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-19-05 | Evidence package — Secure required operational permissions and acceptance evidence | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Helideck & Aviation Interface Readiness | SC-19-05 | WPS-19 | A-S-19-05 | T-S-19-05-01,T-S-19-05-02 | G-S-19-05 | AC-S-19-05 | Aviation Coordinator | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-20-01 | Evidence package — Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Fuel, Emissions, Water & Waste Operational Control | SC-20-01 | WPS-20 | A-S-20-01 | T-S-20-01-01,T-S-20-01-02 | G-S-20-01 | AC-S-20-01 | Environmental Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-20-02 | Evidence package — Verify BDN, fuel samples, changeover procedures and consumption plan | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Fuel, Emissions, Water & Waste Operational Control | SC-20-02 | WPS-20 | A-S-20-02 | T-S-20-02-01,T-S-20-02-02 | G-S-20-02 | AC-S-20-02 | Chief Engineer | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-20-03 | Evidence package — Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Fuel, Emissions, Water & Waste Operational Control | SC-20-03 | WPS-20 | A-S-20-03 | T-S-20-03-01,T-S-20-03-02 | G-S-20-03 | AC-S-20-03 | Chief Engineer | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-20-04 | Evidence package — Commission potable-water and RO systems and obtain laboratory results | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Fuel, Emissions, Water & Waste Operational Control | SC-20-04 | WPS-20 | A-S-20-04 | T-S-20-04-01,T-S-20-04-02 | G-S-20-04 | AC-S-20-04 | Chief Engineer | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-20-05 | Evidence package — Close spill prevention and waste contractor interfaces | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Fuel, Emissions, Water & Waste Operational Control | SC-20-05 | WPS-20 | A-S-20-05 | T-S-20-05-01,T-S-20-05-02 | G-S-20-05 | AC-S-20-05 | Environmental Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-21-01 | Evidence package — Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Digital PMS / CMMS, Spares & Materials Readiness | SC-21-01 | WPS-21 | A-S-21-01 | T-S-21-01-01,T-S-21-01-02 | G-S-21-01 | AC-S-21-01 | Maintenance Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-21-02 | Evidence package — Generate critical defect and overdue-maintenance backlog | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Digital PMS / CMMS, Spares & Materials Readiness | SC-21-02 | WPS-21 | A-S-21-02 | T-S-21-02-01,T-S-21-02-02 | G-S-21-02 | AC-S-21-02 | Maintenance Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-21-03 | Evidence package — Map critical spares/materials to equipment and physically verify stock | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Digital PMS / CMMS, Spares & Materials Readiness | SC-21-03 | WPS-21 | A-S-21-03 | T-S-21-03-01,T-S-21-03-02 | G-S-21-03 | AC-S-21-03 | Stores Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-21-04 | Evidence package — Issue procurement plan for shortages and long-lead items | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Digital PMS / CMMS, Spares & Materials Readiness | SC-21-04 | WPS-21 | A-S-21-04 | T-S-21-04-01,T-S-21-04-02 | G-S-21-04 | AC-S-21-04 | Procurement Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-21-05 | Evidence package — Back up CMMS database and approve mobilization maintenance baseline | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Digital PMS / CMMS, Spares & Materials Readiness | SC-21-05 | WPS-21 | A-S-21-05 | T-S-21-05-01,T-S-21-05-02 | G-S-21-05 | AC-S-21-05 | Maintenance Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-22-01 | Evidence package — Develop approved anchor pattern, deployment sequence and exclusion controls | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Anchor Handling, Control Room & Position Monitoring Operations | SC-22-01 | WPS-22 | A-S-22-01 | T-S-22-01-01,T-S-22-01-02 | G-S-22-01 | AC-S-22-01 | Marine Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-22-02 | Evidence package — Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Anchor Handling, Control Room & Position Monitoring Operations | SC-22-02 | WPS-22 | A-S-22-02 | T-S-22-02-01,T-S-22-02-02 | G-S-22-02 | AC-S-22-02 | Survey Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-22-03 | Evidence package — Test winches, brakes, controls, communications and emergency release | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Anchor Handling, Control Room & Position Monitoring Operations | SC-22-03 | WPS-22 | A-S-22-03 | T-S-22-03-01,T-S-22-03-02 | G-S-22-03 | AC-S-22-03 | Marine Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-22-04 | Evidence package — Approve tug assignment, command hierarchy and standard communications | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Anchor Handling, Control Room & Position Monitoring Operations | SC-22-04 | WPS-22 | A-S-22-04 | T-S-22-04-01,T-S-22-04-02 | G-S-22-04 | AC-S-22-04 | Marine Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-22-05 | Evidence package — Conduct anchor-handling tabletop and operational drill | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Anchor Handling, Control Room & Position Monitoring Operations | SC-22-05 | WPS-22 | A-S-22-05 | T-S-22-05-01,T-S-22-05-02 | G-S-22-05 | AC-S-22-05 | Marine Superintendent | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-23-01 | Evidence package — Approve departmental manpower, competency and rotation matrix | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Crew Mobilization, Medical & Behavioral Safety | SC-23-01 | WPS-23 | A-S-23-01 | T-S-23-01-01,T-S-23-01-02 | G-S-23-01 | AC-S-23-01 | HR Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-23-02 | Evidence package — Verify clinic equipment, medicines, licenses and medevac interface | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Crew Mobilization, Medical & Behavioral Safety | SC-23-02 | WPS-23 | A-S-23-02 | T-S-23-02-01,T-S-23-02-02 | G-S-23-02 | AC-S-23-02 | Medical Coordinator | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-23-03 | Evidence package — Implement fatigue, rest-hour and drug/alcohol policy controls | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Crew Mobilization, Medical & Behavioral Safety | SC-23-03 | WPS-23 | A-S-23-03 | T-S-23-03-01,T-S-23-03-02 | G-S-23-03 | AC-S-23-03 | HSE Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-23-04 | Evidence package — Complete visas, travel, repatriation and crew-change logistics | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Crew Mobilization, Medical & Behavioral Safety | SC-23-04 | WPS-23 | A-S-23-04 | T-S-23-04-01,T-S-23-04-02 | G-S-23-04 | AC-S-23-04 | HR Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-24-01 | Evidence package — Issue integrated emergency response and shore-interface matrix | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Integrated Operational & Emergency Readiness | SC-24-01 | WPS-24 | A-S-24-01 | T-S-24-01-01,T-S-24-01-02 | G-S-24-01 | AC-S-24-01 | HSE Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-24-02 | Evidence package — Define scenario drill programme and measurable acceptance criteria | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Integrated Operational & Emergency Readiness | SC-24-02 | WPS-24 | A-S-24-02 | T-S-24-02-01,T-S-24-02-02 | G-S-24-02 | AC-S-24-02 | HSE Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-24-03 | Evidence package — Conduct marine, aviation, diving, pollution and medevac interface drills | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Integrated Operational & Emergency Readiness | SC-24-03 | WPS-24 | A-S-24-03 | T-S-24-03-01,T-S-24-03-02 | G-S-24-03 | AC-S-24-03 | Project Manager | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.
E-S-24-04 | Evidence package — Close drill findings and issue final operational readiness recommendation | Supplemental Control Evidence | TBC | Rev0 |  |  | Relevant issuing authority / competent person as applicable | Integrated Operational & Emergency Readiness | SC-24-04 | WPS-24 | A-S-24-04 | T-S-24-04-01,T-S-24-04-02 | G-S-24-04 | AC-S-24-04 | Project Director | TBC | Missing |  |  |  | Controlled evidence request; applicability and authority route must be confirmed before acceptance.

## Gates
Gate ID | Gate Name | Objective | Required WPS IDs | Required Activities | Required Deliverables | Critical Gaps Allowed | No-Go Conditions | Acceptance Criteria IDs | Approving Authority | Review Date | Status | Decision | Decision Evidence | Open Conditions | Notes
GATE-0 | Evidence Baseline | Evidence Baseline | WPS-01,WPS-02,WPS-03,WPS-04,WPS-05,WPS-06,WPS-07,WPS-08,WPS-09,WPS-10,WPS-11,WPS-12,WPS-13,WPS-14,WPS-15,WPS-16,WPS-17,WPS-18,WPS-19,WPS-20,WPS-21,WPS-22,WPS-23,WPS-24 | A-R-001,A-R-002,A-R-004,A-R-005,A-R-008,A-R-080,A-R-082,A-R-083,A-R-003,A-R-006,A-R-007,A-R-081,A-R-088,A-R-089,A-R-009,A-R-010,A-R-011,A-R-016,A-R-017,A-R-018,A-R-012,A-R-013,A-R-014,A-R-015,A-R-019,A-R-020,A-R-021,A-R-022,A-R-023,A-R-024,A-R-025,A-R-026,A-R-027,A-R-028,A-R-029,A-R-030,A-R-031,A-R-036,A-R-032,A-R-033,A-R-034,A-R-071,A-R-075,A-R-076,A-R-077,A-R-078,A-R-086,A-R-037,A-R-038,A-R-039,A-R-040,A-R-041,A-R-042,A-R-035,A-R-043,A-R-085,A-R-044,A-R-045,A-R-046,A-R-047,A-R-048,A-R-049,A-R-050,A-R-059,A-R-060,A-R-084,A-R-051,A-R-052,A-R-053,A-R-054,A-R-072,A-R-073,A-R-055,A-R-056,A-R-057,A-R-058,A-R-061,A-R-062,A-R-063,A-R-064,A-R-065,A-R-066,A-R-067,A-R-068,A-R-069,A-R-070,A-R-074,A-R-079,A-R-087,A-S-17-01,A-S-17-02,A-S-17-03,A-S-17-04,A-S-17-05,A-S-18-01,A-S-18-02,A-S-18-03,A-S-18-04,A-S-18-05,A-S-19-01,A-S-19-02,A-S-19-03,A-S-19-04,A-S-19-05,A-S-20-01,A-S-20-02,A-S-20-03,A-S-20-04,A-S-20-05,A-S-21-01,A-S-21-02,A-S-21-03,A-S-21-04,A-S-21-05,A-S-22-01,A-S-22-02,A-S-22-03,A-S-22-04,A-S-22-05,A-S-23-01,A-S-23-02,A-S-23-03,A-S-23-04,A-S-24-01,A-S-24-02,A-S-24-03,A-S-24-04 | D-R-001,D-R-002,D-R-003,D-R-004,D-R-005,D-R-006,D-R-007,D-R-008,D-R-009,D-R-010,D-R-011,D-R-012,D-R-013,D-R-014,D-R-015,D-R-016,D-R-017,D-R-018,D-R-019,D-R-020,D-R-021,D-R-022,D-R-023,D-R-024,D-R-025,D-R-026,D-R-027,D-R-028,D-R-029,D-R-030,D-R-031,D-R-032,D-R-033,D-R-034,D-R-035,D-R-036,D-R-037,D-R-038,D-R-039,D-R-040,D-R-041,D-R-042,D-R-043,D-R-044,D-R-045,D-R-046,D-R-047,D-R-048,D-R-049,D-R-050,D-R-051,D-R-052,D-R-053,D-R-054,D-R-055,D-R-056,D-R-057,D-R-058,D-R-059,D-R-060,D-R-061,D-R-062,D-R-063,D-R-064,D-R-065,D-R-066,D-R-067,D-R-068,D-R-069,D-R-070,D-R-071,D-R-072,D-R-073,D-R-074,D-R-075,D-R-076,D-R-077,D-R-078,D-R-079,D-R-080,D-R-081,D-R-082,D-R-083,D-R-084,D-R-085,D-R-086,D-R-087,D-R-088,D-R-089,D-S-17-01,D-S-17-02,D-S-17-03,D-S-17-04,D-S-17-05,D-S-18-01,D-S-18-02,D-S-18-03,D-S-18-04,D-S-18-05,D-S-19-01,D-S-19-02,D-S-19-03,D-S-19-04,D-S-19-05,D-S-20-01,D-S-20-02,D-S-20-03,D-S-20-04,D-S-20-05,D-S-21-01,D-S-21-02,D-S-21-03,D-S-21-04,D-S-21-05,D-S-22-01,D-S-22-02,D-S-22-03,D-S-22-04,D-S-22-05,D-S-23-01,D-S-23-02,D-S-23-03,D-S-23-04,D-S-24-01,D-S-24-02,D-S-24-03,D-S-24-04 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | No uncontrolled baseline | AC-R-001,AC-R-002,AC-R-003,AC-R-004,AC-R-005,AC-R-006,AC-R-007,AC-R-008,AC-R-009,AC-R-010,AC-R-011,AC-R-012,AC-R-013,AC-R-014,AC-R-015,AC-R-016,AC-R-017,AC-R-018,AC-R-019,AC-R-020,AC-R-021,AC-R-022,AC-R-023,AC-R-024,AC-R-025,AC-R-026,AC-R-027,AC-R-028,AC-R-029,AC-R-030,AC-R-031,AC-R-032,AC-R-033,AC-R-034,AC-R-035,AC-R-036,AC-R-037,AC-R-038,AC-R-039,AC-R-040,AC-R-041,AC-R-042,AC-R-043,AC-R-044,AC-R-045,AC-R-046,AC-R-047,AC-R-048,AC-R-049,AC-R-050,AC-R-051,AC-R-052,AC-R-053,AC-R-054,AC-R-055,AC-R-056,AC-R-057,AC-R-058,AC-R-059,AC-R-060,AC-R-061,AC-R-062,AC-R-063,AC-R-064,AC-R-065,AC-R-066,AC-R-067,AC-R-068,AC-R-069,AC-R-070,AC-R-071,AC-R-072,AC-R-073,AC-R-074,AC-R-075,AC-R-076,AC-R-077,AC-R-078,AC-R-079,AC-R-080,AC-R-081,AC-R-082,AC-R-083,AC-R-084,AC-R-085,AC-R-086,AC-R-087,AC-R-088,AC-R-089,AC-WPS-01-001,AC-WPS-02-001,AC-WPS-03-001,AC-WPS-04-001,AC-WPS-05-001,AC-WPS-06-001,AC-WPS-07-001,AC-WPS-08-001,AC-WPS-09-001,AC-WPS-10-001,AC-WPS-11-001,AC-WPS-12-001,AC-WPS-13-001,AC-WPS-14-001,AC-WPS-15-001,AC-WPS-16-001,AC-S-17-01,AC-S-17-02,AC-S-17-03,AC-S-17-04,AC-S-17-05,AC-S-18-01,AC-S-18-02,AC-S-18-03,AC-S-18-04,AC-S-18-05,AC-S-19-01,AC-S-19-02,AC-S-19-03,AC-S-19-04,AC-S-19-05,AC-S-20-01,AC-S-20-02,AC-S-20-03,AC-S-20-04,AC-S-20-05,AC-S-21-01,AC-S-21-02,AC-S-21-03,AC-S-21-04,AC-S-21-05,AC-S-22-01,AC-S-22-02,AC-S-22-03,AC-S-22-04,AC-S-22-05,AC-S-23-01,AC-S-23-02,AC-S-23-03,AC-S-23-04,AC-S-24-01,AC-S-24-02,AC-S-24-03,AC-S-24-04 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-1 | Class / Reclassification Strategy / Flag / Structural Basis | Confirm current class status and notation, governing rule edition, Flag/statutory basis, structural/stability basis, and formally assess viable class-regime/reclassification paths. | WPS-01,WPS-02,WPS-17,WPS-18 | A-R-001,A-R-002,A-R-004,A-R-005,A-R-008,A-R-080,A-R-082,A-R-083,A-R-003,A-R-006,A-R-007,A-R-081,A-R-088,A-R-089,A-S-17-01,A-S-17-02,A-S-17-03,A-S-17-04,A-S-17-05,A-S-18-01,A-S-18-02,A-S-18-03,A-S-18-04,A-S-18-05 | D-R-001,D-R-002,D-R-003,D-R-004,D-R-005,D-R-006,D-R-007,D-R-008,D-R-080,D-R-081,D-R-082,D-R-083,D-R-088,D-R-089,D-S-17-01,D-S-17-02,D-S-17-03,D-S-17-04,D-S-17-05,D-S-18-01,D-S-18-02,D-S-18-03,D-S-18-04,D-S-18-05 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Current class or reclassification strategy unresolved; notation/scope unverified; rule edition unresolved; structural/stability basis unresolved; or required authority disposition absent. | AC-R-001,AC-R-002,AC-R-003,AC-R-004,AC-R-005,AC-R-006,AC-R-007,AC-R-008,AC-R-080,AC-R-081,AC-R-082,AC-R-083,AC-R-088,AC-R-089,AC-WPS-01-001,AC-WPS-02-001,AC-S-17-01,AC-S-17-02,AC-S-17-03,AC-S-17-04,AC-S-17-05,AC-S-18-01,AC-S-18-02,AC-S-18-03,AC-S-18-04,AC-S-18-05 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-2 | Critical Lifting Basis | Critical Lifting Basis | WPS-03,WPS-04,WPS-05 | A-R-009,A-R-010,A-R-011,A-R-016,A-R-017,A-R-018,A-R-012,A-R-013,A-R-014,A-R-015 | D-R-009,D-R-010,D-R-011,D-R-012,D-R-013,D-R-014,D-R-015,D-R-016,D-R-017,D-R-018 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Unverified critical lifting appliance | AC-R-009,AC-R-010,AC-R-011,AC-R-012,AC-R-013,AC-R-014,AC-R-015,AC-R-016,AC-R-017,AC-R-018,AC-WPS-03-001,AC-WPS-04-001,AC-WPS-05-001 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-3 | Mooring / Pipe-Lay / Site Engineering | Mooring / Pipe-Lay / Site Engineering | WPS-06,WPS-07,WPS-08,WPS-09,WPS-22 | A-R-019,A-R-020,A-R-021,A-R-022,A-R-023,A-R-024,A-R-025,A-R-026,A-R-027,A-R-028,A-R-029,A-R-030,A-R-031,A-R-036,A-R-032,A-R-033,A-R-034,A-R-071,A-R-075,A-R-076,A-R-077,A-R-078,A-R-086,A-S-22-01,A-S-22-02,A-S-22-03,A-S-22-04,A-S-22-05 | D-R-019,D-R-020,D-R-021,D-R-022,D-R-023,D-R-024,D-R-025,D-R-026,D-R-027,D-R-028,D-R-029,D-R-030,D-R-031,D-R-032,D-R-033,D-R-034,D-R-036,D-R-071,D-R-075,D-R-076,D-R-077,D-R-078,D-R-086,D-S-22-01,D-S-22-02,D-S-22-03,D-S-22-04,D-S-22-05 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Missing site inputs or unaccepted analysis | AC-R-019,AC-R-020,AC-R-021,AC-R-022,AC-R-023,AC-R-024,AC-R-025,AC-R-026,AC-R-027,AC-R-028,AC-R-029,AC-R-030,AC-R-031,AC-R-032,AC-R-033,AC-R-034,AC-R-036,AC-R-071,AC-R-075,AC-R-076,AC-R-077,AC-R-078,AC-R-086,AC-WPS-06-001,AC-WPS-07-001,AC-WPS-08-001,AC-WPS-09-001,AC-S-22-01,AC-S-22-02,AC-S-22-03,AC-S-22-04,AC-S-22-05 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-4 | External / Jordan / MWS Requirements | External / Jordan / MWS Requirements | WPS-11,WPS-15,WPS-23,WPS-16 | A-R-035,A-R-043,A-R-085,A-R-055,A-R-056,A-R-057,A-R-058,A-S-23-01,A-S-23-02,A-S-23-03,A-S-23-04,A-R-061,A-R-062,A-R-063,A-R-064,A-R-065,A-R-066,A-R-067,A-R-068,A-R-069,A-R-070,A-R-074,A-R-079,A-R-087 | D-R-035,D-R-043,D-R-055,D-R-056,D-R-057,D-R-058,D-R-061,D-R-062,D-R-063,D-R-064,D-R-065,D-R-066,D-R-067,D-R-068,D-R-069,D-R-070,D-R-074,D-R-079,D-R-085,D-R-087,D-S-23-01,D-S-23-02,D-S-23-03,D-S-23-04 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Required authority/permit route unknown | AC-R-035,AC-R-043,AC-R-055,AC-R-056,AC-R-057,AC-R-058,AC-R-061,AC-R-062,AC-R-063,AC-R-064,AC-R-065,AC-R-066,AC-R-067,AC-R-068,AC-R-069,AC-R-070,AC-R-074,AC-R-079,AC-R-085,AC-R-087,AC-WPS-11-001,AC-WPS-15-001,AC-WPS-16-001,AC-S-23-01,AC-S-23-02,AC-S-23-03,AC-S-23-04 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-5 | Departure / Wet Tow Readiness | Departure / Wet Tow Readiness | WPS-10 | A-R-037,A-R-038,A-R-039,A-R-040,A-R-041,A-R-042 | D-R-037,D-R-038,D-R-039,D-R-040,D-R-041,D-R-042 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Tow/stability/watertight/emergency failure | AC-R-037,AC-R-038,AC-R-039,AC-R-040,AC-R-041,AC-R-042,AC-WPS-10-001 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-6 | Aqaba Arrival / Port Readiness | Aqaba Arrival / Port Readiness | WPS-14,WPS-16 | A-R-051,A-R-052,A-R-053,A-R-054,A-R-072,A-R-073,A-R-061,A-R-062,A-R-063,A-R-064,A-R-065,A-R-066,A-R-067,A-R-068,A-R-069,A-R-070,A-R-074,A-R-079,A-R-087 | D-R-051,D-R-052,D-R-053,D-R-054,D-R-061,D-R-062,D-R-063,D-R-064,D-R-065,D-R-066,D-R-067,D-R-068,D-R-069,D-R-070,D-R-072,D-R-073,D-R-074,D-R-079,D-R-087 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Port/VTS/customs/health route unresolved | AC-R-051,AC-R-052,AC-R-053,AC-R-054,AC-R-061,AC-R-062,AC-R-063,AC-R-064,AC-R-065,AC-R-066,AC-R-067,AC-R-068,AC-R-069,AC-R-070,AC-R-072,AC-R-073,AC-R-074,AC-R-079,AC-R-087,AC-WPS-14-001,AC-WPS-16-001 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-7 | Offshore Systems / Diving / Competence | Offshore Systems / Diving / Competence | WPS-12,WPS-13,WPS-14,WPS-19,WPS-20,WPS-21,WPS-23 | A-R-044,A-R-045,A-R-046,A-R-047,A-R-048,A-R-049,A-R-050,A-R-059,A-R-060,A-R-084,A-R-051,A-R-052,A-R-053,A-R-054,A-R-072,A-R-073,A-S-19-01,A-S-19-02,A-S-19-03,A-S-19-04,A-S-19-05,A-S-20-01,A-S-20-02,A-S-20-03,A-S-20-04,A-S-20-05,A-S-21-01,A-S-21-02,A-S-21-03,A-S-21-04,A-S-21-05,A-S-23-01,A-S-23-02,A-S-23-03,A-S-23-04 | D-R-044,D-R-045,D-R-046,D-R-047,D-R-048,D-R-049,D-R-050,D-R-051,D-R-052,D-R-053,D-R-054,D-R-059,D-R-060,D-R-072,D-R-073,D-R-084,D-S-19-01,D-S-19-02,D-S-19-03,D-S-19-04,D-S-19-05,D-S-20-01,D-S-20-02,D-S-20-03,D-S-20-04,D-S-20-05,D-S-21-01,D-S-21-02,D-S-21-03,D-S-21-04,D-S-21-05,D-S-23-01,D-S-23-02,D-S-23-03,D-S-23-04 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Critical system/person/equipment evidence missing | AC-R-044,AC-R-045,AC-R-046,AC-R-047,AC-R-048,AC-R-049,AC-R-050,AC-R-051,AC-R-052,AC-R-053,AC-R-054,AC-R-059,AC-R-060,AC-R-072,AC-R-073,AC-R-084,AC-WPS-12-001,AC-WPS-13-001,AC-WPS-14-001,AC-S-19-01,AC-S-19-02,AC-S-19-03,AC-S-19-04,AC-S-19-05,AC-S-20-01,AC-S-20-02,AC-S-20-03,AC-S-20-04,AC-S-20-05,AC-S-21-01,AC-S-21-02,AC-S-21-03,AC-S-21-04,AC-S-21-05,AC-S-23-01,AC-S-23-02,AC-S-23-03,AC-S-23-04 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.
GATE-8 | Operational Assurance / Final Decision | Operational Assurance / Final Decision | WPS-13,WPS-16,WPS-20,WPS-24 | A-R-049,A-R-050,A-R-059,A-R-060,A-R-084,A-R-061,A-R-062,A-R-063,A-R-064,A-R-065,A-R-066,A-R-067,A-R-068,A-R-069,A-R-070,A-R-074,A-R-079,A-R-087,A-S-20-01,A-S-20-02,A-S-20-03,A-S-20-04,A-S-20-05,A-S-24-01,A-S-24-02,A-S-24-03,A-S-24-04 | D-R-049,D-R-050,D-R-059,D-R-060,D-R-061,D-R-062,D-R-063,D-R-064,D-R-065,D-R-066,D-R-067,D-R-068,D-R-069,D-R-070,D-R-074,D-R-079,D-R-084,D-R-087,D-S-20-01,D-S-20-02,D-S-20-03,D-S-20-04,D-S-20-05,D-S-24-01,D-S-24-02,D-S-24-03,D-S-24-04 | No Critical gap may be accepted solely by percentage complete; formal authority decision required. | Open critical gap without formal disposition | AC-R-049,AC-R-050,AC-R-059,AC-R-060,AC-R-061,AC-R-062,AC-R-063,AC-R-064,AC-R-065,AC-R-066,AC-R-067,AC-R-068,AC-R-069,AC-R-070,AC-R-074,AC-R-079,AC-R-084,AC-R-087,AC-WPS-13-001,AC-WPS-16-001,AC-S-20-01,AC-S-20-02,AC-S-20-03,AC-S-20-04,AC-S-20-05,AC-S-24-01,AC-S-24-02,AC-S-24-03,AC-S-24-04 | Relevant authority / DNV / Flag / Jordan / MWS / Client as applicable |  | Not Started | Not decided | TBC | TBC | Source gate retained; detailed evidence and signed decision required.

## Execution
Execution ID | WPS ID | Activity / Task Title | Source Type | Canonical Reference | Responsible Department | Discipline Lead | Accountable Manager | Logical Predecessor IDs | Schedule Predecessor IDs | Relationship Type | Lag Days | Planned Start | Planned Finish | Forecast Finish | Actual Start | Actual Finish | Duration Days | Status | Completion % | Weight % | Earned Progress % | Estimated Cost | Approved Budget | Committed Cost | Actual Cost | Estimate at Completion | Budget Variance | Currency | Manpower Required | Planned Manhours | Actual Manhours | Materials Required | Spare Parts Required | Procurement Status | Procurement Lead Time Days | Long Lead Item | Required On Site | Evidence Required | Acceptance Authority | Risk Level | Blocking Gate | Classified Input Ref | Comments | Remaining Estimate | Overdue | Data Quality
T-R-001-01 | WPS-01 | Obtain and control current DNV Class Certificate, Class Status Report, complete notation/scope, class history and records needed to evaluate DNV-RU-SHIP, DNV-RU-OU and alternative IACS class-transfer pathways. | Canonical Task | A-R-001 |  | Rule/WPS owner to be assigned |  | GATE-0 | GATE-0 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-001-02 | WPS-01 | Verify applicability and technical sufficiency: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Canonical Task | A-R-001 |  | Rule/WPS owner to be assigned |  | T-R-001-01 | T-R-001-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-001-03 | WPS-01 | Issue acceptance or escalation record: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Canonical Task | A-R-001 |  | Rule/WPS owner to be assigned |  | T-R-001-02 | T-R-001-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-002-01 | WPS-01 | Obtain and control source evidence: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Canonical Task | A-R-002 |  | Rule/WPS owner to be assigned |  | T-R-001-03 | T-R-001-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-002-02 | WPS-01 | Verify applicability and technical sufficiency: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Canonical Task | A-R-002 |  | Rule/WPS owner to be assigned |  | T-R-002-01 | T-R-002-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-002-03 | WPS-01 | Issue acceptance or escalation record: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Canonical Task | A-R-002 |  | Rule/WPS owner to be assigned |  | T-R-002-02 | T-R-002-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-003-01 | WPS-02 | Obtain and control source evidence: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Canonical Task | A-R-003 |  | Rule/WPS owner to be assigned |  | T-R-002-03 | T-R-002-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-003-02 | WPS-02 | Verify applicability and technical sufficiency: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Canonical Task | A-R-003 |  | Rule/WPS owner to be assigned |  | T-R-003-01 | T-R-003-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-003-03 | WPS-02 | Issue acceptance or escalation record: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Canonical Task | A-R-003 |  | Rule/WPS owner to be assigned |  | T-R-003-02 | T-R-003-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-004-01 | WPS-01 | Obtain and control source evidence: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Canonical Task | A-R-004 |  | Rule/WPS owner to be assigned |  | T-R-003-03 | T-R-003-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-004-02 | WPS-01 | Verify applicability and technical sufficiency: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Canonical Task | A-R-004 |  | Rule/WPS owner to be assigned |  | T-R-004-01 | T-R-004-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-004-03 | WPS-01 | Issue acceptance or escalation record: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Canonical Task | A-R-004 |  | Rule/WPS owner to be assigned |  | T-R-004-02 | T-R-004-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-005-01 | WPS-01 | Obtain and control source evidence: Identify approved drawings and documents forming the class technical basis. | Canonical Task | A-R-005 |  | Rule/WPS owner to be assigned |  | T-R-004-03 | T-R-004-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-005-02 | WPS-01 | Verify applicability and technical sufficiency: Identify approved drawings and documents forming the class technical basis. | Canonical Task | A-R-005 |  | Rule/WPS owner to be assigned |  | T-R-005-01 | T-R-005-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-005-03 | WPS-01 | Issue acceptance or escalation record: Identify approved drawings and documents forming the class technical basis. | Canonical Task | A-R-005 |  | Rule/WPS owner to be assigned |  | T-R-005-02 | T-R-005-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-006-01 | WPS-02 | Obtain and control source evidence: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Canonical Task | A-R-006 |  | Rule/WPS owner to be assigned |  | T-R-005-03 | T-R-005-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-006-02 | WPS-02 | Verify applicability and technical sufficiency: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Canonical Task | A-R-006 |  | Rule/WPS owner to be assigned |  | T-R-006-01 | T-R-006-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-006-03 | WPS-02 | Issue acceptance or escalation record: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Canonical Task | A-R-006 |  | Rule/WPS owner to be assigned |  | T-R-006-02 | T-R-006-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-007-01 | WPS-02 | Obtain and control source evidence: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Canonical Task | A-R-007 |  | Rule/WPS owner to be assigned |  | T-R-006-03 | T-R-006-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-007-02 | WPS-02 | Verify applicability and technical sufficiency: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Canonical Task | A-R-007 |  | Rule/WPS owner to be assigned |  | T-R-007-01 | T-R-007-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-007-03 | WPS-02 | Issue acceptance or escalation record: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Canonical Task | A-R-007 |  | Rule/WPS owner to be assigned |  | T-R-007-02 | T-R-007-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-008-01 | WPS-01 | Obtain and control source evidence: Establish the approved operating limits and service scope relevant to Jordan operations. | Canonical Task | A-R-008 |  | Rule/WPS owner to be assigned |  | T-R-007-03 | T-R-007-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-008-02 | WPS-01 | Verify applicability and technical sufficiency: Establish the approved operating limits and service scope relevant to Jordan operations. | Canonical Task | A-R-008 |  | Rule/WPS owner to be assigned |  | T-R-008-01 | T-R-008-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-008-03 | WPS-01 | Issue acceptance or escalation record: Establish the approved operating limits and service scope relevant to Jordan operations. | Canonical Task | A-R-008 |  | Rule/WPS owner to be assigned |  | T-R-008-02 | T-R-008-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-009-01 | WPS-03 | Obtain and control source evidence: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Canonical Task | A-R-009 |  | Rule/WPS owner to be assigned |  | T-R-008-03 | T-R-008-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-009-02 | WPS-03 | Verify applicability and technical sufficiency: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Canonical Task | A-R-009 |  | Rule/WPS owner to be assigned |  | T-R-009-01 | T-R-009-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-009-03 | WPS-03 | Issue acceptance or escalation record: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Canonical Task | A-R-009 |  | Rule/WPS owner to be assigned |  | T-R-009-02 | T-R-009-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-010-01 | WPS-03 | Obtain and control source evidence: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Canonical Task | A-R-010 |  | Rule/WPS owner to be assigned |  | T-R-009-03 | T-R-009-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-010-02 | WPS-03 | Verify applicability and technical sufficiency: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Canonical Task | A-R-010 |  | Rule/WPS owner to be assigned |  | T-R-010-01 | T-R-010-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-010-03 | WPS-03 | Issue acceptance or escalation record: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Canonical Task | A-R-010 |  | Rule/WPS owner to be assigned |  | T-R-010-02 | T-R-010-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-011-01 | WPS-03 | Obtain and control source evidence: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Canonical Task | A-R-011 |  | Rule/WPS owner to be assigned |  | T-R-010-03 | T-R-010-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-011-02 | WPS-03 | Verify applicability and technical sufficiency: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Canonical Task | A-R-011 |  | Rule/WPS owner to be assigned |  | T-R-011-01 | T-R-011-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-011-03 | WPS-03 | Issue acceptance or escalation record: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Canonical Task | A-R-011 |  | Rule/WPS owner to be assigned |  | T-R-011-02 | T-R-011-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-012-01 | WPS-04 | Obtain and control source evidence: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Canonical Task | A-R-012 |  | Rule/WPS owner to be assigned |  | T-R-011-03 | T-R-011-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-012-02 | WPS-04 | Verify applicability and technical sufficiency: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Canonical Task | A-R-012 |  | Rule/WPS owner to be assigned |  | T-R-012-01 | T-R-012-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-012-03 | WPS-04 | Issue acceptance or escalation record: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Canonical Task | A-R-012 |  | Rule/WPS owner to be assigned |  | T-R-012-02 | T-R-012-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-013-01 | WPS-04 | Obtain and control source evidence: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Canonical Task | A-R-013 |  | Rule/WPS owner to be assigned |  | T-R-012-03 | T-R-012-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-013-02 | WPS-04 | Verify applicability and technical sufficiency: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Canonical Task | A-R-013 |  | Rule/WPS owner to be assigned |  | T-R-013-01 | T-R-013-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-013-03 | WPS-04 | Issue acceptance or escalation record: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Canonical Task | A-R-013 |  | Rule/WPS owner to be assigned |  | T-R-013-02 | T-R-013-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-014-01 | WPS-05 | Obtain and control source evidence: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Canonical Task | A-R-014 |  | Rule/WPS owner to be assigned |  | T-R-013-03 | T-R-013-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-014-02 | WPS-05 | Verify applicability and technical sufficiency: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Canonical Task | A-R-014 |  | Rule/WPS owner to be assigned |  | T-R-014-01 | T-R-014-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-014-03 | WPS-05 | Issue acceptance or escalation record: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Canonical Task | A-R-014 |  | Rule/WPS owner to be assigned |  | T-R-014-02 | T-R-014-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-015-01 | WPS-05 | Obtain and control source evidence: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Canonical Task | A-R-015 |  | Rule/WPS owner to be assigned |  | T-R-014-03 | T-R-014-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-015-02 | WPS-05 | Verify applicability and technical sufficiency: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Canonical Task | A-R-015 |  | Rule/WPS owner to be assigned |  | T-R-015-01 | T-R-015-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-015-03 | WPS-05 | Issue acceptance or escalation record: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Canonical Task | A-R-015 |  | Rule/WPS owner to be assigned |  | T-R-015-02 | T-R-015-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-016-01 | WPS-03 | Obtain and control source evidence: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Canonical Task | A-R-016 |  | Rule/WPS owner to be assigned |  | T-R-015-03 | T-R-015-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-016-02 | WPS-03 | Verify applicability and technical sufficiency: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Canonical Task | A-R-016 |  | Rule/WPS owner to be assigned |  | T-R-016-01 | T-R-016-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-016-03 | WPS-03 | Issue acceptance or escalation record: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Canonical Task | A-R-016 |  | Rule/WPS owner to be assigned |  | T-R-016-02 | T-R-016-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-017-01 | WPS-03 | Obtain and control source evidence: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Canonical Task | A-R-017 |  | Rule/WPS owner to be assigned |  | T-R-016-03 | T-R-016-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-017-02 | WPS-03 | Verify applicability and technical sufficiency: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Canonical Task | A-R-017 |  | Rule/WPS owner to be assigned |  | T-R-017-01 | T-R-017-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-017-03 | WPS-03 | Issue acceptance or escalation record: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Canonical Task | A-R-017 |  | Rule/WPS owner to be assigned |  | T-R-017-02 | T-R-017-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-018-01 | WPS-03 | Obtain and control source evidence: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Canonical Task | A-R-018 |  | Rule/WPS owner to be assigned |  | T-R-017-03 | T-R-017-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-018-02 | WPS-03 | Verify applicability and technical sufficiency: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Canonical Task | A-R-018 |  | Rule/WPS owner to be assigned |  | T-R-018-01 | T-R-018-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-018-03 | WPS-03 | Issue acceptance or escalation record: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Canonical Task | A-R-018 |  | Rule/WPS owner to be assigned |  | T-R-018-02 | T-R-018-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-019-01 | WPS-06 | Obtain and control source evidence: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Canonical Task | A-R-019 |  | Rule/WPS owner to be assigned |  | T-R-018-03 | T-R-018-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-019-02 | WPS-06 | Verify applicability and technical sufficiency: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Canonical Task | A-R-019 |  | Rule/WPS owner to be assigned |  | T-R-019-01 | T-R-019-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-019-03 | WPS-06 | Issue acceptance or escalation record: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Canonical Task | A-R-019 |  | Rule/WPS owner to be assigned |  | T-R-019-02 | T-R-019-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-020-01 | WPS-06 | Obtain and control source evidence: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Canonical Task | A-R-020 |  | Rule/WPS owner to be assigned |  | T-R-019-03 | T-R-019-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-020-02 | WPS-06 | Verify applicability and technical sufficiency: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Canonical Task | A-R-020 |  | Rule/WPS owner to be assigned |  | T-R-020-01 | T-R-020-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-020-03 | WPS-06 | Issue acceptance or escalation record: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Canonical Task | A-R-020 |  | Rule/WPS owner to be assigned |  | T-R-020-02 | T-R-020-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-021-01 | WPS-06 | Obtain and control source evidence: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Canonical Task | A-R-021 |  | Rule/WPS owner to be assigned |  | T-R-020-03 | T-R-020-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-021-02 | WPS-06 | Verify applicability and technical sufficiency: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Canonical Task | A-R-021 |  | Rule/WPS owner to be assigned |  | T-R-021-01 | T-R-021-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-021-03 | WPS-06 | Issue acceptance or escalation record: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Canonical Task | A-R-021 |  | Rule/WPS owner to be assigned |  | T-R-021-02 | T-R-021-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-022-01 | WPS-06 | Obtain and control source evidence: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Canonical Task | A-R-022 |  | Rule/WPS owner to be assigned |  | T-R-021-03 | T-R-021-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-022-02 | WPS-06 | Verify applicability and technical sufficiency: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Canonical Task | A-R-022 |  | Rule/WPS owner to be assigned |  | T-R-022-01 | T-R-022-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-022-03 | WPS-06 | Issue acceptance or escalation record: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Canonical Task | A-R-022 |  | Rule/WPS owner to be assigned |  | T-R-022-02 | T-R-022-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-023-01 | WPS-07 | Obtain and control source evidence: Verify welding stations, coating station and related QA/QC controls. | Canonical Task | A-R-023 |  | Rule/WPS owner to be assigned |  | T-R-022-03 | T-R-022-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-023-02 | WPS-07 | Verify applicability and technical sufficiency: Verify welding stations, coating station and related QA/QC controls. | Canonical Task | A-R-023 |  | Rule/WPS owner to be assigned |  | T-R-023-01 | T-R-023-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-023-03 | WPS-07 | Issue acceptance or escalation record: Verify welding stations, coating station and related QA/QC controls. | Canonical Task | A-R-023 |  | Rule/WPS owner to be assigned |  | T-R-023-02 | T-R-023-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-024-01 | WPS-07 | Obtain and control source evidence: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Canonical Task | A-R-024 |  | Rule/WPS owner to be assigned |  | T-R-023-03 | T-R-023-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-024-02 | WPS-07 | Verify applicability and technical sufficiency: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Canonical Task | A-R-024 |  | Rule/WPS owner to be assigned |  | T-R-024-01 | T-R-024-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-024-03 | WPS-07 | Issue acceptance or escalation record: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Canonical Task | A-R-024 |  | Rule/WPS owner to be assigned |  | T-R-024-02 | T-R-024-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-025-01 | WPS-07 | Obtain and control source evidence: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Canonical Task | A-R-025 |  | Rule/WPS owner to be assigned |  | T-R-024-03 | T-R-024-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-025-02 | WPS-07 | Verify applicability and technical sufficiency: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Canonical Task | A-R-025 |  | Rule/WPS owner to be assigned |  | T-R-025-01 | T-R-025-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-025-03 | WPS-07 | Issue acceptance or escalation record: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Canonical Task | A-R-025 |  | Rule/WPS owner to be assigned |  | T-R-025-02 | T-R-025-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-026-01 | WPS-07 | Obtain and control source evidence: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Canonical Task | A-R-026 |  | Rule/WPS owner to be assigned |  | T-R-025-03 | T-R-025-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-026-02 | WPS-07 | Verify applicability and technical sufficiency: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Canonical Task | A-R-026 |  | Rule/WPS owner to be assigned |  | T-R-026-01 | T-R-026-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-026-03 | WPS-07 | Issue acceptance or escalation record: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Canonical Task | A-R-026 |  | Rule/WPS owner to be assigned |  | T-R-026-02 | T-R-026-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-027-01 | WPS-07 | Obtain and control source evidence: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Canonical Task | A-R-027 |  | Rule/WPS owner to be assigned |  | T-R-026-03 | T-R-026-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-027-02 | WPS-07 | Verify applicability and technical sufficiency: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Canonical Task | A-R-027 |  | Rule/WPS owner to be assigned |  | T-R-027-01 | T-R-027-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-027-03 | WPS-07 | Issue acceptance or escalation record: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Canonical Task | A-R-027 |  | Rule/WPS owner to be assigned |  | T-R-027-02 | T-R-027-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-028-01 | WPS-07 | Obtain and control source evidence: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Canonical Task | A-R-028 |  | Rule/WPS owner to be assigned |  | T-R-027-03 | T-R-027-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-028-02 | WPS-07 | Verify applicability and technical sufficiency: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Canonical Task | A-R-028 |  | Rule/WPS owner to be assigned |  | T-R-028-01 | T-R-028-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-028-03 | WPS-07 | Issue acceptance or escalation record: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Canonical Task | A-R-028 |  | Rule/WPS owner to be assigned |  | T-R-028-02 | T-R-028-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-029-01 | WPS-08 | Obtain and control source evidence: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Canonical Task | A-R-029 |  | Rule/WPS owner to be assigned |  | T-R-028-03 | T-R-028-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-029-02 | WPS-08 | Verify applicability and technical sufficiency: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Canonical Task | A-R-029 |  | Rule/WPS owner to be assigned |  | T-R-029-01 | T-R-029-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-029-03 | WPS-08 | Issue acceptance or escalation record: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Canonical Task | A-R-029 |  | Rule/WPS owner to be assigned |  | T-R-029-02 | T-R-029-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-030-01 | WPS-08 | Obtain and control source evidence: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Canonical Task | A-R-030 |  | Rule/WPS owner to be assigned |  | T-R-029-03 | T-R-029-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-030-02 | WPS-08 | Verify applicability and technical sufficiency: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Canonical Task | A-R-030 |  | Rule/WPS owner to be assigned |  | T-R-030-01 | T-R-030-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-030-03 | WPS-08 | Issue acceptance or escalation record: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Canonical Task | A-R-030 |  | Rule/WPS owner to be assigned |  | T-R-030-02 | T-R-030-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-031-01 | WPS-08 | Obtain and control source evidence: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Canonical Task | A-R-031 |  | Rule/WPS owner to be assigned |  | T-R-030-03 | T-R-030-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-031-02 | WPS-08 | Verify applicability and technical sufficiency: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Canonical Task | A-R-031 |  | Rule/WPS owner to be assigned |  | T-R-031-01 | T-R-031-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-031-03 | WPS-08 | Issue acceptance or escalation record: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Canonical Task | A-R-031 |  | Rule/WPS owner to be assigned |  | T-R-031-02 | T-R-031-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-032-01 | WPS-09 | Obtain and control source evidence: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Canonical Task | A-R-032 |  | Rule/WPS owner to be assigned |  | T-R-031-03 | T-R-031-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-032-02 | WPS-09 | Verify applicability and technical sufficiency: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Canonical Task | A-R-032 |  | Rule/WPS owner to be assigned |  | T-R-032-01 | T-R-032-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-032-03 | WPS-09 | Issue acceptance or escalation record: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Canonical Task | A-R-032 |  | Rule/WPS owner to be assigned |  | T-R-032-02 | T-R-032-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-033-01 | WPS-09 | Obtain and control source evidence: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Canonical Task | A-R-033 |  | Rule/WPS owner to be assigned |  | T-R-032-03 | T-R-032-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-033-02 | WPS-09 | Verify applicability and technical sufficiency: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Canonical Task | A-R-033 |  | Rule/WPS owner to be assigned |  | T-R-033-01 | T-R-033-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-033-03 | WPS-09 | Issue acceptance or escalation record: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Canonical Task | A-R-033 |  | Rule/WPS owner to be assigned |  | T-R-033-02 | T-R-033-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-034-01 | WPS-09 | Obtain and control source evidence: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Canonical Task | A-R-034 |  | Rule/WPS owner to be assigned |  | T-R-033-03 | T-R-033-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-034-02 | WPS-09 | Verify applicability and technical sufficiency: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Canonical Task | A-R-034 |  | Rule/WPS owner to be assigned |  | T-R-034-01 | T-R-034-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-034-03 | WPS-09 | Issue acceptance or escalation record: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Canonical Task | A-R-034 |  | Rule/WPS owner to be assigned |  | T-R-034-02 | T-R-034-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-035-01 | WPS-11 | Obtain and control source evidence: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Canonical Task | A-R-035 |  | Rule/WPS owner to be assigned |  | T-R-034-03 | T-R-034-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-035-02 | WPS-11 | Verify applicability and technical sufficiency: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Canonical Task | A-R-035 |  | Rule/WPS owner to be assigned |  | T-R-035-01 | T-R-035-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-035-03 | WPS-11 | Issue acceptance or escalation record: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Canonical Task | A-R-035 |  | Rule/WPS owner to be assigned |  | T-R-035-02 | T-R-035-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-036-01 | WPS-08 | Obtain and control source evidence: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Canonical Task | A-R-036 |  | Rule/WPS owner to be assigned |  | T-R-035-03 | T-R-035-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-036-02 | WPS-08 | Verify applicability and technical sufficiency: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Canonical Task | A-R-036 |  | Rule/WPS owner to be assigned |  | T-R-036-01 | T-R-036-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-036-03 | WPS-08 | Issue acceptance or escalation record: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Canonical Task | A-R-036 |  | Rule/WPS owner to be assigned |  | T-R-036-02 | T-R-036-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-037-01 | WPS-10 | Obtain and control source evidence: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Canonical Task | A-R-037 |  | Rule/WPS owner to be assigned |  | T-R-036-03 | T-R-036-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-037-02 | WPS-10 | Verify applicability and technical sufficiency: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Canonical Task | A-R-037 |  | Rule/WPS owner to be assigned |  | T-R-037-01 | T-R-037-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-037-03 | WPS-10 | Issue acceptance or escalation record: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Canonical Task | A-R-037 |  | Rule/WPS owner to be assigned |  | T-R-037-02 | T-R-037-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-038-01 | WPS-10 | Obtain and control source evidence: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Canonical Task | A-R-038 |  | Rule/WPS owner to be assigned |  | T-R-037-03 | T-R-037-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-038-02 | WPS-10 | Verify applicability and technical sufficiency: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Canonical Task | A-R-038 |  | Rule/WPS owner to be assigned |  | T-R-038-01 | T-R-038-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-038-03 | WPS-10 | Issue acceptance or escalation record: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Canonical Task | A-R-038 |  | Rule/WPS owner to be assigned |  | T-R-038-02 | T-R-038-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-039-01 | WPS-10 | Obtain and control source evidence: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Canonical Task | A-R-039 |  | Rule/WPS owner to be assigned |  | T-R-038-03 | T-R-038-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-039-02 | WPS-10 | Verify applicability and technical sufficiency: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Canonical Task | A-R-039 |  | Rule/WPS owner to be assigned |  | T-R-039-01 | T-R-039-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-039-03 | WPS-10 | Issue acceptance or escalation record: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Canonical Task | A-R-039 |  | Rule/WPS owner to be assigned |  | T-R-039-02 | T-R-039-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-040-01 | WPS-10 | Obtain and control source evidence: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Canonical Task | A-R-040 |  | Rule/WPS owner to be assigned |  | T-R-039-03 | T-R-039-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-040-02 | WPS-10 | Verify applicability and technical sufficiency: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Canonical Task | A-R-040 |  | Rule/WPS owner to be assigned |  | T-R-040-01 | T-R-040-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-040-03 | WPS-10 | Issue acceptance or escalation record: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Canonical Task | A-R-040 |  | Rule/WPS owner to be assigned |  | T-R-040-02 | T-R-040-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-041-01 | WPS-10 | Obtain and control source evidence: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Canonical Task | A-R-041 |  | Rule/WPS owner to be assigned |  | T-R-040-03 | T-R-040-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-041-02 | WPS-10 | Verify applicability and technical sufficiency: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Canonical Task | A-R-041 |  | Rule/WPS owner to be assigned |  | T-R-041-01 | T-R-041-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-041-03 | WPS-10 | Issue acceptance or escalation record: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Canonical Task | A-R-041 |  | Rule/WPS owner to be assigned |  | T-R-041-02 | T-R-041-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-042-01 | WPS-10 | Obtain and control source evidence: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Canonical Task | A-R-042 |  | Rule/WPS owner to be assigned |  | T-R-041-03 | T-R-041-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-042-02 | WPS-10 | Verify applicability and technical sufficiency: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Canonical Task | A-R-042 |  | Rule/WPS owner to be assigned |  | T-R-042-01 | T-R-042-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-042-03 | WPS-10 | Issue acceptance or escalation record: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Canonical Task | A-R-042 |  | Rule/WPS owner to be assigned |  | T-R-042-02 | T-R-042-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-043-01 | WPS-11 | Obtain and control source evidence: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Canonical Task | A-R-043 |  | Rule/WPS owner to be assigned |  | T-R-042-03 | T-R-042-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-043-02 | WPS-11 | Verify applicability and technical sufficiency: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Canonical Task | A-R-043 |  | Rule/WPS owner to be assigned |  | T-R-043-01 | T-R-043-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-043-03 | WPS-11 | Issue acceptance or escalation record: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Canonical Task | A-R-043 |  | Rule/WPS owner to be assigned |  | T-R-043-02 | T-R-043-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-044-01 | WPS-12 | Obtain and control source evidence: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Canonical Task | A-R-044 |  | Rule/WPS owner to be assigned |  | T-R-043-03 | T-R-043-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-044-02 | WPS-12 | Verify applicability and technical sufficiency: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Canonical Task | A-R-044 |  | Rule/WPS owner to be assigned |  | T-R-044-01 | T-R-044-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-044-03 | WPS-12 | Issue acceptance or escalation record: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Canonical Task | A-R-044 |  | Rule/WPS owner to be assigned |  | T-R-044-02 | T-R-044-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-045-01 | WPS-12 | Obtain and control source evidence: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Canonical Task | A-R-045 |  | Rule/WPS owner to be assigned |  | T-R-044-03 | T-R-044-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-045-02 | WPS-12 | Verify applicability and technical sufficiency: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Canonical Task | A-R-045 |  | Rule/WPS owner to be assigned |  | T-R-045-01 | T-R-045-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-045-03 | WPS-12 | Issue acceptance or escalation record: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Canonical Task | A-R-045 |  | Rule/WPS owner to be assigned |  | T-R-045-02 | T-R-045-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-046-01 | WPS-12 | Obtain and control source evidence: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Canonical Task | A-R-046 |  | Rule/WPS owner to be assigned |  | T-R-045-03 | T-R-045-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-046-02 | WPS-12 | Verify applicability and technical sufficiency: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Canonical Task | A-R-046 |  | Rule/WPS owner to be assigned |  | T-R-046-01 | T-R-046-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-046-03 | WPS-12 | Issue acceptance or escalation record: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Canonical Task | A-R-046 |  | Rule/WPS owner to be assigned |  | T-R-046-02 | T-R-046-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-047-01 | WPS-12 | Obtain and control source evidence: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Canonical Task | A-R-047 |  | Rule/WPS owner to be assigned |  | T-R-046-03 | T-R-046-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-047-02 | WPS-12 | Verify applicability and technical sufficiency: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Canonical Task | A-R-047 |  | Rule/WPS owner to be assigned |  | T-R-047-01 | T-R-047-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-047-03 | WPS-12 | Issue acceptance or escalation record: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Canonical Task | A-R-047 |  | Rule/WPS owner to be assigned |  | T-R-047-02 | T-R-047-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-048-01 | WPS-12 | Obtain and control source evidence: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Canonical Task | A-R-048 |  | Rule/WPS owner to be assigned |  | T-R-047-03 | T-R-047-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-048-02 | WPS-12 | Verify applicability and technical sufficiency: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Canonical Task | A-R-048 |  | Rule/WPS owner to be assigned |  | T-R-048-01 | T-R-048-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-048-03 | WPS-12 | Issue acceptance or escalation record: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Canonical Task | A-R-048 |  | Rule/WPS owner to be assigned |  | T-R-048-02 | T-R-048-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-049-01 | WPS-13 | Obtain and control source evidence: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Canonical Task | A-R-049 |  | Rule/WPS owner to be assigned |  | T-R-048-03 | T-R-048-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-049-02 | WPS-13 | Verify applicability and technical sufficiency: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Canonical Task | A-R-049 |  | Rule/WPS owner to be assigned |  | T-R-049-01 | T-R-049-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-049-03 | WPS-13 | Issue acceptance or escalation record: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Canonical Task | A-R-049 |  | Rule/WPS owner to be assigned |  | T-R-049-02 | T-R-049-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-050-01 | WPS-13 | Obtain and control source evidence: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Canonical Task | A-R-050 |  | Rule/WPS owner to be assigned |  | T-R-049-03 | T-R-049-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-050-02 | WPS-13 | Verify applicability and technical sufficiency: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Canonical Task | A-R-050 |  | Rule/WPS owner to be assigned |  | T-R-050-01 | T-R-050-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-050-03 | WPS-13 | Issue acceptance or escalation record: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Canonical Task | A-R-050 |  | Rule/WPS owner to be assigned |  | T-R-050-02 | T-R-050-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-051-01 | WPS-14 | Obtain and control source evidence: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Canonical Task | A-R-051 |  | Rule/WPS owner to be assigned |  | T-R-050-03 | T-R-050-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-051-02 | WPS-14 | Verify applicability and technical sufficiency: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Canonical Task | A-R-051 |  | Rule/WPS owner to be assigned |  | T-R-051-01 | T-R-051-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-051-03 | WPS-14 | Issue acceptance or escalation record: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Canonical Task | A-R-051 |  | Rule/WPS owner to be assigned |  | T-R-051-02 | T-R-051-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-052-01 | WPS-14 | Obtain and control source evidence: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Canonical Task | A-R-052 |  | Rule/WPS owner to be assigned |  | T-R-051-03 | T-R-051-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-052-02 | WPS-14 | Verify applicability and technical sufficiency: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Canonical Task | A-R-052 |  | Rule/WPS owner to be assigned |  | T-R-052-01 | T-R-052-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-052-03 | WPS-14 | Issue acceptance or escalation record: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Canonical Task | A-R-052 |  | Rule/WPS owner to be assigned |  | T-R-052-02 | T-R-052-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-053-01 | WPS-14 | Obtain and control source evidence: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Canonical Task | A-R-053 |  | Rule/WPS owner to be assigned |  | T-R-052-03 | T-R-052-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-053-02 | WPS-14 | Verify applicability and technical sufficiency: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Canonical Task | A-R-053 |  | Rule/WPS owner to be assigned |  | T-R-053-01 | T-R-053-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-053-03 | WPS-14 | Issue acceptance or escalation record: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Canonical Task | A-R-053 |  | Rule/WPS owner to be assigned |  | T-R-053-02 | T-R-053-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-054-01 | WPS-14 | Obtain and control source evidence: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Canonical Task | A-R-054 |  | Rule/WPS owner to be assigned |  | T-R-053-03 | T-R-053-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-054-02 | WPS-14 | Verify applicability and technical sufficiency: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Canonical Task | A-R-054 |  | Rule/WPS owner to be assigned |  | T-R-054-01 | T-R-054-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-054-03 | WPS-14 | Issue acceptance or escalation record: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Canonical Task | A-R-054 |  | Rule/WPS owner to be assigned |  | T-R-054-02 | T-R-054-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-055-01 | WPS-15 | Obtain and control source evidence: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Canonical Task | A-R-055 |  | Rule/WPS owner to be assigned |  | T-R-054-03 | T-R-054-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-055-02 | WPS-15 | Verify applicability and technical sufficiency: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Canonical Task | A-R-055 |  | Rule/WPS owner to be assigned |  | T-R-055-01 | T-R-055-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-055-03 | WPS-15 | Issue acceptance or escalation record: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Canonical Task | A-R-055 |  | Rule/WPS owner to be assigned |  | T-R-055-02 | T-R-055-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-056-01 | WPS-15 | Obtain and control source evidence: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Canonical Task | A-R-056 |  | Rule/WPS owner to be assigned |  | T-R-055-03 | T-R-055-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-056-02 | WPS-15 | Verify applicability and technical sufficiency: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Canonical Task | A-R-056 |  | Rule/WPS owner to be assigned |  | T-R-056-01 | T-R-056-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-056-03 | WPS-15 | Issue acceptance or escalation record: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Canonical Task | A-R-056 |  | Rule/WPS owner to be assigned |  | T-R-056-02 | T-R-056-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-057-01 | WPS-15 | Obtain and control source evidence: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Canonical Task | A-R-057 |  | Rule/WPS owner to be assigned |  | T-R-056-03 | T-R-056-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-057-02 | WPS-15 | Verify applicability and technical sufficiency: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Canonical Task | A-R-057 |  | Rule/WPS owner to be assigned |  | T-R-057-01 | T-R-057-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-057-03 | WPS-15 | Issue acceptance or escalation record: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Canonical Task | A-R-057 |  | Rule/WPS owner to be assigned |  | T-R-057-02 | T-R-057-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-058-01 | WPS-15 | Obtain and control source evidence: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Canonical Task | A-R-058 |  | Rule/WPS owner to be assigned |  | T-R-057-03 | T-R-057-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-058-02 | WPS-15 | Verify applicability and technical sufficiency: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Canonical Task | A-R-058 |  | Rule/WPS owner to be assigned |  | T-R-058-01 | T-R-058-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-058-03 | WPS-15 | Issue acceptance or escalation record: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Canonical Task | A-R-058 |  | Rule/WPS owner to be assigned |  | T-R-058-02 | T-R-058-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-059-01 | WPS-13 | Obtain and control source evidence: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Canonical Task | A-R-059 |  | Rule/WPS owner to be assigned |  | T-R-058-03 | T-R-058-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-059-02 | WPS-13 | Verify applicability and technical sufficiency: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Canonical Task | A-R-059 |  | Rule/WPS owner to be assigned |  | T-R-059-01 | T-R-059-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-059-03 | WPS-13 | Issue acceptance or escalation record: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Canonical Task | A-R-059 |  | Rule/WPS owner to be assigned |  | T-R-059-02 | T-R-059-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-060-01 | WPS-13 | Obtain and control source evidence: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Canonical Task | A-R-060 |  | Rule/WPS owner to be assigned |  | T-R-059-03 | T-R-059-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-060-02 | WPS-13 | Verify applicability and technical sufficiency: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Canonical Task | A-R-060 |  | Rule/WPS owner to be assigned |  | T-R-060-01 | T-R-060-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-060-03 | WPS-13 | Issue acceptance or escalation record: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Canonical Task | A-R-060 |  | Rule/WPS owner to be assigned |  | T-R-060-02 | T-R-060-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-061-01 | WPS-16 | Obtain and control source evidence: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Canonical Task | A-R-061 |  | Rule/WPS owner to be assigned |  | T-R-060-03 | T-R-060-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-061-02 | WPS-16 | Verify applicability and technical sufficiency: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Canonical Task | A-R-061 |  | Rule/WPS owner to be assigned |  | T-R-061-01 | T-R-061-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-061-03 | WPS-16 | Issue acceptance or escalation record: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Canonical Task | A-R-061 |  | Rule/WPS owner to be assigned |  | T-R-061-02 | T-R-061-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-062-01 | WPS-16 | Obtain and control source evidence: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Canonical Task | A-R-062 |  | Rule/WPS owner to be assigned |  | T-R-061-03 | T-R-061-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-062-02 | WPS-16 | Verify applicability and technical sufficiency: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Canonical Task | A-R-062 |  | Rule/WPS owner to be assigned |  | T-R-062-01 | T-R-062-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-062-03 | WPS-16 | Issue acceptance or escalation record: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Canonical Task | A-R-062 |  | Rule/WPS owner to be assigned |  | T-R-062-02 | T-R-062-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-063-01 | WPS-16 | Obtain and control source evidence: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Canonical Task | A-R-063 |  | Rule/WPS owner to be assigned |  | T-R-062-03 | T-R-062-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-063-02 | WPS-16 | Verify applicability and technical sufficiency: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Canonical Task | A-R-063 |  | Rule/WPS owner to be assigned |  | T-R-063-01 | T-R-063-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-063-03 | WPS-16 | Issue acceptance or escalation record: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Canonical Task | A-R-063 |  | Rule/WPS owner to be assigned |  | T-R-063-02 | T-R-063-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-064-01 | WPS-16 | Obtain and control source evidence: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Canonical Task | A-R-064 |  | Rule/WPS owner to be assigned |  | T-R-063-03 | T-R-063-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-064-02 | WPS-16 | Verify applicability and technical sufficiency: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Canonical Task | A-R-064 |  | Rule/WPS owner to be assigned |  | T-R-064-01 | T-R-064-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-064-03 | WPS-16 | Issue acceptance or escalation record: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Canonical Task | A-R-064 |  | Rule/WPS owner to be assigned |  | T-R-064-02 | T-R-064-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-065-01 | WPS-16 | Obtain and control source evidence: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Canonical Task | A-R-065 |  | Rule/WPS owner to be assigned |  | T-R-064-03 | T-R-064-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-065-02 | WPS-16 | Verify applicability and technical sufficiency: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Canonical Task | A-R-065 |  | Rule/WPS owner to be assigned |  | T-R-065-01 | T-R-065-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-065-03 | WPS-16 | Issue acceptance or escalation record: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Canonical Task | A-R-065 |  | Rule/WPS owner to be assigned |  | T-R-065-02 | T-R-065-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-066-01 | WPS-16 | Obtain and control source evidence: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Canonical Task | A-R-066 |  | Rule/WPS owner to be assigned |  | T-R-065-03 | T-R-065-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-066-02 | WPS-16 | Verify applicability and technical sufficiency: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Canonical Task | A-R-066 |  | Rule/WPS owner to be assigned |  | T-R-066-01 | T-R-066-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-066-03 | WPS-16 | Issue acceptance or escalation record: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Canonical Task | A-R-066 |  | Rule/WPS owner to be assigned |  | T-R-066-02 | T-R-066-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-067-01 | WPS-16 | Obtain and control source evidence: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Canonical Task | A-R-067 |  | Rule/WPS owner to be assigned |  | T-R-066-03 | T-R-066-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-067-02 | WPS-16 | Verify applicability and technical sufficiency: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Canonical Task | A-R-067 |  | Rule/WPS owner to be assigned |  | T-R-067-01 | T-R-067-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-067-03 | WPS-16 | Issue acceptance or escalation record: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Canonical Task | A-R-067 |  | Rule/WPS owner to be assigned |  | T-R-067-02 | T-R-067-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-068-01 | WPS-16 | Obtain and control source evidence: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Canonical Task | A-R-068 |  | Rule/WPS owner to be assigned |  | T-R-067-03 | T-R-067-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-068-02 | WPS-16 | Verify applicability and technical sufficiency: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Canonical Task | A-R-068 |  | Rule/WPS owner to be assigned |  | T-R-068-01 | T-R-068-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-068-03 | WPS-16 | Issue acceptance or escalation record: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Canonical Task | A-R-068 |  | Rule/WPS owner to be assigned |  | T-R-068-02 | T-R-068-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-069-01 | WPS-16 | Obtain and control source evidence: Determine ISM applicability and required interface; do not assume applicability. | Canonical Task | A-R-069 |  | Rule/WPS owner to be assigned |  | T-R-068-03 | T-R-068-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-069-02 | WPS-16 | Verify applicability and technical sufficiency: Determine ISM applicability and required interface; do not assume applicability. | Canonical Task | A-R-069 |  | Rule/WPS owner to be assigned |  | T-R-069-01 | T-R-069-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-069-03 | WPS-16 | Issue acceptance or escalation record: Determine ISM applicability and required interface; do not assume applicability. | Canonical Task | A-R-069 |  | Rule/WPS owner to be assigned |  | T-R-069-02 | T-R-069-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-070-01 | WPS-16 | Obtain and control source evidence: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Canonical Task | A-R-070 |  | Rule/WPS owner to be assigned |  | T-R-069-03 | T-R-069-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-070-02 | WPS-16 | Verify applicability and technical sufficiency: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Canonical Task | A-R-070 |  | Rule/WPS owner to be assigned |  | T-R-070-01 | T-R-070-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-070-03 | WPS-16 | Issue acceptance or escalation record: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Canonical Task | A-R-070 |  | Rule/WPS owner to be assigned |  | T-R-070-02 | T-R-070-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-071-01 | WPS-09 | Obtain and control source evidence: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Canonical Task | A-R-071 |  | Rule/WPS owner to be assigned |  | T-R-070-03 | T-R-070-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-071-02 | WPS-09 | Verify applicability and technical sufficiency: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Canonical Task | A-R-071 |  | Rule/WPS owner to be assigned |  | T-R-071-01 | T-R-071-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-071-03 | WPS-09 | Issue acceptance or escalation record: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Canonical Task | A-R-071 |  | Rule/WPS owner to be assigned |  | T-R-071-02 | T-R-071-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-072-01 | WPS-14 | Obtain and control source evidence: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Canonical Task | A-R-072 |  | Rule/WPS owner to be assigned |  | T-R-071-03 | T-R-071-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-072-02 | WPS-14 | Verify applicability and technical sufficiency: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Canonical Task | A-R-072 |  | Rule/WPS owner to be assigned |  | T-R-072-01 | T-R-072-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-072-03 | WPS-14 | Issue acceptance or escalation record: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Canonical Task | A-R-072 |  | Rule/WPS owner to be assigned |  | T-R-072-02 | T-R-072-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-073-01 | WPS-14 | Obtain and control source evidence: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Canonical Task | A-R-073 |  | Rule/WPS owner to be assigned |  | T-R-072-03 | T-R-072-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-073-02 | WPS-14 | Verify applicability and technical sufficiency: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Canonical Task | A-R-073 |  | Rule/WPS owner to be assigned |  | T-R-073-01 | T-R-073-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-073-03 | WPS-14 | Issue acceptance or escalation record: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Canonical Task | A-R-073 |  | Rule/WPS owner to be assigned |  | T-R-073-02 | T-R-073-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-074-01 | WPS-16 | Obtain and control source evidence: Establish casualty/incident reporting requirements for events in Jordanian waters. | Canonical Task | A-R-074 |  | Rule/WPS owner to be assigned |  | T-R-073-03 | T-R-073-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-074-02 | WPS-16 | Verify applicability and technical sufficiency: Establish casualty/incident reporting requirements for events in Jordanian waters. | Canonical Task | A-R-074 |  | Rule/WPS owner to be assigned |  | T-R-074-01 | T-R-074-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-074-03 | WPS-16 | Issue acceptance or escalation record: Establish casualty/incident reporting requirements for events in Jordanian waters. | Canonical Task | A-R-074 |  | Rule/WPS owner to be assigned |  | T-R-074-02 | T-R-074-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-075-01 | WPS-09 | Obtain and control source evidence: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Canonical Task | A-R-075 |  | Rule/WPS owner to be assigned |  | T-R-074-03 | T-R-074-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-075-02 | WPS-09 | Verify applicability and technical sufficiency: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Canonical Task | A-R-075 |  | Rule/WPS owner to be assigned |  | T-R-075-01 | T-R-075-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-075-03 | WPS-09 | Issue acceptance or escalation record: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Canonical Task | A-R-075 |  | Rule/WPS owner to be assigned |  | T-R-075-02 | T-R-075-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-076-01 | WPS-09 | Obtain and control source evidence: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Canonical Task | A-R-076 |  | Rule/WPS owner to be assigned |  | T-R-075-03 | T-R-075-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-076-02 | WPS-09 | Verify applicability and technical sufficiency: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Canonical Task | A-R-076 |  | Rule/WPS owner to be assigned |  | T-R-076-01 | T-R-076-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-076-03 | WPS-09 | Issue acceptance or escalation record: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Canonical Task | A-R-076 |  | Rule/WPS owner to be assigned |  | T-R-076-02 | T-R-076-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-077-01 | WPS-09 | Obtain and control source evidence: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Canonical Task | A-R-077 |  | Rule/WPS owner to be assigned |  | T-R-076-03 | T-R-076-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-077-02 | WPS-09 | Verify applicability and technical sufficiency: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Canonical Task | A-R-077 |  | Rule/WPS owner to be assigned |  | T-R-077-01 | T-R-077-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-077-03 | WPS-09 | Issue acceptance or escalation record: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Canonical Task | A-R-077 |  | Rule/WPS owner to be assigned |  | T-R-077-02 | T-R-077-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-078-01 | WPS-09 | Obtain and control source evidence: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Canonical Task | A-R-078 |  | Rule/WPS owner to be assigned |  | T-R-077-03 | T-R-077-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-078-02 | WPS-09 | Verify applicability and technical sufficiency: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Canonical Task | A-R-078 |  | Rule/WPS owner to be assigned |  | T-R-078-01 | T-R-078-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-078-03 | WPS-09 | Issue acceptance or escalation record: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Canonical Task | A-R-078 |  | Rule/WPS owner to be assigned |  | T-R-078-02 | T-R-078-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-079-01 | WPS-16 | Obtain and control source evidence: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Canonical Task | A-R-079 |  | Rule/WPS owner to be assigned |  | T-R-078-03 | T-R-078-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-079-02 | WPS-16 | Verify applicability and technical sufficiency: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Canonical Task | A-R-079 |  | Rule/WPS owner to be assigned |  | T-R-079-01 | T-R-079-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-079-03 | WPS-16 | Issue acceptance or escalation record: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Canonical Task | A-R-079 |  | Rule/WPS owner to be assigned |  | T-R-079-02 | T-R-079-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-080-01 | WPS-01 | Obtain and control source evidence: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Canonical Task | A-R-080 |  | Rule/WPS owner to be assigned |  | T-R-079-03 | T-R-079-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-080-02 | WPS-01 | Verify applicability and technical sufficiency: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Canonical Task | A-R-080 |  | Rule/WPS owner to be assigned |  | T-R-080-01 | T-R-080-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-080-03 | WPS-01 | Issue acceptance or escalation record: Review applicable IACS Unified Requirements and IACS Recommendation 198 as cross-check/supporting references only where incorporated through the governing DNV/class basis; do not treat IACS material as independent statutory requirements. | Canonical Task | A-R-080 |  | Rule/WPS owner to be assigned |  | T-R-080-02 | T-R-080-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-081-01 | WPS-02 | Obtain and control source evidence: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Canonical Task | A-R-081 |  | Rule/WPS owner to be assigned |  | T-R-080-03 | T-R-080-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-081-02 | WPS-02 | Verify applicability and technical sufficiency: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Canonical Task | A-R-081 |  | Rule/WPS owner to be assigned |  | T-R-081-01 | T-R-081-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-081-03 | WPS-02 | Issue acceptance or escalation record: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Canonical Task | A-R-081 |  | Rule/WPS owner to be assigned |  | T-R-081-02 | T-R-081-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-082-01 | WPS-01 | Obtain and control source evidence: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Canonical Task | A-R-082 |  | Rule/WPS owner to be assigned |  | T-R-081-03 | T-R-081-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-082-02 | WPS-01 | Verify applicability and technical sufficiency: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Canonical Task | A-R-082 |  | Rule/WPS owner to be assigned |  | T-R-082-01 | T-R-082-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-082-03 | WPS-01 | Issue acceptance or escalation record: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Canonical Task | A-R-082 |  | Rule/WPS owner to be assigned |  | T-R-082-02 | T-R-082-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-083-01 | WPS-01 | Obtain and control source evidence: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Canonical Task | A-R-083 |  | Rule/WPS owner to be assigned |  | T-R-082-03 | T-R-082-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-083-02 | WPS-01 | Verify applicability and technical sufficiency: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Canonical Task | A-R-083 |  | Rule/WPS owner to be assigned |  | T-R-083-01 | T-R-083-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-083-03 | WPS-01 | Issue acceptance or escalation record: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Canonical Task | A-R-083 |  | Rule/WPS owner to be assigned |  | T-R-083-02 | T-R-083-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-084-01 | WPS-13 | Obtain and control source evidence: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Canonical Task | A-R-084 |  | Rule/WPS owner to be assigned |  | T-R-083-03 | T-R-083-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-084-02 | WPS-13 | Verify applicability and technical sufficiency: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Canonical Task | A-R-084 |  | Rule/WPS owner to be assigned |  | T-R-084-01 | T-R-084-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-084-03 | WPS-13 | Issue acceptance or escalation record: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Canonical Task | A-R-084 |  | Rule/WPS owner to be assigned |  | T-R-084-02 | T-R-084-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-085-01 | WPS-11 | Obtain and control source evidence: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Canonical Task | A-R-085 |  | Rule/WPS owner to be assigned |  | T-R-084-03 | T-R-084-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-085-02 | WPS-11 | Verify applicability and technical sufficiency: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Canonical Task | A-R-085 |  | Rule/WPS owner to be assigned |  | T-R-085-01 | T-R-085-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-085-03 | WPS-11 | Issue acceptance or escalation record: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Canonical Task | A-R-085 |  | Rule/WPS owner to be assigned |  | T-R-085-02 | T-R-085-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-086-01 | WPS-09 | Obtain and control source evidence: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Canonical Task | A-R-086 |  | Rule/WPS owner to be assigned |  | T-R-085-03 | T-R-085-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-086-02 | WPS-09 | Verify applicability and technical sufficiency: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Canonical Task | A-R-086 |  | Rule/WPS owner to be assigned |  | T-R-086-01 | T-R-086-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-086-03 | WPS-09 | Issue acceptance or escalation record: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Canonical Task | A-R-086 |  | Rule/WPS owner to be assigned |  | T-R-086-02 | T-R-086-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-087-01 | WPS-16 | Obtain and control source evidence: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Canonical Task | A-R-087 |  | Rule/WPS owner to be assigned |  | T-R-086-03 | T-R-086-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-087-02 | WPS-16 | Verify applicability and technical sufficiency: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Canonical Task | A-R-087 |  | Rule/WPS owner to be assigned |  | T-R-087-01 | T-R-087-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-087-03 | WPS-16 | Issue acceptance or escalation record: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Canonical Task | A-R-087 |  | Rule/WPS owner to be assigned |  | T-R-087-02 | T-R-087-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-088-01 | WPS-02 | Obtain and control source evidence: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Canonical Task | A-R-088 |  | Rule/WPS owner to be assigned |  | T-R-087-03 | T-R-087-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-088-02 | WPS-02 | Verify applicability and technical sufficiency: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Canonical Task | A-R-088 |  | Rule/WPS owner to be assigned |  | T-R-088-01 | T-R-088-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-088-03 | WPS-02 | Issue acceptance or escalation record: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Canonical Task | A-R-088 |  | Rule/WPS owner to be assigned |  | T-R-088-02 | T-R-088-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-089-01 | WPS-02 | Obtain and control source evidence: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Canonical Task | A-R-089 |  | Rule/WPS owner to be assigned |  | T-R-088-03 | T-R-088-03 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-089-02 | WPS-02 | Verify applicability and technical sufficiency: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Canonical Task | A-R-089 |  | Rule/WPS owner to be assigned |  | T-R-089-01 | T-R-089-01 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
T-R-089-03 | WPS-02 | Issue acceptance or escalation record: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Canonical Task | A-R-089 |  | Rule/WPS owner to be assigned |  | T-R-089-02 | T-R-089-02 | Finish-to-Start | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  |  |  | Major |  |  | No actual dates assigned. Evidence-dependent closure only.
WPS-17-01 | WPS-17 | Obtain formal DNV suspension notice, class status and violation summary | Supplemental Functional Activity | Cross-reference canonical rules | Class & Regulatory | Class Manager | Project Director | WPS-01,WPS-02 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | DNV | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-17-02 | WPS-17 | Agree DNV reinstatement survey scope and attendance plan | Supplemental Functional Activity | Cross-reference canonical rules | Class & Regulatory | Class Manager | Project Director | WPS-17-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | DNV | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-17-03 | WPS-17 | Complete hull, machinery, electrical and statutory condition assessment | Supplemental Functional Activity | Cross-reference canonical rules | Technical | Technical Superintendent | Project Director | WPS-17-02 | WPS-21-01 | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | DNV / Flag | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-17-04 | WPS-17 | Execute repairs, tests and survey closeout | Supplemental Functional Activity | Cross-reference canonical rules | Technical | Project Manager | Project Director | WPS-17-03 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | DNV / Flag | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-17-05 | WPS-17 | Receive formal DNV reinstatement decision and updated class status | Supplemental Functional Activity | Cross-reference canonical rules | Class & Regulatory | Class Manager | Project Director | WPS-17-04 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | DNV | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-18-01 | WPS-18 | Issue neutral request for information to candidate IACS societies | Supplemental Functional Activity | Cross-reference canonical rules | Class & Regulatory | Class Manager | Project Director | WPS-01,WPS-02 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Candidate IACS society | Major | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-18-02 | WPS-18 | Prepare transfer technical dossier and disclosure register | Supplemental Functional Activity | Cross-reference canonical rules | Class & Regulatory | Class Manager | Project Director | WPS-18-01 | WPS-21-01 | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Candidate IACS society | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-18-03 | WPS-18 | Perform comparative gap, cost and schedule assessment | Supplemental Functional Activity | Cross-reference canonical rules | PMO | Project Controls Manager | Project Director | WPS-18-02,WPS-17-02 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Owner / Management | Major | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-18-04 | WPS-18 | Record management and authority path decision | Supplemental Functional Activity | Cross-reference canonical rules | PMO | Project Director | Project Director | WPS-18-03 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Flag / JMA / Client / MWS as applicable | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-18-05 | WPS-18 | If selected, complete transfer surveys and obtain certificate | Supplemental Functional Activity | Cross-reference canonical rules | Class & Regulatory | Class Manager | Project Director | WPS-18-04 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Selected IACS society / Flag | Critical | GATE-1 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-19-01 | WPS-19 | Confirm helideck status, intended aircraft and authority jurisdiction | Supplemental Functional Activity | Cross-reference canonical rules | Aviation / HSE | Aviation Coordinator | Project Director | WPS-14,WPS-16 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | ECAA / Jordan CARC / Flag as applicable | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-19-02 | WPS-19 | Review helideck structural, obstacle, marking, lighting and access basis | Supplemental Functional Activity | Cross-reference canonical rules | Aviation / Technical | Aviation Coordinator | Project Director | WPS-19-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Competent aviation authority / Class | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-19-03 | WPS-19 | Review flight operations and marine-aviation interface manual | Supplemental Functional Activity | Cross-reference canonical rules | Aviation / Marine | Aviation Coordinator | Project Director | WPS-19-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Competent aviation authority / Client | Major | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-19-04 | WPS-19 | Verify helideck firefighting, rescue, PPE and trained team | Supplemental Functional Activity | Cross-reference canonical rules | HSE / Aviation | HSE Manager | Project Director | WPS-19-02,WPS-14 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Competent aviation authority / Client | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-19-05 | WPS-19 | Secure required operational permissions and acceptance evidence | Supplemental Functional Activity | Cross-reference canonical rules | Aviation / Regulatory | Aviation Coordinator | Project Director | WPS-19-02,WPS-19-03,WPS-19-04 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Competent authorities | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-20-01 | WPS-20 | Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Supplemental Functional Activity | Cross-reference canonical rules | Environmental / Marine | Environmental Manager | Project Director | WPS-09,WPS-16 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Flag / JMA / ASEZA | Critical | GATE-7/8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-20-02 | WPS-20 | Verify BDN, fuel samples, changeover procedures and consumption plan | Supplemental Functional Activity | Cross-reference canonical rules | Engineering | Chief Engineer | Project Director | WPS-20-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Flag / JMA / ASEZA as applicable | Major | GATE-7/8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-20-03 | WPS-20 | Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Supplemental Functional Activity | Cross-reference canonical rules | Engineering / Environmental | Chief Engineer | Project Director | WPS-09,WPS-13,WPS-20-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | JMA / ASEZA / Port reception facility | Critical | GATE-7/8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-20-04 | WPS-20 | Commission potable-water and RO systems and obtain laboratory results | Supplemental Functional Activity | Cross-reference canonical rules | Engineering / Medical | Chief Engineer | Project Director | WPS-13 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Port Health / competent laboratory | Major | GATE-7/8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-20-05 | WPS-20 | Close spill prevention and waste contractor interfaces | Supplemental Functional Activity | Cross-reference canonical rules | Environmental / Logistics | Environmental Manager | Project Director | WPS-20-02,WPS-20-03 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | ASEZA / Client | Critical | GATE-8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-21-01 | WPS-21 | Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Supplemental Functional Activity | Cross-reference canonical rules | Maintenance | Maintenance Superintendent | Project Director | WPS-13 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Internal QA / Class as applicable | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-21-02 | WPS-21 | Generate critical defect and overdue-maintenance backlog | Supplemental Functional Activity | Cross-reference canonical rules | Maintenance | Maintenance Superintendent | Project Director | WPS-21-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Technical Manager | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-21-03 | WPS-21 | Map critical spares/materials to equipment and physically verify stock | Supplemental Functional Activity | Cross-reference canonical rules | Warehouse / Maintenance | Stores Manager | Project Director | WPS-21-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Technical Manager | Critical | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-21-04 | WPS-21 | Issue procurement plan for shortages and long-lead items | Supplemental Functional Activity | Cross-reference canonical rules | Procurement | Procurement Manager | Project Director | WPS-21-02,WPS-21-03 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Project Director | Major | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-21-05 | WPS-21 | Back up CMMS database and approve mobilization maintenance baseline | Supplemental Functional Activity | Cross-reference canonical rules | Maintenance / IT | Maintenance Superintendent | Project Director | WPS-21-02,WPS-21-03,WPS-21-04 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Technical Manager | Major | GATE-7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-22-01 | WPS-22 | Develop approved anchor pattern, deployment sequence and exclusion controls | Supplemental Functional Activity | Cross-reference canonical rules | Marine / Survey | Marine Superintendent | Project Director | WPS-08,WPS-09 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Client / MWS / ASEZA as applicable | Critical | GATE-3 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-22-02 | WPS-22 | Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Supplemental Functional Activity | Cross-reference canonical rules | Marine / E&I | Survey Manager | Project Director | WPS-14,WPS-22-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | OEM / MWS / Class as applicable | Critical | GATE-3 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-22-03 | WPS-22 | Test winches, brakes, controls, communications and emergency release | Supplemental Functional Activity | Cross-reference canonical rules | Marine / Mechanical | Marine Superintendent | Project Director | WPS-08,WPS-13,WPS-22-02 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Class / MWS / competent person | Critical | GATE-3 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-22-04 | WPS-22 | Approve tug assignment, command hierarchy and standard communications | Supplemental Functional Activity | Cross-reference canonical rules | Marine Operations | Marine Superintendent | Project Director | WPS-22-01,WPS-22-03 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Harbour Master / Tug operators / MWS | Critical | GATE-3 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-22-05 | WPS-22 | Conduct anchor-handling tabletop and operational drill | Supplemental Functional Activity | Cross-reference canonical rules | Marine / HSE | Marine Superintendent | Project Director | WPS-22-02,WPS-22-03,WPS-22-04 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Client / MWS | Critical | GATE-3 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-23-01 | WPS-23 | Approve departmental manpower, competency and rotation matrix | Supplemental Functional Activity | Cross-reference canonical rules | HR / Operations | HR Manager | Project Director | WPS-15 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Flag / Client as applicable | Critical | GATE-4/7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-23-02 | WPS-23 | Verify clinic equipment, medicines, licenses and medevac interface | Supplemental Functional Activity | Cross-reference canonical rules | Medical / HSE | Medical Coordinator | Project Director | WPS-23-01,WPS-19-03 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Port Health / competent authorities | Major | GATE-4/7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-23-03 | WPS-23 | Implement fatigue, rest-hour and drug/alcohol policy controls | Supplemental Functional Activity | Cross-reference canonical rules | HR / HSE | HSE Manager | Project Director | WPS-23-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Flag / Client as applicable | Major | GATE-4/7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-23-04 | WPS-23 | Complete visas, travel, repatriation and crew-change logistics | Supplemental Functional Activity | Cross-reference canonical rules | HR / Logistics | HR Manager | Project Director | WPS-16,WPS-23-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Immigration / Agent | Major | GATE-4/7 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-24-01 | WPS-24 | Issue integrated emergency response and shore-interface matrix | Supplemental Functional Activity | Cross-reference canonical rules | HSE | HSE Manager | Project Director | WPS-09,WPS-10,WPS-12,WPS-14,WPS-19,WPS-20,WPS-22,WPS-23 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Client / JMA / ASEZA / Civil Defence as applicable | Critical | GATE-8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-24-02 | WPS-24 | Define scenario drill programme and measurable acceptance criteria | Supplemental Functional Activity | Cross-reference canonical rules | HSE / Operations | HSE Manager | Project Director | WPS-24-01 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Client / competent authorities | Critical | GATE-8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-24-03 | WPS-24 | Conduct marine, aviation, diving, pollution and medevac interface drills | Supplemental Functional Activity | Cross-reference canonical rules | All Departments | Project Manager | Project Director | WPS-24-02,WPS-19-04,WPS-22-05,WPS-23-02 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Client / competent authorities | Critical | GATE-8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
WPS-24-04 | WPS-24 | Close drill findings and issue final operational readiness recommendation | Supplemental Functional Activity | Cross-reference canonical rules | PMO | Project Director | Project Director | WPS-24-03,WPS-17-05,WPS-18-04,WPS-20-05,WPS-21-05 |  | FS | 0 | [6 empty] | Not Started | 0% | 0% |  | 0 | 0 | 0 | 0 |  |  | USD | 0 | 0 | 0 |  |  | Not Started | 0 | No |  | Accepted report/certificate/record appropriate to activity | Owner / Client / competent authorities | Critical | GATE-8 | External classified-data reference only where required | Thresholds and statutory applicability require competent-authority confirmation.
Formulas:
Overdue = IF(AND(ISNUMBER([@[Planned Finish]]),[@[Planned Finish]]<TODAY(),[@[Completion %]]<1),"OVERDUE","")

## Functional
Functional_Activity_ID | WPS_ID | WPS_Name | Deliverable_Name | Governing_Rule_Ref | Activity_Seq_No | Activity_Type | Detailed_Activity_Desc | Responsible_Owner | External_Authority | Prerequisite_Activity_ID | Evidence_Document_Type | Evidence_Output | Final_Acceptance_Criteria | Risk_Level | Jordan_Context_Note | Canonical_Acceptance_Criteria_ID | Gap_ID | Canonical_Activity_ID | Canonical_Deliverable_ID | Readiness_Gate
F-R-001-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-001 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-001 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-001: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit. | Rule/WPS owner | DNV Rules for Classification |  | Current DNV Class Certificate + class status | Evidence Register / controlled source record | Required evidence for R-001 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-001 | G-001 | A-R-001 | D-R-001 | GATE-1
F-R-001-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-001 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-001 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV Rules for Classification | F-R-001-01 | Current DNV Class Certificate + class status; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-001 | G-001 | A-R-001 | D-R-001 | GATE-1
F-R-001-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-001 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-001 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-001: Determine the governing DNV class regime for the non-self-propelled PMS-11 unit.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Rules for Classification | F-R-001-03 | Current DNV Class Certificate + class status | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-001 | G-001 | A-R-001 | D-R-001 | GATE-1
F-R-002-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-002 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-002 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-002: Confirm complete class notation and qualifiers; do not infer notation from vessel description. | Rule/WPS owner | DNV Class Certificate |  | Current DNV Class Certificate | Evidence Register / controlled source record | Required evidence for R-002 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-002 | G-002 | A-R-002 | D-R-002 | GATE-1
F-R-002-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-002 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-002 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Confirm complete class notation and qualifiers; do not infer notation from vessel description.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV Class Certificate | F-R-002-01 | Current DNV Class Certificate; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-002 | G-002 | A-R-002 | D-R-002 | GATE-1
F-R-002-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-002 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-002 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-002: Confirm complete class notation and qualifiers; do not infer notation from vessel description.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Class Certificate | F-R-002-03 | Current DNV Class Certificate | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-002 | G-002 | A-R-002 | D-R-002 | GATE-1
F-R-003-01 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-003 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-003 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-003: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions. | Rule/WPS owner | DNV Rules |  | Class basis + rule edition evidence | Evidence Register / controlled source record | Required evidence for R-003 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-003 | G-003 | A-R-003 | D-R-003 | GATE-1
F-R-003-02 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-003 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-003 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV Rules | F-R-003-01 | Class basis + rule edition evidence; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical |  | AC-R-003 | G-003 | A-R-003 | D-R-003 | GATE-1
F-R-003-04 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-003 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-003 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-003: Determine exact current/legacy rule editions governing the existing unit and any applicable transition provisions.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Rules | F-R-003-03 | Class basis + rule edition evidence | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-003 | G-003 | A-R-003 | D-R-003 | GATE-1
F-R-004-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-004 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-004 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-004: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness. | Rule/WPS owner | DNV Class Status |  | Class Status Report + survey records | Evidence Register / controlled source record | Required evidence for R-004 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-004 | G-004 | A-R-004 | D-R-004 | GATE-1
F-R-004-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-004 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-004 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV Class Status | F-R-004-01 | Class Status Report + survey records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-004 | G-004 | A-R-004 | D-R-004 | GATE-1
F-R-004-03 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-004 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-004 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-004, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV Class Status | F-R-004-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-004 | G-004 | A-R-004 | D-R-004 | GATE-1
F-R-004-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-004 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-004 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-004: Identify conditions of class, recommendations, memoranda, exemptions and dispensations affecting readiness.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Class Status | F-R-004-03 | Class Status Report + survey records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-004 | G-004 | A-R-004 | D-R-004 | GATE-1
F-R-005-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-005 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-005 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-005: Identify approved drawings and documents forming the class technical basis. | Rule/WPS owner | DNV Class File |  | Approved drawings list / class file | Evidence Register / controlled source record | Required evidence for R-005 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-005 | G-005 | A-R-005 | D-R-005 | GATE-1
F-R-005-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-005 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-005 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Identify approved drawings and documents forming the class technical basis.. | Responsible technical/functional owner | DNV Class File | F-R-005-01 | Approved drawings list / class file | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical |  | AC-R-005 | G-005 | A-R-005 | D-R-005 | GATE-1
F-R-005-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-005 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-005 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-005: Identify approved drawings and documents forming the class technical basis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Class File | F-R-005-03 | Approved drawings list / class file | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-005 | G-005 | A-R-005 | D-R-005 | GATE-1
F-R-006-01 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-006 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-006 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-006: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization. | Rule/WPS owner | DNV Survey/Certification |  | Survey status/history | Evidence Register / controlled source record | Required evidence for R-006 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-006 | G-006 | A-R-006 | D-R-006 | GATE-1
F-R-006-02 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-006 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-006 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV Survey/Certification | F-R-006-01 | Survey status/history; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-006 | G-006 | A-R-006 | D-R-006 | GATE-1
F-R-006-03 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-006 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-006 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-006, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV Survey/Certification | F-R-006-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-006 | G-006 | A-R-006 | D-R-006 | GATE-1
F-R-006-04 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-006 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-006 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-006: Identify survey scheme, due surveys and outstanding survey items relevant to mobilization.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Survey/Certification | F-R-006-03 | Survey status/history | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-006 | G-006 | A-R-006 | D-R-006 | GATE-1
F-R-007-01 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-007 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-007 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-007: Assess effects of modifications, conversion, change of service or operating area on class requirements. | Rule/WPS owner | DNV Rules |  | Modification history + approvals | Evidence Register / controlled source record | Required evidence for R-007 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-007 | G-007 | A-R-007 | D-R-007 | GATE-1
F-R-007-02 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-007 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-007 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Assess effects of modifications, conversion, change of service or operating area on class requirements.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV Rules | F-R-007-01 | Modification history + approvals; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical |  | AC-R-007 | G-007 | A-R-007 | D-R-007 | GATE-1
F-R-007-04 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-007 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-007 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-007: Assess effects of modifications, conversion, change of service or operating area on class requirements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Rules | F-R-007-03 | Modification history + approvals | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-007 | G-007 | A-R-007 | D-R-007 | GATE-1
F-R-008-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-008 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-008 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-008: Establish the approved operating limits and service scope relevant to Jordan operations. | Rule/WPS owner | DNV Class File |  | Certificate + approved operational documents | Evidence Register / controlled source record | Required evidence for R-008 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-008 | G-008 | A-R-008 | D-R-008 | GATE-1
F-R-008-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-008 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-008 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish the approved operating limits and service scope relevant to Jordan operations.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV Class File | F-R-008-01 | Certificate + approved operational documents; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-008 | G-008 | A-R-008 | D-R-008 | GATE-1
F-R-008-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-008 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-008 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-008: Establish the approved operating limits and service scope relevant to Jordan operations.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Class File | F-R-008-03 | Certificate + approved operational documents | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-008 | G-008 | A-R-008 | D-R-008 | GATE-1
F-R-009-01 | WPS-03 | Lifting Appliances & Loose Gear | D-R-009 ¦ Lifting Appliances & Loose Gear | R-009 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-009: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances. | Rule/WPS owner | SOLAS / DNV |  | Flag/statutory basis + appliance register | Evidence Register / controlled source record | Required evidence for R-009 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-009 | G-009 | A-R-009 | D-R-009 | GATE-2
F-R-009-02 | WPS-03 | Lifting Appliances & Loose Gear | D-R-009 ¦ Lifting Appliances & Loose Gear | R-009 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances.. | Responsible technical/functional owner | SOLAS / DNV | F-R-009-01 | Flag/statutory basis + appliance register | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical |  | AC-R-009 | G-009 | A-R-009 | D-R-009 | GATE-2
F-R-009-03 | WPS-03 | Lifting Appliances & Loose Gear | D-R-009 ¦ Lifting Appliances & Loose Gear | R-009 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-009, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | SOLAS / DNV | F-R-009-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-009 | G-009 | A-R-009 | D-R-009 | GATE-2
F-R-009-04 | WPS-03 | Lifting Appliances & Loose Gear | D-R-009 ¦ Lifting Appliances & Loose Gear | R-009 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-009: Determine applicability/pathway of SOLAS II-1/3-13 for permanently installed lifting appliances.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | SOLAS / DNV | F-R-009-03 | Flag/statutory basis + appliance register | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-009 | G-009 | A-R-009 | D-R-009 | GATE-2
F-R-010-01 | WPS-03 | Lifting Appliances & Loose Gear | D-R-010 ¦ Lifting Appliances & Loose Gear | R-010 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-010: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11. | Rule/WPS owner | SOLAS / DNV |  | Flag acceptance + technical basis | Evidence Register / controlled source record | Required evidence for R-010 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-010 | G-010 | A-R-010 | D-R-010 | GATE-2
F-R-010-02 | WPS-03 | Lifting Appliances & Loose Gear | D-R-010 ¦ Lifting Appliances & Loose Gear | R-010 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11.. | Responsible technical/functional owner | SOLAS / DNV | F-R-010-01 | Flag acceptance + technical basis | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical |  | AC-R-010 | G-010 | A-R-010 | D-R-010 | GATE-2
F-R-010-04 | WPS-03 | Lifting Appliances & Loose Gear | D-R-010 ¦ Lifting Appliances & Loose Gear | R-010 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-010: Determine whether an offshore-construction alternative-standard pathway is accepted by the Administration for PMS-11.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | SOLAS / DNV | F-R-010-03 | Flag acceptance + technical basis | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-010 | G-010 | A-R-010 | D-R-010 | GATE-2
F-R-011-01 | WPS-03 | Lifting Appliances & Loose Gear | D-R-011 ¦ Lifting Appliances & Loose Gear | R-011 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-011: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance. | Rule/WPS owner | DNV / SOLAS |  | Register + certificates + examination/load-test records | Evidence Register / controlled source record | Required evidence for R-011 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-011 | G-011 | A-R-011 | D-R-011 | GATE-2
F-R-011-02 | WPS-03 | Lifting Appliances & Loose Gear | D-R-011 ¦ Lifting Appliances & Loose Gear | R-011 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / SOLAS | F-R-011-01 | Register + certificates + examination/load-test records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-011 | G-011 | A-R-011 | D-R-011 | GATE-2
F-R-011-03 | WPS-03 | Lifting Appliances & Loose Gear | D-R-011 ¦ Lifting Appliances & Loose Gear | R-011 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-011, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / SOLAS | F-R-011-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-011 | G-011 | A-R-011 | D-R-011 | GATE-2
F-R-011-04 | WPS-03 | Lifting Appliances & Loose Gear | D-R-011 ¦ Lifting Appliances & Loose Gear | R-011 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-011: Establish required examination, load-test, certification and lifting-appliance register controls for each applicable appliance.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / SOLAS | F-R-011-03 | Register + certificates + examination/load-test records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-011 | G-011 | A-R-011 | D-R-011 | GATE-2
F-R-012-01 | WPS-04 | HMC 5500 Derrick Crane | D-R-012 ¦ HMC 5500 Derrick Crane | R-012 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-012: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices. | Rule/WPS owner | DNV / OEM |  | HMC 5500 technical/certification file | Evidence Register / controlled source record | Required evidence for R-012 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-012 | G-012 | A-R-012 | D-R-012 | GATE-2
F-R-012-02 | WPS-04 | HMC 5500 Derrick Crane | D-R-012 ¦ HMC 5500 Derrick Crane | R-012 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / OEM | F-R-012-01 | HMC 5500 technical/certification file; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-012 | G-012 | A-R-012 | D-R-012 | GATE-2
F-R-012-04 | WPS-04 | HMC 5500 Derrick Crane | D-R-012 ¦ HMC 5500 Derrick Crane | R-012 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-012: Verify HMC 5500 identity, configuration, SWL/load chart, structure, foundations, wires, hooks, blocks, sheaves, brakes and safety devices.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / OEM | F-R-012-03 | HMC 5500 technical/certification file | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-012 | G-012 | A-R-012 | D-R-012 | GATE-2
F-R-013-01 | WPS-04 | HMC 5500 Derrick Crane | D-R-013 ¦ HMC 5500 Derrick Crane | R-013 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-013: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation. | Rule/WPS owner | DNV / Project |  | Crane manual, load charts, limits, procedures | Evidence Register / controlled source record | Required evidence for R-013 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-013 | G-013 | A-R-013 | D-R-013 | GATE-2
F-R-013-02 | WPS-04 | HMC 5500 Derrick Crane | D-R-013 ¦ HMC 5500 Derrick Crane | R-013 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Project | F-R-013-01 | Crane manual, load charts, limits, procedures; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-013 | G-013 | A-R-013 | D-R-013 | GATE-2
F-R-013-04 | WPS-04 | HMC 5500 Derrick Crane | D-R-013 ¦ HMC 5500 Derrick Crane | R-013 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-013: Verify HMC 5500 operating limits, dynamic effects, load cases, emergency arrangements and operator documentation.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-013-03 | Crane manual, load charts, limits, procedures | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-013 | G-013 | A-R-013 | D-R-013 | GATE-2
F-R-014-01 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-014 ¦ Link-Belt LS 718 Crawler Crane | R-014 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-014: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving. | Rule/WPS owner | OEM / DNV |  | OEM/configuration file | Evidence Register / controlled source record | Required evidence for R-014 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-014 | G-014 | A-R-014 | D-R-014 | GATE-2
F-R-014-02 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-014 ¦ Link-Belt LS 718 Crawler Crane | R-014 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | OEM / DNV | F-R-014-01 | OEM/configuration file; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-014 | G-014 | A-R-014 | D-R-014 | GATE-2
F-R-014-04 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-014 ¦ Link-Belt LS 718 Crawler Crane | R-014 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-014: Verify Link-Belt LS 718 identity, serial number, configuration, SWL/load chart, boom and reeving.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | OEM / DNV | F-R-014-03 | OEM/configuration file | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-014 | G-014 | A-R-014 | D-R-014 | GATE-2
F-R-015-01 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-015 ¦ Link-Belt LS 718 Crawler Crane | R-015 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-015: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations. | Rule/WPS owner | DNV / Engineering |  | Engineering assessment + load chart + deck data | Evidence Register / controlled source record | Required evidence for R-015 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-015 | G-015 | A-R-015 | D-R-015 | GATE-2
F-R-015-02 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-015 ¦ Link-Belt LS 718 Crawler Crane | R-015 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Engineering | F-R-015-01 | Engineering assessment + load chart + deck data; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-015 | G-015 | A-R-015 | D-R-015 | GATE-2
F-R-015-03 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-015 ¦ Link-Belt LS 718 Crawler Crane | R-015 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-015, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Engineering | F-R-015-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-015 | G-015 | A-R-015 | D-R-015 | GATE-2
F-R-015-04 | WPS-05 | Link-Belt LS 718 Crawler Crane | D-R-015 ¦ Link-Belt LS 718 Crawler Crane | R-015 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-015: Verify LS 718 offshore suitability, deck/foundation loads, stability effects and operating limitations.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Engineering | F-R-015-03 | Engineering assessment + load chart + deck data | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-015 | G-015 | A-R-015 | D-R-015 | GATE-2
F-R-016-01 | WPS-03 | Lifting Appliances & Loose Gear | D-R-016 ¦ Lifting Appliances & Loose Gear | R-016 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-016: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits. | Rule/WPS owner | DNV / OEM |  | Winch certificate/test/exam/OEM file | Evidence Register / controlled source record | Required evidence for R-016 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-016 | G-016 | A-R-016 | D-R-016 | GATE-2
F-R-016-02 | WPS-03 | Lifting Appliances & Loose Gear | D-R-016 ¦ Lifting Appliances & Loose Gear | R-016 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / OEM | F-R-016-01 | Winch certificate/test/exam/OEM file; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-016 | G-016 | A-R-016 | D-R-016 | GATE-2
F-R-016-03 | WPS-03 | Lifting Appliances & Loose Gear | D-R-016 ¦ Lifting Appliances & Loose Gear | R-016 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-016, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / OEM | F-R-016-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-016 | G-016 | A-R-016 | D-R-016 | GATE-2
F-R-016-04 | WPS-03 | Lifting Appliances & Loose Gear | D-R-016 ¦ Lifting Appliances & Loose Gear | R-016 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-016: Verify recovery winch 50 t, wire, foundations, brake/control systems, examination and operating limits.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / OEM | F-R-016-03 | Winch certificate/test/exam/OEM file | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-016 | G-016 | A-R-016 | D-R-016 | GATE-2
F-R-017-01 | WPS-03 | Lifting Appliances & Loose Gear | D-R-017 ¦ Lifting Appliances & Loose Gear | R-017 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-017: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing. | Rule/WPS owner | DNV / OEM |  | Tugger certificates/tests/exams | Evidence Register / controlled source record | Required evidence for R-017 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-017 | G-017 | A-R-017 | D-R-017 | GATE-2
F-R-017-02 | WPS-03 | Lifting Appliances & Loose Gear | D-R-017 ¦ Lifting Appliances & Loose Gear | R-017 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / OEM | F-R-017-01 | Tugger certificates/tests/exams; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-017 | G-017 | A-R-017 | D-R-017 | GATE-2
F-R-017-03 | WPS-03 | Lifting Appliances & Loose Gear | D-R-017 ¦ Lifting Appliances & Loose Gear | R-017 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-017, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / OEM | F-R-017-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-017 | G-017 | A-R-017 | D-R-017 | GATE-2
F-R-017-04 | WPS-03 | Lifting Appliances & Loose Gear | D-R-017 ¦ Lifting Appliances & Loose Gear | R-017 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-017: Verify four 25 MT side tugger winches, foundations, wires, brakes, controls and examination/testing.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / OEM | F-R-017-03 | Tugger certificates/tests/exams | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-017 | G-017 | A-R-017 | D-R-017 | GATE-2
F-R-018-01 | WPS-03 | Lifting Appliances & Loose Gear | D-R-018 ¦ Lifting Appliances & Loose Gear | R-018 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-018: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability. | Rule/WPS owner | DNV / Statutory / OEM |  | Loose-gear register + certificates/exams | Evidence Register / controlled source record | Required evidence for R-018 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-018 | G-018 | A-R-018 | D-R-018 | GATE-2
F-R-018-02 | WPS-03 | Lifting Appliances & Loose Gear | D-R-018 ¦ Lifting Appliances & Loose Gear | R-018 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Statutory / OEM | F-R-018-01 | Loose-gear register + certificates/exams; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-018 | G-018 | A-R-018 | D-R-018 | GATE-2
F-R-018-03 | WPS-03 | Lifting Appliances & Loose Gear | D-R-018 ¦ Lifting Appliances & Loose Gear | R-018 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-018, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Statutory / OEM | F-R-018-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-018 | G-018 | A-R-018 | D-R-018 | GATE-2
F-R-018-04 | WPS-03 | Lifting Appliances & Loose Gear | D-R-018 ¦ Lifting Appliances & Loose Gear | R-018 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-018: Verify lifting beams, spreaders, slings, shackles, hooks, blocks and other loose gear by identification, rating, examination and traceability.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Statutory / OEM | F-R-018-03 | Loose-gear register + certificates/exams | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-018 | G-018 | A-R-018 | D-R-018 | GATE-2
F-R-019-01 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-019 ¦ Pipe-Lay Spread & Tensioner | R-019 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-019: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11. | Rule/WPS owner | DNV Rules |  | Class basis + applicable rule edition | Evidence Register / controlled source record | Required evidence for R-019 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-019 | G-019 | A-R-019 | D-R-019 | GATE-3
F-R-019-02 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-019 ¦ Pipe-Lay Spread & Tensioner | R-019 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV Rules | F-R-019-01 | Class basis + applicable rule edition; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical |  | AC-R-019 | G-019 | A-R-019 | D-R-019 | GATE-3
F-R-019-04 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-019 ¦ Pipe-Lay Spread & Tensioner | R-019 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-019: Establish DNV class basis for the pipe-laying function and exact Pipe Laying Vessel section applicable to PMS-11.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Rules | F-R-019-03 | Class basis + applicable rule edition | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-019 | G-019 | A-R-019 | D-R-019 | GATE-3
F-R-020-01 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-020 ¦ Pipe-Lay Spread & Tensioner | R-020 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-020: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe. | Rule/WPS owner | DNV / OEM / Project |  | CRC drawings/manuals/tests | Evidence Register / controlled source record | Required evidence for R-020 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-020 | G-020 | A-R-020 | D-R-020 | GATE-3
F-R-020-02 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-020 ¦ Pipe-Lay Spread & Tensioner | R-020 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / OEM / Project | F-R-020-01 | CRC drawings/manuals/tests; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-020 | G-020 | A-R-020 | D-R-020 | GATE-3
F-R-020-04 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-020 ¦ Pipe-Lay Spread & Tensioner | R-020 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-020: Verify CRC pipe-lay spread configuration and operating envelope for up to 30-in pipe.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / OEM / Project | F-R-020-03 | CRC drawings/manuals/tests | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-020 | G-020 | A-R-020 | D-R-020 | GATE-3
F-R-021-01 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-021 ¦ Pipe-Lay Spread & Tensioner | R-021 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-021: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests. | Rule/WPS owner | OEM / DNV / Project |  | Tensioner certificate/manual/test records | Evidence Register / controlled source record | Required evidence for R-021 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-021 | G-021 | A-R-021 | D-R-021 | GATE-3
F-R-021-02 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-021 ¦ Pipe-Lay Spread & Tensioner | R-021 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | OEM / DNV / Project | F-R-021-01 | Tensioner certificate/manual/test records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-021 | G-021 | A-R-021 | D-R-021 | GATE-3
F-R-021-03 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-021 ¦ Pipe-Lay Spread & Tensioner | R-021 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-021, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | OEM / DNV / Project | F-R-021-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-021 | G-021 | A-R-021 | D-R-021 | GATE-3
F-R-021-04 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-021 ¦ Pipe-Lay Spread & Tensioner | R-021 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-021: Verify Holland CHT 50L26 tensioner rating, configuration, controls, brakes and tests.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | OEM / DNV / Project | F-R-021-03 | Tensioner certificate/manual/test records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-021 | G-021 | A-R-021 | D-R-021 | GATE-3
F-R-022-01 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-022 ¦ Pipe-Lay Spread & Tensioner | R-022 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-022: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces. | Rule/WPS owner | DNV / Engineering |  | Drawings + calculations + inspection/test records | Evidence Register / controlled source record | Required evidence for R-022 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-022 | G-022 | A-R-022 | D-R-022 | GATE-3
F-R-022-02 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-022 ¦ Pipe-Lay Spread & Tensioner | R-022 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Engineering | F-R-022-01 | Drawings + calculations + inspection/test records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-022 | G-022 | A-R-022 | D-R-022 | GATE-3
F-R-022-03 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-022 ¦ Pipe-Lay Spread & Tensioner | R-022 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-022, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Engineering | F-R-022-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-022 | G-022 | A-R-022 | D-R-022 | GATE-3
F-R-022-04 | WPS-06 | Pipe-Lay Spread & Tensioner | D-R-022 ¦ Pipe-Lay Spread & Tensioner | R-022 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-022: Verify pipe handling, rollers/tracks, lowering arrangement and structural interfaces.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Engineering | F-R-022-03 | Drawings + calculations + inspection/test records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-022 | G-022 | A-R-022 | D-R-022 | GATE-3
F-R-023-01 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-023 ¦ Pipeline Installation, Welding & NDT | R-023 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-023: Verify welding stations, coating station and related QA/QC controls. | Rule/WPS owner | Project / Industry |  | Welding/coating procedures + qualifications | Evidence Register / controlled source record | Required evidence for R-023 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-023 | G-023 | A-R-023 | D-R-023 | GATE-3
F-R-023-02 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-023 ¦ Pipeline Installation, Welding & NDT | R-023 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify welding stations, coating station and related QA/QC controls.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Project / Industry | F-R-023-01 | Welding/coating procedures + qualifications; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-023 | G-023 | A-R-023 | D-R-023 | GATE-3
F-R-023-04 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-023 ¦ Pipeline Installation, Welding & NDT | R-023 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-023: Verify welding stations, coating station and related QA/QC controls.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Project / Industry | F-R-023-03 | Welding/coating procedures + qualifications | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-023 | G-023 | A-R-023 | D-R-023 | GATE-3
F-R-024-01 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-024 ¦ Pipeline Installation, Welding & NDT | R-024 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-024: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work. | Rule/WPS owner | Statutory / Project |  | Equipment certificates + personnel qualifications + procedures | Evidence Register / controlled source record | Required evidence for R-024 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-024 | G-024 | A-R-024 | D-R-024 | GATE-3
F-R-024-02 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-024 ¦ Pipeline Installation, Welding & NDT | R-024 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Statutory / Project | F-R-024-01 | Equipment certificates + personnel qualifications + procedures; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-024 | G-024 | A-R-024 | D-R-024 | GATE-3
F-R-024-03 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-024 ¦ Pipeline Installation, Welding & NDT | R-024 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-024, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Statutory / Project | F-R-024-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-024 | G-024 | A-R-024 | D-R-024 | GATE-3
F-R-024-04 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-024 ¦ Pipeline Installation, Welding & NDT | R-024 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-024: Verify X-ray/NDT equipment, radiation controls and personnel competency applicable to project work.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Statutory / Project | F-R-024-03 | Equipment certificates + personnel qualifications + procedures | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-024 | G-024 | A-R-024 | D-R-024 | GATE-3
F-R-025-01 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-025 ¦ Pipeline Installation, Welding & NDT | R-025 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-025: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis. | Rule/WPS owner | DNV / Project |  | Installation analysis + operating limits + procedures | Evidence Register / controlled source record | Required evidence for R-025 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-025 | G-025 | A-R-025 | D-R-025 | GATE-3
F-R-025-02 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-025 ¦ Pipeline Installation, Welding & NDT | R-025 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV / Project | F-R-025-01 | Installation analysis + operating limits + procedures; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical |  | AC-R-025 | G-025 | A-R-025 | D-R-025 | GATE-3
F-R-025-04 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-025 ¦ Pipeline Installation, Welding & NDT | R-025 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-025: Establish pipe-lay operating limits, tension calculations, emergency recovery and abandonment/recovery basis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-025-03 | Installation analysis + operating limits + procedures | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-025 | G-025 | A-R-025 | D-R-025 | GATE-3
F-R-026-01 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-026 ¦ Pipeline Installation, Welding & NDT | R-026 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-026: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements. | Rule/WPS owner | DNV |  | Project design basis/specification | Evidence Register / controlled source record | Required evidence for R-026 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-026 | G-026 | A-R-026 | D-R-026 | GATE-3
F-R-026-02 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-026 ¦ Pipeline Installation, Welding & NDT | R-026 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV | F-R-026-01 | Project design basis/specification; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Major |  | AC-R-026 | G-026 | A-R-026 | D-R-026 | GATE-3
F-R-026-04 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-026 ¦ Pipeline Installation, Welding & NDT | R-026 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-026: Apply DNV-ST-F101 where it is the governing/project pipeline design basis; distinguish pipeline design from vessel/class requirements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV | F-R-026-03 | Project design basis/specification | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-026 | G-026 | A-R-026 | D-R-026 | GATE-3
F-R-027-01 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-027 ¦ Pipeline Installation, Welding & NDT | R-027 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-027: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115). | Rule/WPS owner | DNV |  | Project specification + engineering basis | Evidence Register / controlled source record | Required evidence for R-027 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-027 | G-027 | A-R-027 | D-R-027 | GATE-3
F-R-027-02 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-027 ¦ Pipeline Installation, Welding & NDT | R-027 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115).; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV | F-R-027-01 | Project specification + engineering basis; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Major |  | AC-R-027 | G-027 | A-R-027 | D-R-027 | GATE-3
F-R-027-04 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-027 ¦ Pipeline Installation, Welding & NDT | R-027 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-027: Identify applicable DNV pipeline RPs only where required by the project/design basis (e.g. F102/F108/F109/F110/F114/F115).. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV | F-R-027-03 | Project specification + engineering basis | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-027 | G-027 | A-R-027 | D-R-027 | GATE-3
F-R-028-01 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-028 ¦ Pipeline Installation, Welding & NDT | R-028 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-028: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads. | Rule/WPS owner | DNV / Project |  | Installation analysis package | Evidence Register / controlled source record | Required evidence for R-028 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-028 | G-028 | A-R-028 | D-R-028 | GATE-3
F-R-028-02 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-028 ¦ Pipeline Installation, Welding & NDT | R-028 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Project | F-R-028-01 | Installation analysis package; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-028 | G-028 | A-R-028 | D-R-028 | GATE-3
F-R-028-03 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-028 ¦ Pipeline Installation, Welding & NDT | R-028 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-028, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Project | F-R-028-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-028 | G-028 | A-R-028 | D-R-028 | GATE-3
F-R-028-04 | WPS-07 | Pipeline Installation, Welding & NDT | D-R-028 ¦ Pipeline Installation, Welding & NDT | R-028 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-028: Establish installation analysis requirements for lay, touchdown, tension, stability, free spans and relevant environmental loads.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-028-03 | Installation analysis package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-028 | G-028 | A-R-028 | D-R-028 | GATE-3
F-R-029-01 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-029 ¦ Eight-Point Mooring & Anchoring | R-029 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-029: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches. | Rule/WPS owner | DNV / IACS |  | Mooring arrangement + equipment certificates | Evidence Register / controlled source record | Required evidence for R-029 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-029 | G-029 | A-R-029 | D-R-029 | GATE-3
F-R-029-02 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-029 ¦ Eight-Point Mooring & Anchoring | R-029 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / IACS | F-R-029-01 | Mooring arrangement + equipment certificates; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-029 | G-029 | A-R-029 | D-R-029 | GATE-3
F-R-029-03 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-029 ¦ Eight-Point Mooring & Anchoring | R-029 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-029, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / IACS | F-R-029-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-029 | G-029 | A-R-029 | D-R-029 | GATE-3
F-R-029-04 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-029 ¦ Eight-Point Mooring & Anchoring | R-029 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-029: Verify complete 8-point mooring equipment inventory: anchors, wires, terminations, shackles, connectors, fairleads and winches.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / IACS | F-R-029-03 | Mooring arrangement + equipment certificates | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-029 | G-029 | A-R-029 | D-R-029 | GATE-3
F-R-030-01 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-030 ¦ Eight-Point Mooring & Anchoring | R-030 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-030: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements. | Rule/WPS owner | DNV / OEM |  | Winch manuals/tests/exams | Evidence Register / controlled source record | Required evidence for R-030 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-030 | G-030 | A-R-030 | D-R-030 | GATE-3
F-R-030-02 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-030 ¦ Eight-Point Mooring & Anchoring | R-030 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / OEM | F-R-030-01 | Winch manuals/tests/exams; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-030 | G-030 | A-R-030 | D-R-030 | GATE-3
F-R-030-03 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-030 ¦ Eight-Point Mooring & Anchoring | R-030 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-030, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / OEM | F-R-030-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-030 | G-030 | A-R-030 | D-R-030 | GATE-3
F-R-030-04 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-030 ¦ Eight-Point Mooring & Anchoring | R-030 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-030: Verify mooring winches, drums, brakes, clutches, controls and emergency recovery arrangements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / OEM | F-R-030-03 | Winch manuals/tests/exams | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-030 | G-030 | A-R-030 | D-R-030 | GATE-3
F-R-031-01 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-031 ¦ Eight-Point Mooring & Anchoring | R-031 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-031: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases. | Rule/WPS owner | DNV / Engineering |  | Mooring analysis + environmental design basis | Evidence Register / controlled source record | Required evidence for R-031 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-031 | G-031 | A-R-031 | D-R-031 | GATE-3
F-R-031-02 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-031 ¦ Eight-Point Mooring & Anchoring | R-031 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV / Engineering | F-R-031-01 | Mooring analysis + environmental design basis; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-031 | G-031 | A-R-031 | D-R-031 | GATE-3
F-R-031-04 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-031 ¦ Eight-Point Mooring & Anchoring | R-031 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-031: Establish engineering basis for 8-point mooring: environmental loads, line tensions, anchor holding, scope, pretension, clearances and failure cases.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Engineering | F-R-031-03 | Mooring analysis + environmental design basis | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-031 | G-031 | A-R-031 | D-R-031 | GATE-3
F-R-032-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-032 ¦ Aqaba Site, Environmental & Pollution Constraints | R-032 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-032: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions. | Rule/WPS owner | DNV / Project |  | Verified survey/geotech package | Evidence Register / controlled source record | Required evidence for R-032 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-032 | G-032 | A-R-032 | D-R-032 | GATE-3
F-R-032-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-032 ¦ Aqaba Site, Environmental & Pollution Constraints | R-032 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Project | F-R-032-01 | Verified survey/geotech package; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-032 | G-032 | A-R-032 | D-R-032 | GATE-3
F-R-032-03 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-032 ¦ Aqaba Site, Environmental & Pollution Constraints | R-032 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-032, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Project | F-R-032-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-032 | G-032 | A-R-032 | D-R-032 | GATE-3
F-R-032-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-032 ¦ Aqaba Site, Environmental & Pollution Constraints | R-032 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-032: Establish required site data: coordinates, bathymetry, water depth, geotechnical/soil data and seabed conditions.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-032-03 | Verified survey/geotech package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-032 | G-032 | A-R-032 | D-R-032 | GATE-3
F-R-033-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-033 ¦ Aqaba Site, Environmental & Pollution Constraints | R-033 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-033: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints. | Rule/WPS owner | Project / Jordan / ASEZA |  | Subsea asset register + approved site layout | Evidence Register / controlled source record | Required evidence for R-033 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-033 | G-033 | A-R-033 | D-R-033 | GATE-3
F-R-033-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-033 ¦ Aqaba Site, Environmental & Pollution Constraints | R-033 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints.. | Responsible technical/functional owner | Project / Jordan / ASEZA | F-R-033-01 | Subsea asset register + approved site layout | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-033 | G-033 | A-R-033 | D-R-033 | GATE-3
F-R-033-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-033 ¦ Aqaba Site, Environmental & Pollution Constraints | R-033 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-033: Account for subsea pipelines, cables, structures, anchor corridors and clearance constraints.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Project / Jordan / ASEZA | F-R-033-03 | Subsea asset register + approved site layout | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-033 | G-033 | A-R-033 | D-R-033 | GATE-3
F-R-034-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-034 ¦ Aqaba Site, Environmental & Pollution Constraints | R-034 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-034: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis. | Rule/WPS owner | DNV / Project |  | Metocean design basis | Evidence Register / controlled source record | Required evidence for R-034 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-034 | G-034 | A-R-034 | D-R-034 | GATE-3
F-R-034-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-034 ¦ Aqaba Site, Environmental & Pollution Constraints | R-034 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV / Project | F-R-034-01 | Metocean design basis; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-034 | G-034 | A-R-034 | D-R-034 | GATE-3
F-R-034-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-034 ¦ Aqaba Site, Environmental & Pollution Constraints | R-034 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-034: Establish environmental criteria: wind, waves, current, water level and operational limits for mooring analysis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-034-03 | Metocean design basis | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-034 | G-034 | A-R-034 | D-R-034 | GATE-3
F-R-035-01 | WPS-11 | Marine Warranty / Independent Verification | D-R-035 ¦ Marine Warranty / Independent Verification | R-035 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-035: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation. | Rule/WPS owner | DNV / Project |  | MWS scope + approval documents | Evidence Register / controlled source record | Required evidence for R-035 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-035 | G-035 | A-R-035 | D-R-035 | GATE-4
F-R-035-02 | WPS-11 | Marine Warranty / Independent Verification | D-R-035 ¦ Marine Warranty / Independent Verification | R-035 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV / Project | F-R-035-01 | MWS scope + approval documents; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-035 | G-035 | A-R-035 | D-R-035 | GATE-4
F-R-035-04 | WPS-11 | Marine Warranty / Independent Verification | D-R-035 ¦ Marine Warranty / Independent Verification | R-035 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-035: Determine requirements for independent verification/MWS of mooring deployment, analysis and operation.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-035-03 | MWS scope + approval documents | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-035 | G-035 | A-R-035 | D-R-035 | GATE-4
F-R-036-01 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-036 ¦ Eight-Point Mooring & Anchoring | R-036 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-036: Establish anchor handling/deployment/recovery procedures, communications and emergency response. | Rule/WPS owner | Project / Marine |  | Approved procedures + drills/records | Evidence Register / controlled source record | Required evidence for R-036 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-036 | G-036 | A-R-036 | D-R-036 | GATE-3
F-R-036-02 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-036 ¦ Eight-Point Mooring & Anchoring | R-036 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Establish anchor handling/deployment/recovery procedures, communications and emergency response.. | Responsible technical/functional owner | Project / Marine | F-R-036-01 | Approved procedures + drills/records | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-036 | G-036 | A-R-036 | D-R-036 | GATE-3
F-R-036-04 | WPS-08 | Eight-Point Mooring & Anchoring | D-R-036 ¦ Eight-Point Mooring & Anchoring | R-036 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-036: Establish anchor handling/deployment/recovery procedures, communications and emergency response.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Project / Marine | F-R-036-03 | Approved procedures + drills/records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-036 | G-036 | A-R-036 | D-R-036 | GATE-3
F-R-037-01 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-037 ¦ Egypt–Aqaba Wet Tow | R-037 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-037: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings. | Rule/WPS owner | DNV |  | Tow engineering package | Evidence Register / controlled source record | Required evidence for R-037 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-037 | G-037 | A-R-037 | D-R-037 | GATE-5
F-R-037-02 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-037 ¦ Egypt–Aqaba Wet Tow | R-037 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV | F-R-037-01 | Tow engineering package; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-037 | G-037 | A-R-037 | D-R-037 | GATE-5
F-R-037-04 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-037 ¦ Egypt–Aqaba Wet Tow | R-037 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-037: Establish wet-tow engineering basis from Egypt to Aqaba including configuration, tow points, bridle, towline and fittings.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV | F-R-037-03 | Tow engineering package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-037 | G-037 | A-R-037 | D-R-037 | GATE-5
F-R-038-01 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-038 ¦ Egypt–Aqaba Wet Tow | R-038 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-038: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings. | Rule/WPS owner | DNV / Engineering |  | Structural verification | Evidence Register / controlled source record | Required evidence for R-038 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-038 | G-038 | A-R-038 | D-R-038 | GATE-5
F-R-038-02 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-038 ¦ Egypt–Aqaba Wet Tow | R-038 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Engineering | F-R-038-01 | Structural verification; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-038 | G-038 | A-R-038 | D-R-038 | GATE-5
F-R-038-03 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-038 ¦ Egypt–Aqaba Wet Tow | R-038 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-038, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Engineering | F-R-038-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-038 | G-038 | A-R-038 | D-R-038 | GATE-5
F-R-038-04 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-038 ¦ Egypt–Aqaba Wet Tow | R-038 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-038: Verify structural adequacy of towing points, fairleads, bridle connections and towing fittings.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Engineering | F-R-038-03 | Structural verification | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-038 | G-038 | A-R-038 | D-R-038 | GATE-5
F-R-039-01 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-039 ¦ Egypt–Aqaba Wet Tow | R-039 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-039: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable. | Rule/WPS owner | DNV / Flag |  | Stability/tow condition calculations | Evidence Register / controlled source record | Required evidence for R-039 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-039 | G-039 | A-R-039 | D-R-039 | GATE-5
F-R-039-02 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-039 ¦ Egypt–Aqaba Wet Tow | R-039 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag | F-R-039-01 | Stability/tow condition calculations; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-039 | G-039 | A-R-039 | D-R-039 | GATE-5
F-R-039-03 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-039 ¦ Egypt–Aqaba Wet Tow | R-039 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-039, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Flag | F-R-039-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-039 | G-039 | A-R-039 | D-R-039 | GATE-5
F-R-039-04 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-039 ¦ Egypt–Aqaba Wet Tow | R-039 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-039: Verify tow stability, freeboard, draft, ballast and intact/damage considerations as applicable.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag | F-R-039-03 | Stability/tow condition calculations | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-039 | G-039 | A-R-039 | D-R-039 | GATE-5
F-R-040-01 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-040 ¦ Egypt–Aqaba Wet Tow | R-040 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-040: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements. | Rule/WPS owner | Marine / DNV / Project |  | Tug data + tow plan | Evidence Register / controlled source record | Required evidence for R-040 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-040 | G-040 | A-R-040 | D-R-040 | GATE-5
F-R-040-02 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-040 ¦ Egypt–Aqaba Wet Tow | R-040 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | Marine / DNV / Project | F-R-040-01 | Tug data + tow plan; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-040 | G-040 | A-R-040 | D-R-040 | GATE-5
F-R-040-04 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-040 ¦ Egypt–Aqaba Wet Tow | R-040 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-040: Establish tug selection, bollard pull, towline characteristics, communications and emergency towing arrangements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Marine / DNV / Project | F-R-040-03 | Tug data + tow plan | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-040 | G-040 | A-R-040 | D-R-040 | GATE-5
F-R-041-01 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-041 ¦ Egypt–Aqaba Wet Tow | R-041 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-041: Establish route, weather criteria, forecast limits, abort criteria and emergency response. | Rule/WPS owner | DNV / Marine |  | Tow route/weather/emergency plan | Evidence Register / controlled source record | Required evidence for R-041 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-041 | G-041 | A-R-041 | D-R-041 | GATE-5
F-R-041-02 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-041 ¦ Egypt–Aqaba Wet Tow | R-041 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Establish route, weather criteria, forecast limits, abort criteria and emergency response.. | Responsible technical/functional owner | DNV / Marine | F-R-041-01 | Tow route/weather/emergency plan | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-041 | G-041 | A-R-041 | D-R-041 | GATE-5
F-R-041-04 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-041 ¦ Egypt–Aqaba Wet Tow | R-041 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-041: Establish route, weather criteria, forecast limits, abort criteria and emergency response.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Marine | F-R-041-03 | Tow route/weather/emergency plan | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-041 | G-041 | A-R-041 | D-R-041 | GATE-5
F-R-042-01 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-042 ¦ Egypt–Aqaba Wet Tow | R-042 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-042: Define pre-tow inspection, readiness verification and required approval/statement before departure. | Rule/WPS owner | DNV / Flag / MWS |  | Pre-tow inspection + approval | Evidence Register / controlled source record | Required evidence for R-042 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-042 | G-042 | A-R-042 | D-R-042 | GATE-5
F-R-042-02 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-042 ¦ Egypt–Aqaba Wet Tow | R-042 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Define pre-tow inspection, readiness verification and required approval/statement before departure.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag / MWS | F-R-042-01 | Pre-tow inspection + approval; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-042 | G-042 | A-R-042 | D-R-042 | GATE-5
F-R-042-03 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-042 ¦ Egypt–Aqaba Wet Tow | R-042 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-042, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Flag / MWS | F-R-042-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-042 | G-042 | A-R-042 | D-R-042 | GATE-5
F-R-042-04 | WPS-10 | Egypt–Aqaba Wet Tow | D-R-042 ¦ Egypt–Aqaba Wet Tow | R-042 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-042: Define pre-tow inspection, readiness verification and required approval/statement before departure.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / MWS | F-R-042-03 | Pre-tow inspection + approval | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-042 | G-042 | A-R-042 | D-R-042 | GATE-5
F-R-043-01 | WPS-11 | Marine Warranty / Independent Verification | D-R-043 ¦ Marine Warranty / Independent Verification | R-043 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-043: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required. | Rule/WPS owner | DNV / Project |  | MWS scope and approvals | Evidence Register / controlled source record | Required evidence for R-043 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-043 | G-043 | A-R-043 | D-R-043 | GATE-4
F-R-043-02 | WPS-11 | Marine Warranty / Independent Verification | D-R-043 ¦ Marine Warranty / Independent Verification | R-043 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | DNV / Project | F-R-043-01 | MWS scope and approvals; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-043 | G-043 | A-R-043 | D-R-043 | GATE-4
F-R-043-03 | WPS-11 | Marine Warranty / Independent Verification | D-R-043 ¦ Marine Warranty / Independent Verification | R-043 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-043, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Project | F-R-043-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-043 | G-043 | A-R-043 | D-R-043 | GATE-4
F-R-043-04 | WPS-11 | Marine Warranty / Independent Verification | D-R-043 ¦ Marine Warranty / Independent Verification | R-043 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-043: Identify marine operations requiring MWS/independent verification, including tow, load-out, lifting and installation where contractually required.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Project | F-R-043-03 | MWS scope and approvals | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-043 | G-043 | A-R-043 | D-R-043 | GATE-4
F-R-044-01 | WPS-12 | Diving Systems — IMCA Only | D-R-044 ¦ Diving Systems — IMCA Only | R-044 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-044: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness. | Rule/WPS owner | IMCA |  | IMCA inspection report + controlled diving procedures/records | Evidence Register / controlled source record | Required evidence for R-044 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-044 | G-044 | A-R-044 | D-R-044 | GATE-7
F-R-044-02 | WPS-12 | Diving Systems — IMCA Only | D-R-044 ¦ Diving Systems — IMCA Only | R-044 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IMCA | F-R-044-01 | IMCA inspection report + controlled diving procedures/records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-044 | G-044 | A-R-044 | D-R-044 | GATE-7
F-R-044-03 | WPS-12 | Diving Systems — IMCA Only | D-R-044 ¦ Diving Systems — IMCA Only | R-044 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-044, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | IMCA | F-R-044-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-044 | G-044 | A-R-044 | D-R-044 | GATE-7
F-R-044-04 | WPS-12 | Diving Systems — IMCA Only | D-R-044 ¦ Diving Systems — IMCA Only | R-044 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-044: Apply IMCA requirements/guidance as the sole diving-system industry baseline for PMS-11's air and saturation diving readiness.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IMCA | F-R-044-03 | IMCA inspection report + controlled diving procedures/records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-044 | G-044 | A-R-044 | D-R-044 | GATE-7
F-R-045-01 | WPS-12 | Diving Systems — IMCA Only | D-R-045 ¦ Diving Systems — IMCA Only | R-045 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-045: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope. | Rule/WPS owner | IMCA |  | IMCA inspection/evidence package | Evidence Register / controlled source record | Required evidence for R-045 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-045 | G-045 | A-R-045 | D-R-045 | GATE-7
F-R-045-02 | WPS-12 | Diving Systems — IMCA Only | D-R-045 ¦ Diving Systems — IMCA Only | R-045 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IMCA | F-R-045-01 | IMCA inspection/evidence package; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-045 | G-045 | A-R-045 | D-R-045 | GATE-7
F-R-045-03 | WPS-12 | Diving Systems — IMCA Only | D-R-045 ¦ Diving Systems — IMCA Only | R-045 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-045, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | IMCA | F-R-045-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-045 | G-045 | A-R-045 | D-R-045 | GATE-7
F-R-045-04 | WPS-12 | Diving Systems — IMCA Only | D-R-045 ¦ Diving Systems — IMCA Only | R-045 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-045: Verify air-diving spread condition, maintenance, testing, procedures, emergency arrangements and competence against applicable IMCA scope.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IMCA | F-R-045-03 | IMCA inspection/evidence package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-045 | G-045 | A-R-045 | D-R-045 | GATE-7
F-R-046-01 | WPS-12 | Diving Systems — IMCA Only | D-R-046 ¦ Diving Systems — IMCA Only | R-046 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-046: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope. | Rule/WPS owner | IMCA |  | IMCA inspection/evidence package | Evidence Register / controlled source record | Required evidence for R-046 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-046 | G-046 | A-R-046 | D-R-046 | GATE-7
F-R-046-02 | WPS-12 | Diving Systems — IMCA Only | D-R-046 ¦ Diving Systems — IMCA Only | R-046 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IMCA | F-R-046-01 | IMCA inspection/evidence package; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-046 | G-046 | A-R-046 | D-R-046 | GATE-7
F-R-046-04 | WPS-12 | Diving Systems — IMCA Only | D-R-046 ¦ Diving Systems — IMCA Only | R-046 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-046: Verify saturation system/station for 8 persons, life-support, chambers/bells, alarms, communications and emergency systems against applicable IMCA scope.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IMCA | F-R-046-03 | IMCA inspection/evidence package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-046 | G-046 | A-R-046 | D-R-046 | GATE-7
F-R-047-01 | WPS-12 | Diving Systems — IMCA Only | D-R-047 ¦ Diving Systems — IMCA Only | R-047 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-047: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements. | Rule/WPS owner | IMCA |  | Competence matrix + records | Evidence Register / controlled source record | Required evidence for R-047 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-047 | G-047 | A-R-047 | D-R-047 | GATE-7
F-R-047-02 | WPS-12 | Diving Systems — IMCA Only | D-R-047 ¦ Diving Systems — IMCA Only | R-047 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IMCA | F-R-047-01 | Competence matrix + records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-047 | G-047 | A-R-047 | D-R-047 | GATE-7
F-R-047-03 | WPS-12 | Diving Systems — IMCA Only | D-R-047 ¦ Diving Systems — IMCA Only | R-047 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-047, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | IMCA | F-R-047-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-047 | G-047 | A-R-047 | D-R-047 | GATE-7
F-R-047-04 | WPS-12 | Diving Systems — IMCA Only | D-R-047 ¦ Diving Systems — IMCA Only | R-047 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-047: Verify diving personnel competency, medical/training records and role-specific readiness against applicable IMCA requirements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IMCA | F-R-047-03 | Competence matrix + records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-047 | G-047 | A-R-047 | D-R-047 | GATE-7
F-R-048-01 | WPS-12 | Diving Systems — IMCA Only | D-R-048 ¦ Diving Systems — IMCA Only | R-048 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-048: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis. | Rule/WPS owner | IMCA |  | Maintenance/test records + IMCA acceptance | Evidence Register / controlled source record | Required evidence for R-048 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-048 | G-048 | A-R-048 | D-R-048 | GATE-7
F-R-048-02 | WPS-12 | Diving Systems — IMCA Only | D-R-048 ¦ Diving Systems — IMCA Only | R-048 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IMCA | F-R-048-01 | Maintenance/test records + IMCA acceptance; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-048 | G-048 | A-R-048 | D-R-048 | GATE-7
F-R-048-03 | WPS-12 | Diving Systems — IMCA Only | D-R-048 ¦ Diving Systems — IMCA Only | R-048 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-048, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | IMCA | F-R-048-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-048 | G-048 | A-R-048 | D-R-048 | GATE-7
F-R-048-04 | WPS-12 | Diving Systems — IMCA Only | D-R-048 ¦ Diving Systems — IMCA Only | R-048 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-048: Verify diving-system maintenance, examination, test and recordkeeping required by the applicable IMCA inspection basis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IMCA | F-R-048-03 | Maintenance/test records + IMCA acceptance | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-048 | G-048 | A-R-048 | D-R-048 | GATE-7
F-R-049-01 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-049 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-049 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-049: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis. | Rule/WPS owner | DNV / Flag |  | Electrical single-line + tests + survey records | Evidence Register / controlled source record | Required evidence for R-049 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-049 | G-049 | A-R-049 | D-R-049 | GATE-7/8
F-R-049-02 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-049 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-049 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag | F-R-049-01 | Electrical single-line + tests + survey records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-049 | G-049 | A-R-049 | D-R-049 | GATE-7/8
F-R-049-04 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-049 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-049 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-049: Verify generators, switchboards, distribution, protection, emergency power and batteries/UPS against applicable class/statutory basis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag | F-R-049-03 | Electrical single-line + tests + survey records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-049 | G-049 | A-R-049 | D-R-049 | GATE-7/8
F-R-050-01 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-050 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-050 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-050: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns. | Rule/WPS owner | DNV / Flag / OEM |  | P&IDs + tests + maintenance records | Evidence Register / controlled source record | Required evidence for R-050 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-050 | G-050 | A-R-050 | D-R-050 | GATE-7/8
F-R-050-02 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-050 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-050 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag / OEM | F-R-050-01 | P&IDs + tests + maintenance records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-050 | G-050 | A-R-050 | D-R-050 | GATE-7/8
F-R-050-04 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-050 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-050 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-050: Verify ballast, bilge, pumps, fuel, hydraulic and compressed-air systems and associated alarms/shutdowns.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / OEM | F-R-050-03 | P&IDs + tests + maintenance records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-050 | G-050 | A-R-050 | D-R-050 | GATE-7/8
F-R-051-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-051 ¦ Fire, LSA, Emergency, Navigation & Communications | R-051 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-051: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis. | Rule/WPS owner | SOLAS / Flag / DNV |  | FSS certificates/tests + plans | Evidence Register / controlled source record | Required evidence for R-051 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-051 | G-051 | A-R-051 | D-R-051 | GATE-6/7
F-R-051-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-051 ¦ Fire, LSA, Emergency, Navigation & Communications | R-051 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | SOLAS / Flag / DNV | F-R-051-01 | FSS certificates/tests + plans; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-051 | G-051 | A-R-051 | D-R-051 | GATE-6/7
F-R-051-03 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-051 ¦ Fire, LSA, Emergency, Navigation & Communications | R-051 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-051, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | SOLAS / Flag / DNV | F-R-051-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-051 | G-051 | A-R-051 | D-R-051 | GATE-6/7
F-R-051-04 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-051 ¦ Fire, LSA, Emergency, Navigation & Communications | R-051 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-051: Verify fire detection/alarm, firefighting systems, pumps, fixed systems and emergency shutdowns against applicable statutory/class basis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | SOLAS / Flag / DNV | F-R-051-03 | FSS certificates/tests + plans | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-051 | G-051 | A-R-051 | D-R-051 | GATE-6/7
F-R-052-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-052 ¦ Fire, LSA, Emergency, Navigation & Communications | R-052 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-052: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness. | Rule/WPS owner | SOLAS / Flag / DNV |  | LSA certificates + drill records | Evidence Register / controlled source record | Required evidence for R-052 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-052 | G-052 | A-R-052 | D-R-052 | GATE-6/7
F-R-052-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-052 ¦ Fire, LSA, Emergency, Navigation & Communications | R-052 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | SOLAS / Flag / DNV | F-R-052-01 | LSA certificates + drill records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-052 | G-052 | A-R-052 | D-R-052 | GATE-6/7
F-R-052-04 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-052 ¦ Fire, LSA, Emergency, Navigation & Communications | R-052 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-052: Verify LSA, muster, emergency lighting, communications, rescue and drill readiness.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | SOLAS / Flag / DNV | F-R-052-03 | LSA certificates + drill records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-052 | G-052 | A-R-052 | D-R-052 | GATE-6/7
F-R-053-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-053 ¦ Fire, LSA, Emergency, Navigation & Communications | R-053 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-053: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems. | Rule/WPS owner | Flag / DNV / Project |  | Equipment list + calibration/service records | Evidence Register / controlled source record | Required evidence for R-053 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-053 | G-053 | A-R-053 | D-R-053 | GATE-6/7
F-R-053-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-053 ¦ Fire, LSA, Emergency, Navigation & Communications | R-053 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Flag / DNV / Project | F-R-053-01 | Equipment list + calibration/service records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-053 | G-053 | A-R-053 | D-R-053 | GATE-6/7
F-R-053-03 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-053 ¦ Fire, LSA, Emergency, Navigation & Communications | R-053 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-053, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Flag / DNV / Project | F-R-053-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-053 | G-053 | A-R-053 | D-R-053 | GATE-6/7
F-R-053-04 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-053 ¦ Fire, LSA, Emergency, Navigation & Communications | R-053 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-053: Verify navigation/survey equipment, DGPS, gyrocompasses, Navipac, BMS/TMS and communication systems.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Flag / DNV / Project | F-R-053-03 | Equipment list + calibration/service records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-053 | G-053 | A-R-053 | D-R-053 | GATE-6/7
F-R-054-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-054 ¦ Fire, LSA, Emergency, Navigation & Communications | R-054 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-054: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow. | Rule/WPS owner | Jordan JMA |  | JMA/VTS requirements + agent confirmation | Evidence Register / controlled source record | Required evidence for R-054 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-054 | G-054 | A-R-054 | D-R-054 | GATE-6/7
F-R-054-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-054 ¦ Fire, LSA, Emergency, Navigation & Communications | R-054 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan JMA | F-R-054-01 | JMA/VTS requirements + agent confirmation; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-054 | G-054 | A-R-054 | D-R-054 | GATE-6/7
F-R-054-04 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-054 ¦ Fire, LSA, Emergency, Navigation & Communications | R-054 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-054: Verify Jordan VTS, entry/departure, reporting and communications requirements applicable to the barge under tow.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan JMA | F-R-054-03 | JMA/VTS requirements + agent confirmation | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-054 | G-054 | A-R-054 | D-R-054 | GATE-6/7
F-R-055-01 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-055 ¦ Accommodation, Welfare, Manning & Competence | R-055 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-055: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements. | Rule/WPS owner | MLC / Flag / DNV |  | Crew profile + accommodation inspection/certification | Evidence Register / controlled source record | Required evidence for R-055 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-055 | G-055 | A-R-055 | D-R-055 | GATE-4/7
F-R-055-02 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-055 ¦ Accommodation, Welfare, Manning & Competence | R-055 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | MLC / Flag / DNV | F-R-055-01 | Crew profile + accommodation inspection/certification; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-055 | G-055 | A-R-055 | D-R-055 | GATE-4/7
F-R-055-04 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-055 ¦ Accommodation, Welfare, Manning & Competence | R-055 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-055: Determine applicable accommodation, sanitary, ventilation, lighting, mess, recreation, medical and welfare requirements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | MLC / Flag / DNV | F-R-055-03 | Crew profile + accommodation inspection/certification | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-055 | G-055 | A-R-055 | D-R-055 | GATE-4/7
F-R-056-01 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-056 ¦ Accommodation, Welfare, Manning & Competence | R-056 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-056: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls. | Rule/WPS owner | MLC / Flag / Jordan Port Health |  | Health/galley/water evidence | Evidence Register / controlled source record | Required evidence for R-056 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-056 | G-056 | A-R-056 | D-R-056 | GATE-4/7
F-R-056-02 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-056 ¦ Accommodation, Welfare, Manning & Competence | R-056 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | MLC / Flag / Jordan Port Health | F-R-056-01 | Health/galley/water evidence; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-056 | G-056 | A-R-056 | D-R-056 | GATE-4/7
F-R-056-04 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-056 ¦ Accommodation, Welfare, Manning & Competence | R-056 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-056: Verify galley, food storage, refrigeration, potable/drinking water, catering hygiene and food waste controls.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | MLC / Flag / Jordan Port Health | F-R-056-03 | Health/galley/water evidence | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-056 | G-056 | A-R-056 | D-R-056 | GATE-4/7
F-R-057-01 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-057 ¦ Accommodation, Welfare, Manning & Competence | R-057 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-057: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements. | Rule/WPS owner | STCW / Flag / Jordan |  | Crew certification matrix | Evidence Register / controlled source record | Required evidence for R-057 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-057 | G-057 | A-R-057 | D-R-057 | GATE-4/7
F-R-057-02 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-057 ¦ Accommodation, Welfare, Manning & Competence | R-057 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | STCW / Flag / Jordan | F-R-057-01 | Crew certification matrix; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-057 | G-057 | A-R-057 | D-R-057 | GATE-4/7
F-R-057-04 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-057 ¦ Accommodation, Welfare, Manning & Competence | R-057 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-057: Verify minimum safe manning, STCW certificates/endorsements, medical certificates and watchkeeping requirements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | STCW / Flag / Jordan | F-R-057-03 | Crew certification matrix | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-057 | G-057 | A-R-057 | D-R-057 | GATE-4/7
F-R-058-01 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-058 ¦ Accommodation, Welfare, Manning & Competence | R-058 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-058: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable. | Rule/WPS owner | Flag / Project / Company |  | Competence matrix + training records | Evidence Register / controlled source record | Required evidence for R-058 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-058 | G-058 | A-R-058 | D-R-058 | GATE-4/7
F-R-058-02 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-058 ¦ Accommodation, Welfare, Manning & Competence | R-058 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Flag / Project / Company | F-R-058-01 | Competence matrix + training records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-058 | G-058 | A-R-058 | D-R-058 | GATE-4/7
F-R-058-03 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-058 ¦ Accommodation, Welfare, Manning & Competence | R-058 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-058, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Flag / Project / Company | F-R-058-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-058 | G-058 | A-R-058 | D-R-058 | GATE-4/7
F-R-058-04 | WPS-15 | Accommodation, Welfare, Manning & Competence | D-R-058 ¦ Accommodation, Welfare, Manning & Competence | R-058 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-058: Verify equipment familiarization, crane/rigging, NDT/radiography, navigation, mooring and emergency competence as applicable.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Flag / Project / Company | F-R-058-03 | Competence matrix + training records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-058 | G-058 | A-R-058 | D-R-058 | GATE-4/7
F-R-059-01 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-059 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-059 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-059: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements. | Rule/WPS owner | DNV / Flag / OEM / Project |  | PMS matrix + OEM manuals + records | Evidence Register / controlled source record | Required evidence for R-059 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-059 | G-059 | A-R-059 | D-R-059 | GATE-7/8
F-R-059-02 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-059 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-059 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag / OEM / Project | F-R-059-01 | PMS matrix + OEM manuals + records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-059 | G-059 | A-R-059 | D-R-059 | GATE-7/8
F-R-059-03 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-059 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-059 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-059, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Flag / OEM / Project | F-R-059-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-059 | G-059 | A-R-059 | D-R-059 | GATE-7/8
F-R-059-04 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-059 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-059 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-059: Establish maintenance hierarchy: class/statutory, OEM, company PMS and project-specific critical-equipment requirements.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / OEM / Project | F-R-059-03 | PMS matrix + OEM manuals + records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-059 | G-059 | A-R-059 | D-R-059 | GATE-7/8
F-R-060-01 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-060 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-060 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-060: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems. | Rule/WPS owner | DNV / Flag / OEM |  | Certificates, test reports, calibration records | Evidence Register / controlled source record | Required evidence for R-060 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-060 | G-060 | A-R-060 | D-R-060 | GATE-7/8
F-R-060-02 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-060 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-060 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag / OEM | F-R-060-01 | Certificates, test reports, calibration records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-060 | G-060 | A-R-060 | D-R-060 | GATE-7/8
F-R-060-03 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-060 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-060 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-060, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Flag / OEM | F-R-060-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-060 | G-060 | A-R-060 | D-R-060 | GATE-7/8
F-R-060-04 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-060 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-060 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-060: Verify inspection, testing and calibration records for critical equipment and safety/navigation systems.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / OEM | F-R-060-03 | Certificates, test reports, calibration records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-060 | G-060 | A-R-060 | D-R-060 | GATE-7/8
F-R-061-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-061 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-061 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-061: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items. | Rule/WPS owner | DNV / Flag / IMCA |  | Survey matrix + records | Evidence Register / controlled source record | Required evidence for R-061 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-061 | G-061 | A-R-061 | D-R-061 | GATE-4/6/8
F-R-061-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-061 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-061 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag / IMCA | F-R-061-01 | Survey matrix + records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-061 | G-061 | A-R-061 | D-R-061 | GATE-4/6/8
F-R-061-03 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-061 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-061 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-061, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Flag / IMCA | F-R-061-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-061 | G-061 | A-R-061 | D-R-061 | GATE-4/6/8
F-R-061-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-061 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-061 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-061: Build current survey/examination matrix covering hull, machinery, lifting, mooring, diving/IMCA, safety, navigation and statutory items.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / IMCA | F-R-061-03 | Survey matrix + records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-061 | G-061 | A-R-061 | D-R-061 | GATE-4/6/8
F-R-062-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-062 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-062 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-062: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records. | Rule/WPS owner | DNV / Flag / Project |  | Controlled document register | Evidence Register / controlled source record | Required evidence for R-062 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-062 | G-062 | A-R-062 | D-R-062 | GATE-4/6/8
F-R-062-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-062 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-062 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV / Flag / Project | F-R-062-01 | Controlled document register; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-062 | G-062 | A-R-062 | D-R-062 | GATE-4/6/8
F-R-062-03 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-062 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-062 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-062, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV / Flag / Project | F-R-062-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-062 | G-062 | A-R-062 | D-R-062 | GATE-4/6/8
F-R-062-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-062 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-062 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-062: Maintain controlled technical documentation: GA, stability, manuals, drawings, procedures, certificates, tests and inspection records.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV / Flag / Project | F-R-062-03 | Controlled document register | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-062 | G-062 | A-R-062 | D-R-062 | GATE-4/6/8
F-R-063-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-063 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-063 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-063: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow. | Rule/WPS owner | Jordan Maritime Commission |  | Agent/JMA entry requirements | Evidence Register / controlled source record | Required evidence for R-063 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-063 | G-063 | A-R-063 | D-R-063 | GATE-4/6/8
F-R-063-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-063 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-063 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-063-01 | Agent/JMA entry requirements; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-063 | G-063 | A-R-063 | D-R-063 | GATE-4/6/8
F-R-063-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-063 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-063 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-063: Apply Jordan entry/departure and VTS requirements to PMS-11 as a foreign non-self-propelled barge under tow.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-063-03 | Agent/JMA entry requirements | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-063 | G-063 | A-R-063 | D-R-063 | GATE-4/6/8
F-R-064-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-064 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-064 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-064: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port. | Rule/WPS owner | Jordan Maritime Commission |  | PSC readiness package | Evidence Register / controlled source record | Required evidence for R-064 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-064 | G-064 | A-R-064 | D-R-064 | GATE-4/6/8
F-R-064-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-064 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-064 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port.. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-064-01 | PSC readiness package | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-064 | G-064 | A-R-064 | D-R-064 | GATE-4/6/8
F-R-064-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-064 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-064 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-064: Prepare for Jordan Port State Control requirements applicable to foreign vessels in Jordanian territorial waters/port.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-064-03 | PSC readiness package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-064 | G-064 | A-R-064 | D-R-064 | GATE-4/6/8
F-R-065-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-065 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-065 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-065: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA. | Rule/WPS owner | Jordan Maritime Commission |  | JMA survey requirements + reports | Evidence Register / controlled source record | Required evidence for R-065 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-065 | G-065 | A-R-065 | D-R-065 | GATE-4/6/8
F-R-065-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-065 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-065 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-065-01 | JMA survey requirements + reports; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-065 | G-065 | A-R-065 | D-R-065 | GATE-4/6/8
F-R-065-03 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-065 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-065 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-065, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Jordan Maritime Commission | F-R-065-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-065 | G-065 | A-R-065 | D-R-065 | GATE-4/6/8
F-R-065-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-065 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-065 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-065: Determine Jordan marine survey/inspection requirements and any pre-arrival or operational surveys required by JMA.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-065-03 | JMA survey requirements + reports | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-065 | G-065 | A-R-065 | D-R-065 | GATE-4/6/8
F-R-066-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-066 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-066 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-066: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation. | Rule/WPS owner | Jordan Maritime Commission |  | Health clearance evidence | Evidence Register / controlled source record | Required evidence for R-066 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-066 | G-066 | A-R-066 | D-R-066 | GATE-4/6/8
F-R-066-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-066 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-066 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation.. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-066-01 | Health clearance evidence | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-066 | G-066 | A-R-066 | D-R-066 | GATE-4/6/8
F-R-066-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-066 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-066 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-066: Determine ship health services, fumigation/deratting and port-health requirements applicable to arrival/operation.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-066-03 | Health clearance evidence | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-066 | G-066 | A-R-066 | D-R-066 | GATE-4/6/8
F-R-067-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-067 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-067 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-067: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation. | Rule/WPS owner | Jordan Maritime Commission |  | Agent/service approvals | Evidence Register / controlled source record | Required evidence for R-067 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-067 | G-067 | A-R-067 | D-R-067 | GATE-4/6/8
F-R-067-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-067 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-067 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-067-01 | Agent/service approvals; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-067 | G-067 | A-R-067 | D-R-067 | GATE-4/6/8
F-R-067-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-067 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-067 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-067: Verify shipping-agent, ship-chandler, marine maintenance, water/fuel supply and related service requirements needed for mobilization/operation.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-067-03 | Agent/service approvals | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-067 | G-067 | A-R-067 | D-R-067 | GATE-4/6/8
F-R-068-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-068 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-068 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-068: Determine ISPS applicability and required port/facility/security interface; do not assume applicability. | Rule/WPS owner | Jordan Maritime Commission |  | Security applicability/approval | Evidence Register / controlled source record | Required evidence for R-068 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-068 | G-068 | A-R-068 | D-R-068 | GATE-4/6/8
F-R-068-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-068 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-068 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine ISPS applicability and required port/facility/security interface; do not assume applicability.. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-068-01 | Security applicability/approval | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-068 | G-068 | A-R-068 | D-R-068 | GATE-4/6/8
F-R-068-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-068 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-068 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-068: Determine ISPS applicability and required port/facility/security interface; do not assume applicability.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-068-03 | Security applicability/approval | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-068 | G-068 | A-R-068 | D-R-068 | GATE-4/6/8
F-R-069-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-069 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-069 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-069: Determine ISM applicability and required interface; do not assume applicability. | Rule/WPS owner | Jordan Maritime Commission |  | ISM applicability/approval | Evidence Register / controlled source record | Required evidence for R-069 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-069 | G-069 | A-R-069 | D-R-069 | GATE-4/6/8
F-R-069-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-069 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-069 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine ISM applicability and required interface; do not assume applicability.. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-069-01 | ISM applicability/approval | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-069 | G-069 | A-R-069 | D-R-069 | GATE-4/6/8
F-R-069-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-069 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-069 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-069: Determine ISM applicability and required interface; do not assume applicability.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-069-03 | ISM applicability/approval | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-069 | G-069 | A-R-069 | D-R-069 | GATE-4/6/8
F-R-070-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-070 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-070 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-070: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11. | Rule/WPS owner | Jordan Maritime Commission |  | Certificates + JMA recognition | Evidence Register / controlled source record | Required evidence for R-070 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-070 | G-070 | A-R-070 | D-R-070 | GATE-4/6/8
F-R-070-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-070 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-070 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-070-01 | Certificates + JMA recognition; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-070 | G-070 | A-R-070 | D-R-070 | GATE-4/6/8
F-R-070-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-070 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-070 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-070: Determine Jordan application/recognition requirements for Load Lines and Tonnage instruments as applicable to PMS-11.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-070-03 | Certificates + JMA recognition | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-070 | G-070 | A-R-070 | D-R-070 | GATE-4/6/8
F-R-071-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-071 ¦ Aqaba Site, Environmental & Pollution Constraints | R-071 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-071: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters. | Rule/WPS owner | Jordan Maritime Commission |  | BWM certificate/records where applicable | Evidence Register / controlled source record | Required evidence for R-071 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-071 | G-071 | A-R-071 | D-R-071 | GATE-3
F-R-071-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-071 ¦ Aqaba Site, Environmental & Pollution Constraints | R-071 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-071-01 | BWM certificate/records where applicable; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-071 | G-071 | A-R-071 | D-R-071 | GATE-3
F-R-071-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-071 ¦ Aqaba Site, Environmental & Pollution Constraints | R-071 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-071: Determine ballast-water management requirements applicable to PMS-11 in Jordanian waters.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-071-03 | BWM certificate/records where applicable | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-071 | G-071 | A-R-071 | D-R-071 | GATE-3
F-R-072-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-072 ¦ Fire, LSA, Emergency, Navigation & Communications | R-072 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-072: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11. | Rule/WPS owner | Jordan Maritime Commission |  | Certificates/test records | Evidence Register / controlled source record | Required evidence for R-072 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-072 | G-072 | A-R-072 | D-R-072 | GATE-6/7
F-R-072-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-072 ¦ Fire, LSA, Emergency, Navigation & Communications | R-072 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-072-01 | Certificates/test records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-072 | G-072 | A-R-072 | D-R-072 | GATE-6/7
F-R-072-03 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-072 ¦ Fire, LSA, Emergency, Navigation & Communications | R-072 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-072, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Jordan Maritime Commission | F-R-072-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-072 | G-072 | A-R-072 | D-R-072 | GATE-6/7
F-R-072-04 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-072 ¦ Fire, LSA, Emergency, Navigation & Communications | R-072 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-072: Determine Jordan application of FSS and Fire Test Code requirements to PMS-11.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-072-03 | Certificates/test records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-072 | G-072 | A-R-072 | D-R-072 | GATE-6/7
F-R-073-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-073 ¦ Fire, LSA, Emergency, Navigation & Communications | R-073 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-073: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement. | Rule/WPS owner | Jordan Maritime Commission |  | Pilot/tug/VTS arrangements | Evidence Register / controlled source record | Required evidence for R-073 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-073 | G-073 | A-R-073 | D-R-073 | GATE-6/7
F-R-073-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-073 ¦ Fire, LSA, Emergency, Navigation & Communications | R-073 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-073-01 | Pilot/tug/VTS arrangements; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-073 | G-073 | A-R-073 | D-R-073 | GATE-6/7
F-R-073-04 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | D-R-073 ¦ Fire, LSA, Emergency, Navigation & Communications | R-073 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-073: Verify safe-navigation rules, pilotage/tug requirements and VTS interactions applicable to tow/port movement.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-073-03 | Pilot/tug/VTS arrangements | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-073 | G-073 | A-R-073 | D-R-073 | GATE-6/7
F-R-074-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-074 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-074 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-074: Establish casualty/incident reporting requirements for events in Jordanian waters. | Rule/WPS owner | Jordan Maritime Commission |  | Reporting procedure/contact matrix | Evidence Register / controlled source record | Required evidence for R-074 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-074 | G-074 | A-R-074 | D-R-074 | GATE-4/6/8
F-R-074-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-074 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-074 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Establish casualty/incident reporting requirements for events in Jordanian waters.. | Responsible technical/functional owner | Jordan Maritime Commission | F-R-074-01 | Reporting procedure/contact matrix | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-074 | G-074 | A-R-074 | D-R-074 | GATE-4/6/8
F-R-074-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-074 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-074 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-074: Establish casualty/incident reporting requirements for events in Jordanian waters.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Maritime Commission | F-R-074-03 | Reporting procedure/contact matrix | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-074 | G-074 | A-R-074 | D-R-074 | GATE-4/6/8
F-R-075-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-075 ¦ Aqaba Site, Environmental & Pollution Constraints | R-075 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-075: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits. | Rule/WPS owner | ASEZA |  | Official boundary + permit/control assessment | Evidence Register / controlled source record | Required evidence for R-075 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-075 | G-075 | A-R-075 | D-R-075 | GATE-3
F-R-075-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-075 ¦ Aqaba Site, Environmental & Pollution Constraints | R-075 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits.. | Responsible technical/functional owner | ASEZA | F-R-075-01 | Official boundary + permit/control assessment | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-075 | G-075 | A-R-075 | D-R-075 | GATE-3
F-R-075-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-075 ¦ Aqaba Site, Environmental & Pollution Constraints | R-075 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-075: Determine whether worksite/activity falls within Marine Reserve boundaries/buffer zones and apply relevant controls/permits.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | ASEZA | F-R-075-03 | Official boundary + permit/control assessment | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-075 | G-075 | A-R-075 | D-R-075 | GATE-3
F-R-076-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-076 ¦ Aqaba Site, Environmental & Pollution Constraints | R-076 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-076: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response. | Rule/WPS owner | ASEZA |  | ASEZA environmental requirements/permits | Evidence Register / controlled source record | Required evidence for R-076 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-076 | G-076 | A-R-076 | D-R-076 | GATE-3
F-R-076-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-076 ¦ Aqaba Site, Environmental & Pollution Constraints | R-076 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | ASEZA | F-R-076-01 | ASEZA environmental requirements/permits; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-076 | G-076 | A-R-076 | D-R-076 | GATE-3
F-R-076-03 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-076 ¦ Aqaba Site, Environmental & Pollution Constraints | R-076 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-076, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | ASEZA | F-R-076-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-076 | G-076 | A-R-076 | D-R-076 | GATE-3
F-R-076-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-076 ¦ Aqaba Site, Environmental & Pollution Constraints | R-076 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-076: Determine environmental approval/control requirements for anchoring, pipe laying, diving, marine construction, waste and pollution response.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | ASEZA | F-R-076-03 | ASEZA environmental requirements/permits | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-076 | G-076 | A-R-076 | D-R-076 | GATE-3
F-R-077-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-077 ¦ Aqaba Site, Environmental & Pollution Constraints | R-077 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-077: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities. | Rule/WPS owner | IMO / Jordan JMA |  | Garbage/oil/sewage/waste records | Evidence Register / controlled source record | Required evidence for R-077 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-077 | G-077 | A-R-077 | D-R-077 | GATE-3
F-R-077-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-077 ¦ Aqaba Site, Environmental & Pollution Constraints | R-077 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities.. | Responsible technical/functional owner | IMO / Jordan JMA | F-R-077-01 | Garbage/oil/sewage/waste records | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-077 | G-077 | A-R-077 | D-R-077 | GATE-3
F-R-077-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-077 ¦ Aqaba Site, Environmental & Pollution Constraints | R-077 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-077: Apply MARPOL and Jordan waste/pollution controls relevant to foreign vessel operations and project activities.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IMO / Jordan JMA | F-R-077-03 | Garbage/oil/sewage/waste records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-077 | G-077 | A-R-077 | D-R-077 | GATE-3
F-R-078-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-078 ¦ Aqaba Site, Environmental & Pollution Constraints | R-078 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-078: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba. | Rule/WPS owner | Jordan / Project |  | SOPEP/SMPEP as applicable + project spill plan | Evidence Register / controlled source record | Required evidence for R-078 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-078 | G-078 | A-R-078 | D-R-078 | GATE-3
F-R-078-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-078 ¦ Aqaba Site, Environmental & Pollution Constraints | R-078 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Jordan / Project | F-R-078-01 | SOPEP/SMPEP as applicable + project spill plan; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-078 | G-078 | A-R-078 | D-R-078 | GATE-3
F-R-078-03 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-078 ¦ Aqaba Site, Environmental & Pollution Constraints | R-078 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-078, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Jordan / Project | F-R-078-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-078 | G-078 | A-R-078 | D-R-078 | GATE-3
F-R-078-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-078 ¦ Aqaba Site, Environmental & Pollution Constraints | R-078 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-078: Establish oil/chemical spill prevention, response equipment, reporting and emergency interface for Jordan/Aqaba.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan / Project | F-R-078-03 | SOPEP/SMPEP as applicable + project spill plan | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-078 | G-078 | A-R-078 | D-R-078 | GATE-3
F-R-079-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-079 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-079 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-079: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities. | Rule/WPS owner | Jordan Authorities / Agent |  | Agent checklist + customs/immigration clearance | Evidence Register / controlled source record | Required evidence for R-079 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-079 | G-079 | A-R-079 | D-R-079 | GATE-4/6/8
F-R-079-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-079 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-079 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities.. | Responsible technical/functional owner | Jordan Authorities / Agent | F-R-079-01 | Agent checklist + customs/immigration clearance | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-079 | G-079 | A-R-079 | D-R-079 | GATE-4/6/8
F-R-079-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-079 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-079 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-079: Determine port customs, immigration, crew/passenger and vessel-entry documentation requirements through the Jordan agent/authorities.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Jordan Authorities / Agent | F-R-079-03 | Agent checklist + customs/immigration clearance | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-079 | G-079 | A-R-079 | D-R-079 | GATE-4/6/8
F-R-080-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-080 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-080 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-080: Review IACS Unified Requirements relevant to hull/structure, mooring/anchoring, machinery, electrical, navigation, fire, materials/welding and survey/certification, only where incorporated/applicable through the governing class rules. | Rule/WPS owner | IACS |  | IACS-to-DNV applicability matrix | Evidence Register / controlled source record | Required evidence for R-080 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-080 | G-080 | A-R-080 | D-R-080 | GATE-1
F-R-080-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-080 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-080 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Review IACS Unified Requirements relevant to hull/structure, mooring/anchoring, machinery, electrical, navigation, fire, materials/welding and survey/certification, only where incorporated/applicable through the governing class rules.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IACS | F-R-080-01 | IACS-to-DNV applicability matrix; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-080 | G-080 | A-R-080 | D-R-080 | GATE-1
F-R-080-03 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-080 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-080 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-080, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | IACS | F-R-080-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-080 | G-080 | A-R-080 | D-R-080 | GATE-1
F-R-080-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-080 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-080 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-080: Review IACS Unified Requirements relevant to hull/structure, mooring/anchoring, machinery, electrical, navigation, fire, materials/welding and survey/certification, only where incorporated/applicable through the governing class rules.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IACS | F-R-080-03 | IACS-to-DNV applicability matrix | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-080 | G-080 | A-R-080 | D-R-080 | GATE-1
F-R-081-01 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-081 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-081 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-081: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability. | Rule/WPS owner | IACS |  | Applicability decision | Evidence Register / controlled source record | Required evidence for R-081 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-081 | G-081 | A-R-081 | D-R-081 | GATE-1
F-R-081-02 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-081 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-081 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | IACS | F-R-081-01 | Applicability decision; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-081 | G-081 | A-R-081 | D-R-081 | GATE-1
F-R-081-03 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-081 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-081 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-081, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | IACS | F-R-081-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-081 | G-081 | A-R-081 | D-R-081 | GATE-1
F-R-081-04 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-081 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-081 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-081: Review UR Z15 for mobile offshore unit survey concepts only if PMS-11 falls within its applicability.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IACS | F-R-081-03 | Applicability decision | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-081 | G-081 | A-R-081 | D-R-081 | GATE-1
F-R-082-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-082 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-082 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-082: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis. | Rule/WPS owner | IACS |  | Rule cross-reference | Evidence Register / controlled source record | Required evidence for R-082 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-082 | G-082 | A-R-082 | D-R-082 | GATE-1
F-R-082-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-082 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-082 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis.. | Responsible technical/functional owner | IACS | F-R-082-01 | Rule cross-reference | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major |  | AC-R-082 | G-082 | A-R-082 | D-R-082 | GATE-1
F-R-082-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-082 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-082 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-082: Do not treat IACS URs as independent statutory requirements; use them through DNV/class incorporation or applicable project basis.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | IACS | F-R-082-03 | Rule cross-reference | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-082 | G-082 | A-R-082 | D-R-082 | GATE-1
F-R-083-01 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-083 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-083 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-083: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project. | Rule/WPS owner | Project / Industry |  | Contract/specification | Evidence Register / controlled source record | Required evidence for R-083 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-083 | G-083 | A-R-083 | D-R-083 | GATE-1
F-R-083-02 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-083 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-083 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Project / Industry | F-R-083-01 | Contract/specification; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-083 | G-083 | A-R-083 | D-R-083 | GATE-1
F-R-083-03 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-083 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-083 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-083, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Project / Industry | F-R-083-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-083 | G-083 | A-R-083 | D-R-083 | GATE-1
F-R-083-04 | WPS-01 | Class Basis, Status, Notation & IACS Cross-Check | D-R-083 ¦ Class Basis, Status, Notation & IACS Cross-Check | R-083 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-083: Identify applicable offshore lifting, marine operations, pipe-lay, NDT/welding and maintenance industry standards required by the contract/project.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Project / Industry | F-R-083-03 | Contract/specification | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-083 | G-083 | A-R-083 | D-R-083 | GATE-1
F-R-084-01 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-084 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-084 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-084: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service. | Rule/WPS owner | OEM |  | OEM manuals/records | Evidence Register / controlled source record | Required evidence for R-084 is identified, controlled, traceable and sufficient for the next verification step. | Major |  | AC-R-084 | G-084 | A-R-084 | D-R-084 | GATE-7/8
F-R-084-02 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-084 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-084 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | OEM | F-R-084-01 | OEM manuals/records; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Major |  | AC-R-084 | G-084 | A-R-084 | D-R-084 | GATE-7/8
F-R-084-03 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-084 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-084 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-084, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | OEM | F-R-084-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Major |  | AC-R-084 | G-084 | A-R-084 | D-R-084 | GATE-7/8
F-R-084-04 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | D-R-084 ¦ Machinery, Electrical, Ballast, Mechanical & Maintenance | R-084 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-084: Use OEM manuals, limits, maintenance instructions and technical bulletins as the equipment-specific baseline where equipment is retained in service.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | OEM | F-R-084-03 | OEM manuals/records | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major |  | AC-R-084 | G-084 | A-R-084 | D-R-084 | GATE-7/8
F-R-085-01 | WPS-11 | Marine Warranty / Independent Verification | D-R-085 ¦ Marine Warranty / Independent Verification | R-085 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-085: Use confidential client/MWS requirements as minimum additional requirements; do not invent them. | Rule/WPS owner | Client / MWS |  | Controlled client/MWS requirement register | Evidence Register / controlled source record | Required evidence for R-085 is identified, controlled, traceable and sufficient for the next verification step. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-085 | G-085 | A-R-085 | D-R-085 | GATE-4
F-R-085-02 | WPS-11 | Marine Warranty / Independent Verification | D-R-085 ¦ Marine Warranty / Independent Verification | R-085 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Use confidential client/MWS requirements as minimum additional requirements; do not invent them.. | Responsible technical/functional owner | Client / MWS | F-R-085-01 | Controlled client/MWS requirement register | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-085 | G-085 | A-R-085 | D-R-085 | GATE-4
F-R-085-04 | WPS-11 | Marine Warranty / Independent Verification | D-R-085 ¦ Marine Warranty / Independent Verification | R-085 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-085: Use confidential client/MWS requirements as minimum additional requirements; do not invent them.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Client / MWS | F-R-085-03 | Controlled client/MWS requirement register | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Major | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-085 | G-085 | A-R-085 | D-R-085 | GATE-4
F-R-086-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-086 ¦ Aqaba Site, Environmental & Pollution Constraints | R-086 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-086: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data. | Rule/WPS owner | Project / Engineering |  | Verified site data package | Evidence Register / controlled source record | Required evidence for R-086 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-086 | G-086 | A-R-086 | D-R-086 | GATE-3
F-R-086-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-086 ¦ Aqaba Site, Environmental & Pollution Constraints | R-086 | 02 | Engineering / Technical Verification | Perform the technical verification/engineering assessment required by the rule: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data.; use only controlled project/site/unit inputs. | Responsible technical/functional owner | Project / Engineering | F-R-086-01 | Verified site data package; calculation/assessment record where applicable | Engineering / Technical Verification | The technical basis is documented, inputs are traceable, applicable limits/assumptions are stated, and the result is accepted or formally dispositioned. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-086 | G-086 | A-R-086 | D-R-086 | GATE-3
F-R-086-04 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | D-R-086 ¦ Aqaba Site, Environmental & Pollution Constraints | R-086 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-086: Do not finalize mooring/anchor pattern, tow criteria or pipe-lay limits without actual site/project data.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Project / Engineering | F-R-086-03 | Verified site data package | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-086 | G-086 | A-R-086 | D-R-086 | GATE-3
F-R-087-01 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-087 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-087 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-087: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence. | Rule/WPS owner | Project Governance |  | Evidence request/status record | Evidence Register / controlled source record | Required evidence for R-087 is identified, controlled, traceable and sufficient for the next verification step. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-087 | G-087 | A-R-087 | D-R-087 | GATE-4/6/8
F-R-087-02 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-087 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-087 | 02 | Applicability / Compliance Verification | Determine and document applicability, required controls and compliance evidence for: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence.. | Responsible technical/functional owner | Project Governance | F-R-087-01 | Evidence request/status record | Applicability / Compliance Verification | Applicability is confirmed or formally dispositioned; required controls and evidence are identified and accepted by the applicable authority/owner. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-087 | G-087 | A-R-087 | D-R-087 | GATE-4/6/8
F-R-087-04 | WPS-16 | Jordan Regulatory, Port, Survey & Controlled Assurance | D-R-087 ¦ Jordan Regulatory, Port, Survey & Controlled Assurance | R-087 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-087: Treat unavailable evidence as an information/verification state until the responsible department confirms availability or absence.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Project Governance | F-R-087-03 | Evidence request/status record | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical | Use actual Aqaba/project/authority data; do not infer site-specific requirements from vessel description. | AC-R-087 | G-087 | A-R-087 | D-R-087 | GATE-4/6/8
F-R-088-01 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-088 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-088 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-088: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario. | Rule/WPS owner | Egyptian Flag / EAMS baseline carried from original 89-rule source set |  | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements | Evidence Register / controlled source record | Required evidence for R-088 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-088 | G-088 | A-R-088 | D-R-088 | GATE-1
F-R-088-02 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-088 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-088 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | Egyptian Flag / EAMS baseline carried from original 89-rule source set | F-R-088-01 | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-088 | G-088 | A-R-088 | D-R-088 | GATE-1
F-R-088-03 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-088 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-088 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-088, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | Egyptian Flag / EAMS baseline carried from original 89-rule source set | F-R-088-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-088 | G-088 | A-R-088 | D-R-088 | GATE-1
F-R-088-04 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-088 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-088 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-088: Establish the applicable Egyptian Flag/EAMS statutory certification, survey, manning, safety, pollution and international-operation requirements for PMS-11 and reconcile them with the Jordan entry/offshore operating scenario.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | Egyptian Flag / EAMS baseline carried from original 89-rule source set | F-R-088-03 | Current Flag statutory certificate set; delegation/RO basis; exemptions/dispensations; survey status; manning/safety/pollution certificates; international-operation/foreign-port requirements | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-088 | G-088 | A-R-088 | D-R-088 | GATE-1
F-R-089-01 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-089 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-089 | 01 | Baseline / Evidence Control | Collect and control the evidence identified for R-089: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions. | Rule/WPS owner | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set |  | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions | Evidence Register / controlled source record | Required evidence for R-089 is identified, controlled, traceable and sufficient for the next verification step. | Critical |  | AC-R-089 | G-089 | A-R-089 | D-R-089 | GATE-1
F-R-089-02 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-089 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-089 | 02 | Inspection / Examination / Test | Execute the applicable inspection/examination/test or physical verification for: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions.; record observed/measured results and deficiencies where applicable. | Responsible technical/functional owner | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set | F-R-089-01 | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions; inspection/examination/test record where applicable | Inspection / Examination / Test | The specified equipment/system/document is verified against the applicable basis; results are recorded; any deficiency is dispositioned before closure. | Critical |  | AC-R-089 | G-089 | A-R-089 | D-R-089 | GATE-1
F-R-089-03 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-089 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-089 | 03 | Deficiency / Rectification Verification | Where the verification identifies a deficiency or outstanding condition for R-089, control the rectification, re-verification/re-test or survey closure as applicable. | Responsible owner / competent verifier | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set | F-R-089-02 | Deficiency record + rectification evidence + re-test/re-survey record where applicable | Conditional closure | No outstanding deficiency remains without a documented authority-approved disposition; rectification and re-verification evidence is linked where required. | Critical |  | AC-R-089 | G-089 | A-R-089 | D-R-089 | GATE-1
F-R-089-04 | WPS-02 | Existing Unit, Flag/Statutory & Rule-Edition Basis | D-R-089 ¦ Existing Unit, Flag/Statutory & Rule-Edition Basis | R-089 | 04 | Acceptance / Authority Disposition | Submit the completed verification package for acceptance/conditional acceptance/escalation for R-089: Establish and verify the hull, structural integrity, stability and load-line technical basis applicable to PMS-11, including approved structural drawings, condition/thickness records, stability documentation and operating-condition restrictions.. | DNV / Egyptian Flag / JMA / ASEZA / Client / MWS / OEM / Competent Person as applicable | DNV Hull / Structural Integrity + DNV Stability / Load Line from original 89-rule source set | F-R-089-03 | Approved GA/structural drawings; stability booklet; loading manual; load-line evidence where applicable; thickness/condition records; survey reports; operating restrictions | Acceptance / Authority Record | Acceptance, conditional acceptance or formal disposition is recorded with authority, restrictions, open conditions and evidence links. | Critical |  | AC-R-089 | G-089 | A-R-089 | D-R-089 | GATE-1
F-HEL-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | Helideck / Helicopter Operations Applicability & Readiness | PROJECT-SCOPE-CHANGE / UNVERIFIED | H-01 | Applicability / Authority Verification | Verify from controlled vessel/project documents whether PMS-11 has an installed helideck/heliport and whether helicopter operations are actually within the intended scope; identify the competent aviation authority and approval route before imposing aviation standards. | Project Technical Manager / Aviation Focal Point | ECAA / Jordan CAA / Client — applicability to be confirmed |  | Approved vessel GA / helideck drawings / project scope / authority correspondence | Controlled applicability decision and authority-route record | The existence, intended use, aircraft type envelope and competent authority route are documented; no aviation compliance claim is made without controlled evidence. | Critical | This requirement was not established as a canonical Rule in the supplied PMS-11 baseline; treat as a change-controlled applicability item. |  |  |  |  | GATE-4/6
F-HEL-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | Helideck / Helicopter Operations Applicability & Readiness | PROJECT-SCOPE-CHANGE / UNVERIFIED | H-02 | Design / Inspection / Verification | If helideck operations are confirmed in scope, verify the physical deck arrangement, markings, lighting, firefighting, rescue/escape arrangements, operational limitations and inspection/certification requirements against the authority-approved basis. | Technical / Safety / Aviation Focal Point | Competent aviation authority / Class / Flag as applicable | F-HEL-01 | Approved helideck basis + inspection/certification records | Helideck inspection/verification package | All applicable physical and operational requirements are evidenced against the approved aviation basis, with deficiencies dispositioned. | Critical | Do not hard-code ICAO/ECAA Part-CAT/Part-145 requirements until the actual aviation activity and authority route are confirmed. |  |  |  |  | GATE-4/6
F-HEL-03 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | Helideck / Helicopter Operations Applicability & Readiness | PROJECT-SCOPE-CHANGE / UNVERIFIED | H-03 | Operations / Emergency Drill | If helicopter operations are confirmed, verify helicopter emergency response interfaces: helideck fire response, rescue, communications, medical response and integration into the vessel emergency plan. | Safety Officer / Master / Aviation Focal Point | Client / Competent authorities as applicable | F-HEL-02 | Drill record / emergency procedure / training records | Helicopter emergency-interface drill record | Emergency interfaces are tested and accepted within the vessel IERP and authority-approved operating basis. | Critical | The source baseline already requires fire/LSA/emergency readiness; the aviation-specific layer remains conditional. |  |  |  |  | GATE-7
F-FUE-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | Fuel / Pollution Control and Emissions Evidence | R-077,R-078 / MARPOL applicability | E-01 | Baseline / Evidence Control | Establish the applicable fuel-quality, bunker-documentation, oil-pollution and emissions-control requirements for the intended Jordan/Aqaba operation from the Flag, port/coastal-state and applicable MARPOL/class basis. | Chief Engineer / Environmental Officer | Egyptian Flag / Jordan competent authority / Class as applicable |  | Applicable regulatory basis + BDN/fuel records where applicable + authority correspondence | Controlled fuel/emissions applicability matrix | The applicable requirements and evidence set are identified; no fixed sulphur limit is assumed without a controlled source. | Critical | The supplied baseline supports MARPOL/pollution control but does not establish the proposed '<0.1% S SECA' statement. |  |  |  |  | GATE-4/6
F-FUE-02 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | Fuel / Pollution Control and Emissions Evidence | R-077,R-078 | E-02 | Inspection / Verification | Verify onboard fuel documentation, bunker delivery records where applicable, fuel sampling/retention arrangements, sludge/waste records and spill-response readiness against the approved requirement matrix. | Chief Engineer / Environmental Officer | Flag / Port / Coastal-state / Class as applicable | F-FUE-01 | BDNs / samples / logs / sludge records / spill kit inspection | Fuel and pollution compliance verification record | Required records are complete, traceable and within the applicable operating period; deficiencies are dispositioned. | Major | Aqaba environmental controls are already a canonical WPS-09 concern; exact local limits remain evidence-dependent. |  |  |  |  | GATE-6
F-PMS-01 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | Planned Maintenance System / CMMS Readiness | R-059,R-060,R-084 | P-01 | Digital System Verification | Audit the PMS/CMMS asset hierarchy, maintenance intervals, overdue work, critical equipment register, defect/deferment control and linkage to class/OEM/statutory requirements. | Superintendent / Maintenance Manager | Internal QA / Class as applicable |  | PMS/CMMS export + maintenance hierarchy + overdue/defect report | Controlled PMS/CMMS audit report | Critical equipment is identifiable, maintenance basis is traceable to the strictest applicable source, and overdue/defect items are dispositioned. | Major | The supplied PMS-11 source explicitly requires a planned-maintenance hierarchy and coverage of cranes, mooring, pipe-lay, diving, electrical, pumps, fire/LSA, navigation and towing equipment. |  |  |  |  | GATE-7/8
F-PMS-02 | WPS-13 | Machinery, Electrical, Ballast, Mechanical & Maintenance | Planned Maintenance System / CMMS Readiness | R-059,R-060,R-084 | P-02 | Physical Verification | Reconcile a sample or full inventory of critical spares and critical equipment condition against PMS/CMMS records; verify that critical defects and deferred work have approved dispositions. | Maintenance Manager / Stores / Superintendent | Internal QA / Class as applicable | F-PMS-01 | Spare-parts inventory / inspection records / defect list | Critical spares and defect reconciliation record | No critical asset is falsely shown as available/maintained; exceptions have documented mitigation and authority acceptance where required. | Major | Do not impose a universal spare list; use equipment criticality, OEM, class/statutory and project requirements. |  |  |  |  | GATE-7/8
F-MOOR-01 | WPS-08 | Eight-Point Mooring & Anchoring | Eight-Point Mooring & Anchoring — Operational Control | R-029,R-030,R-031,R-036 | M-01 | Operational / Control-Room Verification | Verify the installed control-room/bridge arrangements used for anchor handling, including position/line monitoring systems where fitted, alarms, displays, winch controls and communications. | Marine Superintendent / Electrical / Master | Class / MWS / OEM as applicable |  | System inventory + function test + calibration records where applicable | Mooring control-room readiness record | Installed systems are identified and functionally verified against the approved mooring arrangement; unsupported equipment is not assumed to exist. | Critical | The canonical source supports mooring inventory, analysis and operational verification; APMS existence and numeric accuracy limits require equipment/source confirmation. |  |  |  |  | GATE-3
F-MOOR-02 | WPS-08 | Eight-Point Mooring & Anchoring | Eight-Point Mooring & Anchoring — Operational Control | R-030,R-036 | M-02 | Drill / Communication Verification | Conduct an anchor-handling communication drill linking bridge/control room, winch operators and relevant deck personnel; verify emergency communications and command hierarchy. | Master / Marine Superintendent | MWS / Client / Class as applicable | F-MOOR-01 | Drill log / communication test record / procedure | Anchor-handling communications drill record | Command, communication and emergency-release/recovery procedures are understood, tested and recorded. | Critical | The exact emergency release arrangement must be based on the installed equipment and approved procedure. |  |  |  |  | GATE-3
F-MOOR-03 | WPS-08 | Eight-Point Mooring & Anchoring | Eight-Point Mooring & Anchoring — Operational Control | R-030,R-031 | M-03 | Inspection / Test | Verify winch/brake/line/anchor component inspection and testing requirements arising from the approved mooring design and equipment certificates; do not insert a fixed brake percentage unless specified by the governing basis. | Marine / Mechanical Team | Class / MWS / Competent Person as applicable | F-MOOR-01 | Winch test records / certificates / inspection reports | Mooring equipment test and examination dossier | All required tests are completed to the governing acceptance basis and results are within approved limits. | Critical | The proposed 80% SWL criterion in the supplied draft is not adopted without a controlled source. |  |  |  |  | GATE-3
F-HR-01 | WPS-15 | Accommodation, Welfare, Manning & Competence | Crew Welfare, Medical and Competence Readiness | R-055,R-056,R-057,R-058 | HR-01 | Medical / Welfare Verification | Verify sickbay/medical locker/telemedical arrangements, medical equipment, medicines, potable water, food hygiene and public-health interfaces against the applicable Flag/Jordan requirements. | Medic / Safety / HR | Flag / Jordan Health / Port Health as applicable |  | Medical inventory + licences/credentials where required + inspection record | Medical and welfare readiness record | Required medical/welfare arrangements are verified and any jurisdiction-specific licensing or import requirement is formally dispositioned. | Major | The source explicitly calls for medical locker/sickbay/telemedical arrangements and Jordan port-health requirements. |  |  |  |  | GATE-4/7
F-HR-02 | WPS-15 | Accommodation, Welfare, Manning & Competence | Crew Welfare, Medical and Competence Readiness | R-057,R-058 | HR-02 | Fatigue / Behavioural Safety Verification | Verify work/rest-hour controls, competence/familiarization, safety-sensitive role controls and company behavioural policies; include drug/alcohol controls only where supported by company/contract/Flag requirements. | Master / Safety Officer / HR | Flag / Client / Company policy as applicable | F-HR-01 | Work/rest records + competence matrix + applicable policies | Crew safety and fatigue-control verification | Required competence, work/rest and behavioural controls are implemented and records are controlled; no unsupported 'zero tolerance' legal claim is inserted. | Major | The source supports competence and welfare controls; the exact drug/alcohol regime is policy/jurisdiction dependent. |  |  |  |  | GATE-7
F-HR-03 | WPS-15 | Accommodation, Welfare, Manning & Competence | Crew Change and Repatriation Readiness | R-079 / project logistics | HR-03 | Logistics / Regulatory Verification | Establish crew-change, immigration, travel-document, repatriation and agency arrangements for Egypt–Jordan rotations where applicable to the actual manning plan. | HR / Crewing / Project Logistics | Immigration / Agent / Flag / Client as applicable |  | Manning plan + passports/visa evidence where required + agency confirmation | Controlled crew-mobility plan | All required travel/immigration/crew-change dependencies are identified and assigned; no assumption is made that a visa or permit is required until confirmed. | Major | The canonical baseline includes customs/immigration/crew requirements under WPS-16; this adds an operational execution layer. |  |  |  |  | GATE-4/7
F-WAT-01 | WPS-09 | Aqaba Site, Environmental & Pollution Constraints | Water, Sewage, Grey-Water and Waste Readiness | R-077,R-078 / R-056 | W-01 | Commissioning / Testing | Verify potable-water production/treatment, sampling and storage; verify sewage/grey-water arrangements and waste segregation against the applicable Flag/Jordan/port/environmental requirements. | Chief Engineer / Environmental Officer | Flag / Port Health / Jordan environmental authority as applicable |  | Water-quality test results + STP records + waste-management records | Water and waste systems verification dossier | Potable water and wastewater/waste controls meet the applicable controlled requirements; any local discharge restriction is explicitly confirmed rather than assumed. | Major | The source explicitly covers potable water, sewage/grey water and environmental controls. |  |  |  |  | GATE-6/7
F-EMG-01 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | Integrated Emergency Response Readiness | R-051,R-052,R-054,R-074 | EMG-01 | Scenario-Based Drill | Conduct integrated emergency drills covering at least the applicable marine scenarios in the approved emergency plan (e.g., man overboard, fire, loss of position/mooring, pollution event, medical emergency). | Safety Officer / Master | Client / MWS / Port / Civil Defense as applicable |  | Drill plan + attendance + evaluation + corrective-action log | Integrated emergency drill dossier | Scenarios relevant to the actual configuration are exercised, communications are tested, deficiencies are assigned and corrective actions tracked to closure. | Critical | Helideck fire is included only if a helideck is confirmed in scope. |  |  |  |  | GATE-7
F-EMG-02 | WPS-14 | Fire, LSA, Emergency, Navigation & Communications | Integrated Emergency Response Readiness | R-051,R-052 | EMG-02 | Equipment Verification | Verify life-saving, fire-fighting, emergency power, EEBD/escape and launching arrangements, including age/condition-sensitive equipment and any required service/testing. | Chief Mate / Safety / Chief Engineer | Flag / Class / Competent Person as applicable | F-EMG-01 | Certificates / service reports / inspection records | Emergency equipment readiness dossier | All applicable equipment is within required validity/condition limits and any deficiencies are dispositioned before the relevant gate. | Critical | Vintage equipment requires evidence-based inspection; no blanket conclusion is made from age alone. |  |  |  |  | GATE-6/7
WPS-17-01 | WPS-17 | DNV Class Recovery / Reinstatement | D-S-17-01 ¦ Obtain formal DNV suspension notice, class status and violation summary | SC-17-01 | S | Supplemental Operational Control | Obtain formal DNV suspension notice, class status and violation summary | Class Manager | Controlled source / competent authority | WPS-01,WPS-02 | Evidence: E-S-17-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-17-01 | G-S-17-01 | A-S-17-01 | D-S-17-01 | GATE-1
WPS-17-02 | WPS-17 | DNV Class Recovery / Reinstatement | D-S-17-02 ¦ Agree DNV reinstatement survey scope and attendance plan | SC-17-02 | S | Supplemental Operational Control | Agree DNV reinstatement survey scope and attendance plan | Class Manager | Controlled source / competent authority | WPS-17-01 | Evidence: E-S-17-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-17-02 | G-S-17-02 | A-S-17-02 | D-S-17-02 | GATE-1
WPS-17-03 | WPS-17 | DNV Class Recovery / Reinstatement | D-S-17-03 ¦ Complete hull, machinery, electrical and statutory condition assessment | SC-17-03 | S | Supplemental Operational Control | Complete hull, machinery, electrical and statutory condition assessment | Technical Superintendent | Controlled source / competent authority | WPS-17-02 | Evidence: E-S-17-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-17-03 | G-S-17-03 | A-S-17-03 | D-S-17-03 | GATE-1
WPS-17-04 | WPS-17 | DNV Class Recovery / Reinstatement | D-S-17-04 ¦ Execute repairs, tests and survey closeout | SC-17-04 | S | Supplemental Operational Control | Execute repairs, tests and survey closeout | Project Manager | Controlled source / competent authority | WPS-17-03 | Evidence: E-S-17-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-17-04 | G-S-17-04 | A-S-17-04 | D-S-17-04 | GATE-1
WPS-17-05 | WPS-17 | DNV Class Recovery / Reinstatement | D-S-17-05 ¦ Receive formal DNV reinstatement decision and updated class status | SC-17-05 | S | Supplemental Operational Control | Receive formal DNV reinstatement decision and updated class status | Class Manager | Controlled source / competent authority | WPS-17-04 | Evidence: E-S-17-05 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-17-05 | G-S-17-05 | A-S-17-05 | D-S-17-05 | GATE-1
WPS-18-01 | WPS-18 | Alternative IACS Reclassification / Transfer Feasibility | D-S-18-01 ¦ Issue neutral request for information to candidate IACS societies | SC-18-01 | S | Supplemental Operational Control | Issue neutral request for information to candidate IACS societies | Class Manager | Controlled source / competent authority | WPS-01,WPS-02 | Evidence: E-S-18-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-18-01 | G-S-18-01 | A-S-18-01 | D-S-18-01 | GATE-1
WPS-18-02 | WPS-18 | Alternative IACS Reclassification / Transfer Feasibility | D-S-18-02 ¦ Prepare transfer technical dossier and disclosure register | SC-18-02 | S | Supplemental Operational Control | Prepare transfer technical dossier and disclosure register | Class Manager | Controlled source / competent authority | WPS-18-01 | Evidence: E-S-18-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-18-02 | G-S-18-02 | A-S-18-02 | D-S-18-02 | GATE-1
WPS-18-03 | WPS-18 | Alternative IACS Reclassification / Transfer Feasibility | D-S-18-03 ¦ Perform comparative gap, cost and schedule assessment | SC-18-03 | S | Supplemental Operational Control | Perform comparative gap, cost and schedule assessment | Project Controls Manager | Controlled source / competent authority | WPS-18-02,WPS-17-02 | Evidence: E-S-18-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-18-03 | G-S-18-03 | A-S-18-03 | D-S-18-03 | GATE-1
WPS-18-04 | WPS-18 | Alternative IACS Reclassification / Transfer Feasibility | D-S-18-04 ¦ Record management and authority path decision | SC-18-04 | S | Supplemental Operational Control | Record management and authority path decision | Project Director | Controlled source / competent authority | WPS-18-03 | Evidence: E-S-18-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-18-04 | G-S-18-04 | A-S-18-04 | D-S-18-04 | GATE-1
WPS-18-05 | WPS-18 | Alternative IACS Reclassification / Transfer Feasibility | D-S-18-05 ¦ If selected, complete transfer surveys and obtain certificate | SC-18-05 | S | Supplemental Operational Control | If selected, complete transfer surveys and obtain certificate | Class Manager | Controlled source / competent authority | WPS-18-04 | Evidence: E-S-18-05 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-18-05 | G-S-18-05 | A-S-18-05 | D-S-18-05 | GATE-1
WPS-19-01 | WPS-19 | Helideck & Aviation Interface Readiness | D-S-19-01 ¦ Confirm helideck status, intended aircraft and authority jurisdiction | SC-19-01 | S | Supplemental Operational Control | Confirm helideck status, intended aircraft and authority jurisdiction | Aviation Coordinator | Controlled source / competent authority | WPS-14,WPS-16 | Evidence: E-S-19-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-19-01 | G-S-19-01 | A-S-19-01 | D-S-19-01 | GATE-7
WPS-19-02 | WPS-19 | Helideck & Aviation Interface Readiness | D-S-19-02 ¦ Review helideck structural, obstacle, marking, lighting and access basis | SC-19-02 | S | Supplemental Operational Control | Review helideck structural, obstacle, marking, lighting and access basis | Aviation Coordinator | Controlled source / competent authority | WPS-19-01 | Evidence: E-S-19-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-19-02 | G-S-19-02 | A-S-19-02 | D-S-19-02 | GATE-7
WPS-19-03 | WPS-19 | Helideck & Aviation Interface Readiness | D-S-19-03 ¦ Review flight operations and marine-aviation interface manual | SC-19-03 | S | Supplemental Operational Control | Review flight operations and marine-aviation interface manual | Aviation Coordinator | Controlled source / competent authority | WPS-19-01 | Evidence: E-S-19-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-19-03 | G-S-19-03 | A-S-19-03 | D-S-19-03 | GATE-7
WPS-19-04 | WPS-19 | Helideck & Aviation Interface Readiness | D-S-19-04 ¦ Verify helideck firefighting, rescue, PPE and trained team | SC-19-04 | S | Supplemental Operational Control | Verify helideck firefighting, rescue, PPE and trained team | HSE Manager | Controlled source / competent authority | WPS-19-02,WPS-14 | Evidence: E-S-19-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-19-04 | G-S-19-04 | A-S-19-04 | D-S-19-04 | GATE-7
WPS-19-05 | WPS-19 | Helideck & Aviation Interface Readiness | D-S-19-05 ¦ Secure required operational permissions and acceptance evidence | SC-19-05 | S | Supplemental Operational Control | Secure required operational permissions and acceptance evidence | Aviation Coordinator | Controlled source / competent authority | WPS-19-02,WPS-19-03,WPS-19-04 | Evidence: E-S-19-05 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-19-05 | G-S-19-05 | A-S-19-05 | D-S-19-05 | GATE-7
WPS-20-01 | WPS-20 | Fuel, Emissions, Water & Waste Operational Control | D-S-20-01 ¦ Determine applicable fuel sulphur and emissions requirements for route and Aqaba | SC-20-01 | S | Supplemental Operational Control | Determine applicable fuel sulphur and emissions requirements for route and Aqaba | Environmental Manager | Controlled source / competent authority | WPS-09,WPS-16 | Evidence: E-S-20-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-20-01 | G-S-20-01 | A-S-20-01 | D-S-20-01 | GATE-7/8
WPS-20-02 | WPS-20 | Fuel, Emissions, Water & Waste Operational Control | D-S-20-02 ¦ Verify BDN, fuel samples, changeover procedures and consumption plan | SC-20-02 | S | Supplemental Operational Control | Verify BDN, fuel samples, changeover procedures and consumption plan | Chief Engineer | Controlled source / competent authority | WPS-20-01 | Evidence: E-S-20-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-20-02 | G-S-20-02 | A-S-20-02 | D-S-20-02 | GATE-7/8
WPS-20-03 | WPS-20 | Fuel, Emissions, Water & Waste Operational Control | D-S-20-03 ¦ Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | SC-20-03 | S | Supplemental Operational Control | Verify sludge, oily water, sewage and garbage capacity/disposal arrangements | Chief Engineer | Controlled source / competent authority | WPS-09,WPS-13,WPS-20-01 | Evidence: E-S-20-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-20-03 | G-S-20-03 | A-S-20-03 | D-S-20-03 | GATE-7/8
WPS-20-04 | WPS-20 | Fuel, Emissions, Water & Waste Operational Control | D-S-20-04 ¦ Commission potable-water and RO systems and obtain laboratory results | SC-20-04 | S | Supplemental Operational Control | Commission potable-water and RO systems and obtain laboratory results | Chief Engineer | Controlled source / competent authority | WPS-13 | Evidence: E-S-20-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-20-04 | G-S-20-04 | A-S-20-04 | D-S-20-04 | GATE-7/8
WPS-20-05 | WPS-20 | Fuel, Emissions, Water & Waste Operational Control | D-S-20-05 ¦ Close spill prevention and waste contractor interfaces | SC-20-05 | S | Supplemental Operational Control | Close spill prevention and waste contractor interfaces | Environmental Manager | Controlled source / competent authority | WPS-20-02,WPS-20-03 | Evidence: E-S-20-05 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Major |  | AC-S-20-05 | G-S-20-05 | A-S-20-05 | D-S-20-05 | GATE-7/8
WPS-21-01 | WPS-21 | Digital PMS / CMMS, Spares & Materials Readiness | D-S-21-01 ¦ Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | SC-21-01 | S | Supplemental Operational Control | Audit CMMS/PMS asset hierarchy, job plans, intervals and data integrity | Maintenance Superintendent | Controlled source / competent authority | WPS-13 | Evidence: E-S-21-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-21-01 | G-S-21-01 | A-S-21-01 | D-S-21-01 | GATE-7
WPS-21-02 | WPS-21 | Digital PMS / CMMS, Spares & Materials Readiness | D-S-21-02 ¦ Generate critical defect and overdue-maintenance backlog | SC-21-02 | S | Supplemental Operational Control | Generate critical defect and overdue-maintenance backlog | Maintenance Superintendent | Controlled source / competent authority | WPS-21-01 | Evidence: E-S-21-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-21-02 | G-S-21-02 | A-S-21-02 | D-S-21-02 | GATE-7
WPS-21-03 | WPS-21 | Digital PMS / CMMS, Spares & Materials Readiness | D-S-21-03 ¦ Map critical spares/materials to equipment and physically verify stock | SC-21-03 | S | Supplemental Operational Control | Map critical spares/materials to equipment and physically verify stock | Stores Manager | Controlled source / competent authority | WPS-21-01 | Evidence: E-S-21-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-21-03 | G-S-21-03 | A-S-21-03 | D-S-21-03 | GATE-7
WPS-21-04 | WPS-21 | Digital PMS / CMMS, Spares & Materials Readiness | D-S-21-04 ¦ Issue procurement plan for shortages and long-lead items | SC-21-04 | S | Supplemental Operational Control | Issue procurement plan for shortages and long-lead items | Procurement Manager | Controlled source / competent authority | WPS-21-02,WPS-21-03 | Evidence: E-S-21-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-21-04 | G-S-21-04 | A-S-21-04 | D-S-21-04 | GATE-7
WPS-21-05 | WPS-21 | Digital PMS / CMMS, Spares & Materials Readiness | D-S-21-05 ¦ Back up CMMS database and approve mobilization maintenance baseline | SC-21-05 | S | Supplemental Operational Control | Back up CMMS database and approve mobilization maintenance baseline | Maintenance Superintendent | Controlled source / competent authority | WPS-21-02,WPS-21-03,WPS-21-04 | Evidence: E-S-21-05 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-21-05 | G-S-21-05 | A-S-21-05 | D-S-21-05 | GATE-7
WPS-22-01 | WPS-22 | Anchor Handling, Control Room & Position Monitoring Operations | D-S-22-01 ¦ Develop approved anchor pattern, deployment sequence and exclusion controls | SC-22-01 | S | Supplemental Operational Control | Develop approved anchor pattern, deployment sequence and exclusion controls | Marine Superintendent | Controlled source / competent authority | WPS-08,WPS-09 | Evidence: E-S-22-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-22-01 | G-S-22-01 | A-S-22-01 | D-S-22-01 | GATE-3
WPS-22-02 | WPS-22 | Anchor Handling, Control Room & Position Monitoring Operations | D-S-22-02 ¦ Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | SC-22-02 | S | Supplemental Operational Control | Verify control-room/APMS/DGPS/gyro displays, alarms and calibration | Survey Manager | Controlled source / competent authority | WPS-14,WPS-22-01 | Evidence: E-S-22-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-22-02 | G-S-22-02 | A-S-22-02 | D-S-22-02 | GATE-3
WPS-22-03 | WPS-22 | Anchor Handling, Control Room & Position Monitoring Operations | D-S-22-03 ¦ Test winches, brakes, controls, communications and emergency release | SC-22-03 | S | Supplemental Operational Control | Test winches, brakes, controls, communications and emergency release | Marine Superintendent | Controlled source / competent authority | WPS-08,WPS-13,WPS-22-02 | Evidence: E-S-22-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-22-03 | G-S-22-03 | A-S-22-03 | D-S-22-03 | GATE-3
WPS-22-04 | WPS-22 | Anchor Handling, Control Room & Position Monitoring Operations | D-S-22-04 ¦ Approve tug assignment, command hierarchy and standard communications | SC-22-04 | S | Supplemental Operational Control | Approve tug assignment, command hierarchy and standard communications | Marine Superintendent | Controlled source / competent authority | WPS-22-01,WPS-22-03 | Evidence: E-S-22-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-22-04 | G-S-22-04 | A-S-22-04 | D-S-22-04 | GATE-3
WPS-22-05 | WPS-22 | Anchor Handling, Control Room & Position Monitoring Operations | D-S-22-05 ¦ Conduct anchor-handling tabletop and operational drill | SC-22-05 | S | Supplemental Operational Control | Conduct anchor-handling tabletop and operational drill | Marine Superintendent | Controlled source / competent authority | WPS-22-02,WPS-22-03,WPS-22-04 | Evidence: E-S-22-05 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-22-05 | G-S-22-05 | A-S-22-05 | D-S-22-05 | GATE-3
WPS-23-01 | WPS-23 | Crew Mobilization, Medical & Behavioral Safety | D-S-23-01 ¦ Approve departmental manpower, competency and rotation matrix | SC-23-01 | S | Supplemental Operational Control | Approve departmental manpower, competency and rotation matrix | HR Manager | Controlled source / competent authority | WPS-15 | Evidence: E-S-23-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-23-01 | G-S-23-01 | A-S-23-01 | D-S-23-01 | GATE-4/7
WPS-23-02 | WPS-23 | Crew Mobilization, Medical & Behavioral Safety | D-S-23-02 ¦ Verify clinic equipment, medicines, licenses and medevac interface | SC-23-02 | S | Supplemental Operational Control | Verify clinic equipment, medicines, licenses and medevac interface | Medical Coordinator | Controlled source / competent authority | WPS-23-01,WPS-19-03 | Evidence: E-S-23-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-23-02 | G-S-23-02 | A-S-23-02 | D-S-23-02 | GATE-4/7
WPS-23-03 | WPS-23 | Crew Mobilization, Medical & Behavioral Safety | D-S-23-03 ¦ Implement fatigue, rest-hour and drug/alcohol policy controls | SC-23-03 | S | Supplemental Operational Control | Implement fatigue, rest-hour and drug/alcohol policy controls | HSE Manager | Controlled source / competent authority | WPS-23-01 | Evidence: E-S-23-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-23-03 | G-S-23-03 | A-S-23-03 | D-S-23-03 | GATE-4/7
WPS-23-04 | WPS-23 | Crew Mobilization, Medical & Behavioral Safety | D-S-23-04 ¦ Complete visas, travel, repatriation and crew-change logistics | SC-23-04 | S | Supplemental Operational Control | Complete visas, travel, repatriation and crew-change logistics | HR Manager | Controlled source / competent authority | WPS-16,WPS-23-01 | Evidence: E-S-23-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | High |  | AC-S-23-04 | G-S-23-04 | A-S-23-04 | D-S-23-04 | GATE-4/7
WPS-24-01 | WPS-24 | Integrated Operational & Emergency Readiness | D-S-24-01 ¦ Issue integrated emergency response and shore-interface matrix | SC-24-01 | S | Supplemental Operational Control | Issue integrated emergency response and shore-interface matrix | HSE Manager | Controlled source / competent authority | WPS-09,WPS-10,WPS-12,WPS-14,WPS-19,WPS-20,WPS-22,WPS-23 | Evidence: E-S-24-01 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-24-01 | G-S-24-01 | A-S-24-01 | D-S-24-01 | GATE-8
WPS-24-02 | WPS-24 | Integrated Operational & Emergency Readiness | D-S-24-02 ¦ Define scenario drill programme and measurable acceptance criteria | SC-24-02 | S | Supplemental Operational Control | Define scenario drill programme and measurable acceptance criteria | HSE Manager | Controlled source / competent authority | WPS-24-01 | Evidence: E-S-24-02 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-24-02 | G-S-24-02 | A-S-24-02 | D-S-24-02 | GATE-8
WPS-24-03 | WPS-24 | Integrated Operational & Emergency Readiness | D-S-24-03 ¦ Conduct marine, aviation, diving, pollution and medevac interface drills | SC-24-03 | S | Supplemental Operational Control | Conduct marine, aviation, diving, pollution and medevac interface drills | Project Manager | Controlled source / competent authority | WPS-24-02,WPS-19-04,WPS-22-05,WPS-23-02 | Evidence: E-S-24-03 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-24-03 | G-S-24-03 | A-S-24-03 | D-S-24-03 | GATE-8
WPS-24-04 | WPS-24 | Integrated Operational & Emergency Readiness | D-S-24-04 ¦ Close drill findings and issue final operational readiness recommendation | SC-24-04 | S | Supplemental Operational Control | Close drill findings and issue final operational readiness recommendation | Project Director | Controlled source / competent authority | WPS-24-03,WPS-17-05,WPS-18-04,WPS-20-05,WPS-21-05 | Evidence: E-S-24-04 | Document review / inspection / test / drill / authority review | Control completed; evidence accepted; deficiencies dispositioned; authority acceptance recorded. | Critical |  | AC-S-24-04 | G-S-24-04 | A-S-24-04 | D-S-24-04 | GATE-8

## Dependencies
Link ID | Predecessor ID | Successor ID | Relationship | Lag Days | Dependency Class | Rationale | Validated By | Validation Status | Comments
LNK-0001 | GATE-0 | T-R-001-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0002 | GATE-0 | T-R-001-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0003 | T-R-001-01 | T-R-001-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0004 | T-R-001-01 | T-R-001-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0005 | T-R-001-02 | T-R-001-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0006 | T-R-001-02 | T-R-001-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0007 | T-R-001-03 | T-R-002-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0008 | T-R-001-03 | T-R-002-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0009 | T-R-002-01 | T-R-002-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0010 | T-R-002-01 | T-R-002-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0011 | T-R-002-02 | T-R-002-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0012 | T-R-002-02 | T-R-002-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0013 | T-R-002-03 | T-R-003-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0014 | T-R-002-03 | T-R-003-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0015 | T-R-003-01 | T-R-003-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0016 | T-R-003-01 | T-R-003-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0017 | T-R-003-02 | T-R-003-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0018 | T-R-003-02 | T-R-003-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0019 | T-R-003-03 | T-R-004-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0020 | T-R-003-03 | T-R-004-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0021 | T-R-004-01 | T-R-004-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0022 | T-R-004-01 | T-R-004-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0023 | T-R-004-02 | T-R-004-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0024 | T-R-004-02 | T-R-004-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0025 | T-R-004-03 | T-R-005-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0026 | T-R-004-03 | T-R-005-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0027 | T-R-005-01 | T-R-005-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0028 | T-R-005-01 | T-R-005-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0029 | T-R-005-02 | T-R-005-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0030 | T-R-005-02 | T-R-005-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0031 | T-R-005-03 | T-R-006-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0032 | T-R-005-03 | T-R-006-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0033 | T-R-006-01 | T-R-006-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0034 | T-R-006-01 | T-R-006-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0035 | T-R-006-02 | T-R-006-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0036 | T-R-006-02 | T-R-006-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0037 | T-R-006-03 | T-R-007-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0038 | T-R-006-03 | T-R-007-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0039 | T-R-007-01 | T-R-007-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0040 | T-R-007-01 | T-R-007-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0041 | T-R-007-02 | T-R-007-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0042 | T-R-007-02 | T-R-007-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0043 | T-R-007-03 | T-R-008-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0044 | T-R-007-03 | T-R-008-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0045 | T-R-008-01 | T-R-008-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0046 | T-R-008-01 | T-R-008-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0047 | T-R-008-02 | T-R-008-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0048 | T-R-008-02 | T-R-008-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0049 | T-R-008-03 | T-R-009-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0050 | T-R-008-03 | T-R-009-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0051 | T-R-009-01 | T-R-009-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0052 | T-R-009-01 | T-R-009-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0053 | T-R-009-02 | T-R-009-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0054 | T-R-009-02 | T-R-009-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0055 | T-R-009-03 | T-R-010-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0056 | T-R-009-03 | T-R-010-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0057 | T-R-010-01 | T-R-010-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0058 | T-R-010-01 | T-R-010-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0059 | T-R-010-02 | T-R-010-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0060 | T-R-010-02 | T-R-010-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0061 | T-R-010-03 | T-R-011-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0062 | T-R-010-03 | T-R-011-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0063 | T-R-011-01 | T-R-011-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0064 | T-R-011-01 | T-R-011-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0065 | T-R-011-02 | T-R-011-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0066 | T-R-011-02 | T-R-011-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0067 | T-R-011-03 | T-R-012-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0068 | T-R-011-03 | T-R-012-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0069 | T-R-012-01 | T-R-012-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0070 | T-R-012-01 | T-R-012-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0071 | T-R-012-02 | T-R-012-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0072 | T-R-012-02 | T-R-012-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0073 | T-R-012-03 | T-R-013-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0074 | T-R-012-03 | T-R-013-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0075 | T-R-013-01 | T-R-013-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0076 | T-R-013-01 | T-R-013-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0077 | T-R-013-02 | T-R-013-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0078 | T-R-013-02 | T-R-013-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0079 | T-R-013-03 | T-R-014-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0080 | T-R-013-03 | T-R-014-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0081 | T-R-014-01 | T-R-014-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0082 | T-R-014-01 | T-R-014-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0083 | T-R-014-02 | T-R-014-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0084 | T-R-014-02 | T-R-014-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0085 | T-R-014-03 | T-R-015-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0086 | T-R-014-03 | T-R-015-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0087 | T-R-015-01 | T-R-015-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0088 | T-R-015-01 | T-R-015-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0089 | T-R-015-02 | T-R-015-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0090 | T-R-015-02 | T-R-015-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0091 | T-R-015-03 | T-R-016-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0092 | T-R-015-03 | T-R-016-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0093 | T-R-016-01 | T-R-016-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0094 | T-R-016-01 | T-R-016-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0095 | T-R-016-02 | T-R-016-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0096 | T-R-016-02 | T-R-016-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0097 | T-R-016-03 | T-R-017-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0098 | T-R-016-03 | T-R-017-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0099 | T-R-017-01 | T-R-017-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0100 | T-R-017-01 | T-R-017-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0101 | T-R-017-02 | T-R-017-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0102 | T-R-017-02 | T-R-017-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0103 | T-R-017-03 | T-R-018-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0104 | T-R-017-03 | T-R-018-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0105 | T-R-018-01 | T-R-018-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0106 | T-R-018-01 | T-R-018-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0107 | T-R-018-02 | T-R-018-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0108 | T-R-018-02 | T-R-018-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0109 | T-R-018-03 | T-R-019-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0110 | T-R-018-03 | T-R-019-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0111 | T-R-019-01 | T-R-019-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0112 | T-R-019-01 | T-R-019-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0113 | T-R-019-02 | T-R-019-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0114 | T-R-019-02 | T-R-019-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0115 | T-R-019-03 | T-R-020-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0116 | T-R-019-03 | T-R-020-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0117 | T-R-020-01 | T-R-020-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0118 | T-R-020-01 | T-R-020-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0119 | T-R-020-02 | T-R-020-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0120 | T-R-020-02 | T-R-020-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0121 | T-R-020-03 | T-R-021-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0122 | T-R-020-03 | T-R-021-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0123 | T-R-021-01 | T-R-021-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0124 | T-R-021-01 | T-R-021-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0125 | T-R-021-02 | T-R-021-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0126 | T-R-021-02 | T-R-021-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0127 | T-R-021-03 | T-R-022-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0128 | T-R-021-03 | T-R-022-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0129 | T-R-022-01 | T-R-022-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0130 | T-R-022-01 | T-R-022-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0131 | T-R-022-02 | T-R-022-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0132 | T-R-022-02 | T-R-022-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0133 | T-R-022-03 | T-R-023-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0134 | T-R-022-03 | T-R-023-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0135 | T-R-023-01 | T-R-023-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0136 | T-R-023-01 | T-R-023-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0137 | T-R-023-02 | T-R-023-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0138 | T-R-023-02 | T-R-023-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0139 | T-R-023-03 | T-R-024-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0140 | T-R-023-03 | T-R-024-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0141 | T-R-024-01 | T-R-024-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0142 | T-R-024-01 | T-R-024-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0143 | T-R-024-02 | T-R-024-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0144 | T-R-024-02 | T-R-024-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0145 | T-R-024-03 | T-R-025-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0146 | T-R-024-03 | T-R-025-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0147 | T-R-025-01 | T-R-025-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0148 | T-R-025-01 | T-R-025-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0149 | T-R-025-02 | T-R-025-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0150 | T-R-025-02 | T-R-025-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0151 | T-R-025-03 | T-R-026-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0152 | T-R-025-03 | T-R-026-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0153 | T-R-026-01 | T-R-026-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0154 | T-R-026-01 | T-R-026-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0155 | T-R-026-02 | T-R-026-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0156 | T-R-026-02 | T-R-026-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0157 | T-R-026-03 | T-R-027-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0158 | T-R-026-03 | T-R-027-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0159 | T-R-027-01 | T-R-027-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0160 | T-R-027-01 | T-R-027-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0161 | T-R-027-02 | T-R-027-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0162 | T-R-027-02 | T-R-027-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0163 | T-R-027-03 | T-R-028-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0164 | T-R-027-03 | T-R-028-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0165 | T-R-028-01 | T-R-028-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0166 | T-R-028-01 | T-R-028-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0167 | T-R-028-02 | T-R-028-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0168 | T-R-028-02 | T-R-028-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0169 | T-R-028-03 | T-R-029-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0170 | T-R-028-03 | T-R-029-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0171 | T-R-029-01 | T-R-029-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0172 | T-R-029-01 | T-R-029-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0173 | T-R-029-02 | T-R-029-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0174 | T-R-029-02 | T-R-029-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0175 | T-R-029-03 | T-R-030-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0176 | T-R-029-03 | T-R-030-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0177 | T-R-030-01 | T-R-030-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0178 | T-R-030-01 | T-R-030-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0179 | T-R-030-02 | T-R-030-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0180 | T-R-030-02 | T-R-030-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0181 | T-R-030-03 | T-R-031-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0182 | T-R-030-03 | T-R-031-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0183 | T-R-031-01 | T-R-031-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0184 | T-R-031-01 | T-R-031-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0185 | T-R-031-02 | T-R-031-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0186 | T-R-031-02 | T-R-031-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0187 | T-R-031-03 | T-R-032-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0188 | T-R-031-03 | T-R-032-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0189 | T-R-032-01 | T-R-032-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0190 | T-R-032-01 | T-R-032-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0191 | T-R-032-02 | T-R-032-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0192 | T-R-032-02 | T-R-032-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0193 | T-R-032-03 | T-R-033-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0194 | T-R-032-03 | T-R-033-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0195 | T-R-033-01 | T-R-033-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0196 | T-R-033-01 | T-R-033-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0197 | T-R-033-02 | T-R-033-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0198 | T-R-033-02 | T-R-033-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0199 | T-R-033-03 | T-R-034-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0200 | T-R-033-03 | T-R-034-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0201 | T-R-034-01 | T-R-034-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0202 | T-R-034-01 | T-R-034-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0203 | T-R-034-02 | T-R-034-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0204 | T-R-034-02 | T-R-034-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0205 | T-R-034-03 | T-R-035-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0206 | T-R-034-03 | T-R-035-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0207 | T-R-035-01 | T-R-035-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0208 | T-R-035-01 | T-R-035-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0209 | T-R-035-02 | T-R-035-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0210 | T-R-035-02 | T-R-035-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0211 | T-R-035-03 | T-R-036-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0212 | T-R-035-03 | T-R-036-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0213 | T-R-036-01 | T-R-036-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0214 | T-R-036-01 | T-R-036-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0215 | T-R-036-02 | T-R-036-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0216 | T-R-036-02 | T-R-036-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0217 | T-R-036-03 | T-R-037-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0218 | T-R-036-03 | T-R-037-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0219 | T-R-037-01 | T-R-037-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0220 | T-R-037-01 | T-R-037-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0221 | T-R-037-02 | T-R-037-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0222 | T-R-037-02 | T-R-037-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0223 | T-R-037-03 | T-R-038-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0224 | T-R-037-03 | T-R-038-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0225 | T-R-038-01 | T-R-038-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0226 | T-R-038-01 | T-R-038-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0227 | T-R-038-02 | T-R-038-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0228 | T-R-038-02 | T-R-038-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0229 | T-R-038-03 | T-R-039-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0230 | T-R-038-03 | T-R-039-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0231 | T-R-039-01 | T-R-039-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0232 | T-R-039-01 | T-R-039-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0233 | T-R-039-02 | T-R-039-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0234 | T-R-039-02 | T-R-039-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0235 | T-R-039-03 | T-R-040-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0236 | T-R-039-03 | T-R-040-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0237 | T-R-040-01 | T-R-040-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0238 | T-R-040-01 | T-R-040-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0239 | T-R-040-02 | T-R-040-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0240 | T-R-040-02 | T-R-040-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0241 | T-R-040-03 | T-R-041-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0242 | T-R-040-03 | T-R-041-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0243 | T-R-041-01 | T-R-041-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0244 | T-R-041-01 | T-R-041-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0245 | T-R-041-02 | T-R-041-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0246 | T-R-041-02 | T-R-041-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0247 | T-R-041-03 | T-R-042-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0248 | T-R-041-03 | T-R-042-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0249 | T-R-042-01 | T-R-042-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0250 | T-R-042-01 | T-R-042-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0251 | T-R-042-02 | T-R-042-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0252 | T-R-042-02 | T-R-042-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0253 | T-R-042-03 | T-R-043-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0254 | T-R-042-03 | T-R-043-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0255 | T-R-043-01 | T-R-043-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0256 | T-R-043-01 | T-R-043-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0257 | T-R-043-02 | T-R-043-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0258 | T-R-043-02 | T-R-043-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0259 | T-R-043-03 | T-R-044-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0260 | T-R-043-03 | T-R-044-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0261 | T-R-044-01 | T-R-044-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0262 | T-R-044-01 | T-R-044-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0263 | T-R-044-02 | T-R-044-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0264 | T-R-044-02 | T-R-044-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0265 | T-R-044-03 | T-R-045-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0266 | T-R-044-03 | T-R-045-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0267 | T-R-045-01 | T-R-045-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0268 | T-R-045-01 | T-R-045-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0269 | T-R-045-02 | T-R-045-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0270 | T-R-045-02 | T-R-045-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0271 | T-R-045-03 | T-R-046-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0272 | T-R-045-03 | T-R-046-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0273 | T-R-046-01 | T-R-046-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0274 | T-R-046-01 | T-R-046-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0275 | T-R-046-02 | T-R-046-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0276 | T-R-046-02 | T-R-046-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0277 | T-R-046-03 | T-R-047-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0278 | T-R-046-03 | T-R-047-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0279 | T-R-047-01 | T-R-047-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0280 | T-R-047-01 | T-R-047-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0281 | T-R-047-02 | T-R-047-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0282 | T-R-047-02 | T-R-047-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0283 | T-R-047-03 | T-R-048-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0284 | T-R-047-03 | T-R-048-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0285 | T-R-048-01 | T-R-048-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0286 | T-R-048-01 | T-R-048-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0287 | T-R-048-02 | T-R-048-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0288 | T-R-048-02 | T-R-048-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0289 | T-R-048-03 | T-R-049-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0290 | T-R-048-03 | T-R-049-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0291 | T-R-049-01 | T-R-049-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0292 | T-R-049-01 | T-R-049-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0293 | T-R-049-02 | T-R-049-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0294 | T-R-049-02 | T-R-049-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0295 | T-R-049-03 | T-R-050-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0296 | T-R-049-03 | T-R-050-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0297 | T-R-050-01 | T-R-050-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0298 | T-R-050-01 | T-R-050-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0299 | T-R-050-02 | T-R-050-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0300 | T-R-050-02 | T-R-050-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0301 | T-R-050-03 | T-R-051-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0302 | T-R-050-03 | T-R-051-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0303 | T-R-051-01 | T-R-051-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0304 | T-R-051-01 | T-R-051-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0305 | T-R-051-02 | T-R-051-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0306 | T-R-051-02 | T-R-051-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0307 | T-R-051-03 | T-R-052-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0308 | T-R-051-03 | T-R-052-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0309 | T-R-052-01 | T-R-052-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0310 | T-R-052-01 | T-R-052-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0311 | T-R-052-02 | T-R-052-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0312 | T-R-052-02 | T-R-052-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0313 | T-R-052-03 | T-R-053-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0314 | T-R-052-03 | T-R-053-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0315 | T-R-053-01 | T-R-053-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0316 | T-R-053-01 | T-R-053-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0317 | T-R-053-02 | T-R-053-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0318 | T-R-053-02 | T-R-053-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0319 | T-R-053-03 | T-R-054-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0320 | T-R-053-03 | T-R-054-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0321 | T-R-054-01 | T-R-054-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0322 | T-R-054-01 | T-R-054-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0323 | T-R-054-02 | T-R-054-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0324 | T-R-054-02 | T-R-054-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0325 | T-R-054-03 | T-R-055-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0326 | T-R-054-03 | T-R-055-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0327 | T-R-055-01 | T-R-055-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0328 | T-R-055-01 | T-R-055-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0329 | T-R-055-02 | T-R-055-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0330 | T-R-055-02 | T-R-055-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0331 | T-R-055-03 | T-R-056-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0332 | T-R-055-03 | T-R-056-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0333 | T-R-056-01 | T-R-056-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0334 | T-R-056-01 | T-R-056-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0335 | T-R-056-02 | T-R-056-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0336 | T-R-056-02 | T-R-056-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0337 | T-R-056-03 | T-R-057-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0338 | T-R-056-03 | T-R-057-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0339 | T-R-057-01 | T-R-057-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0340 | T-R-057-01 | T-R-057-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0341 | T-R-057-02 | T-R-057-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0342 | T-R-057-02 | T-R-057-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0343 | T-R-057-03 | T-R-058-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0344 | T-R-057-03 | T-R-058-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0345 | T-R-058-01 | T-R-058-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0346 | T-R-058-01 | T-R-058-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0347 | T-R-058-02 | T-R-058-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0348 | T-R-058-02 | T-R-058-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0349 | T-R-058-03 | T-R-059-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0350 | T-R-058-03 | T-R-059-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0351 | T-R-059-01 | T-R-059-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0352 | T-R-059-01 | T-R-059-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0353 | T-R-059-02 | T-R-059-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0354 | T-R-059-02 | T-R-059-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0355 | T-R-059-03 | T-R-060-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0356 | T-R-059-03 | T-R-060-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0357 | T-R-060-01 | T-R-060-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0358 | T-R-060-01 | T-R-060-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0359 | T-R-060-02 | T-R-060-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0360 | T-R-060-02 | T-R-060-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0361 | T-R-060-03 | T-R-061-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0362 | T-R-060-03 | T-R-061-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0363 | T-R-061-01 | T-R-061-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0364 | T-R-061-01 | T-R-061-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0365 | T-R-061-02 | T-R-061-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0366 | T-R-061-02 | T-R-061-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0367 | T-R-061-03 | T-R-062-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0368 | T-R-061-03 | T-R-062-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0369 | T-R-062-01 | T-R-062-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0370 | T-R-062-01 | T-R-062-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0371 | T-R-062-02 | T-R-062-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0372 | T-R-062-02 | T-R-062-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0373 | T-R-062-03 | T-R-063-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0374 | T-R-062-03 | T-R-063-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0375 | T-R-063-01 | T-R-063-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0376 | T-R-063-01 | T-R-063-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0377 | T-R-063-02 | T-R-063-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0378 | T-R-063-02 | T-R-063-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0379 | T-R-063-03 | T-R-064-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0380 | T-R-063-03 | T-R-064-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0381 | T-R-064-01 | T-R-064-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0382 | T-R-064-01 | T-R-064-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0383 | T-R-064-02 | T-R-064-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0384 | T-R-064-02 | T-R-064-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0385 | T-R-064-03 | T-R-065-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0386 | T-R-064-03 | T-R-065-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0387 | T-R-065-01 | T-R-065-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0388 | T-R-065-01 | T-R-065-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0389 | T-R-065-02 | T-R-065-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0390 | T-R-065-02 | T-R-065-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0391 | T-R-065-03 | T-R-066-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0392 | T-R-065-03 | T-R-066-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0393 | T-R-066-01 | T-R-066-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0394 | T-R-066-01 | T-R-066-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0395 | T-R-066-02 | T-R-066-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0396 | T-R-066-02 | T-R-066-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0397 | T-R-066-03 | T-R-067-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0398 | T-R-066-03 | T-R-067-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0399 | T-R-067-01 | T-R-067-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0400 | T-R-067-01 | T-R-067-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0401 | T-R-067-02 | T-R-067-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0402 | T-R-067-02 | T-R-067-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0403 | T-R-067-03 | T-R-068-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0404 | T-R-067-03 | T-R-068-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0405 | T-R-068-01 | T-R-068-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0406 | T-R-068-01 | T-R-068-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0407 | T-R-068-02 | T-R-068-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0408 | T-R-068-02 | T-R-068-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0409 | T-R-068-03 | T-R-069-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0410 | T-R-068-03 | T-R-069-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0411 | T-R-069-01 | T-R-069-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0412 | T-R-069-01 | T-R-069-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0413 | T-R-069-02 | T-R-069-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0414 | T-R-069-02 | T-R-069-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0415 | T-R-069-03 | T-R-070-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0416 | T-R-069-03 | T-R-070-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0417 | T-R-070-01 | T-R-070-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0418 | T-R-070-01 | T-R-070-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0419 | T-R-070-02 | T-R-070-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0420 | T-R-070-02 | T-R-070-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0421 | T-R-070-03 | T-R-071-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0422 | T-R-070-03 | T-R-071-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0423 | T-R-071-01 | T-R-071-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0424 | T-R-071-01 | T-R-071-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0425 | T-R-071-02 | T-R-071-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0426 | T-R-071-02 | T-R-071-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0427 | T-R-071-03 | T-R-072-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0428 | T-R-071-03 | T-R-072-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0429 | T-R-072-01 | T-R-072-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0430 | T-R-072-01 | T-R-072-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0431 | T-R-072-02 | T-R-072-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0432 | T-R-072-02 | T-R-072-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0433 | T-R-072-03 | T-R-073-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0434 | T-R-072-03 | T-R-073-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0435 | T-R-073-01 | T-R-073-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0436 | T-R-073-01 | T-R-073-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0437 | T-R-073-02 | T-R-073-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0438 | T-R-073-02 | T-R-073-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0439 | T-R-073-03 | T-R-074-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0440 | T-R-073-03 | T-R-074-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0441 | T-R-074-01 | T-R-074-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0442 | T-R-074-01 | T-R-074-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0443 | T-R-074-02 | T-R-074-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0444 | T-R-074-02 | T-R-074-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0445 | T-R-074-03 | T-R-075-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0446 | T-R-074-03 | T-R-075-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0447 | T-R-075-01 | T-R-075-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0448 | T-R-075-01 | T-R-075-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0449 | T-R-075-02 | T-R-075-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0450 | T-R-075-02 | T-R-075-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0451 | T-R-075-03 | T-R-076-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0452 | T-R-075-03 | T-R-076-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0453 | T-R-076-01 | T-R-076-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0454 | T-R-076-01 | T-R-076-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0455 | T-R-076-02 | T-R-076-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0456 | T-R-076-02 | T-R-076-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0457 | T-R-076-03 | T-R-077-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0458 | T-R-076-03 | T-R-077-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0459 | T-R-077-01 | T-R-077-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0460 | T-R-077-01 | T-R-077-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0461 | T-R-077-02 | T-R-077-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0462 | T-R-077-02 | T-R-077-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0463 | T-R-077-03 | T-R-078-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0464 | T-R-077-03 | T-R-078-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0465 | T-R-078-01 | T-R-078-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0466 | T-R-078-01 | T-R-078-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0467 | T-R-078-02 | T-R-078-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0468 | T-R-078-02 | T-R-078-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0469 | T-R-078-03 | T-R-079-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0470 | T-R-078-03 | T-R-079-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0471 | T-R-079-01 | T-R-079-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0472 | T-R-079-01 | T-R-079-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0473 | T-R-079-02 | T-R-079-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0474 | T-R-079-02 | T-R-079-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0475 | T-R-079-03 | T-R-080-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0476 | T-R-079-03 | T-R-080-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0477 | T-R-080-01 | T-R-080-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0478 | T-R-080-01 | T-R-080-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0479 | T-R-080-02 | T-R-080-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0480 | T-R-080-02 | T-R-080-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0481 | T-R-080-03 | T-R-081-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0482 | T-R-080-03 | T-R-081-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0483 | T-R-081-01 | T-R-081-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0484 | T-R-081-01 | T-R-081-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0485 | T-R-081-02 | T-R-081-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0486 | T-R-081-02 | T-R-081-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0487 | T-R-081-03 | T-R-082-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0488 | T-R-081-03 | T-R-082-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0489 | T-R-082-01 | T-R-082-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0490 | T-R-082-01 | T-R-082-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0491 | T-R-082-02 | T-R-082-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0492 | T-R-082-02 | T-R-082-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0493 | T-R-082-03 | T-R-083-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0494 | T-R-082-03 | T-R-083-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0495 | T-R-083-01 | T-R-083-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0496 | T-R-083-01 | T-R-083-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0497 | T-R-083-02 | T-R-083-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0498 | T-R-083-02 | T-R-083-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0499 | T-R-083-03 | T-R-084-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0500 | T-R-083-03 | T-R-084-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0501 | T-R-084-01 | T-R-084-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0502 | T-R-084-01 | T-R-084-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0503 | T-R-084-02 | T-R-084-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0504 | T-R-084-02 | T-R-084-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0505 | T-R-084-03 | T-R-085-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0506 | T-R-084-03 | T-R-085-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0507 | T-R-085-01 | T-R-085-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0508 | T-R-085-01 | T-R-085-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0509 | T-R-085-02 | T-R-085-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0510 | T-R-085-02 | T-R-085-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0511 | T-R-085-03 | T-R-086-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0512 | T-R-085-03 | T-R-086-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0513 | T-R-086-01 | T-R-086-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0514 | T-R-086-01 | T-R-086-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0515 | T-R-086-02 | T-R-086-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0516 | T-R-086-02 | T-R-086-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0517 | T-R-086-03 | T-R-087-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0518 | T-R-086-03 | T-R-087-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0519 | T-R-087-01 | T-R-087-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0520 | T-R-087-01 | T-R-087-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0521 | T-R-087-02 | T-R-087-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0522 | T-R-087-02 | T-R-087-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0523 | T-R-087-03 | T-R-088-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0524 | T-R-087-03 | T-R-088-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0525 | T-R-088-01 | T-R-088-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0526 | T-R-088-01 | T-R-088-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0527 | T-R-088-02 | T-R-088-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0528 | T-R-088-02 | T-R-088-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0529 | T-R-088-03 | T-R-089-01 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0530 | T-R-088-03 | T-R-089-01 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0531 | T-R-089-01 | T-R-089-02 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0532 | T-R-089-01 | T-R-089-02 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0533 | T-R-089-02 | T-R-089-03 | Finish-to-Start | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0534 | T-R-089-02 | T-R-089-03 | Finish-to-Start | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0535 | WPS-01 | WPS-17-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0536 | WPS-02 | WPS-17-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0537 | WPS-17-01 | WPS-17-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0538 | WPS-17-02 | WPS-17-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0539 | WPS-21-01 | WPS-17-03 | FS | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0540 | WPS-17-03 | WPS-17-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0541 | WPS-17-04 | WPS-17-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0542 | WPS-01 | WPS-18-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0543 | WPS-02 | WPS-18-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0544 | WPS-18-01 | WPS-18-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0545 | WPS-21-01 | WPS-18-02 | FS | 0 | Schedule | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0546 | WPS-18-02 | WPS-18-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0547 | WPS-17-02 | WPS-18-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0548 | WPS-18-03 | WPS-18-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0549 | WPS-18-04 | WPS-18-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0550 | WPS-14 | WPS-19-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0551 | WPS-16 | WPS-19-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0552 | WPS-19-01 | WPS-19-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0553 | WPS-19-01 | WPS-19-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0554 | WPS-19-02 | WPS-19-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0555 | WPS-14 | WPS-19-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0556 | WPS-19-02 | WPS-19-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0557 | WPS-19-03 | WPS-19-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0558 | WPS-19-04 | WPS-19-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0559 | WPS-09 | WPS-20-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0560 | WPS-16 | WPS-20-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0561 | WPS-20-01 | WPS-20-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0562 | WPS-09 | WPS-20-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0563 | WPS-13 | WPS-20-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0564 | WPS-20-01 | WPS-20-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0565 | WPS-13 | WPS-20-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0566 | WPS-20-02 | WPS-20-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0567 | WPS-20-03 | WPS-20-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0568 | WPS-13 | WPS-21-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0569 | WPS-21-01 | WPS-21-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0570 | WPS-21-01 | WPS-21-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0571 | WPS-21-02 | WPS-21-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0572 | WPS-21-03 | WPS-21-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0573 | WPS-21-02 | WPS-21-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0574 | WPS-21-03 | WPS-21-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0575 | WPS-21-04 | WPS-21-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0576 | WPS-08 | WPS-22-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0577 | WPS-09 | WPS-22-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0578 | WPS-14 | WPS-22-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0579 | WPS-22-01 | WPS-22-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0580 | WPS-08 | WPS-22-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0581 | WPS-13 | WPS-22-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0582 | WPS-22-02 | WPS-22-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0583 | WPS-22-01 | WPS-22-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0584 | WPS-22-03 | WPS-22-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0585 | WPS-22-02 | WPS-22-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0586 | WPS-22-03 | WPS-22-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0587 | WPS-22-04 | WPS-22-05 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0588 | WPS-15 | WPS-23-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0589 | WPS-23-01 | WPS-23-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0590 | WPS-19-03 | WPS-23-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0591 | WPS-23-01 | WPS-23-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0592 | WPS-16 | WPS-23-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0593 | WPS-23-01 | WPS-23-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0594 | WPS-09 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0595 | WPS-10 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0596 | WPS-12 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0597 | WPS-14 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0598 | WPS-19 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0599 | WPS-20 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0600 | WPS-22 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0601 | WPS-23 | WPS-24-01 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0602 | WPS-24-01 | WPS-24-02 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0603 | WPS-24-02 | WPS-24-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0604 | WPS-19-04 | WPS-24-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0605 | WPS-22-05 | WPS-24-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0606 | WPS-23-02 | WPS-24-03 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0607 | WPS-24-03 | WPS-24-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0608 | WPS-17-05 | WPS-24-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0609 | WPS-18-04 | WPS-24-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0610 | WPS-20-05 | WPS-24-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.
LNK-0611 | WPS-21-05 | WPS-24-04 | FS | 0 | Logical | Predecessor provides required input, approval, condition or execution constraint. | To be assigned | Planned | Review when departmental dates are entered.

## Sources
Source Record ID | Source ID | Authority | Source Type | Document Title | Document Number | Edition | Issue Date | Effective Date | URL | Local Copy Available | Verified Against Official Source | Applicability Note | Related Rule IDs | Status | Notes
SRC-001 |  | S01 | DNV | Rules & Standards Explorer | Current official source | Master discovery and cross-reference source for DNV rules, standards, service specifications, RPs and historical editions applicable to PMS-11. | https://www.dnv.com/rules-standards/
SRC-002 |  | S02 | DNV | July 2026 DNV Rules Edition | Published 02 Jul 2026; next entry-into-force date 01 Jan 2027 | Control edition/effective-date logic; prevents treating the latest publication as automatically governing before entry into force. | https://www.dnv.com/news/2026/standards-now-available-the-july-2026-edition-of-the-dnv-class-rules-and-standards-for-ship-and-offshore/
SRC-003 |  | S03 | DNV | DNV-RU-SHIP Pt.5 Ch.11 — Non-self-propelled units | Edition to be confirmed from PMS-11 class basis | Identify and map the class requirements governing a non-self-propelled unit once the applicable class basis is confirmed. | https://www.dnv.com/rules-standards/
SRC-004 |  | S04 | DNV | DNV-RU-SHIP Pt.5 Ch.10 Sec.4 — Pipe Laying Vessel | Edition to be confirmed | Identify and map pipe-laying vessel requirements; do not assume applicability without class-basis confirmation. | https://www.dnv.com/rules-standards/
SRC-005 |  | S05 | DNV | DNV-RU-SHIP Pt.5 Ch.10 Sec.2 — Crane Vessel / applicable lifting framework | Edition to be confirmed | Check whether this or another DNV lifting framework governs PMS-11 lifting functions; the source is used for applicability determination, not as a pre-assumed notation. | https://www.dnv.com/rules-standards/
SRC-006 |  | S06 | DNV | DNV-ST-N001 Marine Operations and Marine Warranty | Edition 2023-12 public source | Provide the engineering/approval basis for marine operations, towage, installation and MWS interfaces where applicable. | https://www.dnv.com/energy/standards-guidelines/dnv-st-n001-marine-operations-and-marine-warranty/
SRC-007 |  | S07 | DNV | DNV-ST-F101 Submarine Pipeline Systems | Current public source | Provide pipeline-system requirements interfacing with pipe-lay operations, kept separate from vessel-class requirements. | https://www.dnv.com/energy/standards-guidelines/dnv-st-f101-submarine-pipeline-systems/
SRC-008 |  | S08 | DNV | DNV-RP-N103 Modelling and analysis of marine operations | Current public source | Provide marine-operation modelling/analysis reference for tow, installation and other operations where applicable. | https://www.dnv.com/rules-standards/rules-and-standards-explorer-plus/list-of-documents-included-in-the-subscription/
SRC-009 |  | S09 | DNV | DNV-RP-N201 Lifting appliances used in subsea operations | Edition 2019-09; amended 2021-09 | Provide lifting-appliance reference for subsea operations and cross-check HMC/diving-related lifting interfaces where applicable. | https://www.dnv.com/energy/standards-guidelines/dnv-rp-n201-lifting-applicances-used-in-subsea-operations/
SRC-010 |  | S10 | DNV | DNV-RP-C205 Environmental conditions and environmental loads | Current public framework | Provide environmental load basis for site-specific engineering where applicable. | https://www.dnv.com/rules-standards/
SRC-011 |  | S11 | IMO | SOLAS / IMO publications | Current | Statutory maritime safety baseline; each chapter/regulation is subject to applicability decision for PMS-11. | https://www.imo.org/en/publications/pages/justpublished.aspx
SRC-012 |  | S12 | IMO | STCW Convention and Code | Current / 2026 materials | Statutory crew certification, watchkeeping and competence baseline. | https://www.imo.org/en/ourwork/humanelement/pages/stcw-convention.aspx
SRC-013 |  | S13 | IMO | MARPOL | Current | Pollution-prevention baseline; each Annex is assessed separately. | https://www.imo.org/en/ourwork/environment/pages/marpol.aspx
SRC-014 |  | S14 | IMO | Surveys and Certification | Current | Explain statutory survey/certification framework and relationship to RO/Flag. | https://www.imo.org/en/ourwork/msas/pages/surveysandcertification.aspx
SRC-015 |  | S15 | IACS | Unified Requirements | Current | Cross-check exact IACS URs only where relevant and determine whether they are incorporated/applicable through DNV rules. | https://iacs.org.uk/resolutions/unified-requirements
SRC-016 |  | S16 | IACS | UR Z15 Rev.4 — Hull, Structure, Equipment and Machinery Surveys of Mobile Offshore Units | Rev.4 Jan 2025 | Specific cross-check for MOU survey applicability; applicability to PMS-11 is not assumed. | https://iacs.org.uk/resolutions/unified-requirements/ur-z/ur-z15-rev3-cln
SRC-017 |  | S17 | IACS | Recommendation 198 — Onboard Lifting Appliances | Apr 2026 | Cross-check lifting documentation, testing and examination; not treated as an independent mandatory rule unless made applicable by governing regime. | https://iacs.org.uk/resolutions/recommendations/181-200/rec-198
SRC-018 |  | S18 | EAMS | Flag State Requirements | Current public | Egyptian Flag statutory baseline and certificate/approval framework. | https://www.eams.gov.eg/PDF/PDF_en/FLAG%20STATE%20REQUIREMENTS%20EN.pdf
SRC-019 |  | S19 | JMA | JMC Regulations | Current public index | Master index for Jordanian maritime regulations and applicability decisions for foreign vessels/barges. | https://jma.gov.jo/en/regulations-and-laws/jmc-regulations/
SRC-020 |  | S20 | JMA | Jordan Maritime Instructions | Current public index | Detailed Jordanian instructions covering PSC, VTS, ISM, FSS, Load Lines, Tonnage, BWM and other controls. | https://jma.gov.jo/%D8%A7%D9%84%D8%AA%D8%B9%D9%84%D9%8A%D9%85%D8%A7%D8%AA/
SRC-021 |  | S21 | JMA | Entry/Departure & VTS Regulation | Public regulation | Control Jordanian territorial-water entry, departure, movement and VTS interface. | https://jma.gov.jo/wp-content/uploads/2021/03/ORGANI1.pdf
SRC-022 |  | S22 | JMA | Port State Control Regulations | 2012; current implementation to verify | Control Jordan PSC inspection basis for foreign vessels and evidence readiness. | https://jma.gov.jo/wp-content/uploads/2022/02/Regulations-of-Port-State-Control-for-the-year-2012-in-the-Hashemite-Kingdom-of-Jordan.pdf
SRC-023 |  | S23 | JMA | Harbor Master Functions Regulations | 2014 | Control Harbor Master requirements affecting movement and port operations. | https://jma.gov.jo/wp-content/uploads/2021/03/Regulations-for-Conducting-Harbor-Master-Functions-for-the-year-2014.pdf
SRC-024 |  | S24 | ASEZA | Directorate of Marine Environment Protection | Current public | Identify Aqaba environmental authority, approvals and control interface. | https://www.aseza.jo/EN/Pages/Directorate_of_Marine_Environment_Protection
SRC-025 |  | S25 | ASEZA | Aqaba Marine Reserve Regulation No.61/2022 | 2022 | Control reserve/buffer boundaries and activity restrictions relevant to anchoring, diving, pipe-lay, discharges and waste. | https://aseza.jo/EBV4.0/Root_Storage/AR/EGOV/Regulation_No-61_of_2022_Aqaba_Marine_Reserve.pdf
SRC-026 |  | S26 | Jordan Customs | Jordan Customs Law — Sea Transport provisions | Current | Control vessel/cargo manifests, customs presentation and sea-transport requirements. | https://jobs.customs.gov.jo/jordan_customs_webpublished/CustomsLawsEn/Law_Sec04.aspx
SRC-027 |  | S27 | Jordan Customs / ASEZA | Aqaba Customs Center / ASEZA customs interface | Current public | Control temporary import/re-export and customs procedures for barge/equipment/stores as applicable. | https://aseza.jo/AR/Pages/%D9%85%D8%AF%D9%8A%D8%B1%D9%8A%D8%A9_%D8%AC%D9%85%D8%B1%D9%83_%D9%85%D9%86%D8%B7%D9%82%D8%A9_%D8%A7%D9%84%D8%A7%D9%82%D8%AA%D8%B5%D8%A7%D8%AF%D9%8A%D8%A9_%D8%A7%D9%84%D8%AE%D8%A7%D8%B5%D8%A9
SRC-028 |  | S28 | IMCA | D014 — International Code of Practice for Offshore Diving | Rev.3.3 Mar 2025 | Primary IMCA offshore diving operational baseline for PMS-11 air/saturation diving. | https://www.imca-int.com/resources/technical-library/document/134b165f-c55b-ee11-8def-6045bdd2c9bc/
SRC-029 |  | S29 | IMCA | D023 — DESIGN for surface orientated air diving systems | Rev.3 Jun 2026 | IMCA design/inspection baseline for the air-diving system. | https://www.imca-int.com/resources/technical-library/document/
SRC-030 |  | S30 | IMCA | D024 — DESIGN for saturation (bell) diving systems | Rev.4 Jun 2026 | IMCA design/inspection/testing/certification baseline for saturation diving systems. | https://www.imca-int.com/resources/technical-library/document/afd42e5e-c55b-ee11-8def-6045bdf1ea43/
SRC-031 |  | S31 | IMCA | D018 — Initial and periodic examination, testing and certification of diving plant and equipment | Rev.3 Jun 2026 | IMCA baseline for diving plant examination, testing and certification. | https://www.imca-int.com/resources/technical-library/document/84afbabf-cb5e-ee11-8def-6045bd10fcec/
SRC-032 |  | S32 | IMCA | D011 — Guidance on auditing of diving systems | Rev.3.2 Aug 2026 | IMCA DESIGN audit/documentation baseline where an IMCA diving-system audit is required. | https://www.imca-int.com/resources/technical-library/document/c0873c5f-c55b-ee11-8dee-6045bdd0ef45/
SRC-033 |  | S33 | IMCA | D088 — Diving certification and verification | Rev.0.2 Feb 2026 | IMCA recognition/verification baseline for diver, supervisor and LST certificates. | https://www.imca-int.com/resources/technical-library/document/e0e05b20-663d-f011-8c4e-6045bdd125e6/
SRC-034 |  | S34 | Egypt Ministry of Transport | MLC 2006 — Egypt | Egypt acceded 2024 | Egyptian implementation context for crew living/working requirements. | https://www.mts.gov.eg/en/%D8%A5%D8%AA%D9%81%D8%A7%D9%82%D9%8A%D8%A9-%D8%A7%D9%84%D8%B9%D9%85%D9%84-%D8%A7%D9%84%D8%A8%D8%AD%D8%B1%D9%8A-2006-mlc-2006-%D9%88%D8%AA%D8%B9%D8%AF%D9%8A%D9%84%D8%A7%D8%AA%D9%87%D8%A7/

## Responsibilities
Responsibility Record ID | WPS ID | Activity ID | Task ID | Rule ID | Owner | Accountable | DNV | Egyptian Flag | Jordan Maritime Commission | ASEZA | Harbor Master / VTS | OEM | Client | MWS | Diving Contractor | Tow Contractor | Status
RACI-001 | WPS-01 | A-R-001 | T-R-001-03 | R-001 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-002 | WPS-02 | A-R-003 | T-R-003-03 | R-003 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-003 | WPS-03 | A-R-009 | T-R-009-03 | R-009 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-004 | WPS-04 | A-R-012 | T-R-012-03 | R-012 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-005 | WPS-05 | A-R-014 | T-R-014-03 | R-014 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-006 | WPS-06 | A-R-019 | T-R-019-03 | R-019 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-007 | WPS-07 | A-R-023 | T-R-023-03 | R-023 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-008 | WPS-08 | A-R-029 | T-R-029-03 | R-029 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-009 | WPS-09 | A-R-032 | T-R-032-03 | R-032 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-010 | WPS-10 | A-R-037 | T-R-037-03 | R-037 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-011 | WPS-11 | A-R-035 | T-R-035-03 | R-035 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-012 | WPS-12 | A-R-044 | T-R-044-03 | R-044 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-013 | WPS-13 | A-R-049 | T-R-049-03 | R-049 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-014 | WPS-14 | A-R-051 | T-R-051-03 | R-051 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-015 | WPS-15 | A-R-055 | T-R-055-03 | R-055 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-016 | WPS-16 | A-R-061 | T-R-061-03 | R-061 | Rule/WPS owner to be assigned | Owner / Project Director | V / C | AP / C | AP / C | AP / C | AP / C | C | AP / C | AP / C | C | C | Open
RACI-017 | WPS-17 | A-S-17-01 | T-S-17-01-02 | SC-17-01 | Class Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-018 | WPS-17 | A-S-17-02 | T-S-17-02-02 | SC-17-02 | Class Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-019 | WPS-17 | A-S-17-03 | T-S-17-03-02 | SC-17-03 | Technical Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-020 | WPS-17 | A-S-17-04 | T-S-17-04-02 | SC-17-04 | Project Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-021 | WPS-17 | A-S-17-05 | T-S-17-05-02 | SC-17-05 | Class Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-022 | WPS-18 | A-S-18-01 | T-S-18-01-02 | SC-18-01 | Class Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-023 | WPS-18 | A-S-18-02 | T-S-18-02-02 | SC-18-02 | Class Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-024 | WPS-18 | A-S-18-03 | T-S-18-03-02 | SC-18-03 | Project Controls Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-025 | WPS-18 | A-S-18-04 | T-S-18-04-02 | SC-18-04 | Project Director | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-026 | WPS-18 | A-S-18-05 | T-S-18-05-02 | SC-18-05 | Class Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-027 | WPS-19 | A-S-19-01 | T-S-19-01-02 | SC-19-01 | Aviation Coordinator | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-028 | WPS-19 | A-S-19-02 | T-S-19-02-02 | SC-19-02 | Aviation Coordinator | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-029 | WPS-19 | A-S-19-03 | T-S-19-03-02 | SC-19-03 | Aviation Coordinator | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-030 | WPS-19 | A-S-19-04 | T-S-19-04-02 | SC-19-04 | HSE Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-031 | WPS-19 | A-S-19-05 | T-S-19-05-02 | SC-19-05 | Aviation Coordinator | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-032 | WPS-20 | A-S-20-01 | T-S-20-01-02 | SC-20-01 | Environmental Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-033 | WPS-20 | A-S-20-02 | T-S-20-02-02 | SC-20-02 | Chief Engineer | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-034 | WPS-20 | A-S-20-03 | T-S-20-03-02 | SC-20-03 | Chief Engineer | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-035 | WPS-20 | A-S-20-04 | T-S-20-04-02 | SC-20-04 | Chief Engineer | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-036 | WPS-20 | A-S-20-05 | T-S-20-05-02 | SC-20-05 | Environmental Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-037 | WPS-21 | A-S-21-01 | T-S-21-01-02 | SC-21-01 | Maintenance Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-038 | WPS-21 | A-S-21-02 | T-S-21-02-02 | SC-21-02 | Maintenance Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-039 | WPS-21 | A-S-21-03 | T-S-21-03-02 | SC-21-03 | Stores Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-040 | WPS-21 | A-S-21-04 | T-S-21-04-02 | SC-21-04 | Procurement Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-041 | WPS-21 | A-S-21-05 | T-S-21-05-02 | SC-21-05 | Maintenance Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-042 | WPS-22 | A-S-22-01 | T-S-22-01-02 | SC-22-01 | Marine Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-043 | WPS-22 | A-S-22-02 | T-S-22-02-02 | SC-22-02 | Survey Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-044 | WPS-22 | A-S-22-03 | T-S-22-03-02 | SC-22-03 | Marine Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-045 | WPS-22 | A-S-22-04 | T-S-22-04-02 | SC-22-04 | Marine Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-046 | WPS-22 | A-S-22-05 | T-S-22-05-02 | SC-22-05 | Marine Superintendent | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-047 | WPS-23 | A-S-23-01 | T-S-23-01-02 | SC-23-01 | HR Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-048 | WPS-23 | A-S-23-02 | T-S-23-02-02 | SC-23-02 | Medical Coordinator | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-049 | WPS-23 | A-S-23-03 | T-S-23-03-02 | SC-23-03 | HSE Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-050 | WPS-23 | A-S-23-04 | T-S-23-04-02 | SC-23-04 | HR Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-051 | WPS-24 | A-S-24-01 | T-S-24-01-02 | SC-24-01 | HSE Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-052 | WPS-24 | A-S-24-02 | T-S-24-02-02 | SC-24-02 | HSE Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-053 | WPS-24 | A-S-24-03 | T-S-24-03-02 | SC-24-03 | Project Manager | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open
RACI-054 | WPS-24 | A-S-24-04 | T-S-24-04-02 | SC-24-04 | Project Director | Project Director | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | As applicable | Open

## Risks
Record ID | Type | Description | Related Rule IDs | Related WPS IDs | Related Gap IDs | Impact | Probability | Risk Rating | Mitigation | Owner | Decision Authority | Assumption Valid Until | Status | Decision Date | Evidence | Notes
RA-001 | Assumption | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-002 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-003 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-004 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-005 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-006 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-007 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-008 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-009 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-010 | Assumption | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-011 | Assumption | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-012 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-013 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-014 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-015 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-016 | Assumption | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-017 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-018 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-019 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
RA-020 | Risk | Evidence-dependent assumption/risk requiring formal verification; no readiness conclusion may be inferred. | R-001:R-089 | WPS-01:WPS-16 | G-001:G-024 | Potential gate or operational no-go | Medium | High | Obtain controlled source evidence, verify, test/analyze and obtain competent-authority disposition. | Owner / relevant WPS lead | Relevant competent authority | TBC | Open | TBC | TBC | Expanded from prior risk register and reference workbook limitations.
D-001 | Decision | Rule universe — 87-rule candidate vs original 89-rule source |  |  |  | Scope/control decision | N/A | N/A | Two explicit source scopes were missing distinctly: Egyptian Flag/statutory basis and hull/structural/stability basis. | Owner / Project Director | Project governance | TBC | Recorded | TBC | Reference workbook | Preserved from reduced-16-WPS source.
D-002 | Decision | WPS universe — 22 old WPS + 24 old WP vs 16 final |  |  |  | Scope/control decision | N/A | N/A | All legacy scopes can be consolidated without deletion. | Owner / Project Director | Project governance | TBC | Recorded | TBC | Reference workbook | Preserved from reduced-16-WPS source.
D-003 | Decision | Diving — Legacy source had broader references |  |  |  | Scope/control decision | N/A | N/A | Final WPS-12 uses IMCA-only project baseline. | Owner / Project Director | Project governance | TBC | Recorded | TBC | Reference workbook | Preserved from reduced-16-WPS source.
D-004 | Decision | WPS-16 — 21-rule catch-all |  |  |  | Scope/control decision | N/A | N/A | Jordan regulatory/port/survey/evidence only; maintenance/environment/OEM/client moved elsewhere. | Owner / Project Director | Project governance | TBC | Recorded | TBC | Reference workbook | Preserved from reduced-16-WPS source.
D-005 | Decision | Source R-065 — Carriage-of-goods source rule |  |  |  | Scope/control decision | N/A | N/A | No distinct carriage function established; reopen if project scope changes. | Owner / Project Director | Project governance | TBC | Recorded | TBC | Reference workbook | Preserved from reduced-16-WPS source.

## Changes
Change ID | Date Raised | Raised By | Change Description | Affected Rule IDs | Affected WPS IDs | Affected Activities | Affected Deliverables | Reason | Impact | Review Authority | Approval Authority | Decision | Revision Required | Status | Closure Evidence

## Relationships
Parent Entity | Parent ID | Child Entity | Child ID | Source Field | Parent Object Key | Child Object Key | Relationship Type | Relationship Role | Required / Optional | Primary / Supporting | Sequence / Priority | Source
Acceptance | AC-R-001 | Activities | A-R-001 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-001 | Evidence | E-001 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-001 | Rules | R-001 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-001 | Tasks | T-R-001-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-001 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-002 | Activities | A-R-002 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-002 | Evidence | E-002 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-002 | Rules | R-002 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-002 | Tasks | T-R-002-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-002 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-003 | Activities | A-R-003 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-003 | Evidence | E-003 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-003 | Rules | R-003 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-003 | Tasks | T-R-003-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-003 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-004 | Activities | A-R-004 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-004 | Evidence | E-004 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-004 | Rules | R-004 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-004 | Tasks | T-R-004-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-004 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-005 | Activities | A-R-005 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-005 | Evidence | E-005 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-005 | Rules | R-005 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-005 | Tasks | T-R-005-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-005 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-006 | Activities | A-R-006 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-006 | Evidence | E-006 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-006 | Rules | R-006 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-006 | Tasks | T-R-006-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-006 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-007 | Activities | A-R-007 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-007 | Evidence | E-007 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-007 | Rules | R-007 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-007 | Tasks | T-R-007-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-007 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-008 | Activities | A-R-008 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-008 | Evidence | E-008 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-008 | Rules | R-008 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-008 | Tasks | T-R-008-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-008 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-009 | Activities | A-R-009 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-009 | Evidence | E-009 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-009 | Rules | R-009 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-009 | Tasks | T-R-009-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-009 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-010 | Activities | A-R-010 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-010 | Evidence | E-010 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-010 | Rules | R-010 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-010 | Tasks | T-R-010-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-010 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-011 | Activities | A-R-011 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-011 | Evidence | E-011 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-011 | Rules | R-011 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-011 | Tasks | T-R-011-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-011 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-012 | Activities | A-R-012 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-012 | Evidence | E-012 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-012 | Rules | R-012 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-012 | Tasks | T-R-012-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-012 | WPS | WPS-04 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-013 | Activities | A-R-013 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-013 | Evidence | E-013 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-013 | Rules | R-013 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-013 | Tasks | T-R-013-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-013 | WPS | WPS-04 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-014 | Activities | A-R-014 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-014 | Evidence | E-014 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-014 | Rules | R-014 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-014 | Tasks | T-R-014-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-014 | WPS | WPS-05 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-015 | Activities | A-R-015 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-015 | Evidence | E-015 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-015 | Rules | R-015 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-015 | Tasks | T-R-015-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-015 | WPS | WPS-05 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-016 | Activities | A-R-016 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-016 | Evidence | E-016 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-016 | Rules | R-016 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-016 | Tasks | T-R-016-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-016 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-017 | Activities | A-R-017 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-017 | Evidence | E-017 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-017 | Rules | R-017 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-017 | Tasks | T-R-017-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-017 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-018 | Activities | A-R-018 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-018 | Evidence | E-018 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-018 | Rules | R-018 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-018 | Tasks | T-R-018-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-018 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-019 | Activities | A-R-019 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-019 | Evidence | E-019 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-019 | Rules | R-019 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-019 | Tasks | T-R-019-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-019 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-020 | Activities | A-R-020 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-020 | Evidence | E-020 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-020 | Rules | R-020 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-020 | Tasks | T-R-020-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-020 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-021 | Activities | A-R-021 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-021 | Evidence | E-021 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-021 | Rules | R-021 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-021 | Tasks | T-R-021-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-021 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-022 | Activities | A-R-022 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-022 | Evidence | E-022 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-022 | Rules | R-022 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-022 | Tasks | T-R-022-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-022 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-023 | Activities | A-R-023 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-023 | Evidence | E-023 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-023 | Rules | R-023 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-023 | Tasks | T-R-023-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-023 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-024 | Activities | A-R-024 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-024 | Evidence | E-024 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-024 | Rules | R-024 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-024 | Tasks | T-R-024-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-024 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-025 | Activities | A-R-025 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-025 | Evidence | E-025 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-025 | Rules | R-025 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-025 | Tasks | T-R-025-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-025 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-026 | Activities | A-R-026 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-026 | Evidence | E-026 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-026 | Rules | R-026 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-026 | Tasks | T-R-026-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-026 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-027 | Activities | A-R-027 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-027 | Evidence | E-027 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-027 | Rules | R-027 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-027 | Tasks | T-R-027-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-027 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-028 | Activities | A-R-028 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-028 | Evidence | E-028 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-028 | Rules | R-028 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-028 | Tasks | T-R-028-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-028 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-029 | Activities | A-R-029 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-029 | Evidence | E-029 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-029 | Rules | R-029 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-029 | Tasks | T-R-029-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-029 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-030 | Activities | A-R-030 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-030 | Evidence | E-030 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-030 | Rules | R-030 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-030 | Tasks | T-R-030-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-030 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-031 | Activities | A-R-031 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-031 | Evidence | E-031 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-031 | Rules | R-031 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-031 | Tasks | T-R-031-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-031 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-032 | Activities | A-R-032 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-032 | Evidence | E-032 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-032 | Rules | R-032 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-032 | Tasks | T-R-032-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-032 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-033 | Activities | A-R-033 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-033 | Evidence | E-033 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-033 | Rules | R-033 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-033 | Tasks | T-R-033-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-033 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-034 | Activities | A-R-034 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-034 | Evidence | E-034 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-034 | Rules | R-034 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-034 | Tasks | T-R-034-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-034 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-035 | Activities | A-R-035 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-035 | Evidence | E-035 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-035 | Rules | R-035 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-035 | Tasks | T-R-035-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-035 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-036 | Activities | A-R-036 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-036 | Evidence | E-036 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-036 | Rules | R-036 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-036 | Tasks | T-R-036-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-036 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-037 | Activities | A-R-037 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-037 | Evidence | E-037 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-037 | Rules | R-037 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-037 | Tasks | T-R-037-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-037 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-038 | Activities | A-R-038 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-038 | Evidence | E-038 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-038 | Rules | R-038 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-038 | Tasks | T-R-038-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-038 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-039 | Activities | A-R-039 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-039 | Evidence | E-039 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-039 | Rules | R-039 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-039 | Tasks | T-R-039-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-039 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-040 | Activities | A-R-040 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-040 | Evidence | E-040 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-040 | Rules | R-040 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-040 | Tasks | T-R-040-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-040 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-041 | Activities | A-R-041 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-041 | Evidence | E-041 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-041 | Rules | R-041 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-041 | Tasks | T-R-041-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-041 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-042 | Activities | A-R-042 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-042 | Evidence | E-042 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-042 | Rules | R-042 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-042 | Tasks | T-R-042-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-042 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-043 | Activities | A-R-043 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-043 | Evidence | E-043 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-043 | Rules | R-043 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-043 | Tasks | T-R-043-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-043 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-044 | Activities | A-R-044 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-044 | Evidence | E-044 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-044 | Rules | R-044 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-044 | Tasks | T-R-044-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-044 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-045 | Activities | A-R-045 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-045 | Evidence | E-045 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-045 | Rules | R-045 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-045 | Tasks | T-R-045-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-045 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-046 | Activities | A-R-046 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-046 | Evidence | E-046 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-046 | Rules | R-046 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-046 | Tasks | T-R-046-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-046 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-047 | Activities | A-R-047 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-047 | Evidence | E-047 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-047 | Rules | R-047 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-047 | Tasks | T-R-047-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-047 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-048 | Activities | A-R-048 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-048 | Evidence | E-048 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-048 | Rules | R-048 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-048 | Tasks | T-R-048-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-048 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-049 | Activities | A-R-049 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-049 | Evidence | E-049 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-049 | Rules | R-049 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-049 | Tasks | T-R-049-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-049 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-050 | Activities | A-R-050 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-050 | Evidence | E-050 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-050 | Rules | R-050 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-050 | Tasks | T-R-050-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-050 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-051 | Activities | A-R-051 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-051 | Evidence | E-051 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-051 | Rules | R-051 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-051 | Tasks | T-R-051-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-051 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-052 | Activities | A-R-052 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-052 | Evidence | E-052 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-052 | Rules | R-052 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-052 | Tasks | T-R-052-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-052 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-053 | Activities | A-R-053 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-053 | Evidence | E-053 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-053 | Rules | R-053 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-053 | Tasks | T-R-053-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-053 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-054 | Activities | A-R-054 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-054 | Evidence | E-054 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-054 | Rules | R-054 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-054 | Tasks | T-R-054-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-054 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-055 | Activities | A-R-055 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-055 | Evidence | E-055 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-055 | Rules | R-055 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-055 | Tasks | T-R-055-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-055 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-056 | Activities | A-R-056 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-056 | Evidence | E-056 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-056 | Rules | R-056 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-056 | Tasks | T-R-056-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-056 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-057 | Activities | A-R-057 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-057 | Evidence | E-057 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-057 | Rules | R-057 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-057 | Tasks | T-R-057-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-057 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-058 | Activities | A-R-058 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-058 | Evidence | E-058 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-058 | Rules | R-058 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-058 | Tasks | T-R-058-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-058 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-059 | Activities | A-R-059 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-059 | Evidence | E-059 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-059 | Rules | R-059 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-059 | Tasks | T-R-059-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-059 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-060 | Activities | A-R-060 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-060 | Evidence | E-060 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-060 | Rules | R-060 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-060 | Tasks | T-R-060-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-060 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-061 | Activities | A-R-061 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-061 | Evidence | E-061 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-061 | Rules | R-061 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-061 | Tasks | T-R-061-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-061 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-062 | Activities | A-R-062 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-062 | Evidence | E-062 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-062 | Rules | R-062 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-062 | Tasks | T-R-062-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-062 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-063 | Activities | A-R-063 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-063 | Evidence | E-063 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-063 | Rules | R-063 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-063 | Tasks | T-R-063-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-063 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-064 | Activities | A-R-064 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-064 | Evidence | E-064 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-064 | Rules | R-064 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-064 | Tasks | T-R-064-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-064 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-065 | Activities | A-R-065 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-065 | Evidence | E-065 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-065 | Rules | R-065 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-065 | Tasks | T-R-065-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-065 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-066 | Activities | A-R-066 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-066 | Evidence | E-066 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-066 | Rules | R-066 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-066 | Tasks | T-R-066-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-066 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-067 | Activities | A-R-067 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-067 | Evidence | E-067 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-067 | Rules | R-067 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-067 | Tasks | T-R-067-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-067 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-068 | Activities | A-R-068 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-068 | Evidence | E-068 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-068 | Rules | R-068 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-068 | Tasks | T-R-068-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-068 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-069 | Activities | A-R-069 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-069 | Evidence | E-069 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-069 | Rules | R-069 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-069 | Tasks | T-R-069-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-069 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-070 | Activities | A-R-070 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-070 | Evidence | E-070 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-070 | Rules | R-070 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-070 | Tasks | T-R-070-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-070 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-071 | Activities | A-R-071 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-071 | Evidence | E-071 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-071 | Rules | R-071 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-071 | Tasks | T-R-071-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-071 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-072 | Activities | A-R-072 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-072 | Evidence | E-072 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-072 | Rules | R-072 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-072 | Tasks | T-R-072-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-072 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-073 | Activities | A-R-073 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-073 | Evidence | E-073 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-073 | Rules | R-073 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-073 | Tasks | T-R-073-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-073 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-074 | Activities | A-R-074 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-074 | Evidence | E-074 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-074 | Rules | R-074 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-074 | Tasks | T-R-074-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-074 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-075 | Activities | A-R-075 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-075 | Evidence | E-075 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-075 | Rules | R-075 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-075 | Tasks | T-R-075-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-075 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-076 | Activities | A-R-076 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-076 | Evidence | E-076 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-076 | Rules | R-076 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-076 | Tasks | T-R-076-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-076 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-077 | Activities | A-R-077 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-077 | Evidence | E-077 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-077 | Rules | R-077 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-077 | Tasks | T-R-077-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-077 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-078 | Activities | A-R-078 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-078 | Evidence | E-078 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-078 | Rules | R-078 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-078 | Tasks | T-R-078-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-078 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-079 | Activities | A-R-079 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-079 | Evidence | E-079 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-079 | Rules | R-079 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-079 | Tasks | T-R-079-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-079 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-080 | Activities | A-R-080 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-080 | Evidence | E-080 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-080 | Rules | R-080 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-080 | Tasks | T-R-080-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-080 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-081 | Activities | A-R-081 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-081 | Evidence | E-081 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-081 | Rules | R-081 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-081 | Tasks | T-R-081-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-081 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-082 | Activities | A-R-082 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-082 | Evidence | E-082 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-082 | Rules | R-082 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-082 | Tasks | T-R-082-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-082 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-083 | Activities | A-R-083 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-083 | Evidence | E-083 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-083 | Rules | R-083 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-083 | Tasks | T-R-083-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-083 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-084 | Activities | A-R-084 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-084 | Evidence | E-084 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-084 | Rules | R-084 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-084 | Tasks | T-R-084-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-084 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-085 | Activities | A-R-085 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-085 | Evidence | E-085 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-085 | Rules | R-085 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-085 | Tasks | T-R-085-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-085 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-086 | Activities | A-R-086 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-086 | Evidence | E-086 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-086 | Rules | R-086 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-086 | Tasks | T-R-086-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-086 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-087 | Activities | A-R-087 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-087 | Evidence | E-087 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-087 | Rules | R-087 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-087 | Tasks | T-R-087-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-087 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-088 | Activities | A-R-088 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-088 | Evidence | E-088 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-088 | Rules | R-088 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-088 | Tasks | T-R-088-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-088 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-R-089 | Activities | A-R-089 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-R-089 | Evidence | E-089 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-R-089 | Rules | R-089 | Rule ID |  |  | DERIVES_FROM_RULE | Structural | Required | Primary |  | SourceField:Rule ID
Acceptance | AC-R-089 | Tasks | T-R-089-03 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-R-089 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-17-01 | Activities | A-S-17-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-17-01 | Evidence | E-S-17-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-17-01 | Tasks | T-S-17-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-17-01 | WPS | WPS-17 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-17-02 | Activities | A-S-17-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-17-02 | Evidence | E-S-17-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-17-02 | Tasks | T-S-17-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-17-02 | WPS | WPS-17 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-17-03 | Activities | A-S-17-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-17-03 | Evidence | E-S-17-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-17-03 | Tasks | T-S-17-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-17-03 | WPS | WPS-17 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-17-04 | Activities | A-S-17-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-17-04 | Evidence | E-S-17-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-17-04 | Tasks | T-S-17-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-17-04 | WPS | WPS-17 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-17-05 | Activities | A-S-17-05 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-17-05 | Evidence | E-S-17-05 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-17-05 | Tasks | T-S-17-05-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-17-05 | WPS | WPS-17 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-18-01 | Activities | A-S-18-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-18-01 | Evidence | E-S-18-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-18-01 | Tasks | T-S-18-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-18-01 | WPS | WPS-18 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-18-02 | Activities | A-S-18-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-18-02 | Evidence | E-S-18-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-18-02 | Tasks | T-S-18-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-18-02 | WPS | WPS-18 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-18-03 | Activities | A-S-18-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-18-03 | Evidence | E-S-18-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-18-03 | Tasks | T-S-18-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-18-03 | WPS | WPS-18 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-18-04 | Activities | A-S-18-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-18-04 | Evidence | E-S-18-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-18-04 | Tasks | T-S-18-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-18-04 | WPS | WPS-18 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-18-05 | Activities | A-S-18-05 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-18-05 | Evidence | E-S-18-05 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-18-05 | Tasks | T-S-18-05-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-18-05 | WPS | WPS-18 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-19-01 | Activities | A-S-19-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-19-01 | Evidence | E-S-19-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-19-01 | Tasks | T-S-19-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-19-01 | WPS | WPS-19 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-19-02 | Activities | A-S-19-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-19-02 | Evidence | E-S-19-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-19-02 | Tasks | T-S-19-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-19-02 | WPS | WPS-19 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-19-03 | Activities | A-S-19-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-19-03 | Evidence | E-S-19-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-19-03 | Tasks | T-S-19-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-19-03 | WPS | WPS-19 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-19-04 | Activities | A-S-19-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-19-04 | Evidence | E-S-19-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-19-04 | Tasks | T-S-19-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-19-04 | WPS | WPS-19 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-19-05 | Activities | A-S-19-05 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-19-05 | Evidence | E-S-19-05 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-19-05 | Tasks | T-S-19-05-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-19-05 | WPS | WPS-19 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-20-01 | Activities | A-S-20-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-20-01 | Evidence | E-S-20-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-20-01 | Tasks | T-S-20-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-20-01 | WPS | WPS-20 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-20-02 | Activities | A-S-20-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-20-02 | Evidence | E-S-20-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-20-02 | Tasks | T-S-20-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-20-02 | WPS | WPS-20 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-20-03 | Activities | A-S-20-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-20-03 | Evidence | E-S-20-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-20-03 | Tasks | T-S-20-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-20-03 | WPS | WPS-20 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-20-04 | Activities | A-S-20-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-20-04 | Evidence | E-S-20-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-20-04 | Tasks | T-S-20-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-20-04 | WPS | WPS-20 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-20-05 | Activities | A-S-20-05 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-20-05 | Evidence | E-S-20-05 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-20-05 | Tasks | T-S-20-05-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-20-05 | WPS | WPS-20 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-21-01 | Activities | A-S-21-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-21-01 | Evidence | E-S-21-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-21-01 | Tasks | T-S-21-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-21-01 | WPS | WPS-21 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-21-02 | Activities | A-S-21-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-21-02 | Evidence | E-S-21-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-21-02 | Tasks | T-S-21-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-21-02 | WPS | WPS-21 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-21-03 | Activities | A-S-21-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-21-03 | Evidence | E-S-21-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-21-03 | Tasks | T-S-21-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-21-03 | WPS | WPS-21 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-21-04 | Activities | A-S-21-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-21-04 | Evidence | E-S-21-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-21-04 | Tasks | T-S-21-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-21-04 | WPS | WPS-21 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-21-05 | Activities | A-S-21-05 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-21-05 | Evidence | E-S-21-05 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-21-05 | Tasks | T-S-21-05-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-21-05 | WPS | WPS-21 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-22-01 | Activities | A-S-22-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-22-01 | Evidence | E-S-22-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-22-01 | Tasks | T-S-22-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-22-01 | WPS | WPS-22 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-22-02 | Activities | A-S-22-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-22-02 | Evidence | E-S-22-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-22-02 | Tasks | T-S-22-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-22-02 | WPS | WPS-22 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-22-03 | Activities | A-S-22-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-22-03 | Evidence | E-S-22-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-22-03 | Tasks | T-S-22-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-22-03 | WPS | WPS-22 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-22-04 | Activities | A-S-22-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-22-04 | Evidence | E-S-22-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-22-04 | Tasks | T-S-22-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-22-04 | WPS | WPS-22 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-22-05 | Activities | A-S-22-05 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-22-05 | Evidence | E-S-22-05 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-22-05 | Tasks | T-S-22-05-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-22-05 | WPS | WPS-22 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-23-01 | Activities | A-S-23-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-23-01 | Evidence | E-S-23-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-23-01 | Tasks | T-S-23-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-23-01 | WPS | WPS-23 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-23-02 | Activities | A-S-23-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-23-02 | Evidence | E-S-23-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-23-02 | Tasks | T-S-23-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-23-02 | WPS | WPS-23 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-23-03 | Activities | A-S-23-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-23-03 | Evidence | E-S-23-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-23-03 | Tasks | T-S-23-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-23-03 | WPS | WPS-23 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-23-04 | Activities | A-S-23-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-23-04 | Evidence | E-S-23-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-23-04 | Tasks | T-S-23-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-23-04 | WPS | WPS-23 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-24-01 | Activities | A-S-24-01 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-24-01 | Evidence | E-S-24-01 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-24-01 | Tasks | T-S-24-01-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-24-01 | WPS | WPS-24 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-24-02 | Activities | A-S-24-02 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-24-02 | Evidence | E-S-24-02 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-24-02 | Tasks | T-S-24-02-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-24-02 | WPS | WPS-24 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-24-03 | Activities | A-S-24-03 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-24-03 | Evidence | E-S-24-03 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-24-03 | Tasks | T-S-24-03-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-24-03 | WPS | WPS-24 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-S-24-04 | Activities | A-S-24-04 | Activity ID |  |  | APPLIES_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Acceptance | AC-S-24-04 | Evidence | E-S-24-04 | Evidence ID |  |  | PROVEN_BY | Structural | Required | Primary |  | SourceField:Evidence ID
Acceptance | AC-S-24-04 | Tasks | T-S-24-04-02 | Task ID |  |  | APPLIES_TO_TASK | Cross-reference | Optional | Primary |  | SourceField:Task ID
Acceptance | AC-S-24-04 | WPS | WPS-24 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-01-001 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-02-001 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-03-001 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-04-001 | WPS | WPS-04 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-05-001 | WPS | WPS-05 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-06-001 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-07-001 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-08-001 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-09-001 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-10-001 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-11-001 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-12-001 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-13-001 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-14-001 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-15-001 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Acceptance | AC-WPS-16-001 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Activities | A-R-001 | Acceptance | AC-R-001 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-001 | Deliverables | D-R-001 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-001 | Rules | R-001 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-001 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-002 | Acceptance | AC-R-002 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-002 | Deliverables | D-R-002 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-002 | Rules | R-002 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-002 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-003 | Acceptance | AC-R-003 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-003 | Deliverables | D-R-003 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-003 | Rules | R-003 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-003 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-004 | Acceptance | AC-R-004 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-004 | Deliverables | D-R-004 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-004 | Rules | R-004 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-004 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-005 | Acceptance | AC-R-005 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-005 | Deliverables | D-R-005 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-005 | Rules | R-005 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-005 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-006 | Acceptance | AC-R-006 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-006 | Deliverables | D-R-006 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-006 | Rules | R-006 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-006 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-007 | Acceptance | AC-R-007 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-007 | Deliverables | D-R-007 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-007 | Rules | R-007 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-007 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-008 | Acceptance | AC-R-008 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-008 | Deliverables | D-R-008 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-008 | Rules | R-008 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-008 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-009 | Acceptance | AC-R-009 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-009 | Deliverables | D-R-009 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-009 | Rules | R-009 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-009 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-010 | Acceptance | AC-R-010 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-010 | Deliverables | D-R-010 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-010 | Rules | R-010 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-010 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-011 | Acceptance | AC-R-011 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-011 | Deliverables | D-R-011 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-011 | Rules | R-011 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-011 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-012 | Acceptance | AC-R-012 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-012 | Deliverables | D-R-012 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-012 | Rules | R-012 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-012 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-013 | Acceptance | AC-R-013 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-013 | Deliverables | D-R-013 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-013 | Rules | R-013 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-013 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-014 | Acceptance | AC-R-014 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-014 | Deliverables | D-R-014 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-014 | Rules | R-014 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-014 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-015 | Acceptance | AC-R-015 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-015 | Deliverables | D-R-015 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-015 | Rules | R-015 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-015 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-016 | Acceptance | AC-R-016 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-016 | Deliverables | D-R-016 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-016 | Rules | R-016 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-016 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-017 | Acceptance | AC-R-017 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-017 | Deliverables | D-R-017 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-017 | Rules | R-017 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-017 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-018 | Acceptance | AC-R-018 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-018 | Deliverables | D-R-018 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-018 | Rules | R-018 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-018 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-019 | Acceptance | AC-R-019 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-019 | Deliverables | D-R-019 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-019 | Rules | R-019 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-019 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-020 | Acceptance | AC-R-020 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-020 | Deliverables | D-R-020 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-020 | Rules | R-020 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-020 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-021 | Acceptance | AC-R-021 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-021 | Deliverables | D-R-021 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-021 | Rules | R-021 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-021 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-022 | Acceptance | AC-R-022 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-022 | Deliverables | D-R-022 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-022 | Rules | R-022 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-022 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-023 | Acceptance | AC-R-023 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-023 | Deliverables | D-R-023 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-023 | Rules | R-023 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-023 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-024 | Acceptance | AC-R-024 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-024 | Deliverables | D-R-024 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-024 | Rules | R-024 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-024 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-025 | Acceptance | AC-R-025 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-025 | Deliverables | D-R-025 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-025 | Rules | R-025 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-025 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-026 | Acceptance | AC-R-026 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-026 | Deliverables | D-R-026 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-026 | Rules | R-026 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-026 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-027 | Acceptance | AC-R-027 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-027 | Deliverables | D-R-027 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-027 | Rules | R-027 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-027 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-028 | Acceptance | AC-R-028 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-028 | Deliverables | D-R-028 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-028 | Rules | R-028 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-028 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-029 | Acceptance | AC-R-029 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-029 | Deliverables | D-R-029 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-029 | Rules | R-029 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-029 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-030 | Acceptance | AC-R-030 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-030 | Deliverables | D-R-030 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-030 | Rules | R-030 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-030 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-031 | Acceptance | AC-R-031 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-031 | Deliverables | D-R-031 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-031 | Rules | R-031 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-031 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-032 | Acceptance | AC-R-032 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-032 | Deliverables | D-R-032 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-032 | Rules | R-032 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-032 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-033 | Acceptance | AC-R-033 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-033 | Deliverables | D-R-033 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-033 | Rules | R-033 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-033 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-034 | Acceptance | AC-R-034 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-034 | Deliverables | D-R-034 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-034 | Rules | R-034 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-034 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-035 | Acceptance | AC-R-035 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-035 | Deliverables | D-R-035 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-035 | Rules | R-035 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-035 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-036 | Acceptance | AC-R-036 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-036 | Deliverables | D-R-036 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-036 | Rules | R-036 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-036 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-037 | Acceptance | AC-R-037 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-037 | Deliverables | D-R-037 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-037 | Rules | R-037 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-037 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-038 | Acceptance | AC-R-038 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-038 | Deliverables | D-R-038 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-038 | Rules | R-038 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-038 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-039 | Acceptance | AC-R-039 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-039 | Deliverables | D-R-039 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-039 | Rules | R-039 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-039 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-040 | Acceptance | AC-R-040 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-040 | Deliverables | D-R-040 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-040 | Rules | R-040 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-040 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-041 | Acceptance | AC-R-041 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-041 | Deliverables | D-R-041 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-041 | Rules | R-041 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-041 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-042 | Acceptance | AC-R-042 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-042 | Deliverables | D-R-042 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-042 | Rules | R-042 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-042 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-043 | Acceptance | AC-R-043 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-043 | Deliverables | D-R-043 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-043 | Rules | R-043 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-043 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-044 | Acceptance | AC-R-044 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-044 | Deliverables | D-R-044 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-044 | Rules | R-044 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-044 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-045 | Acceptance | AC-R-045 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-045 | Deliverables | D-R-045 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-045 | Rules | R-045 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-045 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-046 | Acceptance | AC-R-046 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-046 | Deliverables | D-R-046 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-046 | Rules | R-046 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-046 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-047 | Acceptance | AC-R-047 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-047 | Deliverables | D-R-047 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-047 | Rules | R-047 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-047 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-048 | Acceptance | AC-R-048 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-048 | Deliverables | D-R-048 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-048 | Rules | R-048 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-048 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-049 | Acceptance | AC-R-049 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-049 | Deliverables | D-R-049 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-049 | Rules | R-049 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-049 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-050 | Acceptance | AC-R-050 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-050 | Deliverables | D-R-050 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-050 | Rules | R-050 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-050 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-051 | Acceptance | AC-R-051 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-051 | Deliverables | D-R-051 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-051 | Rules | R-051 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-051 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-052 | Acceptance | AC-R-052 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-052 | Deliverables | D-R-052 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-052 | Rules | R-052 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-052 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-053 | Acceptance | AC-R-053 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-053 | Deliverables | D-R-053 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-053 | Rules | R-053 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-053 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-054 | Acceptance | AC-R-054 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-054 | Deliverables | D-R-054 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-054 | Rules | R-054 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-054 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-055 | Acceptance | AC-R-055 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-055 | Deliverables | D-R-055 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-055 | Rules | R-055 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-055 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-056 | Acceptance | AC-R-056 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-056 | Deliverables | D-R-056 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-056 | Rules | R-056 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-056 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-057 | Acceptance | AC-R-057 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-057 | Deliverables | D-R-057 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-057 | Rules | R-057 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-057 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-058 | Acceptance | AC-R-058 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-058 | Deliverables | D-R-058 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-058 | Rules | R-058 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-058 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-059 | Acceptance | AC-R-059 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-059 | Deliverables | D-R-059 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-059 | Rules | R-059 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-059 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-060 | Acceptance | AC-R-060 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-060 | Deliverables | D-R-060 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-060 | Rules | R-060 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-060 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-061 | Acceptance | AC-R-061 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-061 | Deliverables | D-R-061 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-061 | Rules | R-061 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-061 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-062 | Acceptance | AC-R-062 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-062 | Deliverables | D-R-062 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-062 | Rules | R-062 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-062 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-063 | Acceptance | AC-R-063 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-063 | Deliverables | D-R-063 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-063 | Rules | R-063 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-063 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-064 | Acceptance | AC-R-064 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-064 | Deliverables | D-R-064 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-064 | Rules | R-064 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-064 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-065 | Acceptance | AC-R-065 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-065 | Deliverables | D-R-065 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-065 | Rules | R-065 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-065 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-066 | Acceptance | AC-R-066 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-066 | Deliverables | D-R-066 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-066 | Rules | R-066 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-066 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-067 | Acceptance | AC-R-067 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-067 | Deliverables | D-R-067 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-067 | Rules | R-067 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-067 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-068 | Acceptance | AC-R-068 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-068 | Deliverables | D-R-068 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-068 | Rules | R-068 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-068 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-069 | Acceptance | AC-R-069 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-069 | Deliverables | D-R-069 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-069 | Rules | R-069 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-069 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-070 | Acceptance | AC-R-070 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-070 | Deliverables | D-R-070 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-070 | Rules | R-070 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-070 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-071 | Acceptance | AC-R-071 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-071 | Deliverables | D-R-071 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-071 | Rules | R-071 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-071 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-072 | Acceptance | AC-R-072 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-072 | Deliverables | D-R-072 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-072 | Rules | R-072 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-072 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-073 | Acceptance | AC-R-073 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-073 | Deliverables | D-R-073 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-073 | Rules | R-073 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-073 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-074 | Acceptance | AC-R-074 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-074 | Deliverables | D-R-074 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-074 | Rules | R-074 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-074 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-075 | Acceptance | AC-R-075 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-075 | Deliverables | D-R-075 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-075 | Rules | R-075 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-075 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-076 | Acceptance | AC-R-076 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-076 | Deliverables | D-R-076 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-076 | Rules | R-076 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-076 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-077 | Acceptance | AC-R-077 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-077 | Deliverables | D-R-077 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-077 | Rules | R-077 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-077 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-078 | Acceptance | AC-R-078 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-078 | Deliverables | D-R-078 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-078 | Rules | R-078 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-078 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-079 | Acceptance | AC-R-079 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-079 | Deliverables | D-R-079 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-079 | Rules | R-079 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-079 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-080 | Acceptance | AC-R-080 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-080 | Deliverables | D-R-080 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-080 | Rules | R-080 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-080 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-081 | Acceptance | AC-R-081 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-081 | Deliverables | D-R-081 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-081 | Rules | R-081 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-081 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-082 | Acceptance | AC-R-082 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-082 | Deliverables | D-R-082 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-082 | Rules | R-082 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-082 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-083 | Acceptance | AC-R-083 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-083 | Deliverables | D-R-083 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-083 | Rules | R-083 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-083 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-084 | Acceptance | AC-R-084 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-084 | Deliverables | D-R-084 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-084 | Rules | R-084 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-084 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-085 | Acceptance | AC-R-085 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-085 | Deliverables | D-R-085 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-085 | Rules | R-085 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-085 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-086 | Acceptance | AC-R-086 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-086 | Deliverables | D-R-086 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-086 | Rules | R-086 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-086 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-087 | Acceptance | AC-R-087 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-087 | Deliverables | D-R-087 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-087 | Rules | R-087 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-087 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-088 | Acceptance | AC-R-088 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-088 | Deliverables | D-R-088 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-088 | Rules | R-088 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-088 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-R-089 | Acceptance | AC-R-089 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-R-089 | Deliverables | D-R-089 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-R-089 | Rules | R-089 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Activities | A-R-089 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-17-01 | Acceptance | AC-S-17-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-17-01 | Deliverables | D-S-17-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-17-01 | Gaps | G-S-17-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-17-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-17-02 | Acceptance | AC-S-17-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-17-02 | Deliverables | D-S-17-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-17-02 | Gaps | G-S-17-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-17-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-17-03 | Acceptance | AC-S-17-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-17-03 | Deliverables | D-S-17-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-17-03 | Gaps | G-S-17-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-17-03 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-17-04 | Acceptance | AC-S-17-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-17-04 | Deliverables | D-S-17-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-17-04 | Gaps | G-S-17-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-17-04 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-17-05 | Acceptance | AC-S-17-05 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-17-05 | Deliverables | D-S-17-05 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-17-05 | Gaps | G-S-17-05 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-17-05 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-18-01 | Acceptance | AC-S-18-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-18-01 | Deliverables | D-S-18-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-18-01 | Gaps | G-S-18-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-18-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-18-02 | Acceptance | AC-S-18-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-18-02 | Deliverables | D-S-18-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-18-02 | Gaps | G-S-18-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-18-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-18-03 | Acceptance | AC-S-18-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-18-03 | Deliverables | D-S-18-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-18-03 | Gaps | G-S-18-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-18-03 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-18-04 | Acceptance | AC-S-18-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-18-04 | Deliverables | D-S-18-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-18-04 | Gaps | G-S-18-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-18-04 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-18-05 | Acceptance | AC-S-18-05 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-18-05 | Deliverables | D-S-18-05 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-18-05 | Gaps | G-S-18-05 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-18-05 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-19-01 | Acceptance | AC-S-19-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-19-01 | Deliverables | D-S-19-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-19-01 | Gaps | G-S-19-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-19-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-19-02 | Acceptance | AC-S-19-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-19-02 | Deliverables | D-S-19-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-19-02 | Gaps | G-S-19-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-19-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-19-03 | Acceptance | AC-S-19-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-19-03 | Deliverables | D-S-19-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-19-03 | Gaps | G-S-19-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-19-03 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-19-04 | Acceptance | AC-S-19-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-19-04 | Deliverables | D-S-19-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-19-04 | Gaps | G-S-19-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-19-04 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-19-05 | Acceptance | AC-S-19-05 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-19-05 | Deliverables | D-S-19-05 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-19-05 | Gaps | G-S-19-05 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-19-05 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-20-01 | Acceptance | AC-S-20-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-20-01 | Deliverables | D-S-20-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-20-01 | Gaps | G-S-20-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-20-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-20-02 | Acceptance | AC-S-20-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-20-02 | Deliverables | D-S-20-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-20-02 | Gaps | G-S-20-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-20-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-20-03 | Acceptance | AC-S-20-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-20-03 | Deliverables | D-S-20-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-20-03 | Gaps | G-S-20-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-20-03 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-20-04 | Acceptance | AC-S-20-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-20-04 | Deliverables | D-S-20-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-20-04 | Gaps | G-S-20-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-20-04 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-20-05 | Acceptance | AC-S-20-05 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-20-05 | Deliverables | D-S-20-05 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-20-05 | Gaps | G-S-20-05 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-20-05 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-21-01 | Acceptance | AC-S-21-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-21-01 | Deliverables | D-S-21-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-21-01 | Gaps | G-S-21-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-21-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-21-02 | Acceptance | AC-S-21-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-21-02 | Deliverables | D-S-21-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-21-02 | Gaps | G-S-21-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-21-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-21-03 | Acceptance | AC-S-21-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-21-03 | Deliverables | D-S-21-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-21-03 | Gaps | G-S-21-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-21-03 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-21-04 | Acceptance | AC-S-21-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-21-04 | Deliverables | D-S-21-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-21-04 | Gaps | G-S-21-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-21-04 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-21-05 | Acceptance | AC-S-21-05 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-21-05 | Deliverables | D-S-21-05 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-21-05 | Gaps | G-S-21-05 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-21-05 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-22-01 | Acceptance | AC-S-22-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-22-01 | Deliverables | D-S-22-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-22-01 | Gaps | G-S-22-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-22-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-22-02 | Acceptance | AC-S-22-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-22-02 | Deliverables | D-S-22-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-22-02 | Gaps | G-S-22-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-22-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-22-03 | Acceptance | AC-S-22-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-22-03 | Deliverables | D-S-22-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-22-03 | Gaps | G-S-22-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-22-03 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-22-04 | Acceptance | AC-S-22-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-22-04 | Deliverables | D-S-22-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-22-04 | Gaps | G-S-22-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-22-04 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-22-05 | Acceptance | AC-S-22-05 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-22-05 | Deliverables | D-S-22-05 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-22-05 | Gaps | G-S-22-05 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-22-05 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-23-01 | Acceptance | AC-S-23-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-23-01 | Deliverables | D-S-23-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-23-01 | Gaps | G-S-23-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-23-01 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-23-02 | Acceptance | AC-S-23-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-23-02 | Deliverables | D-S-23-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-23-02 | Gaps | G-S-23-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-23-02 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-23-03 | Acceptance | AC-S-23-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-23-03 | Deliverables | D-S-23-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-23-03 | Gaps | G-S-23-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-23-03 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-23-04 | Acceptance | AC-S-23-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-23-04 | Deliverables | D-S-23-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-23-04 | Gaps | G-S-23-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-23-04 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-24-01 | Acceptance | AC-S-24-01 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-24-01 | Deliverables | D-S-24-01 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-24-01 | Gaps | G-S-24-01 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-24-01 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-24-02 | Acceptance | AC-S-24-02 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-24-02 | Deliverables | D-S-24-02 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-24-02 | Gaps | G-S-24-02 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-24-02 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-24-03 | Acceptance | AC-S-24-03 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-24-03 | Deliverables | D-S-24-03 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-24-03 | Gaps | G-S-24-03 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-24-03 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Activities | A-S-24-04 | Acceptance | AC-S-24-04 | Related Acceptance Criteria IDs |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Related Acceptance Criteria IDs
Activities | A-S-24-04 | Deliverables | D-S-24-04 | Related Deliverable IDs |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Activities | A-S-24-04 | Gaps | G-S-24-04 | Related Gap IDs |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Activities | A-S-24-04 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-001 | Acceptance | AC-R-001 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-001 | Activities | A-R-001 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-001 | Rules | R-001 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-001 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-002 | Acceptance | AC-R-002 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-002 | Activities | A-R-002 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-002 | Rules | R-002 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-002 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-003 | Acceptance | AC-R-003 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-003 | Activities | A-R-003 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-003 | Rules | R-003 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-003 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-004 | Acceptance | AC-R-004 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-004 | Activities | A-R-004 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-004 | Rules | R-004 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-004 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-005 | Acceptance | AC-R-005 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-005 | Activities | A-R-005 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-005 | Rules | R-005 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-005 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-006 | Acceptance | AC-R-006 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-006 | Activities | A-R-006 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-006 | Rules | R-006 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-006 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-007 | Acceptance | AC-R-007 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-007 | Activities | A-R-007 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-007 | Rules | R-007 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-007 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-008 | Acceptance | AC-R-008 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-008 | Activities | A-R-008 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-008 | Rules | R-008 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-008 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-009 | Acceptance | AC-R-009 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-009 | Activities | A-R-009 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-009 | Rules | R-009 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-009 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-010 | Acceptance | AC-R-010 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-010 | Activities | A-R-010 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-010 | Rules | R-010 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-010 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-011 | Acceptance | AC-R-011 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-011 | Activities | A-R-011 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-011 | Rules | R-011 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-011 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-012 | Acceptance | AC-R-012 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-012 | Activities | A-R-012 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-012 | Rules | R-012 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-012 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-013 | Acceptance | AC-R-013 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-013 | Activities | A-R-013 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-013 | Rules | R-013 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-013 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-014 | Acceptance | AC-R-014 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-014 | Activities | A-R-014 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-014 | Rules | R-014 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-014 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-015 | Acceptance | AC-R-015 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-015 | Activities | A-R-015 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-015 | Rules | R-015 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-015 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-016 | Acceptance | AC-R-016 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-016 | Activities | A-R-016 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-016 | Rules | R-016 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-016 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-017 | Acceptance | AC-R-017 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-017 | Activities | A-R-017 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-017 | Rules | R-017 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-017 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-018 | Acceptance | AC-R-018 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-018 | Activities | A-R-018 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-018 | Rules | R-018 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-018 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-019 | Acceptance | AC-R-019 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-019 | Activities | A-R-019 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-019 | Rules | R-019 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-019 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-020 | Acceptance | AC-R-020 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-020 | Activities | A-R-020 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-020 | Rules | R-020 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-020 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-021 | Acceptance | AC-R-021 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-021 | Activities | A-R-021 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-021 | Rules | R-021 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-021 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-022 | Acceptance | AC-R-022 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-022 | Activities | A-R-022 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-022 | Rules | R-022 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-022 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-023 | Acceptance | AC-R-023 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-023 | Activities | A-R-023 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-023 | Rules | R-023 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-023 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-024 | Acceptance | AC-R-024 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-024 | Activities | A-R-024 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-024 | Rules | R-024 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-024 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-025 | Acceptance | AC-R-025 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-025 | Activities | A-R-025 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-025 | Rules | R-025 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-025 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-026 | Acceptance | AC-R-026 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-026 | Activities | A-R-026 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-026 | Rules | R-026 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-026 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-027 | Acceptance | AC-R-027 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-027 | Activities | A-R-027 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-027 | Rules | R-027 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-027 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-028 | Acceptance | AC-R-028 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-028 | Activities | A-R-028 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-028 | Rules | R-028 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-028 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-029 | Acceptance | AC-R-029 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-029 | Activities | A-R-029 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-029 | Rules | R-029 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-029 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-030 | Acceptance | AC-R-030 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-030 | Activities | A-R-030 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-030 | Rules | R-030 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-030 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-031 | Acceptance | AC-R-031 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-031 | Activities | A-R-031 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-031 | Rules | R-031 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-031 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-032 | Acceptance | AC-R-032 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-032 | Activities | A-R-032 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-032 | Rules | R-032 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-032 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-033 | Acceptance | AC-R-033 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-033 | Activities | A-R-033 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-033 | Rules | R-033 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-033 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-034 | Acceptance | AC-R-034 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-034 | Activities | A-R-034 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-034 | Rules | R-034 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-034 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-035 | Acceptance | AC-R-035 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-035 | Activities | A-R-035 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-035 | Rules | R-035 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-035 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-036 | Acceptance | AC-R-036 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-036 | Activities | A-R-036 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-036 | Rules | R-036 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-036 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-037 | Acceptance | AC-R-037 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-037 | Activities | A-R-037 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-037 | Rules | R-037 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-037 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-038 | Acceptance | AC-R-038 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-038 | Activities | A-R-038 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-038 | Rules | R-038 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-038 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-039 | Acceptance | AC-R-039 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-039 | Activities | A-R-039 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-039 | Rules | R-039 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-039 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-040 | Acceptance | AC-R-040 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-040 | Activities | A-R-040 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-040 | Rules | R-040 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-040 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-041 | Acceptance | AC-R-041 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-041 | Activities | A-R-041 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-041 | Rules | R-041 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-041 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-042 | Acceptance | AC-R-042 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-042 | Activities | A-R-042 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-042 | Rules | R-042 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-042 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-043 | Acceptance | AC-R-043 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-043 | Activities | A-R-043 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-043 | Rules | R-043 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-043 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-044 | Acceptance | AC-R-044 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-044 | Activities | A-R-044 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-044 | Rules | R-044 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-044 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-045 | Acceptance | AC-R-045 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-045 | Activities | A-R-045 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-045 | Rules | R-045 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-045 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-046 | Acceptance | AC-R-046 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-046 | Activities | A-R-046 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-046 | Rules | R-046 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-046 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-047 | Acceptance | AC-R-047 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-047 | Activities | A-R-047 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-047 | Rules | R-047 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-047 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-048 | Acceptance | AC-R-048 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-048 | Activities | A-R-048 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-048 | Rules | R-048 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-048 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-049 | Acceptance | AC-R-049 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-049 | Activities | A-R-049 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-049 | Rules | R-049 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-049 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-050 | Acceptance | AC-R-050 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-050 | Activities | A-R-050 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-050 | Rules | R-050 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-050 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-051 | Acceptance | AC-R-051 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-051 | Activities | A-R-051 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-051 | Rules | R-051 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-051 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-052 | Acceptance | AC-R-052 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-052 | Activities | A-R-052 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-052 | Rules | R-052 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-052 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-053 | Acceptance | AC-R-053 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-053 | Activities | A-R-053 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-053 | Rules | R-053 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-053 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-054 | Acceptance | AC-R-054 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-054 | Activities | A-R-054 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-054 | Rules | R-054 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-054 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-055 | Acceptance | AC-R-055 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-055 | Activities | A-R-055 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-055 | Rules | R-055 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-055 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-056 | Acceptance | AC-R-056 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-056 | Activities | A-R-056 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-056 | Rules | R-056 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-056 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-057 | Acceptance | AC-R-057 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-057 | Activities | A-R-057 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-057 | Rules | R-057 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-057 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-058 | Acceptance | AC-R-058 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-058 | Activities | A-R-058 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-058 | Rules | R-058 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-058 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-059 | Acceptance | AC-R-059 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-059 | Activities | A-R-059 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-059 | Rules | R-059 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-059 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-060 | Acceptance | AC-R-060 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-060 | Activities | A-R-060 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-060 | Rules | R-060 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-060 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-061 | Acceptance | AC-R-061 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-061 | Activities | A-R-061 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-061 | Rules | R-061 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-061 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-062 | Acceptance | AC-R-062 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-062 | Activities | A-R-062 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-062 | Rules | R-062 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-062 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-063 | Acceptance | AC-R-063 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-063 | Activities | A-R-063 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-063 | Rules | R-063 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-063 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-064 | Acceptance | AC-R-064 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-064 | Activities | A-R-064 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-064 | Rules | R-064 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-064 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-065 | Acceptance | AC-R-065 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-065 | Activities | A-R-065 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-065 | Rules | R-065 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-065 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-066 | Acceptance | AC-R-066 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-066 | Activities | A-R-066 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-066 | Rules | R-066 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-066 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-067 | Acceptance | AC-R-067 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-067 | Activities | A-R-067 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-067 | Rules | R-067 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-067 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-068 | Acceptance | AC-R-068 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-068 | Activities | A-R-068 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-068 | Rules | R-068 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-068 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-069 | Acceptance | AC-R-069 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-069 | Activities | A-R-069 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-069 | Rules | R-069 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-069 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-070 | Acceptance | AC-R-070 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-070 | Activities | A-R-070 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-070 | Rules | R-070 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-070 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-071 | Acceptance | AC-R-071 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-071 | Activities | A-R-071 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-071 | Rules | R-071 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-071 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-072 | Acceptance | AC-R-072 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-072 | Activities | A-R-072 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-072 | Rules | R-072 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-072 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-073 | Acceptance | AC-R-073 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-073 | Activities | A-R-073 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-073 | Rules | R-073 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-073 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-074 | Acceptance | AC-R-074 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-074 | Activities | A-R-074 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-074 | Rules | R-074 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-074 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-075 | Acceptance | AC-R-075 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-075 | Activities | A-R-075 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-075 | Rules | R-075 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-075 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-076 | Acceptance | AC-R-076 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-076 | Activities | A-R-076 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-076 | Rules | R-076 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-076 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-077 | Acceptance | AC-R-077 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-077 | Activities | A-R-077 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-077 | Rules | R-077 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-077 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-078 | Acceptance | AC-R-078 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-078 | Activities | A-R-078 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-078 | Rules | R-078 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-078 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-079 | Acceptance | AC-R-079 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-079 | Activities | A-R-079 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-079 | Rules | R-079 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-079 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-080 | Acceptance | AC-R-080 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-080 | Activities | A-R-080 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-080 | Rules | R-080 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-080 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-081 | Acceptance | AC-R-081 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-081 | Activities | A-R-081 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-081 | Rules | R-081 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-081 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-082 | Acceptance | AC-R-082 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-082 | Activities | A-R-082 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-082 | Rules | R-082 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-082 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-083 | Acceptance | AC-R-083 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-083 | Activities | A-R-083 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-083 | Rules | R-083 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-083 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-084 | Acceptance | AC-R-084 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-084 | Activities | A-R-084 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-084 | Rules | R-084 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-084 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-085 | Acceptance | AC-R-085 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-085 | Activities | A-R-085 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-085 | Rules | R-085 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-085 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-086 | Acceptance | AC-R-086 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-086 | Activities | A-R-086 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-086 | Rules | R-086 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-086 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-087 | Acceptance | AC-R-087 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-087 | Activities | A-R-087 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-087 | Rules | R-087 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-087 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-088 | Acceptance | AC-R-088 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-088 | Activities | A-R-088 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-088 | Rules | R-088 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-088 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-R-089 | Acceptance | AC-R-089 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-R-089 | Activities | A-R-089 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-R-089 | Rules | R-089 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Deliverables | D-R-089 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-17-01 | Acceptance | AC-S-17-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-17-01 | Activities | A-S-17-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-17-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-17-02 | Acceptance | AC-S-17-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-17-02 | Activities | A-S-17-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-17-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-17-03 | Acceptance | AC-S-17-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-17-03 | Activities | A-S-17-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-17-03 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-17-04 | Acceptance | AC-S-17-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-17-04 | Activities | A-S-17-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-17-04 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-17-05 | Acceptance | AC-S-17-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-17-05 | Activities | A-S-17-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-17-05 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-18-01 | Acceptance | AC-S-18-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-18-01 | Activities | A-S-18-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-18-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-18-02 | Acceptance | AC-S-18-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-18-02 | Activities | A-S-18-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-18-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-18-03 | Acceptance | AC-S-18-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-18-03 | Activities | A-S-18-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-18-03 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-18-04 | Acceptance | AC-S-18-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-18-04 | Activities | A-S-18-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-18-04 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-18-05 | Acceptance | AC-S-18-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-18-05 | Activities | A-S-18-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-18-05 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-19-01 | Acceptance | AC-S-19-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-19-01 | Activities | A-S-19-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-19-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-19-02 | Acceptance | AC-S-19-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-19-02 | Activities | A-S-19-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-19-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-19-03 | Acceptance | AC-S-19-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-19-03 | Activities | A-S-19-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-19-03 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-19-04 | Acceptance | AC-S-19-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-19-04 | Activities | A-S-19-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-19-04 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-19-05 | Acceptance | AC-S-19-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-19-05 | Activities | A-S-19-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-19-05 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-20-01 | Acceptance | AC-S-20-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-20-01 | Activities | A-S-20-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-20-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-20-02 | Acceptance | AC-S-20-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-20-02 | Activities | A-S-20-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-20-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-20-03 | Acceptance | AC-S-20-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-20-03 | Activities | A-S-20-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-20-03 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-20-04 | Acceptance | AC-S-20-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-20-04 | Activities | A-S-20-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-20-04 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-20-05 | Acceptance | AC-S-20-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-20-05 | Activities | A-S-20-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-20-05 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-21-01 | Acceptance | AC-S-21-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-21-01 | Activities | A-S-21-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-21-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-21-02 | Acceptance | AC-S-21-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-21-02 | Activities | A-S-21-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-21-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-21-03 | Acceptance | AC-S-21-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-21-03 | Activities | A-S-21-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-21-03 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-21-04 | Acceptance | AC-S-21-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-21-04 | Activities | A-S-21-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-21-04 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-21-05 | Acceptance | AC-S-21-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-21-05 | Activities | A-S-21-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-21-05 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-22-01 | Acceptance | AC-S-22-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-22-01 | Activities | A-S-22-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-22-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-22-02 | Acceptance | AC-S-22-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-22-02 | Activities | A-S-22-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-22-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-22-03 | Acceptance | AC-S-22-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-22-03 | Activities | A-S-22-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-22-03 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-22-04 | Acceptance | AC-S-22-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-22-04 | Activities | A-S-22-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-22-04 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-22-05 | Acceptance | AC-S-22-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-22-05 | Activities | A-S-22-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-22-05 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-23-01 | Acceptance | AC-S-23-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-23-01 | Activities | A-S-23-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-23-01 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-23-02 | Acceptance | AC-S-23-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-23-02 | Activities | A-S-23-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-23-02 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-23-03 | Acceptance | AC-S-23-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-23-03 | Activities | A-S-23-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-23-03 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-23-04 | Acceptance | AC-S-23-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-23-04 | Activities | A-S-23-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-23-04 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-24-01 | Acceptance | AC-S-24-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-24-01 | Activities | A-S-24-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-24-01 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-24-02 | Acceptance | AC-S-24-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-24-02 | Activities | A-S-24-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-24-02 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-24-03 | Acceptance | AC-S-24-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-24-03 | Activities | A-S-24-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-24-03 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Deliverables | D-S-24-04 | Acceptance | AC-S-24-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Deliverables | D-S-24-04 | Activities | A-S-24-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Deliverables | D-S-24-04 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Evidence | E-001 | Acceptance | AC-R-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-001 | Activities | A-R-001 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-001 | Rules | R-001 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-001 | Tasks | T-R-001-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-001 | Tasks | T-R-001-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-001 | Tasks | T-R-001-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-001 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-002 | Acceptance | AC-R-002 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-002 | Activities | A-R-002 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-002 | Rules | R-002 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-002 | Tasks | T-R-002-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-002 | Tasks | T-R-002-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-002 | Tasks | T-R-002-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-002 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-003 | Acceptance | AC-R-003 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-003 | Activities | A-R-003 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-003 | Rules | R-003 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-003 | Tasks | T-R-003-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-003 | Tasks | T-R-003-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-003 | Tasks | T-R-003-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-003 | WPS | WPS-02 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-004 | Acceptance | AC-R-004 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-004 | Activities | A-R-004 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-004 | Rules | R-004 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-004 | Tasks | T-R-004-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-004 | Tasks | T-R-004-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-004 | Tasks | T-R-004-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-004 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-005 | Acceptance | AC-R-005 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-005 | Activities | A-R-005 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-005 | Rules | R-005 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-005 | Tasks | T-R-005-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-005 | Tasks | T-R-005-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-005 | Tasks | T-R-005-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-005 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-006 | Acceptance | AC-R-006 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-006 | Activities | A-R-006 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-006 | Rules | R-006 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-006 | Tasks | T-R-006-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-006 | Tasks | T-R-006-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-006 | Tasks | T-R-006-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-006 | WPS | WPS-02 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-007 | Acceptance | AC-R-007 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-007 | Activities | A-R-007 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-007 | Rules | R-007 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-007 | Tasks | T-R-007-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-007 | Tasks | T-R-007-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-007 | Tasks | T-R-007-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-007 | WPS | WPS-02 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-008 | Acceptance | AC-R-008 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-008 | Activities | A-R-008 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-008 | Rules | R-008 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-008 | Tasks | T-R-008-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-008 | Tasks | T-R-008-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-008 | Tasks | T-R-008-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-008 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-009 | Acceptance | AC-R-009 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-009 | Activities | A-R-009 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-009 | Rules | R-009 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-009 | Tasks | T-R-009-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-009 | Tasks | T-R-009-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-009 | Tasks | T-R-009-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-009 | WPS | WPS-03 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-010 | Acceptance | AC-R-010 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-010 | Activities | A-R-010 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-010 | Rules | R-010 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-010 | Tasks | T-R-010-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-010 | Tasks | T-R-010-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-010 | Tasks | T-R-010-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-010 | WPS | WPS-03 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-011 | Acceptance | AC-R-011 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-011 | Activities | A-R-011 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-011 | Rules | R-011 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-011 | Tasks | T-R-011-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-011 | Tasks | T-R-011-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-011 | Tasks | T-R-011-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-011 | WPS | WPS-03 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-012 | Acceptance | AC-R-012 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-012 | Activities | A-R-012 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-012 | Rules | R-012 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-012 | Tasks | T-R-012-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-012 | Tasks | T-R-012-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-012 | Tasks | T-R-012-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-012 | WPS | WPS-04 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-013 | Acceptance | AC-R-013 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-013 | Activities | A-R-013 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-013 | Rules | R-013 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-013 | Tasks | T-R-013-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-013 | Tasks | T-R-013-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-013 | Tasks | T-R-013-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-013 | WPS | WPS-04 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-014 | Acceptance | AC-R-014 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-014 | Activities | A-R-014 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-014 | Rules | R-014 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-014 | Tasks | T-R-014-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-014 | Tasks | T-R-014-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-014 | Tasks | T-R-014-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-014 | WPS | WPS-05 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-015 | Acceptance | AC-R-015 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-015 | Activities | A-R-015 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-015 | Rules | R-015 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-015 | Tasks | T-R-015-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-015 | Tasks | T-R-015-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-015 | Tasks | T-R-015-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-015 | WPS | WPS-05 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-016 | Acceptance | AC-R-016 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-016 | Activities | A-R-016 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-016 | Rules | R-016 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-016 | Tasks | T-R-016-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-016 | Tasks | T-R-016-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-016 | Tasks | T-R-016-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-016 | WPS | WPS-03 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-017 | Acceptance | AC-R-017 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-017 | Activities | A-R-017 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-017 | Rules | R-017 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-017 | Tasks | T-R-017-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-017 | Tasks | T-R-017-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-017 | Tasks | T-R-017-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-017 | WPS | WPS-03 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-018 | Acceptance | AC-R-018 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-018 | Activities | A-R-018 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-018 | Rules | R-018 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-018 | Tasks | T-R-018-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-018 | Tasks | T-R-018-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-018 | Tasks | T-R-018-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-018 | WPS | WPS-03 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-019 | Acceptance | AC-R-019 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-019 | Activities | A-R-019 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-019 | Rules | R-019 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-019 | Tasks | T-R-019-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-019 | Tasks | T-R-019-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-019 | Tasks | T-R-019-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-019 | WPS | WPS-06 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-020 | Acceptance | AC-R-020 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-020 | Activities | A-R-020 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-020 | Rules | R-020 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-020 | Tasks | T-R-020-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-020 | Tasks | T-R-020-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-020 | Tasks | T-R-020-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-020 | WPS | WPS-06 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-021 | Acceptance | AC-R-021 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-021 | Activities | A-R-021 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-021 | Rules | R-021 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-021 | Tasks | T-R-021-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-021 | Tasks | T-R-021-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-021 | Tasks | T-R-021-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-021 | WPS | WPS-06 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-022 | Acceptance | AC-R-022 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-022 | Activities | A-R-022 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-022 | Rules | R-022 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-022 | Tasks | T-R-022-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-022 | Tasks | T-R-022-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-022 | Tasks | T-R-022-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-022 | WPS | WPS-06 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-023 | Acceptance | AC-R-023 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-023 | Activities | A-R-023 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-023 | Rules | R-023 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-023 | Tasks | T-R-023-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-023 | Tasks | T-R-023-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-023 | Tasks | T-R-023-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-023 | WPS | WPS-07 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-024 | Acceptance | AC-R-024 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-024 | Activities | A-R-024 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-024 | Rules | R-024 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-024 | Tasks | T-R-024-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-024 | Tasks | T-R-024-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-024 | Tasks | T-R-024-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-024 | WPS | WPS-07 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-025 | Acceptance | AC-R-025 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-025 | Activities | A-R-025 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-025 | Rules | R-025 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-025 | Tasks | T-R-025-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-025 | Tasks | T-R-025-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-025 | Tasks | T-R-025-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-025 | WPS | WPS-07 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-026 | Acceptance | AC-R-026 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-026 | Activities | A-R-026 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-026 | Rules | R-026 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-026 | Tasks | T-R-026-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-026 | Tasks | T-R-026-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-026 | Tasks | T-R-026-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-026 | WPS | WPS-07 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-027 | Acceptance | AC-R-027 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-027 | Activities | A-R-027 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-027 | Rules | R-027 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-027 | Tasks | T-R-027-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-027 | Tasks | T-R-027-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-027 | Tasks | T-R-027-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-027 | WPS | WPS-07 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-028 | Acceptance | AC-R-028 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-028 | Activities | A-R-028 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-028 | Rules | R-028 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-028 | Tasks | T-R-028-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-028 | Tasks | T-R-028-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-028 | Tasks | T-R-028-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-028 | WPS | WPS-07 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-029 | Acceptance | AC-R-029 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-029 | Activities | A-R-029 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-029 | Rules | R-029 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-029 | Tasks | T-R-029-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-029 | Tasks | T-R-029-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-029 | Tasks | T-R-029-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-029 | WPS | WPS-08 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-030 | Acceptance | AC-R-030 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-030 | Activities | A-R-030 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-030 | Rules | R-030 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-030 | Tasks | T-R-030-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-030 | Tasks | T-R-030-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-030 | Tasks | T-R-030-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-030 | WPS | WPS-08 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-031 | Acceptance | AC-R-031 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-031 | Activities | A-R-031 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-031 | Rules | R-031 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-031 | Tasks | T-R-031-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-031 | Tasks | T-R-031-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-031 | Tasks | T-R-031-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-031 | WPS | WPS-08 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-032 | Acceptance | AC-R-032 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-032 | Activities | A-R-032 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-032 | Rules | R-032 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-032 | Tasks | T-R-032-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-032 | Tasks | T-R-032-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-032 | Tasks | T-R-032-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-032 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-033 | Acceptance | AC-R-033 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-033 | Activities | A-R-033 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-033 | Rules | R-033 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-033 | Tasks | T-R-033-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-033 | Tasks | T-R-033-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-033 | Tasks | T-R-033-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-033 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-034 | Acceptance | AC-R-034 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-034 | Activities | A-R-034 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-034 | Rules | R-034 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-034 | Tasks | T-R-034-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-034 | Tasks | T-R-034-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-034 | Tasks | T-R-034-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-034 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-035 | Acceptance | AC-R-035 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-035 | Activities | A-R-035 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-035 | Rules | R-035 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-035 | Tasks | T-R-035-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-035 | Tasks | T-R-035-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-035 | Tasks | T-R-035-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-035 | WPS | WPS-11 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-036 | Acceptance | AC-R-036 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-036 | Activities | A-R-036 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-036 | Rules | R-036 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-036 | Tasks | T-R-036-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-036 | Tasks | T-R-036-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-036 | Tasks | T-R-036-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-036 | WPS | WPS-08 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-037 | Acceptance | AC-R-037 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-037 | Activities | A-R-037 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-037 | Rules | R-037 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-037 | Tasks | T-R-037-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-037 | Tasks | T-R-037-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-037 | Tasks | T-R-037-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-037 | WPS | WPS-10 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-038 | Acceptance | AC-R-038 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-038 | Activities | A-R-038 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-038 | Rules | R-038 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-038 | Tasks | T-R-038-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-038 | Tasks | T-R-038-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-038 | Tasks | T-R-038-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-038 | WPS | WPS-10 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-039 | Acceptance | AC-R-039 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-039 | Activities | A-R-039 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-039 | Rules | R-039 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-039 | Tasks | T-R-039-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-039 | Tasks | T-R-039-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-039 | Tasks | T-R-039-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-039 | WPS | WPS-10 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-040 | Acceptance | AC-R-040 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-040 | Activities | A-R-040 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-040 | Rules | R-040 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-040 | Tasks | T-R-040-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-040 | Tasks | T-R-040-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-040 | Tasks | T-R-040-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-040 | WPS | WPS-10 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-041 | Acceptance | AC-R-041 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-041 | Activities | A-R-041 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-041 | Rules | R-041 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-041 | Tasks | T-R-041-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-041 | Tasks | T-R-041-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-041 | Tasks | T-R-041-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-041 | WPS | WPS-10 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-042 | Acceptance | AC-R-042 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-042 | Activities | A-R-042 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-042 | Rules | R-042 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-042 | Tasks | T-R-042-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-042 | Tasks | T-R-042-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-042 | Tasks | T-R-042-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-042 | WPS | WPS-10 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-043 | Acceptance | AC-R-043 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-043 | Activities | A-R-043 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-043 | Rules | R-043 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-043 | Tasks | T-R-043-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-043 | Tasks | T-R-043-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-043 | Tasks | T-R-043-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-043 | WPS | WPS-11 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-044 | Acceptance | AC-R-044 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-044 | Activities | A-R-044 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-044 | Rules | R-044 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-044 | Tasks | T-R-044-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-044 | Tasks | T-R-044-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-044 | Tasks | T-R-044-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-044 | WPS | WPS-12 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-045 | Acceptance | AC-R-045 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-045 | Activities | A-R-045 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-045 | Rules | R-045 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-045 | Tasks | T-R-045-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-045 | Tasks | T-R-045-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-045 | Tasks | T-R-045-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-045 | WPS | WPS-12 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-046 | Acceptance | AC-R-046 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-046 | Activities | A-R-046 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-046 | Rules | R-046 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-046 | Tasks | T-R-046-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-046 | Tasks | T-R-046-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-046 | Tasks | T-R-046-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-046 | WPS | WPS-12 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-047 | Acceptance | AC-R-047 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-047 | Activities | A-R-047 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-047 | Rules | R-047 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-047 | Tasks | T-R-047-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-047 | Tasks | T-R-047-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-047 | Tasks | T-R-047-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-047 | WPS | WPS-12 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-048 | Acceptance | AC-R-048 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-048 | Activities | A-R-048 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-048 | Rules | R-048 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-048 | Tasks | T-R-048-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-048 | Tasks | T-R-048-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-048 | Tasks | T-R-048-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-048 | WPS | WPS-12 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-049 | Acceptance | AC-R-049 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-049 | Activities | A-R-049 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-049 | Rules | R-049 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-049 | Tasks | T-R-049-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-049 | Tasks | T-R-049-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-049 | Tasks | T-R-049-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-049 | WPS | WPS-13 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-050 | Acceptance | AC-R-050 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-050 | Activities | A-R-050 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-050 | Rules | R-050 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-050 | Tasks | T-R-050-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-050 | Tasks | T-R-050-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-050 | Tasks | T-R-050-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-050 | WPS | WPS-13 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-051 | Acceptance | AC-R-051 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-051 | Activities | A-R-051 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-051 | Rules | R-051 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-051 | Tasks | T-R-051-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-051 | Tasks | T-R-051-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-051 | Tasks | T-R-051-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-051 | WPS | WPS-14 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-052 | Acceptance | AC-R-052 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-052 | Activities | A-R-052 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-052 | Rules | R-052 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-052 | Tasks | T-R-052-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-052 | Tasks | T-R-052-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-052 | Tasks | T-R-052-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-052 | WPS | WPS-14 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-053 | Acceptance | AC-R-053 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-053 | Activities | A-R-053 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-053 | Rules | R-053 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-053 | Tasks | T-R-053-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-053 | Tasks | T-R-053-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-053 | Tasks | T-R-053-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-053 | WPS | WPS-14 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-054 | Acceptance | AC-R-054 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-054 | Activities | A-R-054 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-054 | Rules | R-054 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-054 | Tasks | T-R-054-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-054 | Tasks | T-R-054-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-054 | Tasks | T-R-054-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-054 | WPS | WPS-14 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-055 | Acceptance | AC-R-055 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-055 | Activities | A-R-055 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-055 | Rules | R-055 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-055 | Tasks | T-R-055-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-055 | Tasks | T-R-055-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-055 | Tasks | T-R-055-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-055 | WPS | WPS-15 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-056 | Acceptance | AC-R-056 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-056 | Activities | A-R-056 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-056 | Rules | R-056 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-056 | Tasks | T-R-056-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-056 | Tasks | T-R-056-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-056 | Tasks | T-R-056-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-056 | WPS | WPS-15 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-057 | Acceptance | AC-R-057 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-057 | Activities | A-R-057 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-057 | Rules | R-057 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-057 | Tasks | T-R-057-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-057 | Tasks | T-R-057-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-057 | Tasks | T-R-057-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-057 | WPS | WPS-15 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-058 | Acceptance | AC-R-058 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-058 | Activities | A-R-058 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-058 | Rules | R-058 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-058 | Tasks | T-R-058-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-058 | Tasks | T-R-058-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-058 | Tasks | T-R-058-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-058 | WPS | WPS-15 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-059 | Acceptance | AC-R-059 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-059 | Activities | A-R-059 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-059 | Rules | R-059 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-059 | Tasks | T-R-059-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-059 | Tasks | T-R-059-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-059 | Tasks | T-R-059-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-059 | WPS | WPS-13 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-060 | Acceptance | AC-R-060 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-060 | Activities | A-R-060 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-060 | Rules | R-060 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-060 | Tasks | T-R-060-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-060 | Tasks | T-R-060-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-060 | Tasks | T-R-060-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-060 | WPS | WPS-13 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-061 | Acceptance | AC-R-061 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-061 | Activities | A-R-061 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-061 | Rules | R-061 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-061 | Tasks | T-R-061-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-061 | Tasks | T-R-061-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-061 | Tasks | T-R-061-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-061 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-062 | Acceptance | AC-R-062 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-062 | Activities | A-R-062 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-062 | Rules | R-062 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-062 | Tasks | T-R-062-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-062 | Tasks | T-R-062-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-062 | Tasks | T-R-062-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-062 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-063 | Acceptance | AC-R-063 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-063 | Activities | A-R-063 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-063 | Rules | R-063 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-063 | Tasks | T-R-063-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-063 | Tasks | T-R-063-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-063 | Tasks | T-R-063-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-063 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-064 | Acceptance | AC-R-064 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-064 | Activities | A-R-064 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-064 | Rules | R-064 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-064 | Tasks | T-R-064-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-064 | Tasks | T-R-064-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-064 | Tasks | T-R-064-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-064 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-065 | Acceptance | AC-R-065 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-065 | Activities | A-R-065 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-065 | Rules | R-065 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-065 | Tasks | T-R-065-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-065 | Tasks | T-R-065-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-065 | Tasks | T-R-065-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-065 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-066 | Acceptance | AC-R-066 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-066 | Activities | A-R-066 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-066 | Rules | R-066 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-066 | Tasks | T-R-066-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-066 | Tasks | T-R-066-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-066 | Tasks | T-R-066-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-066 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-067 | Acceptance | AC-R-067 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-067 | Activities | A-R-067 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-067 | Rules | R-067 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-067 | Tasks | T-R-067-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-067 | Tasks | T-R-067-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-067 | Tasks | T-R-067-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-067 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-068 | Acceptance | AC-R-068 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-068 | Activities | A-R-068 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-068 | Rules | R-068 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-068 | Tasks | T-R-068-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-068 | Tasks | T-R-068-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-068 | Tasks | T-R-068-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-068 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-069 | Acceptance | AC-R-069 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-069 | Activities | A-R-069 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-069 | Rules | R-069 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-069 | Tasks | T-R-069-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-069 | Tasks | T-R-069-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-069 | Tasks | T-R-069-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-069 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-070 | Acceptance | AC-R-070 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-070 | Activities | A-R-070 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-070 | Rules | R-070 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-070 | Tasks | T-R-070-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-070 | Tasks | T-R-070-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-070 | Tasks | T-R-070-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-070 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-071 | Acceptance | AC-R-071 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-071 | Activities | A-R-071 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-071 | Rules | R-071 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-071 | Tasks | T-R-071-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-071 | Tasks | T-R-071-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-071 | Tasks | T-R-071-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-071 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-072 | Acceptance | AC-R-072 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-072 | Activities | A-R-072 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-072 | Rules | R-072 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-072 | Tasks | T-R-072-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-072 | Tasks | T-R-072-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-072 | Tasks | T-R-072-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-072 | WPS | WPS-14 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-073 | Acceptance | AC-R-073 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-073 | Activities | A-R-073 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-073 | Rules | R-073 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-073 | Tasks | T-R-073-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-073 | Tasks | T-R-073-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-073 | Tasks | T-R-073-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-073 | WPS | WPS-14 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-074 | Acceptance | AC-R-074 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-074 | Activities | A-R-074 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-074 | Rules | R-074 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-074 | Tasks | T-R-074-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-074 | Tasks | T-R-074-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-074 | Tasks | T-R-074-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-074 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-075 | Acceptance | AC-R-075 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-075 | Activities | A-R-075 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-075 | Rules | R-075 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-075 | Tasks | T-R-075-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-075 | Tasks | T-R-075-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-075 | Tasks | T-R-075-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-075 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-076 | Acceptance | AC-R-076 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-076 | Activities | A-R-076 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-076 | Rules | R-076 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-076 | Tasks | T-R-076-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-076 | Tasks | T-R-076-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-076 | Tasks | T-R-076-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-076 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-077 | Acceptance | AC-R-077 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-077 | Activities | A-R-077 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-077 | Rules | R-077 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-077 | Tasks | T-R-077-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-077 | Tasks | T-R-077-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-077 | Tasks | T-R-077-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-077 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-078 | Acceptance | AC-R-078 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-078 | Activities | A-R-078 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-078 | Rules | R-078 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-078 | Tasks | T-R-078-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-078 | Tasks | T-R-078-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-078 | Tasks | T-R-078-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-078 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-079 | Acceptance | AC-R-079 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-079 | Activities | A-R-079 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-079 | Rules | R-079 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-079 | Tasks | T-R-079-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-079 | Tasks | T-R-079-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-079 | Tasks | T-R-079-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-079 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-080 | Acceptance | AC-R-080 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-080 | Activities | A-R-080 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-080 | Rules | R-080 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-080 | Tasks | T-R-080-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-080 | Tasks | T-R-080-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-080 | Tasks | T-R-080-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-080 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-081 | Acceptance | AC-R-081 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-081 | Activities | A-R-081 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-081 | Rules | R-081 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-081 | Tasks | T-R-081-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-081 | Tasks | T-R-081-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-081 | Tasks | T-R-081-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-081 | WPS | WPS-02 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-082 | Acceptance | AC-R-082 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-082 | Activities | A-R-082 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-082 | Rules | R-082 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-082 | Tasks | T-R-082-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-082 | Tasks | T-R-082-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-082 | Tasks | T-R-082-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-082 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-083 | Acceptance | AC-R-083 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-083 | Activities | A-R-083 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-083 | Rules | R-083 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-083 | Tasks | T-R-083-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-083 | Tasks | T-R-083-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-083 | Tasks | T-R-083-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-083 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-084 | Acceptance | AC-R-084 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-084 | Activities | A-R-084 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-084 | Rules | R-084 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-084 | Tasks | T-R-084-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-084 | Tasks | T-R-084-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-084 | Tasks | T-R-084-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-084 | WPS | WPS-13 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-085 | Acceptance | AC-R-085 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-085 | Activities | A-R-085 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-085 | Rules | R-085 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-085 | Tasks | T-R-085-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-085 | Tasks | T-R-085-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-085 | Tasks | T-R-085-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-085 | WPS | WPS-11 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-086 | Acceptance | AC-R-086 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-086 | Activities | A-R-086 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-086 | Rules | R-086 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-086 | Tasks | T-R-086-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-086 | Tasks | T-R-086-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-086 | Tasks | T-R-086-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-086 | WPS | WPS-09 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-087 | Acceptance | AC-R-087 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-087 | Activities | A-R-087 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-087 | Rules | R-087 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-087 | Tasks | T-R-087-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-087 | Tasks | T-R-087-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-087 | Tasks | T-R-087-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-087 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-088 | Acceptance | AC-R-088 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-088 | Activities | A-R-088 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-088 | Rules | R-088 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-088 | Tasks | T-R-088-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-088 | Tasks | T-R-088-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-088 | Tasks | T-R-088-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-088 | WPS | WPS-02 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-089 | Acceptance | AC-R-089 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-089 | Activities | A-R-089 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-089 | Rules | R-089 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-089 | Tasks | T-R-089-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-089 | Tasks | T-R-089-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-089 | Tasks | T-R-089-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-089 | WPS | WPS-02 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-090 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-090 | Acceptance | AC-WPS-22-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-090 | Activities | A-R-026 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-090 | Gaps | G-018 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-090 | Gaps | G-019 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-090 | Gaps | G-024 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-090 | Rules | R-026 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-090 | Rules | R-050 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-090 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-090 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-091 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-091 | Acceptance | AC-WPS-22-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-091 | Activities | A-R-026 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-091 | Gaps | G-018 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-091 | Gaps | G-019 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-091 | Gaps | G-024 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-091 | Rules | R-026 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-091 | Rules | R-050 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-091 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-091 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-092 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-092 | Acceptance | AC-WPS-22-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-092 | Activities | A-R-026 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-092 | Gaps | G-018 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-092 | Gaps | G-019 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-092 | Gaps | G-024 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-092 | Rules | R-026 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-092 | Rules | R-050 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-092 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-092 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-093 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-093 | Acceptance | AC-WPS-22-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-093 | Activities | A-R-026 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-093 | Gaps | G-018 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-093 | Gaps | G-019 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-093 | Gaps | G-024 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-093 | Rules | R-026 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-093 | Rules | R-050 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-093 | WPS | WPS-16 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-093 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-094 | Acceptance | AC-R-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-094 | Activities | A-R-001 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-094 | Gaps | G-001 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-094 | Rules | R-001 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-094 | Tasks | T-R-001-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-094 | Tasks | T-R-001-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-094 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-095 | Acceptance | AC-R-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-095 | Activities | A-R-001 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-095 | Gaps | G-001 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-095 | Rules | R-001 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-095 | Tasks | T-R-001-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-095 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-096 | Acceptance | AC-R-001 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-096 | Activities | A-R-001 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-096 | Gaps | G-001 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-096 | Rules | R-001 | Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule IDs
Evidence | E-096 | Tasks | T-R-001-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-096 | Tasks | T-R-001-03 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-096 | WPS | WPS-01 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-17-01 | Acceptance | AC-S-17-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-17-01 | Activities | A-S-17-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-17-01 | Gaps | G-S-17-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-17-01 | Tasks | T-S-17-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-01 | Tasks | T-S-17-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-01 | WPS | WPS-17 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-17-02 | Acceptance | AC-S-17-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-17-02 | Activities | A-S-17-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-17-02 | Gaps | G-S-17-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-17-02 | Tasks | T-S-17-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-02 | Tasks | T-S-17-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-02 | WPS | WPS-17 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-17-03 | Acceptance | AC-S-17-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-17-03 | Activities | A-S-17-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-17-03 | Gaps | G-S-17-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-17-03 | Tasks | T-S-17-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-03 | Tasks | T-S-17-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-03 | WPS | WPS-17 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-17-04 | Acceptance | AC-S-17-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-17-04 | Activities | A-S-17-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-17-04 | Gaps | G-S-17-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-17-04 | Tasks | T-S-17-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-04 | Tasks | T-S-17-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-04 | WPS | WPS-17 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-17-05 | Acceptance | AC-S-17-05 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-17-05 | Activities | A-S-17-05 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-17-05 | Gaps | G-S-17-05 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-17-05 | Tasks | T-S-17-05-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-05 | Tasks | T-S-17-05-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-17-05 | WPS | WPS-17 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-18-01 | Acceptance | AC-S-18-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-18-01 | Activities | A-S-18-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-18-01 | Gaps | G-S-18-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-18-01 | Tasks | T-S-18-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-01 | Tasks | T-S-18-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-01 | WPS | WPS-18 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-18-02 | Acceptance | AC-S-18-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-18-02 | Activities | A-S-18-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-18-02 | Gaps | G-S-18-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-18-02 | Tasks | T-S-18-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-02 | Tasks | T-S-18-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-02 | WPS | WPS-18 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-18-03 | Acceptance | AC-S-18-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-18-03 | Activities | A-S-18-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-18-03 | Gaps | G-S-18-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-18-03 | Tasks | T-S-18-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-03 | Tasks | T-S-18-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-03 | WPS | WPS-18 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-18-04 | Acceptance | AC-S-18-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-18-04 | Activities | A-S-18-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-18-04 | Gaps | G-S-18-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-18-04 | Tasks | T-S-18-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-04 | Tasks | T-S-18-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-04 | WPS | WPS-18 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-18-05 | Acceptance | AC-S-18-05 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-18-05 | Activities | A-S-18-05 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-18-05 | Gaps | G-S-18-05 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-18-05 | Tasks | T-S-18-05-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-05 | Tasks | T-S-18-05-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-18-05 | WPS | WPS-18 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-19-01 | Acceptance | AC-S-19-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-19-01 | Activities | A-S-19-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-19-01 | Gaps | G-S-19-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-19-01 | Tasks | T-S-19-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-01 | Tasks | T-S-19-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-01 | WPS | WPS-19 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-19-02 | Acceptance | AC-S-19-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-19-02 | Activities | A-S-19-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-19-02 | Gaps | G-S-19-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-19-02 | Tasks | T-S-19-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-02 | Tasks | T-S-19-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-02 | WPS | WPS-19 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-19-03 | Acceptance | AC-S-19-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-19-03 | Activities | A-S-19-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-19-03 | Gaps | G-S-19-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-19-03 | Tasks | T-S-19-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-03 | Tasks | T-S-19-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-03 | WPS | WPS-19 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-19-04 | Acceptance | AC-S-19-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-19-04 | Activities | A-S-19-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-19-04 | Gaps | G-S-19-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-19-04 | Tasks | T-S-19-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-04 | Tasks | T-S-19-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-04 | WPS | WPS-19 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-19-05 | Acceptance | AC-S-19-05 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-19-05 | Activities | A-S-19-05 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-19-05 | Gaps | G-S-19-05 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-19-05 | Tasks | T-S-19-05-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-05 | Tasks | T-S-19-05-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-19-05 | WPS | WPS-19 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-20-01 | Acceptance | AC-S-20-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-20-01 | Activities | A-S-20-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-20-01 | Gaps | G-S-20-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-20-01 | Tasks | T-S-20-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-01 | Tasks | T-S-20-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-01 | WPS | WPS-20 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-20-02 | Acceptance | AC-S-20-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-20-02 | Activities | A-S-20-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-20-02 | Gaps | G-S-20-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-20-02 | Tasks | T-S-20-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-02 | Tasks | T-S-20-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-02 | WPS | WPS-20 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-20-03 | Acceptance | AC-S-20-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-20-03 | Activities | A-S-20-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-20-03 | Gaps | G-S-20-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-20-03 | Tasks | T-S-20-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-03 | Tasks | T-S-20-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-03 | WPS | WPS-20 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-20-04 | Acceptance | AC-S-20-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-20-04 | Activities | A-S-20-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-20-04 | Gaps | G-S-20-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-20-04 | Tasks | T-S-20-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-04 | Tasks | T-S-20-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-04 | WPS | WPS-20 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-20-05 | Acceptance | AC-S-20-05 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-20-05 | Activities | A-S-20-05 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-20-05 | Gaps | G-S-20-05 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-20-05 | Tasks | T-S-20-05-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-05 | Tasks | T-S-20-05-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-20-05 | WPS | WPS-20 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-21-01 | Acceptance | AC-S-21-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-21-01 | Activities | A-S-21-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-21-01 | Gaps | G-S-21-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-21-01 | Tasks | T-S-21-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-01 | Tasks | T-S-21-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-01 | WPS | WPS-21 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-21-02 | Acceptance | AC-S-21-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-21-02 | Activities | A-S-21-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-21-02 | Gaps | G-S-21-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-21-02 | Tasks | T-S-21-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-02 | Tasks | T-S-21-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-02 | WPS | WPS-21 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-21-03 | Acceptance | AC-S-21-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-21-03 | Activities | A-S-21-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-21-03 | Gaps | G-S-21-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-21-03 | Tasks | T-S-21-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-03 | Tasks | T-S-21-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-03 | WPS | WPS-21 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-21-04 | Acceptance | AC-S-21-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-21-04 | Activities | A-S-21-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-21-04 | Gaps | G-S-21-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-21-04 | Tasks | T-S-21-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-04 | Tasks | T-S-21-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-04 | WPS | WPS-21 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-21-05 | Acceptance | AC-S-21-05 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-21-05 | Activities | A-S-21-05 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-21-05 | Gaps | G-S-21-05 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-21-05 | Tasks | T-S-21-05-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-05 | Tasks | T-S-21-05-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-21-05 | WPS | WPS-21 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-22-01 | Acceptance | AC-S-22-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-22-01 | Activities | A-S-22-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-22-01 | Gaps | G-S-22-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-22-01 | Tasks | T-S-22-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-01 | Tasks | T-S-22-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-01 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-22-02 | Acceptance | AC-S-22-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-22-02 | Activities | A-S-22-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-22-02 | Gaps | G-S-22-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-22-02 | Tasks | T-S-22-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-02 | Tasks | T-S-22-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-02 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-22-03 | Acceptance | AC-S-22-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-22-03 | Activities | A-S-22-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-22-03 | Gaps | G-S-22-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-22-03 | Tasks | T-S-22-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-03 | Tasks | T-S-22-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-03 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-22-04 | Acceptance | AC-S-22-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-22-04 | Activities | A-S-22-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-22-04 | Gaps | G-S-22-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-22-04 | Tasks | T-S-22-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-04 | Tasks | T-S-22-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-04 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-22-05 | Acceptance | AC-S-22-05 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-22-05 | Activities | A-S-22-05 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-22-05 | Gaps | G-S-22-05 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-22-05 | Tasks | T-S-22-05-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-05 | Tasks | T-S-22-05-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-22-05 | WPS | WPS-22 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-23-01 | Acceptance | AC-S-23-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-23-01 | Activities | A-S-23-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-23-01 | Gaps | G-S-23-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-23-01 | Tasks | T-S-23-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-01 | Tasks | T-S-23-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-01 | WPS | WPS-23 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-23-02 | Acceptance | AC-S-23-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-23-02 | Activities | A-S-23-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-23-02 | Gaps | G-S-23-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-23-02 | Tasks | T-S-23-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-02 | Tasks | T-S-23-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-02 | WPS | WPS-23 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-23-03 | Acceptance | AC-S-23-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-23-03 | Activities | A-S-23-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-23-03 | Gaps | G-S-23-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-23-03 | Tasks | T-S-23-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-03 | Tasks | T-S-23-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-03 | WPS | WPS-23 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-23-04 | Acceptance | AC-S-23-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-23-04 | Activities | A-S-23-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-23-04 | Gaps | G-S-23-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-23-04 | Tasks | T-S-23-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-04 | Tasks | T-S-23-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-23-04 | WPS | WPS-23 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-24-01 | Acceptance | AC-S-24-01 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-24-01 | Activities | A-S-24-01 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-24-01 | Gaps | G-S-24-01 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-24-01 | Tasks | T-S-24-01-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-01 | Tasks | T-S-24-01-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-01 | WPS | WPS-24 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-24-02 | Acceptance | AC-S-24-02 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-24-02 | Activities | A-S-24-02 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-24-02 | Gaps | G-S-24-02 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-24-02 | Tasks | T-S-24-02-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-02 | Tasks | T-S-24-02-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-02 | WPS | WPS-24 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-24-03 | Acceptance | AC-S-24-03 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-24-03 | Activities | A-S-24-03 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-24-03 | Gaps | G-S-24-03 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-24-03 | Tasks | T-S-24-03-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-03 | Tasks | T-S-24-03-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-03 | WPS | WPS-24 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Evidence | E-S-24-04 | Acceptance | AC-S-24-04 | Acceptance Criteria IDs |  |  | SUPPORTS_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Evidence | E-S-24-04 | Activities | A-S-24-04 | Activity IDs |  |  | SUPPORTS_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Activity IDs
Evidence | E-S-24-04 | Gaps | G-S-24-04 | Gap IDs |  |  | SUPPORTS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap IDs
Evidence | E-S-24-04 | Tasks | T-S-24-04-01 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-04 | Tasks | T-S-24-04-02 | Task IDs |  |  | SUPPORTS_TASK | Cross-reference | Optional | Primary |  | SourceField:Task IDs
Evidence | E-S-24-04 | WPS | WPS-24 | WPS IDs |  |  | SUPPORTS_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS IDs
Execution | T-R-001-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-001-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-001-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-002-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-002-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-002-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-003-01 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-003-02 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-003-03 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-004-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-004-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-004-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-005-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-005-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-005-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-006-01 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-006-02 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-006-03 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-007-01 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-007-02 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-007-03 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-008-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-008-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-008-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-009-01 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-009-02 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-009-03 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-010-01 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-010-02 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-010-03 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-011-01 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-011-02 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-011-03 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-012-01 | WPS | WPS-04 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-012-02 | WPS | WPS-04 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-012-03 | WPS | WPS-04 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-013-01 | WPS | WPS-04 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-013-02 | WPS | WPS-04 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-013-03 | WPS | WPS-04 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-014-01 | WPS | WPS-05 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-014-02 | WPS | WPS-05 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-014-03 | WPS | WPS-05 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-015-01 | WPS | WPS-05 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-015-02 | WPS | WPS-05 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-015-03 | WPS | WPS-05 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-016-01 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-016-02 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-016-03 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-017-01 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-017-02 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-017-03 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-018-01 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-018-02 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-018-03 | WPS | WPS-03 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-019-01 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-019-02 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-019-03 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-020-01 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-020-02 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-020-03 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-021-01 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-021-02 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-021-03 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-022-01 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-022-02 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-022-03 | WPS | WPS-06 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-023-01 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-023-02 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-023-03 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-024-01 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-024-02 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-024-03 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-025-01 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-025-02 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-025-03 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-026-01 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-026-02 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-026-03 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-027-01 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-027-02 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-027-03 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-028-01 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-028-02 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-028-03 | WPS | WPS-07 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-029-01 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-029-02 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-029-03 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-030-01 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-030-02 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-030-03 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-031-01 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-031-02 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-031-03 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-032-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-032-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-032-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-033-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-033-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-033-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-034-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-034-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-034-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-035-01 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-035-02 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-035-03 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-036-01 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-036-02 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-036-03 | WPS | WPS-08 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-037-01 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-037-02 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-037-03 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-038-01 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-038-02 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-038-03 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-039-01 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-039-02 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-039-03 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-040-01 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-040-02 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-040-03 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-041-01 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-041-02 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-041-03 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-042-01 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-042-02 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-042-03 | WPS | WPS-10 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-043-01 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-043-02 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-043-03 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-044-01 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-044-02 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-044-03 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-045-01 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-045-02 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-045-03 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-046-01 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-046-02 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-046-03 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-047-01 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-047-02 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-047-03 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-048-01 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-048-02 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-048-03 | WPS | WPS-12 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-049-01 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-049-02 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-049-03 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-050-01 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-050-02 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-050-03 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-051-01 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-051-02 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-051-03 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-052-01 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-052-02 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-052-03 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-053-01 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-053-02 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-053-03 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-054-01 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-054-02 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-054-03 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-055-01 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-055-02 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-055-03 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-056-01 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-056-02 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-056-03 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-057-01 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-057-02 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-057-03 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-058-01 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-058-02 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-058-03 | WPS | WPS-15 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-059-01 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-059-02 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-059-03 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-060-01 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-060-02 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-060-03 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-061-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-061-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-061-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-062-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-062-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-062-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-063-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-063-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-063-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-064-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-064-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-064-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-065-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-065-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-065-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-066-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-066-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-066-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-067-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-067-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-067-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-068-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-068-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-068-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-069-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-069-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-069-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-070-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-070-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-070-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-071-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-071-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-071-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-072-01 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-072-02 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-072-03 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-073-01 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-073-02 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-073-03 | WPS | WPS-14 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-074-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-074-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-074-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-075-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-075-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-075-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-076-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-076-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-076-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-077-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-077-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-077-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-078-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-078-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-078-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-079-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-079-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-079-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-080-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-080-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-080-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-081-01 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-081-02 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-081-03 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-082-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-082-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-082-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-083-01 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-083-02 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-083-03 | WPS | WPS-01 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-084-01 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-084-02 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-084-03 | WPS | WPS-13 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-085-01 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-085-02 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-085-03 | WPS | WPS-11 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-086-01 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-086-02 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-086-03 | WPS | WPS-09 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-087-01 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-087-02 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-087-03 | WPS | WPS-16 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-088-01 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-088-02 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-088-03 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-089-01 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-089-02 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | T-R-089-03 | WPS | WPS-02 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-17-01 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-17-01 | WPS | WPS-17 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-17-02 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-17-02 | WPS | WPS-17 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-17-03 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-17-03 | WPS | WPS-17 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-17-04 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-17-04 | WPS | WPS-17 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-17-05 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-17-05 | WPS | WPS-17 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-18-01 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-18-01 | WPS | WPS-18 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-18-02 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-18-02 | WPS | WPS-18 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-18-03 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-18-03 | WPS | WPS-18 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-18-04 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-18-04 | WPS | WPS-18 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-18-05 | Gates | GATE-1 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-18-05 | WPS | WPS-18 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-19-01 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-19-01 | WPS | WPS-19 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-19-02 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-19-02 | WPS | WPS-19 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-19-03 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-19-03 | WPS | WPS-19 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-19-04 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-19-04 | WPS | WPS-19 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-19-05 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-19-05 | WPS | WPS-19 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-20-01 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-20-01 | WPS | WPS-20 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-20-02 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-20-02 | WPS | WPS-20 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-20-03 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-20-03 | WPS | WPS-20 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-20-04 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-20-04 | WPS | WPS-20 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-20-05 | Gates | GATE-8 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-20-05 | WPS | WPS-20 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-21-01 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-21-01 | WPS | WPS-21 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-21-02 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-21-02 | WPS | WPS-21 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-21-03 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-21-03 | WPS | WPS-21 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-21-04 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-21-04 | WPS | WPS-21 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-21-05 | Gates | GATE-7 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-21-05 | WPS | WPS-21 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-22-01 | Gates | GATE-3 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-22-01 | WPS | WPS-22 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-22-02 | Gates | GATE-3 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-22-02 | WPS | WPS-22 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-22-03 | Gates | GATE-3 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-22-03 | WPS | WPS-22 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-22-04 | Gates | GATE-3 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-22-04 | WPS | WPS-22 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-22-05 | Gates | GATE-3 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-22-05 | WPS | WPS-22 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-23-01 | Gates | GATE-4 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-23-01 | WPS | WPS-23 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-23-02 | Gates | GATE-4 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-23-02 | WPS | WPS-23 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-23-03 | Gates | GATE-4 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-23-03 | WPS | WPS-23 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-23-04 | Gates | GATE-4 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-23-04 | WPS | WPS-23 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-24-01 | Gates | GATE-8 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-24-01 | WPS | WPS-24 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-24-02 | Gates | GATE-8 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-24-02 | WPS | WPS-24 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-24-03 | Gates | GATE-8 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-24-03 | WPS | WPS-24 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Execution | WPS-24-04 | Gates | GATE-8 | Blocking Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocking Gate
Execution | WPS-24-04 | WPS | WPS-24 | WPS ID |  |  | EXECUTES_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Functional | F-EMG-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-EMG-01 | Rules | R-051 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-EMG-01 | Rules | R-052 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-EMG-01 | Rules | R-054 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-EMG-01 | Rules | R-074 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-EMG-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-EMG-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-EMG-02 | Rules | R-051 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-EMG-02 | Rules | R-052 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-EMG-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-FUE-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-FUE-01 | Rules | R-077 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-FUE-01 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-FUE-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-FUE-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-FUE-02 | Rules | R-077 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-FUE-02 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-FUE-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-HEL-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-HEL-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-HEL-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-HEL-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-HEL-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-HEL-03 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-HR-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-HR-01 | Rules | R-055 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-01 | Rules | R-056 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-01 | Rules | R-057 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-01 | Rules | R-058 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-01 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-HR-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-HR-02 | Rules | R-057 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-02 | Rules | R-058 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-02 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-HR-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-HR-03 | Rules | R-079 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-HR-03 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-MOOR-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-MOOR-01 | Rules | R-029 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-01 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-01 | Rules | R-031 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-01 | Rules | R-036 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-01 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-MOOR-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-MOOR-02 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-02 | Rules | R-036 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-02 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-MOOR-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-MOOR-03 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-03 | Rules | R-031 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-MOOR-03 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-PMS-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-PMS-01 | Rules | R-059 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-PMS-01 | Rules | R-060 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-PMS-01 | Rules | R-084 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-PMS-01 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-PMS-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-PMS-02 | Rules | R-059 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-PMS-02 | Rules | R-060 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-PMS-02 | Rules | R-084 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-PMS-02 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-001-01 | Acceptance | AC-R-001 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-001-01 | Activities | A-R-001 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-001-01 | Deliverables | D-R-001 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-001-01 | Gaps | G-001 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-001-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-001-01 | Rules | R-001 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-001-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-001-02 | Acceptance | AC-R-001 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-001-02 | Activities | A-R-001 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-001-02 | Deliverables | D-R-001 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-001-02 | Gaps | G-001 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-001-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-001-02 | Rules | R-001 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-001-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-001-04 | Acceptance | AC-R-001 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-001-04 | Activities | A-R-001 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-001-04 | Deliverables | D-R-001 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-001-04 | Gaps | G-001 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-001-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-001-04 | Rules | R-001 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-001-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-002-01 | Acceptance | AC-R-002 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-002-01 | Activities | A-R-002 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-002-01 | Deliverables | D-R-002 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-002-01 | Gaps | G-002 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-002-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-002-01 | Rules | R-002 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-002-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-002-02 | Acceptance | AC-R-002 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-002-02 | Activities | A-R-002 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-002-02 | Deliverables | D-R-002 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-002-02 | Gaps | G-002 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-002-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-002-02 | Rules | R-002 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-002-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-002-04 | Acceptance | AC-R-002 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-002-04 | Activities | A-R-002 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-002-04 | Deliverables | D-R-002 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-002-04 | Gaps | G-002 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-002-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-002-04 | Rules | R-002 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-002-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-003-01 | Acceptance | AC-R-003 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-003-01 | Activities | A-R-003 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-003-01 | Deliverables | D-R-003 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-003-01 | Gaps | G-003 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-003-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-003-01 | Rules | R-003 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-003-01 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-003-02 | Acceptance | AC-R-003 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-003-02 | Activities | A-R-003 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-003-02 | Deliverables | D-R-003 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-003-02 | Gaps | G-003 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-003-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-003-02 | Rules | R-003 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-003-02 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-003-04 | Acceptance | AC-R-003 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-003-04 | Activities | A-R-003 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-003-04 | Deliverables | D-R-003 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-003-04 | Gaps | G-003 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-003-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-003-04 | Rules | R-003 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-003-04 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-004-01 | Acceptance | AC-R-004 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-004-01 | Activities | A-R-004 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-004-01 | Deliverables | D-R-004 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-004-01 | Gaps | G-004 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-004-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-004-01 | Rules | R-004 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-004-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-004-02 | Acceptance | AC-R-004 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-004-02 | Activities | A-R-004 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-004-02 | Deliverables | D-R-004 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-004-02 | Gaps | G-004 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-004-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-004-02 | Rules | R-004 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-004-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-004-03 | Acceptance | AC-R-004 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-004-03 | Activities | A-R-004 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-004-03 | Deliverables | D-R-004 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-004-03 | Gaps | G-004 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-004-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-004-03 | Rules | R-004 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-004-03 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-004-04 | Acceptance | AC-R-004 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-004-04 | Activities | A-R-004 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-004-04 | Deliverables | D-R-004 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-004-04 | Gaps | G-004 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-004-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-004-04 | Rules | R-004 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-004-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-005-01 | Acceptance | AC-R-005 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-005-01 | Activities | A-R-005 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-005-01 | Deliverables | D-R-005 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-005-01 | Gaps | G-005 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-005-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-005-01 | Rules | R-005 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-005-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-005-02 | Acceptance | AC-R-005 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-005-02 | Activities | A-R-005 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-005-02 | Deliverables | D-R-005 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-005-02 | Gaps | G-005 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-005-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-005-02 | Rules | R-005 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-005-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-005-04 | Acceptance | AC-R-005 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-005-04 | Activities | A-R-005 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-005-04 | Deliverables | D-R-005 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-005-04 | Gaps | G-005 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-005-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-005-04 | Rules | R-005 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-005-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-006-01 | Acceptance | AC-R-006 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-006-01 | Activities | A-R-006 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-006-01 | Deliverables | D-R-006 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-006-01 | Gaps | G-006 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-006-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-006-01 | Rules | R-006 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-006-01 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-006-02 | Acceptance | AC-R-006 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-006-02 | Activities | A-R-006 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-006-02 | Deliverables | D-R-006 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-006-02 | Gaps | G-006 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-006-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-006-02 | Rules | R-006 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-006-02 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-006-03 | Acceptance | AC-R-006 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-006-03 | Activities | A-R-006 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-006-03 | Deliverables | D-R-006 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-006-03 | Gaps | G-006 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-006-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-006-03 | Rules | R-006 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-006-03 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-006-04 | Acceptance | AC-R-006 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-006-04 | Activities | A-R-006 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-006-04 | Deliverables | D-R-006 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-006-04 | Gaps | G-006 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-006-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-006-04 | Rules | R-006 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-006-04 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-007-01 | Acceptance | AC-R-007 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-007-01 | Activities | A-R-007 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-007-01 | Deliverables | D-R-007 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-007-01 | Gaps | G-007 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-007-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-007-01 | Rules | R-007 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-007-01 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-007-02 | Acceptance | AC-R-007 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-007-02 | Activities | A-R-007 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-007-02 | Deliverables | D-R-007 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-007-02 | Gaps | G-007 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-007-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-007-02 | Rules | R-007 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-007-02 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-007-04 | Acceptance | AC-R-007 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-007-04 | Activities | A-R-007 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-007-04 | Deliverables | D-R-007 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-007-04 | Gaps | G-007 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-007-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-007-04 | Rules | R-007 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-007-04 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-008-01 | Acceptance | AC-R-008 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-008-01 | Activities | A-R-008 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-008-01 | Deliverables | D-R-008 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-008-01 | Gaps | G-008 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-008-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-008-01 | Rules | R-008 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-008-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-008-02 | Acceptance | AC-R-008 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-008-02 | Activities | A-R-008 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-008-02 | Deliverables | D-R-008 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-008-02 | Gaps | G-008 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-008-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-008-02 | Rules | R-008 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-008-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-008-04 | Acceptance | AC-R-008 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-008-04 | Activities | A-R-008 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-008-04 | Deliverables | D-R-008 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-008-04 | Gaps | G-008 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-008-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-008-04 | Rules | R-008 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-008-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-009-01 | Acceptance | AC-R-009 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-009-01 | Activities | A-R-009 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-009-01 | Deliverables | D-R-009 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-009-01 | Gaps | G-009 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-009-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-009-01 | Rules | R-009 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-009-01 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-009-02 | Acceptance | AC-R-009 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-009-02 | Activities | A-R-009 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-009-02 | Deliverables | D-R-009 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-009-02 | Gaps | G-009 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-009-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-009-02 | Rules | R-009 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-009-02 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-009-03 | Acceptance | AC-R-009 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-009-03 | Activities | A-R-009 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-009-03 | Deliverables | D-R-009 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-009-03 | Gaps | G-009 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-009-03 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-009-03 | Rules | R-009 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-009-03 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-009-04 | Acceptance | AC-R-009 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-009-04 | Activities | A-R-009 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-009-04 | Deliverables | D-R-009 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-009-04 | Gaps | G-009 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-009-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-009-04 | Rules | R-009 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-009-04 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-010-01 | Acceptance | AC-R-010 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-010-01 | Activities | A-R-010 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-010-01 | Deliverables | D-R-010 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-010-01 | Gaps | G-010 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-010-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-010-01 | Rules | R-010 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-010-01 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-010-02 | Acceptance | AC-R-010 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-010-02 | Activities | A-R-010 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-010-02 | Deliverables | D-R-010 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-010-02 | Gaps | G-010 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-010-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-010-02 | Rules | R-010 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-010-02 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-010-04 | Acceptance | AC-R-010 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-010-04 | Activities | A-R-010 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-010-04 | Deliverables | D-R-010 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-010-04 | Gaps | G-010 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-010-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-010-04 | Rules | R-010 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-010-04 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-011-01 | Acceptance | AC-R-011 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-011-01 | Activities | A-R-011 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-011-01 | Deliverables | D-R-011 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-011-01 | Gaps | G-011 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-011-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-011-01 | Rules | R-011 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-011-01 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-011-02 | Acceptance | AC-R-011 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-011-02 | Activities | A-R-011 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-011-02 | Deliverables | D-R-011 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-011-02 | Gaps | G-011 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-011-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-011-02 | Rules | R-011 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-011-02 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-011-03 | Acceptance | AC-R-011 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-011-03 | Activities | A-R-011 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-011-03 | Deliverables | D-R-011 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-011-03 | Gaps | G-011 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-011-03 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-011-03 | Rules | R-011 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-011-03 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-011-04 | Acceptance | AC-R-011 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-011-04 | Activities | A-R-011 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-011-04 | Deliverables | D-R-011 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-011-04 | Gaps | G-011 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-011-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-011-04 | Rules | R-011 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-011-04 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-012-01 | Acceptance | AC-R-012 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-012-01 | Activities | A-R-012 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-012-01 | Deliverables | D-R-012 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-012-01 | Gaps | G-012 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-012-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-012-01 | Rules | R-012 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-012-01 | WPS | WPS-04 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-012-02 | Acceptance | AC-R-012 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-012-02 | Activities | A-R-012 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-012-02 | Deliverables | D-R-012 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-012-02 | Gaps | G-012 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-012-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-012-02 | Rules | R-012 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-012-02 | WPS | WPS-04 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-012-04 | Acceptance | AC-R-012 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-012-04 | Activities | A-R-012 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-012-04 | Deliverables | D-R-012 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-012-04 | Gaps | G-012 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-012-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-012-04 | Rules | R-012 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-012-04 | WPS | WPS-04 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-013-01 | Acceptance | AC-R-013 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-013-01 | Activities | A-R-013 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-013-01 | Deliverables | D-R-013 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-013-01 | Gaps | G-013 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-013-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-013-01 | Rules | R-013 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-013-01 | WPS | WPS-04 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-013-02 | Acceptance | AC-R-013 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-013-02 | Activities | A-R-013 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-013-02 | Deliverables | D-R-013 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-013-02 | Gaps | G-013 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-013-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-013-02 | Rules | R-013 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-013-02 | WPS | WPS-04 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-013-04 | Acceptance | AC-R-013 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-013-04 | Activities | A-R-013 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-013-04 | Deliverables | D-R-013 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-013-04 | Gaps | G-013 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-013-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-013-04 | Rules | R-013 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-013-04 | WPS | WPS-04 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-014-01 | Acceptance | AC-R-014 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-014-01 | Activities | A-R-014 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-014-01 | Deliverables | D-R-014 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-014-01 | Gaps | G-014 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-014-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-014-01 | Rules | R-014 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-014-01 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-014-02 | Acceptance | AC-R-014 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-014-02 | Activities | A-R-014 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-014-02 | Deliverables | D-R-014 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-014-02 | Gaps | G-014 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-014-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-014-02 | Rules | R-014 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-014-02 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-014-04 | Acceptance | AC-R-014 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-014-04 | Activities | A-R-014 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-014-04 | Deliverables | D-R-014 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-014-04 | Gaps | G-014 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-014-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-014-04 | Rules | R-014 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-014-04 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-015-01 | Acceptance | AC-R-015 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-015-01 | Activities | A-R-015 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-015-01 | Deliverables | D-R-015 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-015-01 | Gaps | G-015 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-015-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-015-01 | Rules | R-015 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-015-01 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-015-02 | Acceptance | AC-R-015 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-015-02 | Activities | A-R-015 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-015-02 | Deliverables | D-R-015 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-015-02 | Gaps | G-015 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-015-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-015-02 | Rules | R-015 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-015-02 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-015-03 | Acceptance | AC-R-015 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-015-03 | Activities | A-R-015 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-015-03 | Deliverables | D-R-015 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-015-03 | Gaps | G-015 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-015-03 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-015-03 | Rules | R-015 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-015-03 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-015-04 | Acceptance | AC-R-015 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-015-04 | Activities | A-R-015 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-015-04 | Deliverables | D-R-015 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-015-04 | Gaps | G-015 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-015-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-015-04 | Rules | R-015 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-015-04 | WPS | WPS-05 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-016-01 | Acceptance | AC-R-016 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-016-01 | Activities | A-R-016 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-016-01 | Deliverables | D-R-016 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-016-01 | Gaps | G-016 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-016-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-016-01 | Rules | R-016 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-016-01 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-016-02 | Acceptance | AC-R-016 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-016-02 | Activities | A-R-016 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-016-02 | Deliverables | D-R-016 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-016-02 | Gaps | G-016 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-016-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-016-02 | Rules | R-016 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-016-02 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-016-03 | Acceptance | AC-R-016 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-016-03 | Activities | A-R-016 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-016-03 | Deliverables | D-R-016 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-016-03 | Gaps | G-016 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-016-03 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-016-03 | Rules | R-016 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-016-03 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-016-04 | Acceptance | AC-R-016 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-016-04 | Activities | A-R-016 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-016-04 | Deliverables | D-R-016 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-016-04 | Gaps | G-016 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-016-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-016-04 | Rules | R-016 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-016-04 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-017-01 | Acceptance | AC-R-017 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-017-01 | Activities | A-R-017 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-017-01 | Deliverables | D-R-017 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-017-01 | Gaps | G-017 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-017-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-017-01 | Rules | R-017 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-017-01 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-017-02 | Acceptance | AC-R-017 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-017-02 | Activities | A-R-017 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-017-02 | Deliverables | D-R-017 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-017-02 | Gaps | G-017 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-017-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-017-02 | Rules | R-017 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-017-02 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-017-03 | Acceptance | AC-R-017 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-017-03 | Activities | A-R-017 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-017-03 | Deliverables | D-R-017 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-017-03 | Gaps | G-017 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-017-03 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-017-03 | Rules | R-017 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-017-03 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-017-04 | Acceptance | AC-R-017 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-017-04 | Activities | A-R-017 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-017-04 | Deliverables | D-R-017 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-017-04 | Gaps | G-017 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-017-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-017-04 | Rules | R-017 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-017-04 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-018-01 | Acceptance | AC-R-018 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-018-01 | Activities | A-R-018 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-018-01 | Deliverables | D-R-018 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-018-01 | Gaps | G-018 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-018-01 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-018-01 | Rules | R-018 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-018-01 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-018-02 | Acceptance | AC-R-018 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-018-02 | Activities | A-R-018 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-018-02 | Deliverables | D-R-018 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-018-02 | Gaps | G-018 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-018-02 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-018-02 | Rules | R-018 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-018-02 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-018-03 | Acceptance | AC-R-018 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-018-03 | Activities | A-R-018 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-018-03 | Deliverables | D-R-018 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-018-03 | Gaps | G-018 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-018-03 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-018-03 | Rules | R-018 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-018-03 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-018-04 | Acceptance | AC-R-018 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-018-04 | Activities | A-R-018 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-018-04 | Deliverables | D-R-018 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-018-04 | Gaps | G-018 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-018-04 | Gates | GATE-2 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-018-04 | Rules | R-018 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-018-04 | WPS | WPS-03 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-019-01 | Acceptance | AC-R-019 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-019-01 | Activities | A-R-019 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-019-01 | Deliverables | D-R-019 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-019-01 | Gaps | G-019 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-019-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-019-01 | Rules | R-019 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-019-01 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-019-02 | Acceptance | AC-R-019 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-019-02 | Activities | A-R-019 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-019-02 | Deliverables | D-R-019 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-019-02 | Gaps | G-019 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-019-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-019-02 | Rules | R-019 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-019-02 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-019-04 | Acceptance | AC-R-019 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-019-04 | Activities | A-R-019 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-019-04 | Deliverables | D-R-019 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-019-04 | Gaps | G-019 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-019-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-019-04 | Rules | R-019 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-019-04 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-020-01 | Acceptance | AC-R-020 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-020-01 | Activities | A-R-020 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-020-01 | Deliverables | D-R-020 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-020-01 | Gaps | G-020 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-020-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-020-01 | Rules | R-020 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-020-01 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-020-02 | Acceptance | AC-R-020 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-020-02 | Activities | A-R-020 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-020-02 | Deliverables | D-R-020 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-020-02 | Gaps | G-020 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-020-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-020-02 | Rules | R-020 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-020-02 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-020-04 | Acceptance | AC-R-020 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-020-04 | Activities | A-R-020 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-020-04 | Deliverables | D-R-020 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-020-04 | Gaps | G-020 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-020-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-020-04 | Rules | R-020 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-020-04 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-021-01 | Acceptance | AC-R-021 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-021-01 | Activities | A-R-021 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-021-01 | Deliverables | D-R-021 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-021-01 | Gaps | G-021 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-021-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-021-01 | Rules | R-021 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-021-01 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-021-02 | Acceptance | AC-R-021 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-021-02 | Activities | A-R-021 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-021-02 | Deliverables | D-R-021 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-021-02 | Gaps | G-021 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-021-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-021-02 | Rules | R-021 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-021-02 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-021-03 | Acceptance | AC-R-021 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-021-03 | Activities | A-R-021 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-021-03 | Deliverables | D-R-021 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-021-03 | Gaps | G-021 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-021-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-021-03 | Rules | R-021 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-021-03 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-021-04 | Acceptance | AC-R-021 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-021-04 | Activities | A-R-021 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-021-04 | Deliverables | D-R-021 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-021-04 | Gaps | G-021 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-021-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-021-04 | Rules | R-021 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-021-04 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-022-01 | Acceptance | AC-R-022 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-022-01 | Activities | A-R-022 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-022-01 | Deliverables | D-R-022 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-022-01 | Gaps | G-022 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-022-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-022-01 | Rules | R-022 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-022-01 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-022-02 | Acceptance | AC-R-022 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-022-02 | Activities | A-R-022 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-022-02 | Deliverables | D-R-022 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-022-02 | Gaps | G-022 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-022-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-022-02 | Rules | R-022 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-022-02 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-022-03 | Acceptance | AC-R-022 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-022-03 | Activities | A-R-022 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-022-03 | Deliverables | D-R-022 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-022-03 | Gaps | G-022 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-022-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-022-03 | Rules | R-022 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-022-03 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-022-04 | Acceptance | AC-R-022 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-022-04 | Activities | A-R-022 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-022-04 | Deliverables | D-R-022 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-022-04 | Gaps | G-022 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-022-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-022-04 | Rules | R-022 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-022-04 | WPS | WPS-06 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-023-01 | Acceptance | AC-R-023 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-023-01 | Activities | A-R-023 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-023-01 | Deliverables | D-R-023 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-023-01 | Gaps | G-023 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-023-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-023-01 | Rules | R-023 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-023-01 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-023-02 | Acceptance | AC-R-023 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-023-02 | Activities | A-R-023 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-023-02 | Deliverables | D-R-023 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-023-02 | Gaps | G-023 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-023-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-023-02 | Rules | R-023 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-023-02 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-023-04 | Acceptance | AC-R-023 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-023-04 | Activities | A-R-023 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-023-04 | Deliverables | D-R-023 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-023-04 | Gaps | G-023 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-023-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-023-04 | Rules | R-023 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-023-04 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-024-01 | Acceptance | AC-R-024 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-024-01 | Activities | A-R-024 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-024-01 | Deliverables | D-R-024 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-024-01 | Gaps | G-024 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-024-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-024-01 | Rules | R-024 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-024-01 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-024-02 | Acceptance | AC-R-024 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-024-02 | Activities | A-R-024 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-024-02 | Deliverables | D-R-024 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-024-02 | Gaps | G-024 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-024-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-024-02 | Rules | R-024 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-024-02 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-024-03 | Acceptance | AC-R-024 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-024-03 | Activities | A-R-024 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-024-03 | Deliverables | D-R-024 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-024-03 | Gaps | G-024 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-024-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-024-03 | Rules | R-024 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-024-03 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-024-04 | Acceptance | AC-R-024 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-024-04 | Activities | A-R-024 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-024-04 | Deliverables | D-R-024 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-024-04 | Gaps | G-024 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-024-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-024-04 | Rules | R-024 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-024-04 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-025-01 | Acceptance | AC-R-025 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-025-01 | Activities | A-R-025 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-025-01 | Deliverables | D-R-025 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-025-01 | Gaps | G-025 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-025-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-025-01 | Rules | R-025 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-025-01 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-025-02 | Acceptance | AC-R-025 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-025-02 | Activities | A-R-025 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-025-02 | Deliverables | D-R-025 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-025-02 | Gaps | G-025 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-025-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-025-02 | Rules | R-025 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-025-02 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-025-04 | Acceptance | AC-R-025 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-025-04 | Activities | A-R-025 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-025-04 | Deliverables | D-R-025 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-025-04 | Gaps | G-025 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-025-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-025-04 | Rules | R-025 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-025-04 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-026-01 | Acceptance | AC-R-026 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-026-01 | Activities | A-R-026 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-026-01 | Deliverables | D-R-026 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-026-01 | Gaps | G-026 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-026-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-026-01 | Rules | R-026 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-026-01 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-026-02 | Acceptance | AC-R-026 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-026-02 | Activities | A-R-026 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-026-02 | Deliverables | D-R-026 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-026-02 | Gaps | G-026 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-026-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-026-02 | Rules | R-026 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-026-02 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-026-04 | Acceptance | AC-R-026 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-026-04 | Activities | A-R-026 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-026-04 | Deliverables | D-R-026 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-026-04 | Gaps | G-026 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-026-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-026-04 | Rules | R-026 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-026-04 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-027-01 | Acceptance | AC-R-027 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-027-01 | Activities | A-R-027 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-027-01 | Deliverables | D-R-027 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-027-01 | Gaps | G-027 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-027-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-027-01 | Rules | R-027 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-027-01 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-027-02 | Acceptance | AC-R-027 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-027-02 | Activities | A-R-027 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-027-02 | Deliverables | D-R-027 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-027-02 | Gaps | G-027 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-027-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-027-02 | Rules | R-027 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-027-02 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-027-04 | Acceptance | AC-R-027 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-027-04 | Activities | A-R-027 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-027-04 | Deliverables | D-R-027 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-027-04 | Gaps | G-027 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-027-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-027-04 | Rules | R-027 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-027-04 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-028-01 | Acceptance | AC-R-028 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-028-01 | Activities | A-R-028 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-028-01 | Deliverables | D-R-028 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-028-01 | Gaps | G-028 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-028-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-028-01 | Rules | R-028 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-028-01 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-028-02 | Acceptance | AC-R-028 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-028-02 | Activities | A-R-028 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-028-02 | Deliverables | D-R-028 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-028-02 | Gaps | G-028 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-028-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-028-02 | Rules | R-028 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-028-02 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-028-03 | Acceptance | AC-R-028 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-028-03 | Activities | A-R-028 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-028-03 | Deliverables | D-R-028 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-028-03 | Gaps | G-028 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-028-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-028-03 | Rules | R-028 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-028-03 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-028-04 | Acceptance | AC-R-028 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-028-04 | Activities | A-R-028 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-028-04 | Deliverables | D-R-028 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-028-04 | Gaps | G-028 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-028-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-028-04 | Rules | R-028 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-028-04 | WPS | WPS-07 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-029-01 | Acceptance | AC-R-029 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-029-01 | Activities | A-R-029 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-029-01 | Deliverables | D-R-029 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-029-01 | Gaps | G-029 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-029-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-029-01 | Rules | R-029 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-029-01 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-029-02 | Acceptance | AC-R-029 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-029-02 | Activities | A-R-029 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-029-02 | Deliverables | D-R-029 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-029-02 | Gaps | G-029 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-029-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-029-02 | Rules | R-029 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-029-02 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-029-03 | Acceptance | AC-R-029 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-029-03 | Activities | A-R-029 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-029-03 | Deliverables | D-R-029 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-029-03 | Gaps | G-029 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-029-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-029-03 | Rules | R-029 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-029-03 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-029-04 | Acceptance | AC-R-029 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-029-04 | Activities | A-R-029 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-029-04 | Deliverables | D-R-029 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-029-04 | Gaps | G-029 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-029-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-029-04 | Rules | R-029 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-029-04 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-030-01 | Acceptance | AC-R-030 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-030-01 | Activities | A-R-030 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-030-01 | Deliverables | D-R-030 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-030-01 | Gaps | G-030 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-030-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-030-01 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-030-01 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-030-02 | Acceptance | AC-R-030 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-030-02 | Activities | A-R-030 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-030-02 | Deliverables | D-R-030 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-030-02 | Gaps | G-030 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-030-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-030-02 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-030-02 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-030-03 | Acceptance | AC-R-030 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-030-03 | Activities | A-R-030 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-030-03 | Deliverables | D-R-030 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-030-03 | Gaps | G-030 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-030-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-030-03 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-030-03 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-030-04 | Acceptance | AC-R-030 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-030-04 | Activities | A-R-030 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-030-04 | Deliverables | D-R-030 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-030-04 | Gaps | G-030 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-030-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-030-04 | Rules | R-030 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-030-04 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-031-01 | Acceptance | AC-R-031 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-031-01 | Activities | A-R-031 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-031-01 | Deliverables | D-R-031 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-031-01 | Gaps | G-031 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-031-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-031-01 | Rules | R-031 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-031-01 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-031-02 | Acceptance | AC-R-031 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-031-02 | Activities | A-R-031 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-031-02 | Deliverables | D-R-031 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-031-02 | Gaps | G-031 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-031-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-031-02 | Rules | R-031 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-031-02 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-031-04 | Acceptance | AC-R-031 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-031-04 | Activities | A-R-031 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-031-04 | Deliverables | D-R-031 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-031-04 | Gaps | G-031 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-031-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-031-04 | Rules | R-031 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-031-04 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-032-01 | Acceptance | AC-R-032 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-032-01 | Activities | A-R-032 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-032-01 | Deliverables | D-R-032 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-032-01 | Gaps | G-032 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-032-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-032-01 | Rules | R-032 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-032-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-032-02 | Acceptance | AC-R-032 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-032-02 | Activities | A-R-032 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-032-02 | Deliverables | D-R-032 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-032-02 | Gaps | G-032 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-032-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-032-02 | Rules | R-032 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-032-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-032-03 | Acceptance | AC-R-032 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-032-03 | Activities | A-R-032 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-032-03 | Deliverables | D-R-032 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-032-03 | Gaps | G-032 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-032-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-032-03 | Rules | R-032 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-032-03 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-032-04 | Acceptance | AC-R-032 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-032-04 | Activities | A-R-032 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-032-04 | Deliverables | D-R-032 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-032-04 | Gaps | G-032 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-032-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-032-04 | Rules | R-032 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-032-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-033-01 | Acceptance | AC-R-033 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-033-01 | Activities | A-R-033 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-033-01 | Deliverables | D-R-033 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-033-01 | Gaps | G-033 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-033-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-033-01 | Rules | R-033 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-033-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-033-02 | Acceptance | AC-R-033 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-033-02 | Activities | A-R-033 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-033-02 | Deliverables | D-R-033 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-033-02 | Gaps | G-033 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-033-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-033-02 | Rules | R-033 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-033-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-033-04 | Acceptance | AC-R-033 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-033-04 | Activities | A-R-033 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-033-04 | Deliverables | D-R-033 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-033-04 | Gaps | G-033 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-033-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-033-04 | Rules | R-033 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-033-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-034-01 | Acceptance | AC-R-034 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-034-01 | Activities | A-R-034 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-034-01 | Deliverables | D-R-034 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-034-01 | Gaps | G-034 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-034-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-034-01 | Rules | R-034 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-034-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-034-02 | Acceptance | AC-R-034 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-034-02 | Activities | A-R-034 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-034-02 | Deliverables | D-R-034 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-034-02 | Gaps | G-034 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-034-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-034-02 | Rules | R-034 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-034-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-034-04 | Acceptance | AC-R-034 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-034-04 | Activities | A-R-034 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-034-04 | Deliverables | D-R-034 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-034-04 | Gaps | G-034 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-034-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-034-04 | Rules | R-034 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-034-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-035-01 | Acceptance | AC-R-035 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-035-01 | Activities | A-R-035 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-035-01 | Deliverables | D-R-035 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-035-01 | Gaps | G-035 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-035-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-035-01 | Rules | R-035 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-035-01 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-035-02 | Acceptance | AC-R-035 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-035-02 | Activities | A-R-035 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-035-02 | Deliverables | D-R-035 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-035-02 | Gaps | G-035 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-035-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-035-02 | Rules | R-035 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-035-02 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-035-04 | Acceptance | AC-R-035 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-035-04 | Activities | A-R-035 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-035-04 | Deliverables | D-R-035 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-035-04 | Gaps | G-035 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-035-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-035-04 | Rules | R-035 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-035-04 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-036-01 | Acceptance | AC-R-036 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-036-01 | Activities | A-R-036 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-036-01 | Deliverables | D-R-036 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-036-01 | Gaps | G-036 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-036-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-036-01 | Rules | R-036 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-036-01 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-036-02 | Acceptance | AC-R-036 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-036-02 | Activities | A-R-036 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-036-02 | Deliverables | D-R-036 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-036-02 | Gaps | G-036 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-036-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-036-02 | Rules | R-036 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-036-02 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-036-04 | Acceptance | AC-R-036 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-036-04 | Activities | A-R-036 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-036-04 | Deliverables | D-R-036 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-036-04 | Gaps | G-036 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-036-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-036-04 | Rules | R-036 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-036-04 | WPS | WPS-08 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-037-01 | Acceptance | AC-R-037 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-037-01 | Activities | A-R-037 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-037-01 | Deliverables | D-R-037 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-037-01 | Gaps | G-037 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-037-01 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-037-01 | Rules | R-037 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-037-01 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-037-02 | Acceptance | AC-R-037 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-037-02 | Activities | A-R-037 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-037-02 | Deliverables | D-R-037 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-037-02 | Gaps | G-037 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-037-02 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-037-02 | Rules | R-037 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-037-02 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-037-04 | Acceptance | AC-R-037 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-037-04 | Activities | A-R-037 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-037-04 | Deliverables | D-R-037 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-037-04 | Gaps | G-037 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-037-04 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-037-04 | Rules | R-037 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-037-04 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-038-01 | Acceptance | AC-R-038 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-038-01 | Activities | A-R-038 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-038-01 | Deliverables | D-R-038 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-038-01 | Gaps | G-038 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-038-01 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-038-01 | Rules | R-038 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-038-01 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-038-02 | Acceptance | AC-R-038 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-038-02 | Activities | A-R-038 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-038-02 | Deliverables | D-R-038 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-038-02 | Gaps | G-038 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-038-02 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-038-02 | Rules | R-038 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-038-02 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-038-03 | Acceptance | AC-R-038 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-038-03 | Activities | A-R-038 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-038-03 | Deliverables | D-R-038 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-038-03 | Gaps | G-038 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-038-03 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-038-03 | Rules | R-038 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-038-03 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-038-04 | Acceptance | AC-R-038 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-038-04 | Activities | A-R-038 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-038-04 | Deliverables | D-R-038 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-038-04 | Gaps | G-038 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-038-04 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-038-04 | Rules | R-038 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-038-04 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-039-01 | Acceptance | AC-R-039 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-039-01 | Activities | A-R-039 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-039-01 | Deliverables | D-R-039 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-039-01 | Gaps | G-039 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-039-01 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-039-01 | Rules | R-039 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-039-01 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-039-02 | Acceptance | AC-R-039 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-039-02 | Activities | A-R-039 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-039-02 | Deliverables | D-R-039 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-039-02 | Gaps | G-039 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-039-02 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-039-02 | Rules | R-039 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-039-02 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-039-03 | Acceptance | AC-R-039 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-039-03 | Activities | A-R-039 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-039-03 | Deliverables | D-R-039 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-039-03 | Gaps | G-039 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-039-03 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-039-03 | Rules | R-039 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-039-03 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-039-04 | Acceptance | AC-R-039 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-039-04 | Activities | A-R-039 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-039-04 | Deliverables | D-R-039 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-039-04 | Gaps | G-039 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-039-04 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-039-04 | Rules | R-039 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-039-04 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-040-01 | Acceptance | AC-R-040 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-040-01 | Activities | A-R-040 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-040-01 | Deliverables | D-R-040 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-040-01 | Gaps | G-040 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-040-01 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-040-01 | Rules | R-040 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-040-01 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-040-02 | Acceptance | AC-R-040 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-040-02 | Activities | A-R-040 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-040-02 | Deliverables | D-R-040 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-040-02 | Gaps | G-040 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-040-02 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-040-02 | Rules | R-040 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-040-02 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-040-04 | Acceptance | AC-R-040 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-040-04 | Activities | A-R-040 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-040-04 | Deliverables | D-R-040 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-040-04 | Gaps | G-040 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-040-04 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-040-04 | Rules | R-040 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-040-04 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-041-01 | Acceptance | AC-R-041 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-041-01 | Activities | A-R-041 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-041-01 | Deliverables | D-R-041 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-041-01 | Gaps | G-041 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-041-01 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-041-01 | Rules | R-041 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-041-01 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-041-02 | Acceptance | AC-R-041 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-041-02 | Activities | A-R-041 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-041-02 | Deliverables | D-R-041 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-041-02 | Gaps | G-041 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-041-02 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-041-02 | Rules | R-041 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-041-02 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-041-04 | Acceptance | AC-R-041 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-041-04 | Activities | A-R-041 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-041-04 | Deliverables | D-R-041 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-041-04 | Gaps | G-041 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-041-04 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-041-04 | Rules | R-041 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-041-04 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-042-01 | Acceptance | AC-R-042 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-042-01 | Activities | A-R-042 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-042-01 | Deliverables | D-R-042 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-042-01 | Gaps | G-042 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-042-01 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-042-01 | Rules | R-042 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-042-01 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-042-02 | Acceptance | AC-R-042 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-042-02 | Activities | A-R-042 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-042-02 | Deliverables | D-R-042 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-042-02 | Gaps | G-042 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-042-02 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-042-02 | Rules | R-042 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-042-02 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-042-03 | Acceptance | AC-R-042 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-042-03 | Activities | A-R-042 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-042-03 | Deliverables | D-R-042 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-042-03 | Gaps | G-042 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-042-03 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-042-03 | Rules | R-042 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-042-03 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-042-04 | Acceptance | AC-R-042 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-042-04 | Activities | A-R-042 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-042-04 | Deliverables | D-R-042 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-042-04 | Gaps | G-042 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-042-04 | Gates | GATE-5 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-042-04 | Rules | R-042 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-042-04 | WPS | WPS-10 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-043-01 | Acceptance | AC-R-043 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-043-01 | Activities | A-R-043 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-043-01 | Deliverables | D-R-043 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-043-01 | Gaps | G-043 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-043-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-043-01 | Rules | R-043 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-043-01 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-043-02 | Acceptance | AC-R-043 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-043-02 | Activities | A-R-043 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-043-02 | Deliverables | D-R-043 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-043-02 | Gaps | G-043 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-043-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-043-02 | Rules | R-043 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-043-02 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-043-03 | Acceptance | AC-R-043 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-043-03 | Activities | A-R-043 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-043-03 | Deliverables | D-R-043 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-043-03 | Gaps | G-043 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-043-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-043-03 | Rules | R-043 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-043-03 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-043-04 | Acceptance | AC-R-043 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-043-04 | Activities | A-R-043 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-043-04 | Deliverables | D-R-043 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-043-04 | Gaps | G-043 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-043-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-043-04 | Rules | R-043 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-043-04 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-044-01 | Acceptance | AC-R-044 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-044-01 | Activities | A-R-044 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-044-01 | Deliverables | D-R-044 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-044-01 | Gaps | G-044 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-044-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-044-01 | Rules | R-044 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-044-01 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-044-02 | Acceptance | AC-R-044 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-044-02 | Activities | A-R-044 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-044-02 | Deliverables | D-R-044 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-044-02 | Gaps | G-044 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-044-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-044-02 | Rules | R-044 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-044-02 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-044-03 | Acceptance | AC-R-044 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-044-03 | Activities | A-R-044 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-044-03 | Deliverables | D-R-044 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-044-03 | Gaps | G-044 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-044-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-044-03 | Rules | R-044 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-044-03 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-044-04 | Acceptance | AC-R-044 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-044-04 | Activities | A-R-044 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-044-04 | Deliverables | D-R-044 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-044-04 | Gaps | G-044 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-044-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-044-04 | Rules | R-044 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-044-04 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-045-01 | Acceptance | AC-R-045 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-045-01 | Activities | A-R-045 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-045-01 | Deliverables | D-R-045 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-045-01 | Gaps | G-045 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-045-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-045-01 | Rules | R-045 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-045-01 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-045-02 | Acceptance | AC-R-045 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-045-02 | Activities | A-R-045 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-045-02 | Deliverables | D-R-045 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-045-02 | Gaps | G-045 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-045-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-045-02 | Rules | R-045 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-045-02 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-045-03 | Acceptance | AC-R-045 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-045-03 | Activities | A-R-045 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-045-03 | Deliverables | D-R-045 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-045-03 | Gaps | G-045 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-045-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-045-03 | Rules | R-045 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-045-03 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-045-04 | Acceptance | AC-R-045 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-045-04 | Activities | A-R-045 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-045-04 | Deliverables | D-R-045 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-045-04 | Gaps | G-045 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-045-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-045-04 | Rules | R-045 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-045-04 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-046-01 | Acceptance | AC-R-046 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-046-01 | Activities | A-R-046 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-046-01 | Deliverables | D-R-046 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-046-01 | Gaps | G-046 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-046-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-046-01 | Rules | R-046 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-046-01 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-046-02 | Acceptance | AC-R-046 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-046-02 | Activities | A-R-046 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-046-02 | Deliverables | D-R-046 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-046-02 | Gaps | G-046 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-046-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-046-02 | Rules | R-046 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-046-02 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-046-04 | Acceptance | AC-R-046 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-046-04 | Activities | A-R-046 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-046-04 | Deliverables | D-R-046 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-046-04 | Gaps | G-046 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-046-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-046-04 | Rules | R-046 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-046-04 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-047-01 | Acceptance | AC-R-047 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-047-01 | Activities | A-R-047 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-047-01 | Deliverables | D-R-047 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-047-01 | Gaps | G-047 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-047-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-047-01 | Rules | R-047 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-047-01 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-047-02 | Acceptance | AC-R-047 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-047-02 | Activities | A-R-047 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-047-02 | Deliverables | D-R-047 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-047-02 | Gaps | G-047 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-047-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-047-02 | Rules | R-047 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-047-02 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-047-03 | Acceptance | AC-R-047 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-047-03 | Activities | A-R-047 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-047-03 | Deliverables | D-R-047 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-047-03 | Gaps | G-047 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-047-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-047-03 | Rules | R-047 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-047-03 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-047-04 | Acceptance | AC-R-047 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-047-04 | Activities | A-R-047 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-047-04 | Deliverables | D-R-047 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-047-04 | Gaps | G-047 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-047-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-047-04 | Rules | R-047 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-047-04 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-048-01 | Acceptance | AC-R-048 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-048-01 | Activities | A-R-048 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-048-01 | Deliverables | D-R-048 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-048-01 | Gaps | G-048 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-048-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-048-01 | Rules | R-048 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-048-01 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-048-02 | Acceptance | AC-R-048 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-048-02 | Activities | A-R-048 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-048-02 | Deliverables | D-R-048 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-048-02 | Gaps | G-048 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-048-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-048-02 | Rules | R-048 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-048-02 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-048-03 | Acceptance | AC-R-048 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-048-03 | Activities | A-R-048 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-048-03 | Deliverables | D-R-048 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-048-03 | Gaps | G-048 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-048-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-048-03 | Rules | R-048 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-048-03 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-048-04 | Acceptance | AC-R-048 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-048-04 | Activities | A-R-048 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-048-04 | Deliverables | D-R-048 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-048-04 | Gaps | G-048 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-048-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-048-04 | Rules | R-048 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-048-04 | WPS | WPS-12 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-049-01 | Acceptance | AC-R-049 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-049-01 | Activities | A-R-049 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-049-01 | Deliverables | D-R-049 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-049-01 | Gaps | G-049 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-049-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-049-01 | Rules | R-049 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-049-01 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-049-02 | Acceptance | AC-R-049 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-049-02 | Activities | A-R-049 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-049-02 | Deliverables | D-R-049 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-049-02 | Gaps | G-049 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-049-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-049-02 | Rules | R-049 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-049-02 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-049-04 | Acceptance | AC-R-049 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-049-04 | Activities | A-R-049 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-049-04 | Deliverables | D-R-049 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-049-04 | Gaps | G-049 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-049-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-049-04 | Rules | R-049 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-049-04 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-050-01 | Acceptance | AC-R-050 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-050-01 | Activities | A-R-050 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-050-01 | Deliverables | D-R-050 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-050-01 | Gaps | G-050 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-050-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-050-01 | Rules | R-050 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-050-01 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-050-02 | Acceptance | AC-R-050 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-050-02 | Activities | A-R-050 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-050-02 | Deliverables | D-R-050 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-050-02 | Gaps | G-050 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-050-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-050-02 | Rules | R-050 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-050-02 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-050-04 | Acceptance | AC-R-050 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-050-04 | Activities | A-R-050 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-050-04 | Deliverables | D-R-050 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-050-04 | Gaps | G-050 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-050-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-050-04 | Rules | R-050 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-050-04 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-051-01 | Acceptance | AC-R-051 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-051-01 | Activities | A-R-051 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-051-01 | Deliverables | D-R-051 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-051-01 | Gaps | G-051 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-051-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-051-01 | Rules | R-051 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-051-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-051-02 | Acceptance | AC-R-051 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-051-02 | Activities | A-R-051 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-051-02 | Deliverables | D-R-051 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-051-02 | Gaps | G-051 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-051-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-051-02 | Rules | R-051 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-051-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-051-03 | Acceptance | AC-R-051 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-051-03 | Activities | A-R-051 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-051-03 | Deliverables | D-R-051 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-051-03 | Gaps | G-051 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-051-03 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-051-03 | Rules | R-051 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-051-03 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-051-04 | Acceptance | AC-R-051 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-051-04 | Activities | A-R-051 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-051-04 | Deliverables | D-R-051 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-051-04 | Gaps | G-051 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-051-04 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-051-04 | Rules | R-051 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-051-04 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-052-01 | Acceptance | AC-R-052 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-052-01 | Activities | A-R-052 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-052-01 | Deliverables | D-R-052 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-052-01 | Gaps | G-052 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-052-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-052-01 | Rules | R-052 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-052-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-052-02 | Acceptance | AC-R-052 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-052-02 | Activities | A-R-052 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-052-02 | Deliverables | D-R-052 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-052-02 | Gaps | G-052 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-052-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-052-02 | Rules | R-052 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-052-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-052-04 | Acceptance | AC-R-052 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-052-04 | Activities | A-R-052 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-052-04 | Deliverables | D-R-052 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-052-04 | Gaps | G-052 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-052-04 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-052-04 | Rules | R-052 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-052-04 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-053-01 | Acceptance | AC-R-053 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-053-01 | Activities | A-R-053 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-053-01 | Deliverables | D-R-053 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-053-01 | Gaps | G-053 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-053-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-053-01 | Rules | R-053 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-053-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-053-02 | Acceptance | AC-R-053 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-053-02 | Activities | A-R-053 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-053-02 | Deliverables | D-R-053 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-053-02 | Gaps | G-053 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-053-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-053-02 | Rules | R-053 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-053-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-053-03 | Acceptance | AC-R-053 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-053-03 | Activities | A-R-053 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-053-03 | Deliverables | D-R-053 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-053-03 | Gaps | G-053 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-053-03 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-053-03 | Rules | R-053 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-053-03 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-053-04 | Acceptance | AC-R-053 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-053-04 | Activities | A-R-053 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-053-04 | Deliverables | D-R-053 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-053-04 | Gaps | G-053 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-053-04 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-053-04 | Rules | R-053 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-053-04 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-054-01 | Acceptance | AC-R-054 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-054-01 | Activities | A-R-054 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-054-01 | Deliverables | D-R-054 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-054-01 | Gaps | G-054 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-054-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-054-01 | Rules | R-054 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-054-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-054-02 | Acceptance | AC-R-054 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-054-02 | Activities | A-R-054 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-054-02 | Deliverables | D-R-054 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-054-02 | Gaps | G-054 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-054-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-054-02 | Rules | R-054 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-054-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-054-04 | Acceptance | AC-R-054 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-054-04 | Activities | A-R-054 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-054-04 | Deliverables | D-R-054 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-054-04 | Gaps | G-054 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-054-04 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-054-04 | Rules | R-054 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-054-04 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-055-01 | Acceptance | AC-R-055 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-055-01 | Activities | A-R-055 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-055-01 | Deliverables | D-R-055 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-055-01 | Gaps | G-055 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-055-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-055-01 | Rules | R-055 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-055-01 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-055-02 | Acceptance | AC-R-055 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-055-02 | Activities | A-R-055 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-055-02 | Deliverables | D-R-055 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-055-02 | Gaps | G-055 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-055-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-055-02 | Rules | R-055 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-055-02 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-055-04 | Acceptance | AC-R-055 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-055-04 | Activities | A-R-055 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-055-04 | Deliverables | D-R-055 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-055-04 | Gaps | G-055 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-055-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-055-04 | Rules | R-055 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-055-04 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-056-01 | Acceptance | AC-R-056 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-056-01 | Activities | A-R-056 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-056-01 | Deliverables | D-R-056 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-056-01 | Gaps | G-056 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-056-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-056-01 | Rules | R-056 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-056-01 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-056-02 | Acceptance | AC-R-056 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-056-02 | Activities | A-R-056 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-056-02 | Deliverables | D-R-056 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-056-02 | Gaps | G-056 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-056-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-056-02 | Rules | R-056 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-056-02 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-056-04 | Acceptance | AC-R-056 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-056-04 | Activities | A-R-056 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-056-04 | Deliverables | D-R-056 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-056-04 | Gaps | G-056 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-056-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-056-04 | Rules | R-056 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-056-04 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-057-01 | Acceptance | AC-R-057 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-057-01 | Activities | A-R-057 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-057-01 | Deliverables | D-R-057 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-057-01 | Gaps | G-057 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-057-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-057-01 | Rules | R-057 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-057-01 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-057-02 | Acceptance | AC-R-057 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-057-02 | Activities | A-R-057 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-057-02 | Deliverables | D-R-057 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-057-02 | Gaps | G-057 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-057-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-057-02 | Rules | R-057 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-057-02 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-057-04 | Acceptance | AC-R-057 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-057-04 | Activities | A-R-057 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-057-04 | Deliverables | D-R-057 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-057-04 | Gaps | G-057 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-057-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-057-04 | Rules | R-057 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-057-04 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-058-01 | Acceptance | AC-R-058 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-058-01 | Activities | A-R-058 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-058-01 | Deliverables | D-R-058 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-058-01 | Gaps | G-058 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-058-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-058-01 | Rules | R-058 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-058-01 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-058-02 | Acceptance | AC-R-058 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-058-02 | Activities | A-R-058 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-058-02 | Deliverables | D-R-058 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-058-02 | Gaps | G-058 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-058-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-058-02 | Rules | R-058 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-058-02 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-058-03 | Acceptance | AC-R-058 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-058-03 | Activities | A-R-058 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-058-03 | Deliverables | D-R-058 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-058-03 | Gaps | G-058 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-058-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-058-03 | Rules | R-058 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-058-03 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-058-04 | Acceptance | AC-R-058 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-058-04 | Activities | A-R-058 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-058-04 | Deliverables | D-R-058 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-058-04 | Gaps | G-058 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-058-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-058-04 | Rules | R-058 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-058-04 | WPS | WPS-15 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-059-01 | Acceptance | AC-R-059 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-059-01 | Activities | A-R-059 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-059-01 | Deliverables | D-R-059 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-059-01 | Gaps | G-059 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-059-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-059-01 | Rules | R-059 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-059-01 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-059-02 | Acceptance | AC-R-059 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-059-02 | Activities | A-R-059 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-059-02 | Deliverables | D-R-059 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-059-02 | Gaps | G-059 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-059-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-059-02 | Rules | R-059 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-059-02 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-059-03 | Acceptance | AC-R-059 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-059-03 | Activities | A-R-059 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-059-03 | Deliverables | D-R-059 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-059-03 | Gaps | G-059 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-059-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-059-03 | Rules | R-059 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-059-03 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-059-04 | Acceptance | AC-R-059 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-059-04 | Activities | A-R-059 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-059-04 | Deliverables | D-R-059 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-059-04 | Gaps | G-059 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-059-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-059-04 | Rules | R-059 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-059-04 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-060-01 | Acceptance | AC-R-060 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-060-01 | Activities | A-R-060 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-060-01 | Deliverables | D-R-060 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-060-01 | Gaps | G-060 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-060-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-060-01 | Rules | R-060 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-060-01 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-060-02 | Acceptance | AC-R-060 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-060-02 | Activities | A-R-060 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-060-02 | Deliverables | D-R-060 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-060-02 | Gaps | G-060 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-060-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-060-02 | Rules | R-060 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-060-02 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-060-03 | Acceptance | AC-R-060 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-060-03 | Activities | A-R-060 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-060-03 | Deliverables | D-R-060 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-060-03 | Gaps | G-060 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-060-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-060-03 | Rules | R-060 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-060-03 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-060-04 | Acceptance | AC-R-060 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-060-04 | Activities | A-R-060 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-060-04 | Deliverables | D-R-060 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-060-04 | Gaps | G-060 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-060-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-060-04 | Rules | R-060 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-060-04 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-061-01 | Acceptance | AC-R-061 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-061-01 | Activities | A-R-061 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-061-01 | Deliverables | D-R-061 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-061-01 | Gaps | G-061 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-061-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-061-01 | Rules | R-061 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-061-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-061-02 | Acceptance | AC-R-061 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-061-02 | Activities | A-R-061 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-061-02 | Deliverables | D-R-061 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-061-02 | Gaps | G-061 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-061-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-061-02 | Rules | R-061 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-061-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-061-03 | Acceptance | AC-R-061 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-061-03 | Activities | A-R-061 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-061-03 | Deliverables | D-R-061 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-061-03 | Gaps | G-061 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-061-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-061-03 | Rules | R-061 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-061-03 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-061-04 | Acceptance | AC-R-061 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-061-04 | Activities | A-R-061 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-061-04 | Deliverables | D-R-061 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-061-04 | Gaps | G-061 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-061-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-061-04 | Rules | R-061 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-061-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-062-01 | Acceptance | AC-R-062 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-062-01 | Activities | A-R-062 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-062-01 | Deliverables | D-R-062 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-062-01 | Gaps | G-062 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-062-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-062-01 | Rules | R-062 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-062-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-062-02 | Acceptance | AC-R-062 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-062-02 | Activities | A-R-062 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-062-02 | Deliverables | D-R-062 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-062-02 | Gaps | G-062 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-062-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-062-02 | Rules | R-062 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-062-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-062-03 | Acceptance | AC-R-062 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-062-03 | Activities | A-R-062 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-062-03 | Deliverables | D-R-062 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-062-03 | Gaps | G-062 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-062-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-062-03 | Rules | R-062 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-062-03 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-062-04 | Acceptance | AC-R-062 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-062-04 | Activities | A-R-062 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-062-04 | Deliverables | D-R-062 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-062-04 | Gaps | G-062 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-062-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-062-04 | Rules | R-062 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-062-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-063-01 | Acceptance | AC-R-063 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-063-01 | Activities | A-R-063 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-063-01 | Deliverables | D-R-063 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-063-01 | Gaps | G-063 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-063-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-063-01 | Rules | R-063 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-063-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-063-02 | Acceptance | AC-R-063 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-063-02 | Activities | A-R-063 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-063-02 | Deliverables | D-R-063 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-063-02 | Gaps | G-063 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-063-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-063-02 | Rules | R-063 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-063-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-063-04 | Acceptance | AC-R-063 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-063-04 | Activities | A-R-063 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-063-04 | Deliverables | D-R-063 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-063-04 | Gaps | G-063 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-063-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-063-04 | Rules | R-063 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-063-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-064-01 | Acceptance | AC-R-064 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-064-01 | Activities | A-R-064 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-064-01 | Deliverables | D-R-064 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-064-01 | Gaps | G-064 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-064-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-064-01 | Rules | R-064 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-064-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-064-02 | Acceptance | AC-R-064 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-064-02 | Activities | A-R-064 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-064-02 | Deliverables | D-R-064 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-064-02 | Gaps | G-064 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-064-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-064-02 | Rules | R-064 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-064-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-064-04 | Acceptance | AC-R-064 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-064-04 | Activities | A-R-064 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-064-04 | Deliverables | D-R-064 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-064-04 | Gaps | G-064 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-064-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-064-04 | Rules | R-064 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-064-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-065-01 | Acceptance | AC-R-065 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-065-01 | Activities | A-R-065 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-065-01 | Deliverables | D-R-065 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-065-01 | Gaps | G-065 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-065-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-065-01 | Rules | R-065 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-065-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-065-02 | Acceptance | AC-R-065 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-065-02 | Activities | A-R-065 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-065-02 | Deliverables | D-R-065 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-065-02 | Gaps | G-065 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-065-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-065-02 | Rules | R-065 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-065-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-065-03 | Acceptance | AC-R-065 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-065-03 | Activities | A-R-065 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-065-03 | Deliverables | D-R-065 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-065-03 | Gaps | G-065 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-065-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-065-03 | Rules | R-065 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-065-03 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-065-04 | Acceptance | AC-R-065 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-065-04 | Activities | A-R-065 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-065-04 | Deliverables | D-R-065 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-065-04 | Gaps | G-065 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-065-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-065-04 | Rules | R-065 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-065-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-066-01 | Acceptance | AC-R-066 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-066-01 | Activities | A-R-066 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-066-01 | Deliverables | D-R-066 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-066-01 | Gaps | G-066 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-066-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-066-01 | Rules | R-066 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-066-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-066-02 | Acceptance | AC-R-066 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-066-02 | Activities | A-R-066 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-066-02 | Deliverables | D-R-066 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-066-02 | Gaps | G-066 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-066-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-066-02 | Rules | R-066 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-066-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-066-04 | Acceptance | AC-R-066 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-066-04 | Activities | A-R-066 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-066-04 | Deliverables | D-R-066 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-066-04 | Gaps | G-066 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-066-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-066-04 | Rules | R-066 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-066-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-067-01 | Acceptance | AC-R-067 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-067-01 | Activities | A-R-067 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-067-01 | Deliverables | D-R-067 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-067-01 | Gaps | G-067 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-067-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-067-01 | Rules | R-067 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-067-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-067-02 | Acceptance | AC-R-067 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-067-02 | Activities | A-R-067 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-067-02 | Deliverables | D-R-067 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-067-02 | Gaps | G-067 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-067-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-067-02 | Rules | R-067 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-067-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-067-04 | Acceptance | AC-R-067 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-067-04 | Activities | A-R-067 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-067-04 | Deliverables | D-R-067 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-067-04 | Gaps | G-067 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-067-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-067-04 | Rules | R-067 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-067-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-068-01 | Acceptance | AC-R-068 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-068-01 | Activities | A-R-068 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-068-01 | Deliverables | D-R-068 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-068-01 | Gaps | G-068 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-068-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-068-01 | Rules | R-068 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-068-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-068-02 | Acceptance | AC-R-068 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-068-02 | Activities | A-R-068 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-068-02 | Deliverables | D-R-068 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-068-02 | Gaps | G-068 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-068-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-068-02 | Rules | R-068 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-068-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-068-04 | Acceptance | AC-R-068 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-068-04 | Activities | A-R-068 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-068-04 | Deliverables | D-R-068 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-068-04 | Gaps | G-068 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-068-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-068-04 | Rules | R-068 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-068-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-069-01 | Acceptance | AC-R-069 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-069-01 | Activities | A-R-069 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-069-01 | Deliverables | D-R-069 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-069-01 | Gaps | G-069 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-069-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-069-01 | Rules | R-069 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-069-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-069-02 | Acceptance | AC-R-069 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-069-02 | Activities | A-R-069 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-069-02 | Deliverables | D-R-069 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-069-02 | Gaps | G-069 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-069-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-069-02 | Rules | R-069 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-069-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-069-04 | Acceptance | AC-R-069 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-069-04 | Activities | A-R-069 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-069-04 | Deliverables | D-R-069 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-069-04 | Gaps | G-069 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-069-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-069-04 | Rules | R-069 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-069-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-070-01 | Acceptance | AC-R-070 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-070-01 | Activities | A-R-070 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-070-01 | Deliverables | D-R-070 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-070-01 | Gaps | G-070 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-070-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-070-01 | Rules | R-070 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-070-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-070-02 | Acceptance | AC-R-070 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-070-02 | Activities | A-R-070 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-070-02 | Deliverables | D-R-070 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-070-02 | Gaps | G-070 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-070-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-070-02 | Rules | R-070 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-070-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-070-04 | Acceptance | AC-R-070 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-070-04 | Activities | A-R-070 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-070-04 | Deliverables | D-R-070 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-070-04 | Gaps | G-070 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-070-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-070-04 | Rules | R-070 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-070-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-071-01 | Acceptance | AC-R-071 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-071-01 | Activities | A-R-071 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-071-01 | Deliverables | D-R-071 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-071-01 | Gaps | G-071 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-071-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-071-01 | Rules | R-071 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-071-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-071-02 | Acceptance | AC-R-071 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-071-02 | Activities | A-R-071 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-071-02 | Deliverables | D-R-071 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-071-02 | Gaps | G-071 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-071-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-071-02 | Rules | R-071 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-071-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-071-04 | Acceptance | AC-R-071 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-071-04 | Activities | A-R-071 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-071-04 | Deliverables | D-R-071 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-071-04 | Gaps | G-071 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-071-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-071-04 | Rules | R-071 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-071-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-072-01 | Acceptance | AC-R-072 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-072-01 | Activities | A-R-072 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-072-01 | Deliverables | D-R-072 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-072-01 | Gaps | G-072 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-072-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-072-01 | Rules | R-072 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-072-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-072-02 | Acceptance | AC-R-072 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-072-02 | Activities | A-R-072 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-072-02 | Deliverables | D-R-072 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-072-02 | Gaps | G-072 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-072-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-072-02 | Rules | R-072 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-072-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-072-03 | Acceptance | AC-R-072 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-072-03 | Activities | A-R-072 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-072-03 | Deliverables | D-R-072 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-072-03 | Gaps | G-072 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-072-03 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-072-03 | Rules | R-072 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-072-03 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-072-04 | Acceptance | AC-R-072 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-072-04 | Activities | A-R-072 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-072-04 | Deliverables | D-R-072 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-072-04 | Gaps | G-072 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-072-04 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-072-04 | Rules | R-072 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-072-04 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-073-01 | Acceptance | AC-R-073 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-073-01 | Activities | A-R-073 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-073-01 | Deliverables | D-R-073 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-073-01 | Gaps | G-073 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-073-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-073-01 | Rules | R-073 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-073-01 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-073-02 | Acceptance | AC-R-073 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-073-02 | Activities | A-R-073 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-073-02 | Deliverables | D-R-073 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-073-02 | Gaps | G-073 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-073-02 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-073-02 | Rules | R-073 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-073-02 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-073-04 | Acceptance | AC-R-073 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-073-04 | Activities | A-R-073 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-073-04 | Deliverables | D-R-073 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-073-04 | Gaps | G-073 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-073-04 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-073-04 | Rules | R-073 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-073-04 | WPS | WPS-14 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-074-01 | Acceptance | AC-R-074 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-074-01 | Activities | A-R-074 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-074-01 | Deliverables | D-R-074 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-074-01 | Gaps | G-074 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-074-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-074-01 | Rules | R-074 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-074-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-074-02 | Acceptance | AC-R-074 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-074-02 | Activities | A-R-074 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-074-02 | Deliverables | D-R-074 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-074-02 | Gaps | G-074 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-074-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-074-02 | Rules | R-074 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-074-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-074-04 | Acceptance | AC-R-074 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-074-04 | Activities | A-R-074 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-074-04 | Deliverables | D-R-074 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-074-04 | Gaps | G-074 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-074-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-074-04 | Rules | R-074 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-074-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-075-01 | Acceptance | AC-R-075 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-075-01 | Activities | A-R-075 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-075-01 | Deliverables | D-R-075 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-075-01 | Gaps | G-075 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-075-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-075-01 | Rules | R-075 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-075-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-075-02 | Acceptance | AC-R-075 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-075-02 | Activities | A-R-075 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-075-02 | Deliverables | D-R-075 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-075-02 | Gaps | G-075 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-075-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-075-02 | Rules | R-075 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-075-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-075-04 | Acceptance | AC-R-075 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-075-04 | Activities | A-R-075 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-075-04 | Deliverables | D-R-075 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-075-04 | Gaps | G-075 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-075-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-075-04 | Rules | R-075 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-075-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-076-01 | Acceptance | AC-R-076 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-076-01 | Activities | A-R-076 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-076-01 | Deliverables | D-R-076 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-076-01 | Gaps | G-076 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-076-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-076-01 | Rules | R-076 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-076-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-076-02 | Acceptance | AC-R-076 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-076-02 | Activities | A-R-076 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-076-02 | Deliverables | D-R-076 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-076-02 | Gaps | G-076 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-076-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-076-02 | Rules | R-076 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-076-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-076-03 | Acceptance | AC-R-076 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-076-03 | Activities | A-R-076 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-076-03 | Deliverables | D-R-076 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-076-03 | Gaps | G-076 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-076-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-076-03 | Rules | R-076 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-076-03 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-076-04 | Acceptance | AC-R-076 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-076-04 | Activities | A-R-076 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-076-04 | Deliverables | D-R-076 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-076-04 | Gaps | G-076 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-076-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-076-04 | Rules | R-076 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-076-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-077-01 | Acceptance | AC-R-077 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-077-01 | Activities | A-R-077 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-077-01 | Deliverables | D-R-077 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-077-01 | Gaps | G-077 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-077-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-077-01 | Rules | R-077 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-077-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-077-02 | Acceptance | AC-R-077 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-077-02 | Activities | A-R-077 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-077-02 | Deliverables | D-R-077 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-077-02 | Gaps | G-077 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-077-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-077-02 | Rules | R-077 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-077-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-077-04 | Acceptance | AC-R-077 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-077-04 | Activities | A-R-077 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-077-04 | Deliverables | D-R-077 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-077-04 | Gaps | G-077 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-077-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-077-04 | Rules | R-077 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-077-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-078-01 | Acceptance | AC-R-078 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-078-01 | Activities | A-R-078 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-078-01 | Deliverables | D-R-078 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-078-01 | Gaps | G-078 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-078-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-078-01 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-078-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-078-02 | Acceptance | AC-R-078 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-078-02 | Activities | A-R-078 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-078-02 | Deliverables | D-R-078 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-078-02 | Gaps | G-078 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-078-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-078-02 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-078-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-078-03 | Acceptance | AC-R-078 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-078-03 | Activities | A-R-078 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-078-03 | Deliverables | D-R-078 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-078-03 | Gaps | G-078 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-078-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-078-03 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-078-03 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-078-04 | Acceptance | AC-R-078 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-078-04 | Activities | A-R-078 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-078-04 | Deliverables | D-R-078 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-078-04 | Gaps | G-078 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-078-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-078-04 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-078-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-079-01 | Acceptance | AC-R-079 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-079-01 | Activities | A-R-079 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-079-01 | Deliverables | D-R-079 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-079-01 | Gaps | G-079 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-079-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-079-01 | Rules | R-079 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-079-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-079-02 | Acceptance | AC-R-079 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-079-02 | Activities | A-R-079 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-079-02 | Deliverables | D-R-079 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-079-02 | Gaps | G-079 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-079-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-079-02 | Rules | R-079 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-079-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-079-04 | Acceptance | AC-R-079 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-079-04 | Activities | A-R-079 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-079-04 | Deliverables | D-R-079 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-079-04 | Gaps | G-079 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-079-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-079-04 | Rules | R-079 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-079-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-080-01 | Acceptance | AC-R-080 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-080-01 | Activities | A-R-080 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-080-01 | Deliverables | D-R-080 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-080-01 | Gaps | G-080 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-080-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-080-01 | Rules | R-080 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-080-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-080-02 | Acceptance | AC-R-080 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-080-02 | Activities | A-R-080 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-080-02 | Deliverables | D-R-080 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-080-02 | Gaps | G-080 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-080-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-080-02 | Rules | R-080 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-080-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-080-03 | Acceptance | AC-R-080 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-080-03 | Activities | A-R-080 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-080-03 | Deliverables | D-R-080 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-080-03 | Gaps | G-080 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-080-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-080-03 | Rules | R-080 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-080-03 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-080-04 | Acceptance | AC-R-080 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-080-04 | Activities | A-R-080 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-080-04 | Deliverables | D-R-080 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-080-04 | Gaps | G-080 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-080-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-080-04 | Rules | R-080 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-080-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-081-01 | Acceptance | AC-R-081 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-081-01 | Activities | A-R-081 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-081-01 | Deliverables | D-R-081 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-081-01 | Gaps | G-081 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-081-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-081-01 | Rules | R-081 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-081-01 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-081-02 | Acceptance | AC-R-081 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-081-02 | Activities | A-R-081 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-081-02 | Deliverables | D-R-081 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-081-02 | Gaps | G-081 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-081-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-081-02 | Rules | R-081 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-081-02 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-081-03 | Acceptance | AC-R-081 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-081-03 | Activities | A-R-081 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-081-03 | Deliverables | D-R-081 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-081-03 | Gaps | G-081 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-081-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-081-03 | Rules | R-081 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-081-03 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-081-04 | Acceptance | AC-R-081 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-081-04 | Activities | A-R-081 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-081-04 | Deliverables | D-R-081 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-081-04 | Gaps | G-081 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-081-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-081-04 | Rules | R-081 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-081-04 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-082-01 | Acceptance | AC-R-082 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-082-01 | Activities | A-R-082 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-082-01 | Deliverables | D-R-082 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-082-01 | Gaps | G-082 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-082-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-082-01 | Rules | R-082 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-082-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-082-02 | Acceptance | AC-R-082 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-082-02 | Activities | A-R-082 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-082-02 | Deliverables | D-R-082 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-082-02 | Gaps | G-082 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-082-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-082-02 | Rules | R-082 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-082-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-082-04 | Acceptance | AC-R-082 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-082-04 | Activities | A-R-082 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-082-04 | Deliverables | D-R-082 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-082-04 | Gaps | G-082 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-082-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-082-04 | Rules | R-082 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-082-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-083-01 | Acceptance | AC-R-083 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-083-01 | Activities | A-R-083 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-083-01 | Deliverables | D-R-083 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-083-01 | Gaps | G-083 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-083-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-083-01 | Rules | R-083 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-083-01 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-083-02 | Acceptance | AC-R-083 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-083-02 | Activities | A-R-083 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-083-02 | Deliverables | D-R-083 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-083-02 | Gaps | G-083 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-083-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-083-02 | Rules | R-083 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-083-02 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-083-03 | Acceptance | AC-R-083 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-083-03 | Activities | A-R-083 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-083-03 | Deliverables | D-R-083 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-083-03 | Gaps | G-083 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-083-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-083-03 | Rules | R-083 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-083-03 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-083-04 | Acceptance | AC-R-083 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-083-04 | Activities | A-R-083 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-083-04 | Deliverables | D-R-083 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-083-04 | Gaps | G-083 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-083-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-083-04 | Rules | R-083 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-083-04 | WPS | WPS-01 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-084-01 | Acceptance | AC-R-084 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-084-01 | Activities | A-R-084 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-084-01 | Deliverables | D-R-084 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-084-01 | Gaps | G-084 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-084-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-084-01 | Rules | R-084 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-084-01 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-084-02 | Acceptance | AC-R-084 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-084-02 | Activities | A-R-084 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-084-02 | Deliverables | D-R-084 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-084-02 | Gaps | G-084 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-084-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-084-02 | Rules | R-084 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-084-02 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-084-03 | Acceptance | AC-R-084 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-084-03 | Activities | A-R-084 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-084-03 | Deliverables | D-R-084 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-084-03 | Gaps | G-084 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-084-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-084-03 | Rules | R-084 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-084-03 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-084-04 | Acceptance | AC-R-084 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-084-04 | Activities | A-R-084 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-084-04 | Deliverables | D-R-084 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-084-04 | Gaps | G-084 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-084-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-084-04 | Rules | R-084 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-084-04 | WPS | WPS-13 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-085-01 | Acceptance | AC-R-085 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-085-01 | Activities | A-R-085 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-085-01 | Deliverables | D-R-085 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-085-01 | Gaps | G-085 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-085-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-085-01 | Rules | R-085 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-085-01 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-085-02 | Acceptance | AC-R-085 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-085-02 | Activities | A-R-085 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-085-02 | Deliverables | D-R-085 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-085-02 | Gaps | G-085 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-085-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-085-02 | Rules | R-085 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-085-02 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-085-04 | Acceptance | AC-R-085 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-085-04 | Activities | A-R-085 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-085-04 | Deliverables | D-R-085 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-085-04 | Gaps | G-085 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-085-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-085-04 | Rules | R-085 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-085-04 | WPS | WPS-11 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-086-01 | Acceptance | AC-R-086 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-086-01 | Activities | A-R-086 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-086-01 | Deliverables | D-R-086 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-086-01 | Gaps | G-086 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-086-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-086-01 | Rules | R-086 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-086-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-086-02 | Acceptance | AC-R-086 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-086-02 | Activities | A-R-086 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-086-02 | Deliverables | D-R-086 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-086-02 | Gaps | G-086 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-086-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-086-02 | Rules | R-086 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-086-02 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-086-04 | Acceptance | AC-R-086 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-086-04 | Activities | A-R-086 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-086-04 | Deliverables | D-R-086 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-086-04 | Gaps | G-086 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-086-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-086-04 | Rules | R-086 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-086-04 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-087-01 | Acceptance | AC-R-087 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-087-01 | Activities | A-R-087 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-087-01 | Deliverables | D-R-087 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-087-01 | Gaps | G-087 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-087-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-087-01 | Rules | R-087 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-087-01 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-087-02 | Acceptance | AC-R-087 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-087-02 | Activities | A-R-087 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-087-02 | Deliverables | D-R-087 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-087-02 | Gaps | G-087 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-087-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-087-02 | Rules | R-087 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-087-02 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-087-04 | Acceptance | AC-R-087 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-087-04 | Activities | A-R-087 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-087-04 | Deliverables | D-R-087 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-087-04 | Gaps | G-087 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-087-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-087-04 | Rules | R-087 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-087-04 | WPS | WPS-16 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-088-01 | Acceptance | AC-R-088 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-088-01 | Activities | A-R-088 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-088-01 | Deliverables | D-R-088 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-088-01 | Gaps | G-088 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-088-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-088-01 | Rules | R-088 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-088-01 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-088-02 | Acceptance | AC-R-088 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-088-02 | Activities | A-R-088 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-088-02 | Deliverables | D-R-088 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-088-02 | Gaps | G-088 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-088-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-088-02 | Rules | R-088 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-088-02 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-088-03 | Acceptance | AC-R-088 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-088-03 | Activities | A-R-088 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-088-03 | Deliverables | D-R-088 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-088-03 | Gaps | G-088 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-088-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-088-03 | Rules | R-088 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-088-03 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-088-04 | Acceptance | AC-R-088 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-088-04 | Activities | A-R-088 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-088-04 | Deliverables | D-R-088 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-088-04 | Gaps | G-088 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-088-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-088-04 | Rules | R-088 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-088-04 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-089-01 | Acceptance | AC-R-089 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-089-01 | Activities | A-R-089 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-089-01 | Deliverables | D-R-089 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-089-01 | Gaps | G-089 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-089-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-089-01 | Rules | R-089 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-089-01 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-089-02 | Acceptance | AC-R-089 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-089-02 | Activities | A-R-089 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-089-02 | Deliverables | D-R-089 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-089-02 | Gaps | G-089 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-089-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-089-02 | Rules | R-089 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-089-02 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-089-03 | Acceptance | AC-R-089 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-089-03 | Activities | A-R-089 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-089-03 | Deliverables | D-R-089 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-089-03 | Gaps | G-089 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-089-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-089-03 | Rules | R-089 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-089-03 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-R-089-04 | Acceptance | AC-R-089 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | F-R-089-04 | Activities | A-R-089 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | F-R-089-04 | Deliverables | D-R-089 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | F-R-089-04 | Gaps | G-089 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | F-R-089-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-R-089-04 | Rules | R-089 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-R-089-04 | WPS | WPS-02 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | F-WAT-01 | Gates | GATE-6 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | F-WAT-01 | Rules | R-056 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-WAT-01 | Rules | R-077 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-WAT-01 | Rules | R-078 | Governing_Rule_Ref |  |  | FUNCTIONAL_GOVERNED_BY | Cross-reference | Optional | Primary |  | SourceField:Governing_Rule_Ref
Functional | F-WAT-01 | WPS | WPS-09 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-17-01 | Acceptance | AC-S-17-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-17-01 | Activities | A-S-17-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-17-01 | Deliverables | D-S-17-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-17-01 | Gaps | G-S-17-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-17-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-17-01 | WPS | WPS-17 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-17-02 | Acceptance | AC-S-17-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-17-02 | Activities | A-S-17-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-17-02 | Deliverables | D-S-17-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-17-02 | Gaps | G-S-17-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-17-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-17-02 | WPS | WPS-17 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-17-03 | Acceptance | AC-S-17-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-17-03 | Activities | A-S-17-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-17-03 | Deliverables | D-S-17-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-17-03 | Gaps | G-S-17-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-17-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-17-03 | WPS | WPS-17 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-17-04 | Acceptance | AC-S-17-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-17-04 | Activities | A-S-17-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-17-04 | Deliverables | D-S-17-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-17-04 | Gaps | G-S-17-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-17-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-17-04 | WPS | WPS-17 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-17-05 | Acceptance | AC-S-17-05 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-17-05 | Activities | A-S-17-05 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-17-05 | Deliverables | D-S-17-05 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-17-05 | Gaps | G-S-17-05 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-17-05 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-17-05 | WPS | WPS-17 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-18-01 | Acceptance | AC-S-18-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-18-01 | Activities | A-S-18-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-18-01 | Deliverables | D-S-18-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-18-01 | Gaps | G-S-18-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-18-01 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-18-01 | WPS | WPS-18 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-18-02 | Acceptance | AC-S-18-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-18-02 | Activities | A-S-18-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-18-02 | Deliverables | D-S-18-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-18-02 | Gaps | G-S-18-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-18-02 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-18-02 | WPS | WPS-18 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-18-03 | Acceptance | AC-S-18-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-18-03 | Activities | A-S-18-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-18-03 | Deliverables | D-S-18-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-18-03 | Gaps | G-S-18-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-18-03 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-18-03 | WPS | WPS-18 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-18-04 | Acceptance | AC-S-18-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-18-04 | Activities | A-S-18-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-18-04 | Deliverables | D-S-18-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-18-04 | Gaps | G-S-18-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-18-04 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-18-04 | WPS | WPS-18 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-18-05 | Acceptance | AC-S-18-05 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-18-05 | Activities | A-S-18-05 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-18-05 | Deliverables | D-S-18-05 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-18-05 | Gaps | G-S-18-05 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-18-05 | Gates | GATE-1 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-18-05 | WPS | WPS-18 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-19-01 | Acceptance | AC-S-19-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-19-01 | Activities | A-S-19-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-19-01 | Deliverables | D-S-19-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-19-01 | Gaps | G-S-19-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-19-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-19-01 | WPS | WPS-19 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-19-02 | Acceptance | AC-S-19-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-19-02 | Activities | A-S-19-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-19-02 | Deliverables | D-S-19-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-19-02 | Gaps | G-S-19-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-19-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-19-02 | WPS | WPS-19 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-19-03 | Acceptance | AC-S-19-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-19-03 | Activities | A-S-19-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-19-03 | Deliverables | D-S-19-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-19-03 | Gaps | G-S-19-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-19-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-19-03 | WPS | WPS-19 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-19-04 | Acceptance | AC-S-19-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-19-04 | Activities | A-S-19-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-19-04 | Deliverables | D-S-19-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-19-04 | Gaps | G-S-19-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-19-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-19-04 | WPS | WPS-19 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-19-05 | Acceptance | AC-S-19-05 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-19-05 | Activities | A-S-19-05 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-19-05 | Deliverables | D-S-19-05 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-19-05 | Gaps | G-S-19-05 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-19-05 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-19-05 | WPS | WPS-19 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-20-01 | Acceptance | AC-S-20-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-20-01 | Activities | A-S-20-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-20-01 | Deliverables | D-S-20-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-20-01 | Gaps | G-S-20-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-20-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-20-01 | WPS | WPS-20 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-20-02 | Acceptance | AC-S-20-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-20-02 | Activities | A-S-20-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-20-02 | Deliverables | D-S-20-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-20-02 | Gaps | G-S-20-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-20-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-20-02 | WPS | WPS-20 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-20-03 | Acceptance | AC-S-20-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-20-03 | Activities | A-S-20-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-20-03 | Deliverables | D-S-20-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-20-03 | Gaps | G-S-20-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-20-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-20-03 | WPS | WPS-20 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-20-04 | Acceptance | AC-S-20-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-20-04 | Activities | A-S-20-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-20-04 | Deliverables | D-S-20-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-20-04 | Gaps | G-S-20-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-20-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-20-04 | WPS | WPS-20 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-20-05 | Acceptance | AC-S-20-05 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-20-05 | Activities | A-S-20-05 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-20-05 | Deliverables | D-S-20-05 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-20-05 | Gaps | G-S-20-05 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-20-05 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-20-05 | WPS | WPS-20 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-21-01 | Acceptance | AC-S-21-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-21-01 | Activities | A-S-21-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-21-01 | Deliverables | D-S-21-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-21-01 | Gaps | G-S-21-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-21-01 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-21-01 | WPS | WPS-21 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-21-02 | Acceptance | AC-S-21-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-21-02 | Activities | A-S-21-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-21-02 | Deliverables | D-S-21-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-21-02 | Gaps | G-S-21-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-21-02 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-21-02 | WPS | WPS-21 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-21-03 | Acceptance | AC-S-21-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-21-03 | Activities | A-S-21-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-21-03 | Deliverables | D-S-21-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-21-03 | Gaps | G-S-21-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-21-03 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-21-03 | WPS | WPS-21 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-21-04 | Acceptance | AC-S-21-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-21-04 | Activities | A-S-21-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-21-04 | Deliverables | D-S-21-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-21-04 | Gaps | G-S-21-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-21-04 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-21-04 | WPS | WPS-21 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-21-05 | Acceptance | AC-S-21-05 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-21-05 | Activities | A-S-21-05 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-21-05 | Deliverables | D-S-21-05 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-21-05 | Gaps | G-S-21-05 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-21-05 | Gates | GATE-7 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-21-05 | WPS | WPS-21 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-22-01 | Acceptance | AC-S-22-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-22-01 | Activities | A-S-22-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-22-01 | Deliverables | D-S-22-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-22-01 | Gaps | G-S-22-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-22-01 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-22-01 | WPS | WPS-22 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-22-02 | Acceptance | AC-S-22-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-22-02 | Activities | A-S-22-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-22-02 | Deliverables | D-S-22-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-22-02 | Gaps | G-S-22-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-22-02 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-22-02 | WPS | WPS-22 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-22-03 | Acceptance | AC-S-22-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-22-03 | Activities | A-S-22-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-22-03 | Deliverables | D-S-22-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-22-03 | Gaps | G-S-22-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-22-03 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-22-03 | WPS | WPS-22 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-22-04 | Acceptance | AC-S-22-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-22-04 | Activities | A-S-22-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-22-04 | Deliverables | D-S-22-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-22-04 | Gaps | G-S-22-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-22-04 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-22-04 | WPS | WPS-22 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-22-05 | Acceptance | AC-S-22-05 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-22-05 | Activities | A-S-22-05 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-22-05 | Deliverables | D-S-22-05 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-22-05 | Gaps | G-S-22-05 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-22-05 | Gates | GATE-3 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-22-05 | WPS | WPS-22 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-23-01 | Acceptance | AC-S-23-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-23-01 | Activities | A-S-23-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-23-01 | Deliverables | D-S-23-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-23-01 | Gaps | G-S-23-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-23-01 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-23-01 | WPS | WPS-23 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-23-02 | Acceptance | AC-S-23-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-23-02 | Activities | A-S-23-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-23-02 | Deliverables | D-S-23-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-23-02 | Gaps | G-S-23-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-23-02 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-23-02 | WPS | WPS-23 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-23-03 | Acceptance | AC-S-23-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-23-03 | Activities | A-S-23-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-23-03 | Deliverables | D-S-23-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-23-03 | Gaps | G-S-23-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-23-03 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-23-03 | WPS | WPS-23 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-23-04 | Acceptance | AC-S-23-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-23-04 | Activities | A-S-23-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-23-04 | Deliverables | D-S-23-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-23-04 | Gaps | G-S-23-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-23-04 | Gates | GATE-4 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-23-04 | WPS | WPS-23 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-24-01 | Acceptance | AC-S-24-01 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-24-01 | Activities | A-S-24-01 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-24-01 | Deliverables | D-S-24-01 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-24-01 | Gaps | G-S-24-01 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-24-01 | Gates | GATE-8 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-24-01 | WPS | WPS-24 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-24-02 | Acceptance | AC-S-24-02 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-24-02 | Activities | A-S-24-02 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-24-02 | Deliverables | D-S-24-02 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-24-02 | Gaps | G-S-24-02 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-24-02 | Gates | GATE-8 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-24-02 | WPS | WPS-24 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-24-03 | Acceptance | AC-S-24-03 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-24-03 | Activities | A-S-24-03 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-24-03 | Deliverables | D-S-24-03 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-24-03 | Gaps | G-S-24-03 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-24-03 | Gates | GATE-8 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-24-03 | WPS | WPS-24 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Functional | WPS-24-04 | Acceptance | AC-S-24-04 | Canonical_Acceptance_Criteria_ID |  |  | FUNCTIONAL_MAPPED_TO_ACCEPTANCE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Acceptance_Criteria_ID
Functional | WPS-24-04 | Activities | A-S-24-04 | Canonical_Activity_ID |  |  | FUNCTIONAL_MAPPED_TO_ACTIVITY | Cross-reference | Optional | Primary |  | SourceField:Canonical_Activity_ID
Functional | WPS-24-04 | Deliverables | D-S-24-04 | Canonical_Deliverable_ID |  |  | FUNCTIONAL_MAPPED_TO_DELIVERABLE | Cross-reference | Optional | Primary |  | SourceField:Canonical_Deliverable_ID
Functional | WPS-24-04 | Gaps | G-S-24-04 | Gap_ID |  |  | FUNCTIONAL_MAPPED_TO_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap_ID
Functional | WPS-24-04 | Gates | GATE-8 | Readiness_Gate |  |  | FUNCTIONAL_READINESS_GATE | Cross-reference | Optional | Primary |  | SourceField:Readiness_Gate
Functional | WPS-24-04 | WPS | WPS-24 | WPS_ID |  |  | FUNCTIONAL_BELONGS_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS_ID
Gaps | G-001 | Activities | A-R-001 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-001 | Deliverables | D-R-001 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-001 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-001 | Rules | R-001 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-001 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-002 | Activities | A-R-002 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-002 | Deliverables | D-R-002 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-002 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-002 | Rules | R-002 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-002 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-003 | Activities | A-R-003 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-003 | Deliverables | D-R-003 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-003 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-003 | Rules | R-003 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-003 | WPS | WPS-02 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-004 | Activities | A-R-004 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-004 | Deliverables | D-R-004 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-004 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-004 | Rules | R-004 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-004 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-005 | Activities | A-R-005 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-005 | Deliverables | D-R-005 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-005 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-005 | Rules | R-005 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-005 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-006 | Activities | A-R-006 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-006 | Deliverables | D-R-006 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-006 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-006 | Rules | R-006 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-006 | WPS | WPS-02 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-007 | Activities | A-R-007 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-007 | Deliverables | D-R-007 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-007 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-007 | Rules | R-007 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-007 | WPS | WPS-02 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-008 | Activities | A-R-008 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-008 | Deliverables | D-R-008 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-008 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-008 | Rules | R-008 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-008 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-009 | Activities | A-R-009 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-009 | Deliverables | D-R-009 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-009 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-009 | Rules | R-009 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-009 | WPS | WPS-03 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-010 | Activities | A-R-010 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-010 | Deliverables | D-R-010 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-010 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-010 | Rules | R-010 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-010 | WPS | WPS-03 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-011 | Activities | A-R-011 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-011 | Deliverables | D-R-011 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-011 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-011 | Rules | R-011 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-011 | WPS | WPS-03 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-012 | Activities | A-R-012 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-012 | Deliverables | D-R-012 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-012 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-012 | Rules | R-012 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-012 | WPS | WPS-04 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-013 | Activities | A-R-013 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-013 | Deliverables | D-R-013 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-013 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-013 | Rules | R-013 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-013 | WPS | WPS-04 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-014 | Activities | A-R-014 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-014 | Deliverables | D-R-014 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-014 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-014 | Rules | R-014 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-014 | WPS | WPS-05 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-015 | Activities | A-R-015 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-015 | Deliverables | D-R-015 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-015 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-015 | Rules | R-015 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-015 | WPS | WPS-05 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-016 | Activities | A-R-016 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-016 | Deliverables | D-R-016 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-016 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-016 | Rules | R-016 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-016 | WPS | WPS-03 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-017 | Activities | A-R-017 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-017 | Deliverables | D-R-017 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-017 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-017 | Rules | R-017 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-017 | WPS | WPS-03 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-018 | Activities | A-R-018 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-018 | Deliverables | D-R-018 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-018 | Gates | GATE-2 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-018 | Rules | R-018 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-018 | WPS | WPS-03 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-019 | Activities | A-R-019 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-019 | Deliverables | D-R-019 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-019 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-019 | Rules | R-019 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-019 | WPS | WPS-06 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-020 | Activities | A-R-020 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-020 | Deliverables | D-R-020 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-020 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-020 | Rules | R-020 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-020 | WPS | WPS-06 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-021 | Activities | A-R-021 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-021 | Deliverables | D-R-021 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-021 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-021 | Rules | R-021 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-021 | WPS | WPS-06 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-022 | Activities | A-R-022 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-022 | Deliverables | D-R-022 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-022 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-022 | Rules | R-022 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-022 | WPS | WPS-06 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-023 | Activities | A-R-023 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-023 | Deliverables | D-R-023 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-023 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-023 | Rules | R-023 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-023 | WPS | WPS-07 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-024 | Activities | A-R-024 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-024 | Deliverables | D-R-024 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-024 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-024 | Rules | R-024 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-024 | WPS | WPS-07 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-025 | Activities | A-R-025 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-025 | Deliverables | D-R-025 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-025 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-025 | Rules | R-025 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-025 | WPS | WPS-07 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-026 | Activities | A-R-026 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-026 | Deliverables | D-R-026 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-026 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-026 | Rules | R-026 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-026 | WPS | WPS-07 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-027 | Activities | A-R-027 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-027 | Deliverables | D-R-027 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-027 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-027 | Rules | R-027 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-027 | WPS | WPS-07 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-028 | Activities | A-R-028 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-028 | Deliverables | D-R-028 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-028 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-028 | Rules | R-028 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-028 | WPS | WPS-07 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-029 | Activities | A-R-029 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-029 | Deliverables | D-R-029 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-029 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-029 | Rules | R-029 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-029 | WPS | WPS-08 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-030 | Activities | A-R-030 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-030 | Deliverables | D-R-030 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-030 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-030 | Rules | R-030 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-030 | WPS | WPS-08 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-031 | Activities | A-R-031 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-031 | Deliverables | D-R-031 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-031 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-031 | Rules | R-031 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-031 | WPS | WPS-08 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-032 | Activities | A-R-032 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-032 | Deliverables | D-R-032 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-032 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-032 | Rules | R-032 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-032 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-033 | Activities | A-R-033 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-033 | Deliverables | D-R-033 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-033 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-033 | Rules | R-033 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-033 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-034 | Activities | A-R-034 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-034 | Deliverables | D-R-034 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-034 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-034 | Rules | R-034 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-034 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-035 | Activities | A-R-035 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-035 | Deliverables | D-R-035 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-035 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-035 | Rules | R-035 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-035 | WPS | WPS-11 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-036 | Activities | A-R-036 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-036 | Deliverables | D-R-036 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-036 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-036 | Rules | R-036 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-036 | WPS | WPS-08 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-037 | Activities | A-R-037 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-037 | Deliverables | D-R-037 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-037 | Gates | GATE-5 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-037 | Rules | R-037 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-037 | WPS | WPS-10 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-038 | Activities | A-R-038 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-038 | Deliverables | D-R-038 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-038 | Gates | GATE-5 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-038 | Rules | R-038 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-038 | WPS | WPS-10 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-039 | Activities | A-R-039 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-039 | Deliverables | D-R-039 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-039 | Gates | GATE-5 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-039 | Rules | R-039 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-039 | WPS | WPS-10 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-040 | Activities | A-R-040 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-040 | Deliverables | D-R-040 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-040 | Gates | GATE-5 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-040 | Rules | R-040 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-040 | WPS | WPS-10 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-041 | Activities | A-R-041 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-041 | Deliverables | D-R-041 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-041 | Gates | GATE-5 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-041 | Rules | R-041 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-041 | WPS | WPS-10 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-042 | Activities | A-R-042 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-042 | Deliverables | D-R-042 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-042 | Gates | GATE-5 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-042 | Rules | R-042 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-042 | WPS | WPS-10 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-043 | Activities | A-R-043 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-043 | Deliverables | D-R-043 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-043 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-043 | Rules | R-043 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-043 | WPS | WPS-11 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-044 | Activities | A-R-044 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-044 | Deliverables | D-R-044 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-044 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-044 | Rules | R-044 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-044 | WPS | WPS-12 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-045 | Activities | A-R-045 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-045 | Deliverables | D-R-045 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-045 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-045 | Rules | R-045 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-045 | WPS | WPS-12 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-046 | Activities | A-R-046 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-046 | Deliverables | D-R-046 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-046 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-046 | Rules | R-046 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-046 | WPS | WPS-12 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-047 | Activities | A-R-047 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-047 | Deliverables | D-R-047 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-047 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-047 | Rules | R-047 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-047 | WPS | WPS-12 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-048 | Activities | A-R-048 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-048 | Deliverables | D-R-048 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-048 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-048 | Rules | R-048 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-048 | WPS | WPS-12 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-049 | Activities | A-R-049 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-049 | Deliverables | D-R-049 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-049 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-049 | Rules | R-049 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-049 | WPS | WPS-13 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-050 | Activities | A-R-050 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-050 | Deliverables | D-R-050 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-050 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-050 | Rules | R-050 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-050 | WPS | WPS-13 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-051 | Activities | A-R-051 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-051 | Deliverables | D-R-051 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-051 | Gates | GATE-6 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-051 | Rules | R-051 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-051 | WPS | WPS-14 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-052 | Activities | A-R-052 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-052 | Deliverables | D-R-052 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-052 | Gates | GATE-6 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-052 | Rules | R-052 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-052 | WPS | WPS-14 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-053 | Activities | A-R-053 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-053 | Deliverables | D-R-053 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-053 | Gates | GATE-6 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-053 | Rules | R-053 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-053 | WPS | WPS-14 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-054 | Activities | A-R-054 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-054 | Deliverables | D-R-054 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-054 | Gates | GATE-6 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-054 | Rules | R-054 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-054 | WPS | WPS-14 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-055 | Activities | A-R-055 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-055 | Deliverables | D-R-055 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-055 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-055 | Rules | R-055 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-055 | WPS | WPS-15 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-056 | Activities | A-R-056 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-056 | Deliverables | D-R-056 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-056 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-056 | Rules | R-056 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-056 | WPS | WPS-15 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-057 | Activities | A-R-057 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-057 | Deliverables | D-R-057 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-057 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-057 | Rules | R-057 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-057 | WPS | WPS-15 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-058 | Activities | A-R-058 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-058 | Deliverables | D-R-058 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-058 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-058 | Rules | R-058 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-058 | WPS | WPS-15 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-059 | Activities | A-R-059 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-059 | Deliverables | D-R-059 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-059 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-059 | Rules | R-059 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-059 | WPS | WPS-13 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-060 | Activities | A-R-060 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-060 | Deliverables | D-R-060 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-060 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-060 | Rules | R-060 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-060 | WPS | WPS-13 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-061 | Activities | A-R-061 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-061 | Deliverables | D-R-061 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-061 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-061 | Rules | R-061 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-061 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-062 | Activities | A-R-062 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-062 | Deliverables | D-R-062 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-062 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-062 | Rules | R-062 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-062 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-063 | Activities | A-R-063 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-063 | Deliverables | D-R-063 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-063 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-063 | Rules | R-063 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-063 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-064 | Activities | A-R-064 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-064 | Deliverables | D-R-064 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-064 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-064 | Rules | R-064 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-064 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-065 | Activities | A-R-065 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-065 | Deliverables | D-R-065 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-065 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-065 | Rules | R-065 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-065 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-066 | Activities | A-R-066 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-066 | Deliverables | D-R-066 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-066 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-066 | Rules | R-066 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-066 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-067 | Activities | A-R-067 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-067 | Deliverables | D-R-067 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-067 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-067 | Rules | R-067 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-067 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-068 | Activities | A-R-068 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-068 | Deliverables | D-R-068 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-068 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-068 | Rules | R-068 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-068 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-069 | Activities | A-R-069 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-069 | Deliverables | D-R-069 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-069 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-069 | Rules | R-069 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-069 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-070 | Activities | A-R-070 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-070 | Deliverables | D-R-070 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-070 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-070 | Rules | R-070 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-070 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-071 | Activities | A-R-071 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-071 | Deliverables | D-R-071 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-071 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-071 | Rules | R-071 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-071 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-072 | Activities | A-R-072 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-072 | Deliverables | D-R-072 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-072 | Gates | GATE-6 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-072 | Rules | R-072 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-072 | WPS | WPS-14 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-073 | Activities | A-R-073 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-073 | Deliverables | D-R-073 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-073 | Gates | GATE-6 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-073 | Rules | R-073 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-073 | WPS | WPS-14 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-074 | Activities | A-R-074 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-074 | Deliverables | D-R-074 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-074 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-074 | Rules | R-074 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-074 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-075 | Activities | A-R-075 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-075 | Deliverables | D-R-075 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-075 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-075 | Rules | R-075 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-075 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-076 | Activities | A-R-076 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-076 | Deliverables | D-R-076 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-076 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-076 | Rules | R-076 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-076 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-077 | Activities | A-R-077 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-077 | Deliverables | D-R-077 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-077 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-077 | Rules | R-077 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-077 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-078 | Activities | A-R-078 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-078 | Deliverables | D-R-078 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-078 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-078 | Rules | R-078 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-078 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-079 | Activities | A-R-079 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-079 | Deliverables | D-R-079 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-079 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-079 | Rules | R-079 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-079 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-080 | Activities | A-R-080 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-080 | Deliverables | D-R-080 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-080 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-080 | Rules | R-080 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-080 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-081 | Activities | A-R-081 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-081 | Deliverables | D-R-081 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-081 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-081 | Rules | R-081 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-081 | WPS | WPS-02 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-082 | Activities | A-R-082 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-082 | Deliverables | D-R-082 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-082 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-082 | Rules | R-082 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-082 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-083 | Activities | A-R-083 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-083 | Deliverables | D-R-083 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-083 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-083 | Rules | R-083 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-083 | WPS | WPS-01 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-084 | Activities | A-R-084 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-084 | Deliverables | D-R-084 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-084 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-084 | Rules | R-084 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-084 | WPS | WPS-13 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-085 | Activities | A-R-085 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-085 | Deliverables | D-R-085 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-085 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-085 | Rules | R-085 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-085 | WPS | WPS-11 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-086 | Activities | A-R-086 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-086 | Deliverables | D-R-086 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-086 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-086 | Rules | R-086 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-086 | WPS | WPS-09 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-087 | Activities | A-R-087 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-087 | Deliverables | D-R-087 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-087 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-087 | Rules | R-087 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-087 | WPS | WPS-16 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-088 | Activities | A-R-088 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-088 | Deliverables | D-R-088 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-088 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-088 | Rules | R-088 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-088 | WPS | WPS-02 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-089 | Activities | A-R-089 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-089 | Deliverables | D-R-089 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-089 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-089 | Rules | R-089 | Source Rule IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Source Rule IDs
Gaps | G-089 | WPS | WPS-02 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-17-01 | Activities | A-S-17-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-17-01 | Deliverables | D-S-17-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-17-01 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-17-01 | WPS | WPS-17 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-17-02 | Activities | A-S-17-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-17-02 | Deliverables | D-S-17-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-17-02 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-17-02 | WPS | WPS-17 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-17-03 | Activities | A-S-17-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-17-03 | Deliverables | D-S-17-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-17-03 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-17-03 | WPS | WPS-17 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-17-04 | Activities | A-S-17-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-17-04 | Deliverables | D-S-17-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-17-04 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-17-04 | WPS | WPS-17 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-17-05 | Activities | A-S-17-05 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-17-05 | Deliverables | D-S-17-05 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-17-05 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-17-05 | WPS | WPS-17 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-18-01 | Activities | A-S-18-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-18-01 | Deliverables | D-S-18-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-18-01 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-18-01 | WPS | WPS-18 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-18-02 | Activities | A-S-18-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-18-02 | Deliverables | D-S-18-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-18-02 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-18-02 | WPS | WPS-18 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-18-03 | Activities | A-S-18-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-18-03 | Deliverables | D-S-18-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-18-03 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-18-03 | WPS | WPS-18 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-18-04 | Activities | A-S-18-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-18-04 | Deliverables | D-S-18-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-18-04 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-18-04 | WPS | WPS-18 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-18-05 | Activities | A-S-18-05 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-18-05 | Deliverables | D-S-18-05 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-18-05 | Gates | GATE-1 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-18-05 | WPS | WPS-18 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-19-01 | Activities | A-S-19-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-19-01 | Deliverables | D-S-19-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-19-01 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-19-01 | WPS | WPS-19 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-19-02 | Activities | A-S-19-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-19-02 | Deliverables | D-S-19-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-19-02 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-19-02 | WPS | WPS-19 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-19-03 | Activities | A-S-19-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-19-03 | Deliverables | D-S-19-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-19-03 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-19-03 | WPS | WPS-19 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-19-04 | Activities | A-S-19-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-19-04 | Deliverables | D-S-19-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-19-04 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-19-04 | WPS | WPS-19 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-19-05 | Activities | A-S-19-05 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-19-05 | Deliverables | D-S-19-05 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-19-05 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-19-05 | WPS | WPS-19 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-20-01 | Activities | A-S-20-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-20-01 | Deliverables | D-S-20-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-20-01 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-20-01 | WPS | WPS-20 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-20-02 | Activities | A-S-20-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-20-02 | Deliverables | D-S-20-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-20-02 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-20-02 | WPS | WPS-20 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-20-03 | Activities | A-S-20-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-20-03 | Deliverables | D-S-20-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-20-03 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-20-03 | WPS | WPS-20 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-20-04 | Activities | A-S-20-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-20-04 | Deliverables | D-S-20-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-20-04 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-20-04 | WPS | WPS-20 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-20-05 | Activities | A-S-20-05 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-20-05 | Deliverables | D-S-20-05 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-20-05 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-20-05 | WPS | WPS-20 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-21-01 | Activities | A-S-21-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-21-01 | Deliverables | D-S-21-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-21-01 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-21-01 | WPS | WPS-21 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-21-02 | Activities | A-S-21-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-21-02 | Deliverables | D-S-21-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-21-02 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-21-02 | WPS | WPS-21 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-21-03 | Activities | A-S-21-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-21-03 | Deliverables | D-S-21-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-21-03 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-21-03 | WPS | WPS-21 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-21-04 | Activities | A-S-21-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-21-04 | Deliverables | D-S-21-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-21-04 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-21-04 | WPS | WPS-21 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-21-05 | Activities | A-S-21-05 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-21-05 | Deliverables | D-S-21-05 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-21-05 | Gates | GATE-7 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-21-05 | WPS | WPS-21 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-22-01 | Activities | A-S-22-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-22-01 | Deliverables | D-S-22-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-22-01 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-22-01 | WPS | WPS-22 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-22-02 | Activities | A-S-22-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-22-02 | Deliverables | D-S-22-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-22-02 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-22-02 | WPS | WPS-22 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-22-03 | Activities | A-S-22-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-22-03 | Deliverables | D-S-22-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-22-03 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-22-03 | WPS | WPS-22 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-22-04 | Activities | A-S-22-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-22-04 | Deliverables | D-S-22-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-22-04 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-22-04 | WPS | WPS-22 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-22-05 | Activities | A-S-22-05 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-22-05 | Deliverables | D-S-22-05 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-22-05 | Gates | GATE-3 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-22-05 | WPS | WPS-22 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-23-01 | Activities | A-S-23-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-23-01 | Deliverables | D-S-23-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-23-01 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-23-01 | WPS | WPS-23 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-23-02 | Activities | A-S-23-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-23-02 | Deliverables | D-S-23-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-23-02 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-23-02 | WPS | WPS-23 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-23-03 | Activities | A-S-23-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-23-03 | Deliverables | D-S-23-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-23-03 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-23-03 | WPS | WPS-23 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-23-04 | Activities | A-S-23-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-23-04 | Deliverables | D-S-23-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-23-04 | Gates | GATE-4 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-23-04 | WPS | WPS-23 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-24-01 | Activities | A-S-24-01 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-24-01 | Deliverables | D-S-24-01 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-24-01 | Gates | GATE-8 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-24-01 | WPS | WPS-24 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-24-02 | Activities | A-S-24-02 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-24-02 | Deliverables | D-S-24-02 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-24-02 | Gates | GATE-8 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-24-02 | WPS | WPS-24 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-24-03 | Activities | A-S-24-03 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-24-03 | Deliverables | D-S-24-03 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-24-03 | Gates | GATE-8 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-24-03 | WPS | WPS-24 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gaps | G-S-24-04 | Activities | A-S-24-04 | Related Activity IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Activity IDs
Gaps | G-S-24-04 | Deliverables | D-S-24-04 | Related Deliverable IDs |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable IDs
Gaps | G-S-24-04 | Gates | GATE-8 | Blocked Gate |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Blocked Gate
Gaps | G-S-24-04 | WPS | WPS-24 | Related WPS IDs |  |  | BLOCKS_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Gates | GATE-0 | Acceptance | AC-R-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-002 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-003 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-004 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-005 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-006 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-007 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-008 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-009 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-010 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-011 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-012 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-013 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-014 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-015 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-016 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-017 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-018 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-019 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-020 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-021 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-022 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-023 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-024 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-025 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-026 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-027 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-028 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-029 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-030 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-031 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-032 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-033 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-034 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-035 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-036 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-037 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-038 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-039 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-040 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-041 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-042 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-043 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-044 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-045 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-046 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-047 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-048 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-049 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-050 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-051 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-052 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-053 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-054 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-055 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-056 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-057 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-058 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-059 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-060 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-061 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-062 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-063 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-064 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-065 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-066 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-067 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-068 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-069 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-070 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-071 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-072 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-073 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-074 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-075 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-076 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-077 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-078 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-079 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-080 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-081 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-082 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-083 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-084 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-085 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-086 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-087 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-088 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-R-089 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-17-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-17-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-17-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-17-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-17-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-18-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-18-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-18-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-18-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-18-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-19-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-19-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-19-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-19-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-19-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-20-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-20-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-20-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-20-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-20-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-21-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-21-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-21-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-21-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-21-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-22-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-22-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-22-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-22-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-22-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-23-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-23-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-23-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-23-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-24-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-24-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-24-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-S-24-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-01-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-02-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-03-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-04-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-05-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-06-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-07-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-08-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-09-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-10-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-11-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-12-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-13-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-14-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-15-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-0 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-002 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-003 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-004 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-005 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-006 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-007 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-008 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-080 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-081 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-082 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-083 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-088 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-R-089 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-17-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-17-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-17-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-17-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-17-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-18-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-18-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-18-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-18-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-S-18-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-WPS-01-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-1 | Acceptance | AC-WPS-02-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-009 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-010 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-011 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-012 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-013 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-014 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-015 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-016 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-017 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-R-018 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-WPS-03-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-WPS-04-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-2 | Acceptance | AC-WPS-05-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-019 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-020 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-021 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-022 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-023 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-024 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-025 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-026 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-027 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-028 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-029 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-030 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-031 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-032 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-033 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-034 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-036 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-071 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-075 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-076 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-077 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-078 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-R-086 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-S-22-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-S-22-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-S-22-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-S-22-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-S-22-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-WPS-06-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-WPS-07-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-WPS-08-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-3 | Acceptance | AC-WPS-09-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-035 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-043 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-055 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-056 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-057 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-058 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-061 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-062 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-063 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-064 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-065 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-066 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-067 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-068 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-069 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-070 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-074 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-079 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-085 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-R-087 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-S-23-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-S-23-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-S-23-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-S-23-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-WPS-11-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-WPS-15-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-4 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-R-037 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-R-038 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-R-039 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-R-040 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-R-041 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-R-042 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-5 | Acceptance | AC-WPS-10-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-051 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-052 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-053 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-054 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-061 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-062 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-063 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-064 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-065 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-066 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-067 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-068 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-069 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-070 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-072 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-073 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-074 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-079 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-R-087 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-WPS-14-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-6 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-044 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-045 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-046 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-047 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-048 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-049 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-050 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-051 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-052 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-053 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-054 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-059 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-060 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-072 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-073 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-R-084 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-19-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-19-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-19-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-19-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-19-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-20-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-20-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-20-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-20-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-20-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-21-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-21-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-21-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-21-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-21-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-23-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-23-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-23-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-S-23-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-WPS-12-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-WPS-13-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-7 | Acceptance | AC-WPS-14-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-049 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-050 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-059 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-060 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-061 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-062 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-063 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-064 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-065 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-066 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-067 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-068 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-069 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-070 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-074 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-079 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-084 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-R-087 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-20-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-20-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-20-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-20-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-20-05 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-24-01 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-24-02 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-24-03 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-S-24-04 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-WPS-13-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Gates | GATE-8 | Acceptance | AC-WPS-16-001 | Acceptance Criteria IDs |  |  | GATE_VERIFIES | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria IDs
Responsibilities | RACI-001 | Activities | A-R-001 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-001 | Rules | R-001 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-001 | Tasks | T-R-001-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-001 | WPS | WPS-01 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-002 | Activities | A-R-003 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-002 | Rules | R-003 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-002 | Tasks | T-R-003-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-002 | WPS | WPS-02 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-003 | Activities | A-R-009 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-003 | Rules | R-009 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-003 | Tasks | T-R-009-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-003 | WPS | WPS-03 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-004 | Activities | A-R-012 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-004 | Rules | R-012 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-004 | Tasks | T-R-012-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-004 | WPS | WPS-04 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-005 | Activities | A-R-014 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-005 | Rules | R-014 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-005 | Tasks | T-R-014-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-005 | WPS | WPS-05 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-006 | Activities | A-R-019 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-006 | Rules | R-019 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-006 | Tasks | T-R-019-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-006 | WPS | WPS-06 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-007 | Activities | A-R-023 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-007 | Rules | R-023 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-007 | Tasks | T-R-023-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-007 | WPS | WPS-07 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-008 | Activities | A-R-029 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-008 | Rules | R-029 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-008 | Tasks | T-R-029-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-008 | WPS | WPS-08 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-009 | Activities | A-R-032 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-009 | Rules | R-032 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-009 | Tasks | T-R-032-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-009 | WPS | WPS-09 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-010 | Activities | A-R-037 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-010 | Rules | R-037 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-010 | Tasks | T-R-037-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-010 | WPS | WPS-10 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-011 | Activities | A-R-035 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-011 | Rules | R-035 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-011 | Tasks | T-R-035-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-011 | WPS | WPS-11 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-012 | Activities | A-R-044 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-012 | Rules | R-044 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-012 | Tasks | T-R-044-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-012 | WPS | WPS-12 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-013 | Activities | A-R-049 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-013 | Rules | R-049 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-013 | Tasks | T-R-049-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-013 | WPS | WPS-13 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-014 | Activities | A-R-051 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-014 | Rules | R-051 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-014 | Tasks | T-R-051-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-014 | WPS | WPS-14 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-015 | Activities | A-R-055 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-015 | Rules | R-055 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-015 | Tasks | T-R-055-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-015 | WPS | WPS-15 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-016 | Activities | A-R-061 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-016 | Rules | R-061 | Rule ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Rule ID
Responsibilities | RACI-016 | Tasks | T-R-061-03 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-016 | WPS | WPS-16 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-017 | Activities | A-S-17-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-017 | Tasks | T-S-17-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-017 | WPS | WPS-17 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-018 | Activities | A-S-17-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-018 | Tasks | T-S-17-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-018 | WPS | WPS-17 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-019 | Activities | A-S-17-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-019 | Tasks | T-S-17-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-019 | WPS | WPS-17 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-020 | Activities | A-S-17-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-020 | Tasks | T-S-17-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-020 | WPS | WPS-17 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-021 | Activities | A-S-17-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-021 | Tasks | T-S-17-05-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-021 | WPS | WPS-17 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-022 | Activities | A-S-18-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-022 | Tasks | T-S-18-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-022 | WPS | WPS-18 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-023 | Activities | A-S-18-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-023 | Tasks | T-S-18-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-023 | WPS | WPS-18 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-024 | Activities | A-S-18-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-024 | Tasks | T-S-18-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-024 | WPS | WPS-18 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-025 | Activities | A-S-18-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-025 | Tasks | T-S-18-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-025 | WPS | WPS-18 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-026 | Activities | A-S-18-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-026 | Tasks | T-S-18-05-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-026 | WPS | WPS-18 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-027 | Activities | A-S-19-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-027 | Tasks | T-S-19-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-027 | WPS | WPS-19 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-028 | Activities | A-S-19-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-028 | Tasks | T-S-19-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-028 | WPS | WPS-19 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-029 | Activities | A-S-19-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-029 | Tasks | T-S-19-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-029 | WPS | WPS-19 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-030 | Activities | A-S-19-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-030 | Tasks | T-S-19-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-030 | WPS | WPS-19 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-031 | Activities | A-S-19-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-031 | Tasks | T-S-19-05-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-031 | WPS | WPS-19 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-032 | Activities | A-S-20-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-032 | Tasks | T-S-20-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-032 | WPS | WPS-20 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-033 | Activities | A-S-20-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-033 | Tasks | T-S-20-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-033 | WPS | WPS-20 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-034 | Activities | A-S-20-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-034 | Tasks | T-S-20-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-034 | WPS | WPS-20 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-035 | Activities | A-S-20-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-035 | Tasks | T-S-20-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-035 | WPS | WPS-20 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-036 | Activities | A-S-20-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-036 | Tasks | T-S-20-05-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-036 | WPS | WPS-20 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-037 | Activities | A-S-21-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-037 | Tasks | T-S-21-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-037 | WPS | WPS-21 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-038 | Activities | A-S-21-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-038 | Tasks | T-S-21-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-038 | WPS | WPS-21 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-039 | Activities | A-S-21-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-039 | Tasks | T-S-21-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-039 | WPS | WPS-21 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-040 | Activities | A-S-21-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-040 | Tasks | T-S-21-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-040 | WPS | WPS-21 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-041 | Activities | A-S-21-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-041 | Tasks | T-S-21-05-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-041 | WPS | WPS-21 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-042 | Activities | A-S-22-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-042 | Tasks | T-S-22-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-042 | WPS | WPS-22 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-043 | Activities | A-S-22-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-043 | Tasks | T-S-22-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-043 | WPS | WPS-22 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-044 | Activities | A-S-22-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-044 | Tasks | T-S-22-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-044 | WPS | WPS-22 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-045 | Activities | A-S-22-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-045 | Tasks | T-S-22-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-045 | WPS | WPS-22 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-046 | Activities | A-S-22-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-046 | Tasks | T-S-22-05-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-046 | WPS | WPS-22 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-047 | Activities | A-S-23-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-047 | Tasks | T-S-23-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-047 | WPS | WPS-23 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-048 | Activities | A-S-23-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-048 | Tasks | T-S-23-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-048 | WPS | WPS-23 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-049 | Activities | A-S-23-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-049 | Tasks | T-S-23-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-049 | WPS | WPS-23 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-050 | Activities | A-S-23-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-050 | Tasks | T-S-23-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-050 | WPS | WPS-23 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-051 | Activities | A-S-24-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-051 | Tasks | T-S-24-01-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-051 | WPS | WPS-24 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-052 | Activities | A-S-24-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-052 | Tasks | T-S-24-02-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-052 | WPS | WPS-24 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-053 | Activities | A-S-24-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-053 | Tasks | T-S-24-03-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-053 | WPS | WPS-24 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Responsibilities | RACI-054 | Activities | A-S-24-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Responsibilities | RACI-054 | Tasks | T-S-24-04-02 | Task ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Task ID
Responsibilities | RACI-054 | WPS | WPS-24 | WPS ID |  |  | RACI_FOR_WPS | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Risks | RA-001 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-001 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-001 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-001 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-002 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-002 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-002 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-002 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-003 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-003 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-003 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-003 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-004 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-004 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-004 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-004 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-005 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-005 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-005 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-005 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-006 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-006 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-006 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-006 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-007 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-007 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-007 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-007 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-008 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-008 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-008 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-008 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-009 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-009 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-009 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-009 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-010 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-010 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-010 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-010 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-011 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-011 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-011 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-011 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-012 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-012 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-012 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-012 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-013 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-013 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-013 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-013 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-014 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-014 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-014 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-014 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-015 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-015 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-015 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-015 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-016 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-016 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-016 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-016 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-017 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-017 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-017 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-017 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-018 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-018 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-018 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-018 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-019 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-019 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-019 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-019 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-020 | Gaps | G-001 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-020 | Gaps | G-024 | Related Gap IDs |  |  | RISK_LINKED_GAP | Cross-reference | Optional | Primary |  | SourceField:Related Gap IDs
Risks | RA-020 | WPS | WPS-01 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Risks | RA-020 | WPS | WPS-16 | Related WPS IDs |  |  | RISK_APPLIES_TO_WPS | Cross-reference | Optional | Primary |  | SourceField:Related WPS IDs
Rules | R-001 | Acceptance | AC-R-001 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-001 | Activities | A-R-001 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-001 | Deliverables | D-R-001 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-001 | Gaps | G-001 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-001 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-002 | Acceptance | AC-R-002 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-002 | Activities | A-R-002 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-002 | Deliverables | D-R-002 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-002 | Gaps | G-002 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-002 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-003 | Acceptance | AC-R-003 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-003 | Activities | A-R-003 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-003 | Deliverables | D-R-003 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-003 | Gaps | G-003 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-003 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-004 | Acceptance | AC-R-004 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-004 | Activities | A-R-004 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-004 | Deliverables | D-R-004 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-004 | Gaps | G-004 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-004 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-005 | Acceptance | AC-R-005 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-005 | Activities | A-R-005 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-005 | Deliverables | D-R-005 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-005 | Gaps | G-005 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-005 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-006 | Acceptance | AC-R-006 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-006 | Activities | A-R-006 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-006 | Deliverables | D-R-006 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-006 | Gaps | G-006 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-006 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-007 | Acceptance | AC-R-007 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-007 | Activities | A-R-007 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-007 | Deliverables | D-R-007 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-007 | Gaps | G-007 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-007 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-008 | Acceptance | AC-R-008 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-008 | Activities | A-R-008 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-008 | Deliverables | D-R-008 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-008 | Gaps | G-008 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-008 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-009 | Acceptance | AC-R-009 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-009 | Activities | A-R-009 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-009 | Deliverables | D-R-009 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-009 | Gaps | G-009 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-009 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-010 | Acceptance | AC-R-010 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-010 | Activities | A-R-010 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-010 | Deliverables | D-R-010 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-010 | Gaps | G-010 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-010 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-011 | Acceptance | AC-R-011 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-011 | Activities | A-R-011 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-011 | Deliverables | D-R-011 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-011 | Gaps | G-011 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-011 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-012 | Acceptance | AC-R-012 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-012 | Activities | A-R-012 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-012 | Deliverables | D-R-012 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-012 | Gaps | G-012 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-012 | WPS | WPS-04 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-013 | Acceptance | AC-R-013 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-013 | Activities | A-R-013 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-013 | Deliverables | D-R-013 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-013 | Gaps | G-013 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-013 | WPS | WPS-04 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-014 | Acceptance | AC-R-014 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-014 | Activities | A-R-014 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-014 | Deliverables | D-R-014 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-014 | Gaps | G-014 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-014 | WPS | WPS-05 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-015 | Acceptance | AC-R-015 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-015 | Activities | A-R-015 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-015 | Deliverables | D-R-015 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-015 | Gaps | G-015 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-015 | WPS | WPS-05 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-016 | Acceptance | AC-R-016 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-016 | Activities | A-R-016 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-016 | Deliverables | D-R-016 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-016 | Gaps | G-016 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-016 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-017 | Acceptance | AC-R-017 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-017 | Activities | A-R-017 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-017 | Deliverables | D-R-017 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-017 | Gaps | G-017 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-017 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-018 | Acceptance | AC-R-018 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-018 | Activities | A-R-018 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-018 | Deliverables | D-R-018 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-018 | Gaps | G-018 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-018 | WPS | WPS-03 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-019 | Acceptance | AC-R-019 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-019 | Activities | A-R-019 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-019 | Deliverables | D-R-019 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-019 | Gaps | G-019 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-019 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-020 | Acceptance | AC-R-020 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-020 | Activities | A-R-020 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-020 | Deliverables | D-R-020 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-020 | Gaps | G-020 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-020 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-021 | Acceptance | AC-R-021 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-021 | Activities | A-R-021 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-021 | Deliverables | D-R-021 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-021 | Gaps | G-021 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-021 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-022 | Acceptance | AC-R-022 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-022 | Activities | A-R-022 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-022 | Deliverables | D-R-022 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-022 | Gaps | G-022 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-022 | WPS | WPS-06 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-023 | Acceptance | AC-R-023 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-023 | Activities | A-R-023 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-023 | Deliverables | D-R-023 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-023 | Gaps | G-023 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-023 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-024 | Acceptance | AC-R-024 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-024 | Activities | A-R-024 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-024 | Deliverables | D-R-024 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-024 | Gaps | G-024 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-024 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-025 | Acceptance | AC-R-025 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-025 | Activities | A-R-025 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-025 | Deliverables | D-R-025 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-025 | Gaps | G-025 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-025 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-026 | Acceptance | AC-R-026 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-026 | Activities | A-R-026 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-026 | Deliverables | D-R-026 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-026 | Gaps | G-026 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-026 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-027 | Acceptance | AC-R-027 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-027 | Activities | A-R-027 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-027 | Deliverables | D-R-027 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-027 | Gaps | G-027 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-027 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-028 | Acceptance | AC-R-028 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-028 | Activities | A-R-028 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-028 | Deliverables | D-R-028 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-028 | Gaps | G-028 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-028 | WPS | WPS-07 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-029 | Acceptance | AC-R-029 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-029 | Activities | A-R-029 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-029 | Deliverables | D-R-029 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-029 | Gaps | G-029 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-029 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-030 | Acceptance | AC-R-030 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-030 | Activities | A-R-030 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-030 | Deliverables | D-R-030 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-030 | Gaps | G-030 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-030 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-031 | Acceptance | AC-R-031 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-031 | Activities | A-R-031 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-031 | Deliverables | D-R-031 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-031 | Gaps | G-031 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-031 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-032 | Acceptance | AC-R-032 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-032 | Activities | A-R-032 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-032 | Deliverables | D-R-032 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-032 | Gaps | G-032 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-032 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-033 | Acceptance | AC-R-033 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-033 | Activities | A-R-033 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-033 | Deliverables | D-R-033 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-033 | Gaps | G-033 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-033 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-034 | Acceptance | AC-R-034 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-034 | Activities | A-R-034 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-034 | Deliverables | D-R-034 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-034 | Gaps | G-034 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-034 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-035 | Acceptance | AC-R-035 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-035 | Activities | A-R-035 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-035 | Deliverables | D-R-035 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-035 | Gaps | G-035 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-035 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-036 | Acceptance | AC-R-036 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-036 | Activities | A-R-036 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-036 | Deliverables | D-R-036 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-036 | Gaps | G-036 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-036 | WPS | WPS-08 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-037 | Acceptance | AC-R-037 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-037 | Activities | A-R-037 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-037 | Deliverables | D-R-037 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-037 | Gaps | G-037 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-037 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-038 | Acceptance | AC-R-038 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-038 | Activities | A-R-038 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-038 | Deliverables | D-R-038 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-038 | Gaps | G-038 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-038 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-039 | Acceptance | AC-R-039 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-039 | Activities | A-R-039 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-039 | Deliverables | D-R-039 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-039 | Gaps | G-039 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-039 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-040 | Acceptance | AC-R-040 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-040 | Activities | A-R-040 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-040 | Deliverables | D-R-040 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-040 | Gaps | G-040 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-040 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-041 | Acceptance | AC-R-041 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-041 | Activities | A-R-041 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-041 | Deliverables | D-R-041 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-041 | Gaps | G-041 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-041 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-042 | Acceptance | AC-R-042 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-042 | Activities | A-R-042 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-042 | Deliverables | D-R-042 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-042 | Gaps | G-042 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-042 | WPS | WPS-10 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-043 | Acceptance | AC-R-043 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-043 | Activities | A-R-043 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-043 | Deliverables | D-R-043 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-043 | Gaps | G-043 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-043 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-044 | Acceptance | AC-R-044 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-044 | Activities | A-R-044 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-044 | Deliverables | D-R-044 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-044 | Gaps | G-044 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-044 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-045 | Acceptance | AC-R-045 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-045 | Activities | A-R-045 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-045 | Deliverables | D-R-045 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-045 | Gaps | G-045 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-045 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-046 | Acceptance | AC-R-046 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-046 | Activities | A-R-046 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-046 | Deliverables | D-R-046 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-046 | Gaps | G-046 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-046 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-047 | Acceptance | AC-R-047 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-047 | Activities | A-R-047 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-047 | Deliverables | D-R-047 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-047 | Gaps | G-047 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-047 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-048 | Acceptance | AC-R-048 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-048 | Activities | A-R-048 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-048 | Deliverables | D-R-048 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-048 | Gaps | G-048 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-048 | WPS | WPS-12 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-049 | Acceptance | AC-R-049 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-049 | Activities | A-R-049 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-049 | Deliverables | D-R-049 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-049 | Gaps | G-049 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-049 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-050 | Acceptance | AC-R-050 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-050 | Activities | A-R-050 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-050 | Deliverables | D-R-050 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-050 | Gaps | G-050 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-050 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-051 | Acceptance | AC-R-051 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-051 | Activities | A-R-051 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-051 | Deliverables | D-R-051 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-051 | Gaps | G-051 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-051 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-052 | Acceptance | AC-R-052 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-052 | Activities | A-R-052 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-052 | Deliverables | D-R-052 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-052 | Gaps | G-052 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-052 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-053 | Acceptance | AC-R-053 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-053 | Activities | A-R-053 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-053 | Deliverables | D-R-053 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-053 | Gaps | G-053 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-053 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-054 | Acceptance | AC-R-054 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-054 | Activities | A-R-054 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-054 | Deliverables | D-R-054 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-054 | Gaps | G-054 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-054 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-055 | Acceptance | AC-R-055 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-055 | Activities | A-R-055 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-055 | Deliverables | D-R-055 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-055 | Gaps | G-055 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-055 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-056 | Acceptance | AC-R-056 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-056 | Activities | A-R-056 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-056 | Deliverables | D-R-056 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-056 | Gaps | G-056 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-056 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-057 | Acceptance | AC-R-057 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-057 | Activities | A-R-057 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-057 | Deliverables | D-R-057 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-057 | Gaps | G-057 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-057 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-058 | Acceptance | AC-R-058 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-058 | Activities | A-R-058 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-058 | Deliverables | D-R-058 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-058 | Gaps | G-058 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-058 | WPS | WPS-15 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-059 | Acceptance | AC-R-059 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-059 | Activities | A-R-059 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-059 | Deliverables | D-R-059 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-059 | Gaps | G-059 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-059 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-060 | Acceptance | AC-R-060 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-060 | Activities | A-R-060 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-060 | Deliverables | D-R-060 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-060 | Gaps | G-060 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-060 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-061 | Acceptance | AC-R-061 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-061 | Activities | A-R-061 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-061 | Deliverables | D-R-061 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-061 | Gaps | G-061 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-061 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-062 | Acceptance | AC-R-062 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-062 | Activities | A-R-062 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-062 | Deliverables | D-R-062 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-062 | Gaps | G-062 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-062 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-063 | Acceptance | AC-R-063 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-063 | Activities | A-R-063 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-063 | Deliverables | D-R-063 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-063 | Gaps | G-063 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-063 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-064 | Acceptance | AC-R-064 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-064 | Activities | A-R-064 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-064 | Deliverables | D-R-064 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-064 | Gaps | G-064 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-064 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-065 | Acceptance | AC-R-065 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-065 | Activities | A-R-065 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-065 | Deliverables | D-R-065 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-065 | Gaps | G-065 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-065 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-066 | Acceptance | AC-R-066 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-066 | Activities | A-R-066 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-066 | Deliverables | D-R-066 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-066 | Gaps | G-066 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-066 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-067 | Acceptance | AC-R-067 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-067 | Activities | A-R-067 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-067 | Deliverables | D-R-067 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-067 | Gaps | G-067 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-067 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-068 | Acceptance | AC-R-068 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-068 | Activities | A-R-068 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-068 | Deliverables | D-R-068 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-068 | Gaps | G-068 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-068 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-069 | Acceptance | AC-R-069 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-069 | Activities | A-R-069 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-069 | Deliverables | D-R-069 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-069 | Gaps | G-069 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-069 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-070 | Acceptance | AC-R-070 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-070 | Activities | A-R-070 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-070 | Deliverables | D-R-070 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-070 | Gaps | G-070 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-070 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-071 | Acceptance | AC-R-071 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-071 | Activities | A-R-071 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-071 | Deliverables | D-R-071 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-071 | Gaps | G-071 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-071 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-072 | Acceptance | AC-R-072 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-072 | Activities | A-R-072 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-072 | Deliverables | D-R-072 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-072 | Gaps | G-072 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-072 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-073 | Acceptance | AC-R-073 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-073 | Activities | A-R-073 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-073 | Deliverables | D-R-073 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-073 | Gaps | G-073 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-073 | WPS | WPS-14 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-074 | Acceptance | AC-R-074 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-074 | Activities | A-R-074 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-074 | Deliverables | D-R-074 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-074 | Gaps | G-074 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-074 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-075 | Acceptance | AC-R-075 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-075 | Activities | A-R-075 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-075 | Deliverables | D-R-075 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-075 | Gaps | G-075 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-075 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-076 | Acceptance | AC-R-076 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-076 | Activities | A-R-076 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-076 | Deliverables | D-R-076 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-076 | Gaps | G-076 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-076 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-077 | Acceptance | AC-R-077 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-077 | Activities | A-R-077 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-077 | Deliverables | D-R-077 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-077 | Gaps | G-077 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-077 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-078 | Acceptance | AC-R-078 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-078 | Activities | A-R-078 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-078 | Deliverables | D-R-078 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-078 | Gaps | G-078 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-078 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-079 | Acceptance | AC-R-079 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-079 | Activities | A-R-079 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-079 | Deliverables | D-R-079 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-079 | Gaps | G-079 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-079 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-080 | Acceptance | AC-R-080 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-080 | Activities | A-R-080 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-080 | Deliverables | D-R-080 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-080 | Gaps | G-080 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-080 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-081 | Acceptance | AC-R-081 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-081 | Activities | A-R-081 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-081 | Deliverables | D-R-081 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-081 | Gaps | G-081 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-081 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-082 | Acceptance | AC-R-082 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-082 | Activities | A-R-082 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-082 | Deliverables | D-R-082 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-082 | Gaps | G-082 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-082 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-083 | Acceptance | AC-R-083 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-083 | Activities | A-R-083 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-083 | Deliverables | D-R-083 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-083 | Gaps | G-083 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-083 | WPS | WPS-01 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-084 | Acceptance | AC-R-084 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-084 | Activities | A-R-084 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-084 | Deliverables | D-R-084 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-084 | Gaps | G-084 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-084 | WPS | WPS-13 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-085 | Acceptance | AC-R-085 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-085 | Activities | A-R-085 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-085 | Deliverables | D-R-085 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-085 | Gaps | G-085 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-085 | WPS | WPS-11 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-086 | Acceptance | AC-R-086 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-086 | Activities | A-R-086 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-086 | Deliverables | D-R-086 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-086 | Gaps | G-086 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-086 | WPS | WPS-09 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-087 | Acceptance | AC-R-087 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-087 | Activities | A-R-087 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-087 | Deliverables | D-R-087 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-087 | Gaps | G-087 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-087 | WPS | WPS-16 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-088 | Acceptance | AC-R-088 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-088 | Activities | A-R-088 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-088 | Deliverables | D-R-088 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-088 | Gaps | G-088 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-088 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Rules | R-089 | Acceptance | AC-R-089 | Acceptance Criteria ID |  |  | VERIFIED_BY | Cross-reference | Optional | Primary |  | SourceField:Acceptance Criteria ID
Rules | R-089 | Activities | A-R-089 | Activity ID |  |  | IMPLEMENTED_BY | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Rules | R-089 | Deliverables | D-R-089 | Deliverable ID |  |  | OUTPUTS | Cross-reference | Optional | Primary |  | SourceField:Deliverable ID
Rules | R-089 | Gaps | G-089 | Gap ID |  |  | HAS_GAP | Cross-reference | Optional | Primary |  | SourceField:Gap ID
Rules | R-089 | WPS | WPS-02 | WPS ID |  |  | APPLIES_TO | Cross-reference | Optional | Primary |  | SourceField:WPS ID
Tasks | T-R-001-01 | Acceptance | AC-R-001 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-001-01 | Activities | A-R-001 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-001-01 | Deliverables | D-R-001 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-001-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-001-02 | Acceptance | AC-R-001 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-001-02 | Activities | A-R-001 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-001-02 | Deliverables | D-R-001 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-001-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-001-03 | Acceptance | AC-R-001 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-001-03 | Activities | A-R-001 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-001-03 | Deliverables | D-R-001 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-001-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-002-01 | Acceptance | AC-R-002 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-002-01 | Activities | A-R-002 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-002-01 | Deliverables | D-R-002 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-002-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-002-02 | Acceptance | AC-R-002 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-002-02 | Activities | A-R-002 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-002-02 | Deliverables | D-R-002 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-002-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-002-03 | Acceptance | AC-R-002 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-002-03 | Activities | A-R-002 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-002-03 | Deliverables | D-R-002 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-002-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-003-01 | Acceptance | AC-R-003 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-003-01 | Activities | A-R-003 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-003-01 | Deliverables | D-R-003 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-003-01 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-003-02 | Acceptance | AC-R-003 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-003-02 | Activities | A-R-003 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-003-02 | Deliverables | D-R-003 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-003-02 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-003-03 | Acceptance | AC-R-003 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-003-03 | Activities | A-R-003 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-003-03 | Deliverables | D-R-003 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-003-03 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-004-01 | Acceptance | AC-R-004 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-004-01 | Activities | A-R-004 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-004-01 | Deliverables | D-R-004 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-004-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-004-02 | Acceptance | AC-R-004 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-004-02 | Activities | A-R-004 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-004-02 | Deliverables | D-R-004 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-004-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-004-03 | Acceptance | AC-R-004 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-004-03 | Activities | A-R-004 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-004-03 | Deliverables | D-R-004 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-004-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-005-01 | Acceptance | AC-R-005 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-005-01 | Activities | A-R-005 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-005-01 | Deliverables | D-R-005 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-005-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-005-02 | Acceptance | AC-R-005 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-005-02 | Activities | A-R-005 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-005-02 | Deliverables | D-R-005 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-005-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-005-03 | Acceptance | AC-R-005 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-005-03 | Activities | A-R-005 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-005-03 | Deliverables | D-R-005 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-005-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-006-01 | Acceptance | AC-R-006 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-006-01 | Activities | A-R-006 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-006-01 | Deliverables | D-R-006 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-006-01 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-006-02 | Acceptance | AC-R-006 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-006-02 | Activities | A-R-006 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-006-02 | Deliverables | D-R-006 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-006-02 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-006-03 | Acceptance | AC-R-006 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-006-03 | Activities | A-R-006 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-006-03 | Deliverables | D-R-006 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-006-03 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-007-01 | Acceptance | AC-R-007 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-007-01 | Activities | A-R-007 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-007-01 | Deliverables | D-R-007 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-007-01 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-007-02 | Acceptance | AC-R-007 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-007-02 | Activities | A-R-007 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-007-02 | Deliverables | D-R-007 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-007-02 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-007-03 | Acceptance | AC-R-007 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-007-03 | Activities | A-R-007 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-007-03 | Deliverables | D-R-007 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-007-03 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-008-01 | Acceptance | AC-R-008 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-008-01 | Activities | A-R-008 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-008-01 | Deliverables | D-R-008 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-008-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-008-02 | Acceptance | AC-R-008 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-008-02 | Activities | A-R-008 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-008-02 | Deliverables | D-R-008 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-008-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-008-03 | Acceptance | AC-R-008 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-008-03 | Activities | A-R-008 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-008-03 | Deliverables | D-R-008 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-008-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-009-01 | Acceptance | AC-R-009 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-009-01 | Activities | A-R-009 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-009-01 | Deliverables | D-R-009 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-009-01 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-009-02 | Acceptance | AC-R-009 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-009-02 | Activities | A-R-009 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-009-02 | Deliverables | D-R-009 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-009-02 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-009-03 | Acceptance | AC-R-009 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-009-03 | Activities | A-R-009 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-009-03 | Deliverables | D-R-009 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-009-03 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-010-01 | Acceptance | AC-R-010 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-010-01 | Activities | A-R-010 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-010-01 | Deliverables | D-R-010 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-010-01 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-010-02 | Acceptance | AC-R-010 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-010-02 | Activities | A-R-010 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-010-02 | Deliverables | D-R-010 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-010-02 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-010-03 | Acceptance | AC-R-010 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-010-03 | Activities | A-R-010 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-010-03 | Deliverables | D-R-010 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-010-03 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-011-01 | Acceptance | AC-R-011 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-011-01 | Activities | A-R-011 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-011-01 | Deliverables | D-R-011 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-011-01 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-011-02 | Acceptance | AC-R-011 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-011-02 | Activities | A-R-011 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-011-02 | Deliverables | D-R-011 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-011-02 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-011-03 | Acceptance | AC-R-011 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-011-03 | Activities | A-R-011 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-011-03 | Deliverables | D-R-011 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-011-03 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-012-01 | Acceptance | AC-R-012 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-012-01 | Activities | A-R-012 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-012-01 | Deliverables | D-R-012 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-012-01 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-012-02 | Acceptance | AC-R-012 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-012-02 | Activities | A-R-012 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-012-02 | Deliverables | D-R-012 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-012-02 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-012-03 | Acceptance | AC-R-012 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-012-03 | Activities | A-R-012 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-012-03 | Deliverables | D-R-012 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-012-03 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-013-01 | Acceptance | AC-R-013 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-013-01 | Activities | A-R-013 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-013-01 | Deliverables | D-R-013 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-013-01 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-013-02 | Acceptance | AC-R-013 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-013-02 | Activities | A-R-013 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-013-02 | Deliverables | D-R-013 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-013-02 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-013-03 | Acceptance | AC-R-013 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-013-03 | Activities | A-R-013 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-013-03 | Deliverables | D-R-013 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-013-03 | WPS | WPS-04 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-014-01 | Acceptance | AC-R-014 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-014-01 | Activities | A-R-014 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-014-01 | Deliverables | D-R-014 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-014-01 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-014-02 | Acceptance | AC-R-014 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-014-02 | Activities | A-R-014 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-014-02 | Deliverables | D-R-014 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-014-02 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-014-03 | Acceptance | AC-R-014 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-014-03 | Activities | A-R-014 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-014-03 | Deliverables | D-R-014 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-014-03 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-015-01 | Acceptance | AC-R-015 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-015-01 | Activities | A-R-015 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-015-01 | Deliverables | D-R-015 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-015-01 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-015-02 | Acceptance | AC-R-015 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-015-02 | Activities | A-R-015 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-015-02 | Deliverables | D-R-015 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-015-02 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-015-03 | Acceptance | AC-R-015 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-015-03 | Activities | A-R-015 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-015-03 | Deliverables | D-R-015 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-015-03 | WPS | WPS-05 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-016-01 | Acceptance | AC-R-016 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-016-01 | Activities | A-R-016 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-016-01 | Deliverables | D-R-016 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-016-01 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-016-02 | Acceptance | AC-R-016 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-016-02 | Activities | A-R-016 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-016-02 | Deliverables | D-R-016 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-016-02 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-016-03 | Acceptance | AC-R-016 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-016-03 | Activities | A-R-016 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-016-03 | Deliverables | D-R-016 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-016-03 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-017-01 | Acceptance | AC-R-017 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-017-01 | Activities | A-R-017 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-017-01 | Deliverables | D-R-017 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-017-01 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-017-02 | Acceptance | AC-R-017 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-017-02 | Activities | A-R-017 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-017-02 | Deliverables | D-R-017 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-017-02 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-017-03 | Acceptance | AC-R-017 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-017-03 | Activities | A-R-017 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-017-03 | Deliverables | D-R-017 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-017-03 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-018-01 | Acceptance | AC-R-018 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-018-01 | Activities | A-R-018 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-018-01 | Deliverables | D-R-018 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-018-01 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-018-02 | Acceptance | AC-R-018 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-018-02 | Activities | A-R-018 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-018-02 | Deliverables | D-R-018 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-018-02 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-018-03 | Acceptance | AC-R-018 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-018-03 | Activities | A-R-018 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-018-03 | Deliverables | D-R-018 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-018-03 | WPS | WPS-03 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-019-01 | Acceptance | AC-R-019 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-019-01 | Activities | A-R-019 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-019-01 | Deliverables | D-R-019 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-019-01 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-019-02 | Acceptance | AC-R-019 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-019-02 | Activities | A-R-019 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-019-02 | Deliverables | D-R-019 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-019-02 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-019-03 | Acceptance | AC-R-019 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-019-03 | Activities | A-R-019 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-019-03 | Deliverables | D-R-019 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-019-03 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-020-01 | Acceptance | AC-R-020 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-020-01 | Activities | A-R-020 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-020-01 | Deliverables | D-R-020 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-020-01 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-020-02 | Acceptance | AC-R-020 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-020-02 | Activities | A-R-020 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-020-02 | Deliverables | D-R-020 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-020-02 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-020-03 | Acceptance | AC-R-020 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-020-03 | Activities | A-R-020 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-020-03 | Deliverables | D-R-020 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-020-03 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-021-01 | Acceptance | AC-R-021 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-021-01 | Activities | A-R-021 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-021-01 | Deliverables | D-R-021 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-021-01 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-021-02 | Acceptance | AC-R-021 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-021-02 | Activities | A-R-021 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-021-02 | Deliverables | D-R-021 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-021-02 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-021-03 | Acceptance | AC-R-021 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-021-03 | Activities | A-R-021 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-021-03 | Deliverables | D-R-021 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-021-03 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-022-01 | Acceptance | AC-R-022 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-022-01 | Activities | A-R-022 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-022-01 | Deliverables | D-R-022 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-022-01 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-022-02 | Acceptance | AC-R-022 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-022-02 | Activities | A-R-022 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-022-02 | Deliverables | D-R-022 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-022-02 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-022-03 | Acceptance | AC-R-022 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-022-03 | Activities | A-R-022 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-022-03 | Deliverables | D-R-022 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-022-03 | WPS | WPS-06 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-023-01 | Acceptance | AC-R-023 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-023-01 | Activities | A-R-023 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-023-01 | Deliverables | D-R-023 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-023-01 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-023-02 | Acceptance | AC-R-023 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-023-02 | Activities | A-R-023 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-023-02 | Deliverables | D-R-023 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-023-02 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-023-03 | Acceptance | AC-R-023 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-023-03 | Activities | A-R-023 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-023-03 | Deliverables | D-R-023 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-023-03 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-024-01 | Acceptance | AC-R-024 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-024-01 | Activities | A-R-024 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-024-01 | Deliverables | D-R-024 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-024-01 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-024-02 | Acceptance | AC-R-024 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-024-02 | Activities | A-R-024 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-024-02 | Deliverables | D-R-024 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-024-02 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-024-03 | Acceptance | AC-R-024 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-024-03 | Activities | A-R-024 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-024-03 | Deliverables | D-R-024 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-024-03 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-025-01 | Acceptance | AC-R-025 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-025-01 | Activities | A-R-025 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-025-01 | Deliverables | D-R-025 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-025-01 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-025-02 | Acceptance | AC-R-025 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-025-02 | Activities | A-R-025 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-025-02 | Deliverables | D-R-025 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-025-02 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-025-03 | Acceptance | AC-R-025 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-025-03 | Activities | A-R-025 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-025-03 | Deliverables | D-R-025 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-025-03 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-026-01 | Acceptance | AC-R-026 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-026-01 | Activities | A-R-026 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-026-01 | Deliverables | D-R-026 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-026-01 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-026-02 | Acceptance | AC-R-026 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-026-02 | Activities | A-R-026 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-026-02 | Deliverables | D-R-026 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-026-02 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-026-03 | Acceptance | AC-R-026 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-026-03 | Activities | A-R-026 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-026-03 | Deliverables | D-R-026 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-026-03 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-027-01 | Acceptance | AC-R-027 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-027-01 | Activities | A-R-027 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-027-01 | Deliverables | D-R-027 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-027-01 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-027-02 | Acceptance | AC-R-027 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-027-02 | Activities | A-R-027 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-027-02 | Deliverables | D-R-027 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-027-02 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-027-03 | Acceptance | AC-R-027 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-027-03 | Activities | A-R-027 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-027-03 | Deliverables | D-R-027 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-027-03 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-028-01 | Acceptance | AC-R-028 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-028-01 | Activities | A-R-028 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-028-01 | Deliverables | D-R-028 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-028-01 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-028-02 | Acceptance | AC-R-028 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-028-02 | Activities | A-R-028 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-028-02 | Deliverables | D-R-028 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-028-02 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-028-03 | Acceptance | AC-R-028 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-028-03 | Activities | A-R-028 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-028-03 | Deliverables | D-R-028 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-028-03 | WPS | WPS-07 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-029-01 | Acceptance | AC-R-029 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-029-01 | Activities | A-R-029 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-029-01 | Deliverables | D-R-029 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-029-01 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-029-02 | Acceptance | AC-R-029 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-029-02 | Activities | A-R-029 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-029-02 | Deliverables | D-R-029 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-029-02 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-029-03 | Acceptance | AC-R-029 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-029-03 | Activities | A-R-029 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-029-03 | Deliverables | D-R-029 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-029-03 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-030-01 | Acceptance | AC-R-030 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-030-01 | Activities | A-R-030 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-030-01 | Deliverables | D-R-030 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-030-01 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-030-02 | Acceptance | AC-R-030 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-030-02 | Activities | A-R-030 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-030-02 | Deliverables | D-R-030 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-030-02 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-030-03 | Acceptance | AC-R-030 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-030-03 | Activities | A-R-030 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-030-03 | Deliverables | D-R-030 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-030-03 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-031-01 | Acceptance | AC-R-031 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-031-01 | Activities | A-R-031 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-031-01 | Deliverables | D-R-031 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-031-01 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-031-02 | Acceptance | AC-R-031 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-031-02 | Activities | A-R-031 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-031-02 | Deliverables | D-R-031 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-031-02 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-031-03 | Acceptance | AC-R-031 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-031-03 | Activities | A-R-031 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-031-03 | Deliverables | D-R-031 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-031-03 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-032-01 | Acceptance | AC-R-032 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-032-01 | Activities | A-R-032 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-032-01 | Deliverables | D-R-032 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-032-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-032-02 | Acceptance | AC-R-032 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-032-02 | Activities | A-R-032 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-032-02 | Deliverables | D-R-032 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-032-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-032-03 | Acceptance | AC-R-032 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-032-03 | Activities | A-R-032 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-032-03 | Deliverables | D-R-032 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-032-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-033-01 | Acceptance | AC-R-033 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-033-01 | Activities | A-R-033 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-033-01 | Deliverables | D-R-033 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-033-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-033-02 | Acceptance | AC-R-033 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-033-02 | Activities | A-R-033 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-033-02 | Deliverables | D-R-033 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-033-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-033-03 | Acceptance | AC-R-033 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-033-03 | Activities | A-R-033 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-033-03 | Deliverables | D-R-033 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-033-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-034-01 | Acceptance | AC-R-034 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-034-01 | Activities | A-R-034 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-034-01 | Deliverables | D-R-034 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-034-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-034-02 | Acceptance | AC-R-034 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-034-02 | Activities | A-R-034 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-034-02 | Deliverables | D-R-034 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-034-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-034-03 | Acceptance | AC-R-034 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-034-03 | Activities | A-R-034 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-034-03 | Deliverables | D-R-034 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-034-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-035-01 | Acceptance | AC-R-035 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-035-01 | Activities | A-R-035 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-035-01 | Deliverables | D-R-035 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-035-01 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-035-02 | Acceptance | AC-R-035 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-035-02 | Activities | A-R-035 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-035-02 | Deliverables | D-R-035 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-035-02 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-035-03 | Acceptance | AC-R-035 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-035-03 | Activities | A-R-035 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-035-03 | Deliverables | D-R-035 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-035-03 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-036-01 | Acceptance | AC-R-036 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-036-01 | Activities | A-R-036 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-036-01 | Deliverables | D-R-036 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-036-01 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-036-02 | Acceptance | AC-R-036 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-036-02 | Activities | A-R-036 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-036-02 | Deliverables | D-R-036 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-036-02 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-036-03 | Acceptance | AC-R-036 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-036-03 | Activities | A-R-036 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-036-03 | Deliverables | D-R-036 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-036-03 | WPS | WPS-08 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-037-01 | Acceptance | AC-R-037 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-037-01 | Activities | A-R-037 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-037-01 | Deliverables | D-R-037 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-037-01 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-037-02 | Acceptance | AC-R-037 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-037-02 | Activities | A-R-037 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-037-02 | Deliverables | D-R-037 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-037-02 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-037-03 | Acceptance | AC-R-037 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-037-03 | Activities | A-R-037 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-037-03 | Deliverables | D-R-037 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-037-03 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-038-01 | Acceptance | AC-R-038 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-038-01 | Activities | A-R-038 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-038-01 | Deliverables | D-R-038 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-038-01 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-038-02 | Acceptance | AC-R-038 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-038-02 | Activities | A-R-038 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-038-02 | Deliverables | D-R-038 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-038-02 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-038-03 | Acceptance | AC-R-038 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-038-03 | Activities | A-R-038 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-038-03 | Deliverables | D-R-038 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-038-03 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-039-01 | Acceptance | AC-R-039 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-039-01 | Activities | A-R-039 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-039-01 | Deliverables | D-R-039 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-039-01 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-039-02 | Acceptance | AC-R-039 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-039-02 | Activities | A-R-039 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-039-02 | Deliverables | D-R-039 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-039-02 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-039-03 | Acceptance | AC-R-039 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-039-03 | Activities | A-R-039 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-039-03 | Deliverables | D-R-039 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-039-03 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-040-01 | Acceptance | AC-R-040 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-040-01 | Activities | A-R-040 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-040-01 | Deliverables | D-R-040 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-040-01 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-040-02 | Acceptance | AC-R-040 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-040-02 | Activities | A-R-040 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-040-02 | Deliverables | D-R-040 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-040-02 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-040-03 | Acceptance | AC-R-040 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-040-03 | Activities | A-R-040 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-040-03 | Deliverables | D-R-040 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-040-03 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-041-01 | Acceptance | AC-R-041 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-041-01 | Activities | A-R-041 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-041-01 | Deliverables | D-R-041 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-041-01 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-041-02 | Acceptance | AC-R-041 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-041-02 | Activities | A-R-041 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-041-02 | Deliverables | D-R-041 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-041-02 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-041-03 | Acceptance | AC-R-041 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-041-03 | Activities | A-R-041 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-041-03 | Deliverables | D-R-041 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-041-03 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-042-01 | Acceptance | AC-R-042 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-042-01 | Activities | A-R-042 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-042-01 | Deliverables | D-R-042 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-042-01 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-042-02 | Acceptance | AC-R-042 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-042-02 | Activities | A-R-042 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-042-02 | Deliverables | D-R-042 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-042-02 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-042-03 | Acceptance | AC-R-042 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-042-03 | Activities | A-R-042 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-042-03 | Deliverables | D-R-042 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-042-03 | WPS | WPS-10 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-043-01 | Acceptance | AC-R-043 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-043-01 | Activities | A-R-043 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-043-01 | Deliverables | D-R-043 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-043-01 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-043-02 | Acceptance | AC-R-043 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-043-02 | Activities | A-R-043 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-043-02 | Deliverables | D-R-043 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-043-02 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-043-03 | Acceptance | AC-R-043 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-043-03 | Activities | A-R-043 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-043-03 | Deliverables | D-R-043 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-043-03 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-044-01 | Acceptance | AC-R-044 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-044-01 | Activities | A-R-044 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-044-01 | Deliverables | D-R-044 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-044-01 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-044-02 | Acceptance | AC-R-044 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-044-02 | Activities | A-R-044 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-044-02 | Deliverables | D-R-044 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-044-02 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-044-03 | Acceptance | AC-R-044 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-044-03 | Activities | A-R-044 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-044-03 | Deliverables | D-R-044 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-044-03 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-045-01 | Acceptance | AC-R-045 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-045-01 | Activities | A-R-045 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-045-01 | Deliverables | D-R-045 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-045-01 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-045-02 | Acceptance | AC-R-045 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-045-02 | Activities | A-R-045 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-045-02 | Deliverables | D-R-045 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-045-02 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-045-03 | Acceptance | AC-R-045 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-045-03 | Activities | A-R-045 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-045-03 | Deliverables | D-R-045 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-045-03 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-046-01 | Acceptance | AC-R-046 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-046-01 | Activities | A-R-046 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-046-01 | Deliverables | D-R-046 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-046-01 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-046-02 | Acceptance | AC-R-046 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-046-02 | Activities | A-R-046 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-046-02 | Deliverables | D-R-046 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-046-02 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-046-03 | Acceptance | AC-R-046 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-046-03 | Activities | A-R-046 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-046-03 | Deliverables | D-R-046 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-046-03 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-047-01 | Acceptance | AC-R-047 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-047-01 | Activities | A-R-047 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-047-01 | Deliverables | D-R-047 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-047-01 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-047-02 | Acceptance | AC-R-047 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-047-02 | Activities | A-R-047 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-047-02 | Deliverables | D-R-047 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-047-02 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-047-03 | Acceptance | AC-R-047 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-047-03 | Activities | A-R-047 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-047-03 | Deliverables | D-R-047 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-047-03 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-048-01 | Acceptance | AC-R-048 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-048-01 | Activities | A-R-048 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-048-01 | Deliverables | D-R-048 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-048-01 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-048-02 | Acceptance | AC-R-048 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-048-02 | Activities | A-R-048 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-048-02 | Deliverables | D-R-048 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-048-02 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-048-03 | Acceptance | AC-R-048 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-048-03 | Activities | A-R-048 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-048-03 | Deliverables | D-R-048 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-048-03 | WPS | WPS-12 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-049-01 | Acceptance | AC-R-049 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-049-01 | Activities | A-R-049 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-049-01 | Deliverables | D-R-049 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-049-01 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-049-02 | Acceptance | AC-R-049 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-049-02 | Activities | A-R-049 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-049-02 | Deliverables | D-R-049 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-049-02 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-049-03 | Acceptance | AC-R-049 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-049-03 | Activities | A-R-049 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-049-03 | Deliverables | D-R-049 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-049-03 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-050-01 | Acceptance | AC-R-050 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-050-01 | Activities | A-R-050 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-050-01 | Deliverables | D-R-050 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-050-01 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-050-02 | Acceptance | AC-R-050 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-050-02 | Activities | A-R-050 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-050-02 | Deliverables | D-R-050 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-050-02 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-050-03 | Acceptance | AC-R-050 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-050-03 | Activities | A-R-050 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-050-03 | Deliverables | D-R-050 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-050-03 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-051-01 | Acceptance | AC-R-051 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-051-01 | Activities | A-R-051 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-051-01 | Deliverables | D-R-051 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-051-01 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-051-02 | Acceptance | AC-R-051 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-051-02 | Activities | A-R-051 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-051-02 | Deliverables | D-R-051 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-051-02 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-051-03 | Acceptance | AC-R-051 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-051-03 | Activities | A-R-051 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-051-03 | Deliverables | D-R-051 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-051-03 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-052-01 | Acceptance | AC-R-052 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-052-01 | Activities | A-R-052 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-052-01 | Deliverables | D-R-052 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-052-01 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-052-02 | Acceptance | AC-R-052 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-052-02 | Activities | A-R-052 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-052-02 | Deliverables | D-R-052 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-052-02 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-052-03 | Acceptance | AC-R-052 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-052-03 | Activities | A-R-052 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-052-03 | Deliverables | D-R-052 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-052-03 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-053-01 | Acceptance | AC-R-053 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-053-01 | Activities | A-R-053 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-053-01 | Deliverables | D-R-053 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-053-01 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-053-02 | Acceptance | AC-R-053 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-053-02 | Activities | A-R-053 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-053-02 | Deliverables | D-R-053 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-053-02 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-053-03 | Acceptance | AC-R-053 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-053-03 | Activities | A-R-053 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-053-03 | Deliverables | D-R-053 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-053-03 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-054-01 | Acceptance | AC-R-054 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-054-01 | Activities | A-R-054 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-054-01 | Deliverables | D-R-054 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-054-01 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-054-02 | Acceptance | AC-R-054 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-054-02 | Activities | A-R-054 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-054-02 | Deliverables | D-R-054 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-054-02 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-054-03 | Acceptance | AC-R-054 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-054-03 | Activities | A-R-054 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-054-03 | Deliverables | D-R-054 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-054-03 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-055-01 | Acceptance | AC-R-055 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-055-01 | Activities | A-R-055 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-055-01 | Deliverables | D-R-055 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-055-01 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-055-02 | Acceptance | AC-R-055 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-055-02 | Activities | A-R-055 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-055-02 | Deliverables | D-R-055 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-055-02 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-055-03 | Acceptance | AC-R-055 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-055-03 | Activities | A-R-055 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-055-03 | Deliverables | D-R-055 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-055-03 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-056-01 | Acceptance | AC-R-056 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-056-01 | Activities | A-R-056 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-056-01 | Deliverables | D-R-056 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-056-01 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-056-02 | Acceptance | AC-R-056 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-056-02 | Activities | A-R-056 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-056-02 | Deliverables | D-R-056 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-056-02 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-056-03 | Acceptance | AC-R-056 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-056-03 | Activities | A-R-056 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-056-03 | Deliverables | D-R-056 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-056-03 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-057-01 | Acceptance | AC-R-057 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-057-01 | Activities | A-R-057 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-057-01 | Deliverables | D-R-057 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-057-01 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-057-02 | Acceptance | AC-R-057 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-057-02 | Activities | A-R-057 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-057-02 | Deliverables | D-R-057 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-057-02 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-057-03 | Acceptance | AC-R-057 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-057-03 | Activities | A-R-057 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-057-03 | Deliverables | D-R-057 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-057-03 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-058-01 | Acceptance | AC-R-058 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-058-01 | Activities | A-R-058 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-058-01 | Deliverables | D-R-058 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-058-01 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-058-02 | Acceptance | AC-R-058 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-058-02 | Activities | A-R-058 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-058-02 | Deliverables | D-R-058 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-058-02 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-058-03 | Acceptance | AC-R-058 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-058-03 | Activities | A-R-058 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-058-03 | Deliverables | D-R-058 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-058-03 | WPS | WPS-15 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-059-01 | Acceptance | AC-R-059 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-059-01 | Activities | A-R-059 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-059-01 | Deliverables | D-R-059 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-059-01 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-059-02 | Acceptance | AC-R-059 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-059-02 | Activities | A-R-059 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-059-02 | Deliverables | D-R-059 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-059-02 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-059-03 | Acceptance | AC-R-059 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-059-03 | Activities | A-R-059 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-059-03 | Deliverables | D-R-059 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-059-03 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-060-01 | Acceptance | AC-R-060 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-060-01 | Activities | A-R-060 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-060-01 | Deliverables | D-R-060 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-060-01 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-060-02 | Acceptance | AC-R-060 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-060-02 | Activities | A-R-060 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-060-02 | Deliverables | D-R-060 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-060-02 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-060-03 | Acceptance | AC-R-060 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-060-03 | Activities | A-R-060 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-060-03 | Deliverables | D-R-060 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-060-03 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-061-01 | Acceptance | AC-R-061 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-061-01 | Activities | A-R-061 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-061-01 | Deliverables | D-R-061 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-061-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-061-02 | Acceptance | AC-R-061 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-061-02 | Activities | A-R-061 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-061-02 | Deliverables | D-R-061 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-061-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-061-03 | Acceptance | AC-R-061 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-061-03 | Activities | A-R-061 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-061-03 | Deliverables | D-R-061 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-061-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-062-01 | Acceptance | AC-R-062 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-062-01 | Activities | A-R-062 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-062-01 | Deliverables | D-R-062 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-062-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-062-02 | Acceptance | AC-R-062 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-062-02 | Activities | A-R-062 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-062-02 | Deliverables | D-R-062 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-062-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-062-03 | Acceptance | AC-R-062 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-062-03 | Activities | A-R-062 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-062-03 | Deliverables | D-R-062 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-062-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-063-01 | Acceptance | AC-R-063 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-063-01 | Activities | A-R-063 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-063-01 | Deliverables | D-R-063 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-063-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-063-02 | Acceptance | AC-R-063 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-063-02 | Activities | A-R-063 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-063-02 | Deliverables | D-R-063 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-063-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-063-03 | Acceptance | AC-R-063 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-063-03 | Activities | A-R-063 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-063-03 | Deliverables | D-R-063 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-063-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-064-01 | Acceptance | AC-R-064 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-064-01 | Activities | A-R-064 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-064-01 | Deliverables | D-R-064 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-064-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-064-02 | Acceptance | AC-R-064 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-064-02 | Activities | A-R-064 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-064-02 | Deliverables | D-R-064 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-064-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-064-03 | Acceptance | AC-R-064 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-064-03 | Activities | A-R-064 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-064-03 | Deliverables | D-R-064 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-064-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-065-01 | Acceptance | AC-R-065 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-065-01 | Activities | A-R-065 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-065-01 | Deliverables | D-R-065 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-065-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-065-02 | Acceptance | AC-R-065 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-065-02 | Activities | A-R-065 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-065-02 | Deliverables | D-R-065 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-065-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-065-03 | Acceptance | AC-R-065 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-065-03 | Activities | A-R-065 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-065-03 | Deliverables | D-R-065 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-065-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-066-01 | Acceptance | AC-R-066 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-066-01 | Activities | A-R-066 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-066-01 | Deliverables | D-R-066 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-066-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-066-02 | Acceptance | AC-R-066 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-066-02 | Activities | A-R-066 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-066-02 | Deliverables | D-R-066 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-066-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-066-03 | Acceptance | AC-R-066 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-066-03 | Activities | A-R-066 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-066-03 | Deliverables | D-R-066 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-066-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-067-01 | Acceptance | AC-R-067 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-067-01 | Activities | A-R-067 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-067-01 | Deliverables | D-R-067 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-067-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-067-02 | Acceptance | AC-R-067 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-067-02 | Activities | A-R-067 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-067-02 | Deliverables | D-R-067 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-067-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-067-03 | Acceptance | AC-R-067 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-067-03 | Activities | A-R-067 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-067-03 | Deliverables | D-R-067 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-067-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-068-01 | Acceptance | AC-R-068 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-068-01 | Activities | A-R-068 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-068-01 | Deliverables | D-R-068 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-068-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-068-02 | Acceptance | AC-R-068 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-068-02 | Activities | A-R-068 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-068-02 | Deliverables | D-R-068 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-068-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-068-03 | Acceptance | AC-R-068 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-068-03 | Activities | A-R-068 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-068-03 | Deliverables | D-R-068 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-068-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-069-01 | Acceptance | AC-R-069 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-069-01 | Activities | A-R-069 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-069-01 | Deliverables | D-R-069 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-069-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-069-02 | Acceptance | AC-R-069 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-069-02 | Activities | A-R-069 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-069-02 | Deliverables | D-R-069 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-069-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-069-03 | Acceptance | AC-R-069 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-069-03 | Activities | A-R-069 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-069-03 | Deliverables | D-R-069 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-069-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-070-01 | Acceptance | AC-R-070 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-070-01 | Activities | A-R-070 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-070-01 | Deliverables | D-R-070 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-070-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-070-02 | Acceptance | AC-R-070 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-070-02 | Activities | A-R-070 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-070-02 | Deliverables | D-R-070 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-070-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-070-03 | Acceptance | AC-R-070 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-070-03 | Activities | A-R-070 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-070-03 | Deliverables | D-R-070 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-070-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-071-01 | Acceptance | AC-R-071 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-071-01 | Activities | A-R-071 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-071-01 | Deliverables | D-R-071 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-071-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-071-02 | Acceptance | AC-R-071 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-071-02 | Activities | A-R-071 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-071-02 | Deliverables | D-R-071 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-071-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-071-03 | Acceptance | AC-R-071 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-071-03 | Activities | A-R-071 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-071-03 | Deliverables | D-R-071 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-071-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-072-01 | Acceptance | AC-R-072 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-072-01 | Activities | A-R-072 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-072-01 | Deliverables | D-R-072 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-072-01 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-072-02 | Acceptance | AC-R-072 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-072-02 | Activities | A-R-072 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-072-02 | Deliverables | D-R-072 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-072-02 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-072-03 | Acceptance | AC-R-072 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-072-03 | Activities | A-R-072 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-072-03 | Deliverables | D-R-072 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-072-03 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-073-01 | Acceptance | AC-R-073 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-073-01 | Activities | A-R-073 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-073-01 | Deliverables | D-R-073 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-073-01 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-073-02 | Acceptance | AC-R-073 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-073-02 | Activities | A-R-073 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-073-02 | Deliverables | D-R-073 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-073-02 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-073-03 | Acceptance | AC-R-073 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-073-03 | Activities | A-R-073 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-073-03 | Deliverables | D-R-073 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-073-03 | WPS | WPS-14 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-074-01 | Acceptance | AC-R-074 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-074-01 | Activities | A-R-074 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-074-01 | Deliverables | D-R-074 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-074-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-074-02 | Acceptance | AC-R-074 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-074-02 | Activities | A-R-074 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-074-02 | Deliverables | D-R-074 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-074-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-074-03 | Acceptance | AC-R-074 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-074-03 | Activities | A-R-074 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-074-03 | Deliverables | D-R-074 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-074-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-075-01 | Acceptance | AC-R-075 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-075-01 | Activities | A-R-075 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-075-01 | Deliverables | D-R-075 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-075-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-075-02 | Acceptance | AC-R-075 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-075-02 | Activities | A-R-075 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-075-02 | Deliverables | D-R-075 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-075-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-075-03 | Acceptance | AC-R-075 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-075-03 | Activities | A-R-075 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-075-03 | Deliverables | D-R-075 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-075-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-076-01 | Acceptance | AC-R-076 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-076-01 | Activities | A-R-076 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-076-01 | Deliverables | D-R-076 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-076-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-076-02 | Acceptance | AC-R-076 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-076-02 | Activities | A-R-076 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-076-02 | Deliverables | D-R-076 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-076-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-076-03 | Acceptance | AC-R-076 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-076-03 | Activities | A-R-076 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-076-03 | Deliverables | D-R-076 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-076-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-077-01 | Acceptance | AC-R-077 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-077-01 | Activities | A-R-077 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-077-01 | Deliverables | D-R-077 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-077-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-077-02 | Acceptance | AC-R-077 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-077-02 | Activities | A-R-077 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-077-02 | Deliverables | D-R-077 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-077-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-077-03 | Acceptance | AC-R-077 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-077-03 | Activities | A-R-077 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-077-03 | Deliverables | D-R-077 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-077-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-078-01 | Acceptance | AC-R-078 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-078-01 | Activities | A-R-078 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-078-01 | Deliverables | D-R-078 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-078-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-078-02 | Acceptance | AC-R-078 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-078-02 | Activities | A-R-078 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-078-02 | Deliverables | D-R-078 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-078-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-078-03 | Acceptance | AC-R-078 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-078-03 | Activities | A-R-078 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-078-03 | Deliverables | D-R-078 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-078-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-079-01 | Acceptance | AC-R-079 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-079-01 | Activities | A-R-079 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-079-01 | Deliverables | D-R-079 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-079-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-079-02 | Acceptance | AC-R-079 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-079-02 | Activities | A-R-079 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-079-02 | Deliverables | D-R-079 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-079-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-079-03 | Acceptance | AC-R-079 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-079-03 | Activities | A-R-079 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-079-03 | Deliverables | D-R-079 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-079-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-080-01 | Acceptance | AC-R-080 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-080-01 | Activities | A-R-080 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-080-01 | Deliverables | D-R-080 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-080-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-080-02 | Acceptance | AC-R-080 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-080-02 | Activities | A-R-080 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-080-02 | Deliverables | D-R-080 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-080-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-080-03 | Acceptance | AC-R-080 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-080-03 | Activities | A-R-080 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-080-03 | Deliverables | D-R-080 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-080-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-081-01 | Acceptance | AC-R-081 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-081-01 | Activities | A-R-081 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-081-01 | Deliverables | D-R-081 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-081-01 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-081-02 | Acceptance | AC-R-081 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-081-02 | Activities | A-R-081 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-081-02 | Deliverables | D-R-081 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-081-02 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-081-03 | Acceptance | AC-R-081 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-081-03 | Activities | A-R-081 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-081-03 | Deliverables | D-R-081 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-081-03 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-082-01 | Acceptance | AC-R-082 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-082-01 | Activities | A-R-082 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-082-01 | Deliverables | D-R-082 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-082-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-082-02 | Acceptance | AC-R-082 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-082-02 | Activities | A-R-082 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-082-02 | Deliverables | D-R-082 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-082-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-082-03 | Acceptance | AC-R-082 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-082-03 | Activities | A-R-082 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-082-03 | Deliverables | D-R-082 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-082-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-083-01 | Acceptance | AC-R-083 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-083-01 | Activities | A-R-083 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-083-01 | Deliverables | D-R-083 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-083-01 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-083-02 | Acceptance | AC-R-083 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-083-02 | Activities | A-R-083 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-083-02 | Deliverables | D-R-083 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-083-02 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-083-03 | Acceptance | AC-R-083 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-083-03 | Activities | A-R-083 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-083-03 | Deliverables | D-R-083 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-083-03 | WPS | WPS-01 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-084-01 | Acceptance | AC-R-084 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-084-01 | Activities | A-R-084 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-084-01 | Deliverables | D-R-084 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-084-01 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-084-02 | Acceptance | AC-R-084 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-084-02 | Activities | A-R-084 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-084-02 | Deliverables | D-R-084 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-084-02 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-084-03 | Acceptance | AC-R-084 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-084-03 | Activities | A-R-084 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-084-03 | Deliverables | D-R-084 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-084-03 | WPS | WPS-13 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-085-01 | Acceptance | AC-R-085 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-085-01 | Activities | A-R-085 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-085-01 | Deliverables | D-R-085 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-085-01 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-085-02 | Acceptance | AC-R-085 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-085-02 | Activities | A-R-085 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-085-02 | Deliverables | D-R-085 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-085-02 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-085-03 | Acceptance | AC-R-085 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-085-03 | Activities | A-R-085 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-085-03 | Deliverables | D-R-085 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-085-03 | WPS | WPS-11 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-086-01 | Acceptance | AC-R-086 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-086-01 | Activities | A-R-086 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-086-01 | Deliverables | D-R-086 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-086-01 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-086-02 | Acceptance | AC-R-086 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-086-02 | Activities | A-R-086 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-086-02 | Deliverables | D-R-086 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-086-02 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-086-03 | Acceptance | AC-R-086 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-086-03 | Activities | A-R-086 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-086-03 | Deliverables | D-R-086 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-086-03 | WPS | WPS-09 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-087-01 | Acceptance | AC-R-087 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-087-01 | Activities | A-R-087 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-087-01 | Deliverables | D-R-087 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-087-01 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-087-02 | Acceptance | AC-R-087 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-087-02 | Activities | A-R-087 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-087-02 | Deliverables | D-R-087 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-087-02 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-087-03 | Acceptance | AC-R-087 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-087-03 | Activities | A-R-087 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-087-03 | Deliverables | D-R-087 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-087-03 | WPS | WPS-16 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-088-01 | Acceptance | AC-R-088 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-088-01 | Activities | A-R-088 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-088-01 | Deliverables | D-R-088 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-088-01 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-088-02 | Acceptance | AC-R-088 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-088-02 | Activities | A-R-088 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-088-02 | Deliverables | D-R-088 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-088-02 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-088-03 | Acceptance | AC-R-088 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-088-03 | Activities | A-R-088 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-088-03 | Deliverables | D-R-088 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-088-03 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-089-01 | Acceptance | AC-R-089 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-089-01 | Activities | A-R-089 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-089-01 | Deliverables | D-R-089 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-089-01 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-089-02 | Acceptance | AC-R-089 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-089-02 | Activities | A-R-089 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-089-02 | Deliverables | D-R-089 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-089-02 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-R-089-03 | Acceptance | AC-R-089 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-R-089-03 | Activities | A-R-089 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-R-089-03 | Deliverables | D-R-089 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-R-089-03 | WPS | WPS-02 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-01-01 | Acceptance | AC-S-17-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-01-01 | Activities | A-S-17-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-01-01 | Deliverables | D-S-17-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-01-01 | Gaps | G-S-17-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-01-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-01-02 | Acceptance | AC-S-17-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-01-02 | Activities | A-S-17-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-01-02 | Deliverables | D-S-17-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-01-02 | Gaps | G-S-17-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-01-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-02-01 | Acceptance | AC-S-17-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-02-01 | Activities | A-S-17-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-02-01 | Deliverables | D-S-17-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-02-01 | Gaps | G-S-17-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-02-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-02-02 | Acceptance | AC-S-17-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-02-02 | Activities | A-S-17-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-02-02 | Deliverables | D-S-17-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-02-02 | Gaps | G-S-17-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-02-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-03-01 | Acceptance | AC-S-17-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-03-01 | Activities | A-S-17-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-03-01 | Deliverables | D-S-17-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-03-01 | Gaps | G-S-17-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-03-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-03-02 | Acceptance | AC-S-17-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-03-02 | Activities | A-S-17-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-03-02 | Deliverables | D-S-17-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-03-02 | Gaps | G-S-17-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-03-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-04-01 | Acceptance | AC-S-17-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-04-01 | Activities | A-S-17-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-04-01 | Deliverables | D-S-17-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-04-01 | Gaps | G-S-17-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-04-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-04-02 | Acceptance | AC-S-17-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-04-02 | Activities | A-S-17-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-04-02 | Deliverables | D-S-17-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-04-02 | Gaps | G-S-17-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-04-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-05-01 | Acceptance | AC-S-17-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-05-01 | Activities | A-S-17-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-05-01 | Deliverables | D-S-17-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-05-01 | Gaps | G-S-17-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-05-01 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-17-05-02 | Acceptance | AC-S-17-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-17-05-02 | Activities | A-S-17-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-17-05-02 | Deliverables | D-S-17-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-17-05-02 | Gaps | G-S-17-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-17-05-02 | WPS | WPS-17 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-01-01 | Acceptance | AC-S-18-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-01-01 | Activities | A-S-18-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-01-01 | Deliverables | D-S-18-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-01-01 | Gaps | G-S-18-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-01-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-01-02 | Acceptance | AC-S-18-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-01-02 | Activities | A-S-18-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-01-02 | Deliverables | D-S-18-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-01-02 | Gaps | G-S-18-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-01-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-02-01 | Acceptance | AC-S-18-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-02-01 | Activities | A-S-18-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-02-01 | Deliverables | D-S-18-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-02-01 | Gaps | G-S-18-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-02-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-02-02 | Acceptance | AC-S-18-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-02-02 | Activities | A-S-18-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-02-02 | Deliverables | D-S-18-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-02-02 | Gaps | G-S-18-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-02-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-03-01 | Acceptance | AC-S-18-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-03-01 | Activities | A-S-18-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-03-01 | Deliverables | D-S-18-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-03-01 | Gaps | G-S-18-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-03-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-03-02 | Acceptance | AC-S-18-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-03-02 | Activities | A-S-18-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-03-02 | Deliverables | D-S-18-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-03-02 | Gaps | G-S-18-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-03-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-04-01 | Acceptance | AC-S-18-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-04-01 | Activities | A-S-18-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-04-01 | Deliverables | D-S-18-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-04-01 | Gaps | G-S-18-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-04-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-04-02 | Acceptance | AC-S-18-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-04-02 | Activities | A-S-18-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-04-02 | Deliverables | D-S-18-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-04-02 | Gaps | G-S-18-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-04-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-05-01 | Acceptance | AC-S-18-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-05-01 | Activities | A-S-18-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-05-01 | Deliverables | D-S-18-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-05-01 | Gaps | G-S-18-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-05-01 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-18-05-02 | Acceptance | AC-S-18-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-18-05-02 | Activities | A-S-18-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-18-05-02 | Deliverables | D-S-18-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-18-05-02 | Gaps | G-S-18-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-18-05-02 | WPS | WPS-18 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-01-01 | Acceptance | AC-S-19-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-01-01 | Activities | A-S-19-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-01-01 | Deliverables | D-S-19-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-01-01 | Gaps | G-S-19-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-01-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-01-02 | Acceptance | AC-S-19-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-01-02 | Activities | A-S-19-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-01-02 | Deliverables | D-S-19-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-01-02 | Gaps | G-S-19-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-01-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-02-01 | Acceptance | AC-S-19-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-02-01 | Activities | A-S-19-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-02-01 | Deliverables | D-S-19-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-02-01 | Gaps | G-S-19-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-02-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-02-02 | Acceptance | AC-S-19-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-02-02 | Activities | A-S-19-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-02-02 | Deliverables | D-S-19-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-02-02 | Gaps | G-S-19-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-02-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-03-01 | Acceptance | AC-S-19-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-03-01 | Activities | A-S-19-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-03-01 | Deliverables | D-S-19-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-03-01 | Gaps | G-S-19-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-03-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-03-02 | Acceptance | AC-S-19-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-03-02 | Activities | A-S-19-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-03-02 | Deliverables | D-S-19-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-03-02 | Gaps | G-S-19-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-03-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-04-01 | Acceptance | AC-S-19-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-04-01 | Activities | A-S-19-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-04-01 | Deliverables | D-S-19-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-04-01 | Gaps | G-S-19-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-04-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-04-02 | Acceptance | AC-S-19-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-04-02 | Activities | A-S-19-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-04-02 | Deliverables | D-S-19-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-04-02 | Gaps | G-S-19-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-04-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-05-01 | Acceptance | AC-S-19-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-05-01 | Activities | A-S-19-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-05-01 | Deliverables | D-S-19-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-05-01 | Gaps | G-S-19-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-05-01 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-19-05-02 | Acceptance | AC-S-19-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-19-05-02 | Activities | A-S-19-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-19-05-02 | Deliverables | D-S-19-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-19-05-02 | Gaps | G-S-19-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-19-05-02 | WPS | WPS-19 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-01-01 | Acceptance | AC-S-20-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-01-01 | Activities | A-S-20-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-01-01 | Deliverables | D-S-20-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-01-01 | Gaps | G-S-20-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-01-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-01-02 | Acceptance | AC-S-20-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-01-02 | Activities | A-S-20-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-01-02 | Deliverables | D-S-20-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-01-02 | Gaps | G-S-20-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-01-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-02-01 | Acceptance | AC-S-20-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-02-01 | Activities | A-S-20-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-02-01 | Deliverables | D-S-20-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-02-01 | Gaps | G-S-20-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-02-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-02-02 | Acceptance | AC-S-20-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-02-02 | Activities | A-S-20-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-02-02 | Deliverables | D-S-20-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-02-02 | Gaps | G-S-20-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-02-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-03-01 | Acceptance | AC-S-20-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-03-01 | Activities | A-S-20-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-03-01 | Deliverables | D-S-20-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-03-01 | Gaps | G-S-20-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-03-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-03-02 | Acceptance | AC-S-20-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-03-02 | Activities | A-S-20-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-03-02 | Deliverables | D-S-20-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-03-02 | Gaps | G-S-20-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-03-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-04-01 | Acceptance | AC-S-20-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-04-01 | Activities | A-S-20-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-04-01 | Deliverables | D-S-20-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-04-01 | Gaps | G-S-20-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-04-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-04-02 | Acceptance | AC-S-20-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-04-02 | Activities | A-S-20-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-04-02 | Deliverables | D-S-20-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-04-02 | Gaps | G-S-20-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-04-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-05-01 | Acceptance | AC-S-20-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-05-01 | Activities | A-S-20-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-05-01 | Deliverables | D-S-20-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-05-01 | Gaps | G-S-20-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-05-01 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-20-05-02 | Acceptance | AC-S-20-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-20-05-02 | Activities | A-S-20-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-20-05-02 | Deliverables | D-S-20-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-20-05-02 | Gaps | G-S-20-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-20-05-02 | WPS | WPS-20 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-01-01 | Acceptance | AC-S-21-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-01-01 | Activities | A-S-21-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-01-01 | Deliverables | D-S-21-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-01-01 | Gaps | G-S-21-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-01-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-01-02 | Acceptance | AC-S-21-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-01-02 | Activities | A-S-21-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-01-02 | Deliverables | D-S-21-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-01-02 | Gaps | G-S-21-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-01-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-02-01 | Acceptance | AC-S-21-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-02-01 | Activities | A-S-21-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-02-01 | Deliverables | D-S-21-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-02-01 | Gaps | G-S-21-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-02-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-02-02 | Acceptance | AC-S-21-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-02-02 | Activities | A-S-21-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-02-02 | Deliverables | D-S-21-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-02-02 | Gaps | G-S-21-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-02-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-03-01 | Acceptance | AC-S-21-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-03-01 | Activities | A-S-21-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-03-01 | Deliverables | D-S-21-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-03-01 | Gaps | G-S-21-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-03-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-03-02 | Acceptance | AC-S-21-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-03-02 | Activities | A-S-21-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-03-02 | Deliverables | D-S-21-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-03-02 | Gaps | G-S-21-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-03-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-04-01 | Acceptance | AC-S-21-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-04-01 | Activities | A-S-21-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-04-01 | Deliverables | D-S-21-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-04-01 | Gaps | G-S-21-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-04-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-04-02 | Acceptance | AC-S-21-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-04-02 | Activities | A-S-21-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-04-02 | Deliverables | D-S-21-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-04-02 | Gaps | G-S-21-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-04-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-05-01 | Acceptance | AC-S-21-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-05-01 | Activities | A-S-21-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-05-01 | Deliverables | D-S-21-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-05-01 | Gaps | G-S-21-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-05-01 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-21-05-02 | Acceptance | AC-S-21-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-21-05-02 | Activities | A-S-21-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-21-05-02 | Deliverables | D-S-21-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-21-05-02 | Gaps | G-S-21-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-21-05-02 | WPS | WPS-21 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-01-01 | Acceptance | AC-S-22-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-01-01 | Activities | A-S-22-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-01-01 | Deliverables | D-S-22-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-01-01 | Gaps | G-S-22-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-01-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-01-02 | Acceptance | AC-S-22-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-01-02 | Activities | A-S-22-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-01-02 | Deliverables | D-S-22-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-01-02 | Gaps | G-S-22-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-01-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-02-01 | Acceptance | AC-S-22-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-02-01 | Activities | A-S-22-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-02-01 | Deliverables | D-S-22-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-02-01 | Gaps | G-S-22-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-02-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-02-02 | Acceptance | AC-S-22-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-02-02 | Activities | A-S-22-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-02-02 | Deliverables | D-S-22-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-02-02 | Gaps | G-S-22-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-02-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-03-01 | Acceptance | AC-S-22-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-03-01 | Activities | A-S-22-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-03-01 | Deliverables | D-S-22-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-03-01 | Gaps | G-S-22-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-03-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-03-02 | Acceptance | AC-S-22-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-03-02 | Activities | A-S-22-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-03-02 | Deliverables | D-S-22-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-03-02 | Gaps | G-S-22-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-03-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-04-01 | Acceptance | AC-S-22-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-04-01 | Activities | A-S-22-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-04-01 | Deliverables | D-S-22-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-04-01 | Gaps | G-S-22-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-04-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-04-02 | Acceptance | AC-S-22-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-04-02 | Activities | A-S-22-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-04-02 | Deliverables | D-S-22-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-04-02 | Gaps | G-S-22-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-04-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-05-01 | Acceptance | AC-S-22-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-05-01 | Activities | A-S-22-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-05-01 | Deliverables | D-S-22-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-05-01 | Gaps | G-S-22-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-05-01 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-22-05-02 | Acceptance | AC-S-22-05 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-22-05-02 | Activities | A-S-22-05 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-22-05-02 | Deliverables | D-S-22-05 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-22-05-02 | Gaps | G-S-22-05 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-22-05-02 | WPS | WPS-22 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-01-01 | Acceptance | AC-S-23-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-01-01 | Activities | A-S-23-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-01-01 | Deliverables | D-S-23-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-01-01 | Gaps | G-S-23-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-01-01 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-01-02 | Acceptance | AC-S-23-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-01-02 | Activities | A-S-23-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-01-02 | Deliverables | D-S-23-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-01-02 | Gaps | G-S-23-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-01-02 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-02-01 | Acceptance | AC-S-23-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-02-01 | Activities | A-S-23-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-02-01 | Deliverables | D-S-23-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-02-01 | Gaps | G-S-23-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-02-01 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-02-02 | Acceptance | AC-S-23-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-02-02 | Activities | A-S-23-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-02-02 | Deliverables | D-S-23-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-02-02 | Gaps | G-S-23-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-02-02 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-03-01 | Acceptance | AC-S-23-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-03-01 | Activities | A-S-23-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-03-01 | Deliverables | D-S-23-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-03-01 | Gaps | G-S-23-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-03-01 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-03-02 | Acceptance | AC-S-23-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-03-02 | Activities | A-S-23-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-03-02 | Deliverables | D-S-23-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-03-02 | Gaps | G-S-23-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-03-02 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-04-01 | Acceptance | AC-S-23-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-04-01 | Activities | A-S-23-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-04-01 | Deliverables | D-S-23-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-04-01 | Gaps | G-S-23-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-04-01 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-23-04-02 | Acceptance | AC-S-23-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-23-04-02 | Activities | A-S-23-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-23-04-02 | Deliverables | D-S-23-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-23-04-02 | Gaps | G-S-23-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-23-04-02 | WPS | WPS-23 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-01-01 | Acceptance | AC-S-24-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-01-01 | Activities | A-S-24-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-01-01 | Deliverables | D-S-24-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-01-01 | Gaps | G-S-24-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-01-01 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-01-02 | Acceptance | AC-S-24-01 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-01-02 | Activities | A-S-24-01 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-01-02 | Deliverables | D-S-24-01 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-01-02 | Gaps | G-S-24-01 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-01-02 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-02-01 | Acceptance | AC-S-24-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-02-01 | Activities | A-S-24-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-02-01 | Deliverables | D-S-24-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-02-01 | Gaps | G-S-24-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-02-01 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-02-02 | Acceptance | AC-S-24-02 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-02-02 | Activities | A-S-24-02 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-02-02 | Deliverables | D-S-24-02 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-02-02 | Gaps | G-S-24-02 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-02-02 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-03-01 | Acceptance | AC-S-24-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-03-01 | Activities | A-S-24-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-03-01 | Deliverables | D-S-24-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-03-01 | Gaps | G-S-24-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-03-01 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-03-02 | Acceptance | AC-S-24-03 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-03-02 | Activities | A-S-24-03 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-03-02 | Deliverables | D-S-24-03 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-03-02 | Gaps | G-S-24-03 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-03-02 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-04-01 | Acceptance | AC-S-24-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-04-01 | Activities | A-S-24-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-04-01 | Deliverables | D-S-24-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-04-01 | Gaps | G-S-24-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-04-01 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
Tasks | T-S-24-04-02 | Acceptance | AC-S-24-04 | Acceptance Criteria ID |  |  | ACCEPTED_BY | Structural | Required | Primary |  | SourceField:Acceptance Criteria ID
Tasks | T-S-24-04-02 | Activities | A-S-24-04 | Activity ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Activity ID
Tasks | T-S-24-04-02 | Deliverables | D-S-24-04 | Related Deliverable ID |  |  | PRODUCES | Cross-reference | Optional | Primary |  | SourceField:Related Deliverable ID
Tasks | T-S-24-04-02 | Gaps | G-S-24-04 | Related Gap ID |  |  | UNDEFINED | Cross-reference | Optional | Primary |  | SourceField:Related Gap ID
Tasks | T-S-24-04-02 | WPS | WPS-24 | WPS ID |  |  | BELONGS_TO_WPS | Structural | Required | Primary |  | SourceField:WPS ID
WPS | WPS-01 | Gates | GATE-1 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-01 | Rules | R-001 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-002 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-004 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-005 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-008 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-080 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-082 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-01 | Rules | R-083 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-02 | Gates | GATE-1 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-02 | Rules | R-003 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-02 | Rules | R-006 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-02 | Rules | R-007 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-02 | Rules | R-081 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-02 | Rules | R-088 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-02 | Rules | R-089 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-03 | Gates | GATE-2 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-03 | Rules | R-009 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-03 | Rules | R-010 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-03 | Rules | R-011 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-03 | Rules | R-016 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-03 | Rules | R-017 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-03 | Rules | R-018 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-04 | Gates | GATE-2 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-04 | Rules | R-012 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-04 | Rules | R-013 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-05 | Gates | GATE-2 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-05 | Rules | R-014 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-05 | Rules | R-015 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-06 | Gates | GATE-3 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-06 | Rules | R-019 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-06 | Rules | R-020 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-06 | Rules | R-021 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-06 | Rules | R-022 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-07 | Gates | GATE-3 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-07 | Rules | R-023 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-07 | Rules | R-024 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-07 | Rules | R-025 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-07 | Rules | R-026 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-07 | Rules | R-027 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-07 | Rules | R-028 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-08 | Gates | GATE-3 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-08 | Rules | R-029 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-08 | Rules | R-030 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-08 | Rules | R-031 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-08 | Rules | R-036 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Gates | GATE-3 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-09 | Rules | R-032 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-033 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-034 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-071 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-075 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-076 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-077 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-078 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-09 | Rules | R-086 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-10 | Gates | GATE-5 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-10 | Rules | R-037 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-10 | Rules | R-038 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-10 | Rules | R-039 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-10 | Rules | R-040 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-10 | Rules | R-041 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-10 | Rules | R-042 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-11 | Gates | GATE-4 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-11 | Rules | R-035 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-11 | Rules | R-043 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-11 | Rules | R-085 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-12 | Gates | GATE-7 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-12 | Rules | R-044 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-12 | Rules | R-045 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-12 | Rules | R-046 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-12 | Rules | R-047 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-12 | Rules | R-048 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-13 | Gates | GATE-7 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-13 | Rules | R-049 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-13 | Rules | R-050 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-13 | Rules | R-059 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-13 | Rules | R-060 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-13 | Rules | R-084 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-14 | Gates | GATE-6 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-14 | Rules | R-051 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-14 | Rules | R-052 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-14 | Rules | R-053 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-14 | Rules | R-054 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-14 | Rules | R-072 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-14 | Rules | R-073 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-15 | Gates | GATE-4 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-15 | Rules | R-055 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-15 | Rules | R-056 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-15 | Rules | R-057 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-15 | Rules | R-058 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Gates | GATE-4 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-16 | Rules | R-061 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-062 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-063 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-064 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-065 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-066 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-067 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-068 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-069 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-070 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-074 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-079 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-16 | Rules | R-087 | Source Rule IDs |  |  | GOVERNED_BY | Structural | Required | Primary |  | SourceField:Source Rule IDs
WPS | WPS-17 | Gates | GATE-1 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-18 | Gates | GATE-1 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-19 | Gates | GATE-7 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-20 | Gates | GATE-7 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-21 | Gates | GATE-7 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-22 | Gates | GATE-3 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-23 | Gates | GATE-4 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-24 | Gates | GATE-8 | Readiness Gate |  |  | READINESS_GATE | Structural | Required | Primary |  | SourceField:Readiness Gate
WPS | WPS-13 | Gates | GATE-7 | Readiness Gate | WPS¦WPS-13 | Gates¦GATE-7 | READINESS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
WPS | WPS-14 | Gates | GATE-6 | Readiness Gate | WPS¦WPS-14 | Gates¦GATE-6 | READINESS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
WPS | WPS-15 | Gates | GATE-4 | Readiness Gate | WPS¦WPS-15 | Gates¦GATE-4 | READINESS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
WPS | WPS-16 | Gates | GATE-4 | Readiness Gate | WPS¦WPS-16 | Gates¦GATE-4 | READINESS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
WPS | WPS-20 | Gates | GATE-7 | Readiness Gate | WPS¦WPS-20 | Gates¦GATE-7 | READINESS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
WPS | WPS-23 | Gates | GATE-4 | Readiness Gate | WPS¦WPS-23 | Gates¦GATE-4 | READINESS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-049 | Gates | GATE-7 | Blocked Gate | Gaps¦G-049 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-050 | Gates | GATE-7 | Blocked Gate | Gaps¦G-050 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-051 | Gates | GATE-6 | Blocked Gate | Gaps¦G-051 | Gates¦GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
Gaps | G-052 | Gates | GATE-6 | Blocked Gate | Gaps¦G-052 | Gates¦GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
Gaps | G-053 | Gates | GATE-6 | Blocked Gate | Gaps¦G-053 | Gates¦GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
Gaps | G-054 | Gates | GATE-6 | Blocked Gate | Gaps¦G-054 | Gates¦GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
Gaps | G-055 | Gates | GATE-4 | Blocked Gate | Gaps¦G-055 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-056 | Gates | GATE-4 | Blocked Gate | Gaps¦G-056 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-057 | Gates | GATE-4 | Blocked Gate | Gaps¦G-057 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-058 | Gates | GATE-4 | Blocked Gate | Gaps¦G-058 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-059 | Gates | GATE-7 | Blocked Gate | Gaps¦G-059 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-060 | Gates | GATE-7 | Blocked Gate | Gaps¦G-060 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-061 | Gates | GATE-4 | Blocked Gate | Gaps¦G-061 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-062 | Gates | GATE-4 | Blocked Gate | Gaps¦G-062 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-063 | Gates | GATE-4 | Blocked Gate | Gaps¦G-063 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-064 | Gates | GATE-4 | Blocked Gate | Gaps¦G-064 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-065 | Gates | GATE-4 | Blocked Gate | Gaps¦G-065 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-066 | Gates | GATE-4 | Blocked Gate | Gaps¦G-066 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-067 | Gates | GATE-4 | Blocked Gate | Gaps¦G-067 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-068 | Gates | GATE-4 | Blocked Gate | Gaps¦G-068 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-069 | Gates | GATE-4 | Blocked Gate | Gaps¦G-069 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-070 | Gates | GATE-4 | Blocked Gate | Gaps¦G-070 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-072 | Gates | GATE-6 | Blocked Gate | Gaps¦G-072 | Gates¦GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
Gaps | G-073 | Gates | GATE-6 | Blocked Gate | Gaps¦G-073 | Gates¦GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-6/7"
Gaps | G-074 | Gates | GATE-4 | Blocked Gate | Gaps¦G-074 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-079 | Gates | GATE-4 | Blocked Gate | Gaps¦G-079 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-084 | Gates | GATE-7 | Blocked Gate | Gaps¦G-084 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-087 | Gates | GATE-4 | Blocked Gate | Gaps¦G-087 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/6/8"
Gaps | G-S-20-01 | Gates | GATE-7 | Blocked Gate | Gaps¦G-S-20-01 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-S-20-02 | Gates | GATE-7 | Blocked Gate | Gaps¦G-S-20-02 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-S-20-03 | Gates | GATE-7 | Blocked Gate | Gaps¦G-S-20-03 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-S-20-04 | Gates | GATE-7 | Blocked Gate | Gaps¦G-S-20-04 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-S-20-05 | Gates | GATE-7 | Blocked Gate | Gaps¦G-S-20-05 | Gates¦GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Gaps | G-S-23-01 | Gates | GATE-4 | Blocked Gate | Gaps¦G-S-23-01 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-S-23-02 | Gates | GATE-4 | Blocked Gate | Gaps¦G-S-23-02 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-S-23-03 | Gates | GATE-4 | Blocked Gate | Gaps¦G-S-23-03 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Gaps | G-S-23-04 | Gates | GATE-4 | Blocked Gate | Gaps¦G-S-23-04 | Gates¦GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Execution | WPS-20-01 | Gates | GATE-7 | Blocking Gate | Execution¦WPS-20-01 | Gates¦GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Execution | WPS-20-02 | Gates | GATE-7 | Blocking Gate | Execution¦WPS-20-02 | Gates¦GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Execution | WPS-20-03 | Gates | GATE-7 | Blocking Gate | Execution¦WPS-20-03 | Gates¦GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Execution | WPS-20-04 | Gates | GATE-7 | Blocking Gate | Execution¦WPS-20-04 | Gates¦GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-7/8"
Execution | WPS-23-01 | Gates | GATE-4 | Blocking Gate | Execution¦WPS-23-01 | Gates¦GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Execution | WPS-23-02 | Gates | GATE-4 | Blocking Gate | Execution¦WPS-23-02 | Gates¦GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Execution | WPS-23-03 | Gates | GATE-4 | Blocking Gate | Execution¦WPS-23-03 | Gates¦GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
Execution | WPS-23-04 | Gates | GATE-4 | Blocking Gate | Execution¦WPS-23-04 | Gates¦GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Structural | Required | Primary |  | Rev.1 expansion of "GATE-4/7"
WPS | WPS-17 | WPS | WPS-01 | Predecessor WPS IDs | WPS¦WPS-17 | WPS¦WPS-01 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-17 | WPS | WPS-02 | Predecessor WPS IDs | WPS¦WPS-17 | WPS¦WPS-02 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-01 | Predecessor WPS IDs | WPS¦WPS-18 | WPS¦WPS-01 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-02 | Predecessor WPS IDs | WPS¦WPS-18 | WPS¦WPS-02 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-19 | WPS | WPS-14 | Predecessor WPS IDs | WPS¦WPS-19 | WPS¦WPS-14 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-19 | WPS | WPS-16 | Predecessor WPS IDs | WPS¦WPS-19 | WPS¦WPS-16 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-20 | WPS | WPS-09 | Predecessor WPS IDs | WPS¦WPS-20 | WPS¦WPS-09 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-20 | WPS | WPS-13 | Predecessor WPS IDs | WPS¦WPS-20 | WPS¦WPS-13 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-20 | WPS | WPS-16 | Predecessor WPS IDs | WPS¦WPS-20 | WPS¦WPS-16 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-22 | WPS | WPS-08 | Predecessor WPS IDs | WPS¦WPS-22 | WPS¦WPS-08 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-22 | WPS | WPS-09 | Predecessor WPS IDs | WPS¦WPS-22 | WPS¦WPS-09 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-22 | WPS | WPS-13 | Predecessor WPS IDs | WPS¦WPS-22 | WPS¦WPS-13 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-22 | WPS | WPS-14 | Predecessor WPS IDs | WPS¦WPS-22 | WPS¦WPS-14 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-23 | WPS | WPS-15 | Predecessor WPS IDs | WPS¦WPS-23 | WPS¦WPS-15 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-23 | WPS | WPS-16 | Predecessor WPS IDs | WPS¦WPS-23 | WPS¦WPS-16 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-09 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-09 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-10 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-10 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-12 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-12 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-14 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-14 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-17 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-17 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-18 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-18 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-19 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-19 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-20 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-20 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-21 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-21 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-22 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-22 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-24 | WPS | WPS-23 | Predecessor WPS IDs | WPS¦WPS-24 | WPS¦WPS-23 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Predecessor WPS IDs" (was missing from canonical link table)
WPS | WPS-17 | WPS | WPS-03 | Successor WPS IDs | WPS¦WPS-17 | WPS¦WPS-03 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-17 | WPS | WPS-10 | Successor WPS IDs | WPS¦WPS-17 | WPS¦WPS-10 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-17 | WPS | WPS-13 | Successor WPS IDs | WPS¦WPS-17 | WPS¦WPS-13 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-17 | WPS | WPS-14 | Successor WPS IDs | WPS¦WPS-17 | WPS¦WPS-14 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-17 | WPS | WPS-16 | Successor WPS IDs | WPS¦WPS-17 | WPS¦WPS-16 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-03 | Successor WPS IDs | WPS¦WPS-18 | WPS¦WPS-03 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-10 | Successor WPS IDs | WPS¦WPS-18 | WPS¦WPS-10 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-13 | Successor WPS IDs | WPS¦WPS-18 | WPS¦WPS-13 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-14 | Successor WPS IDs | WPS¦WPS-18 | WPS¦WPS-14 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-18 | WPS | WPS-16 | Successor WPS IDs | WPS¦WPS-18 | WPS¦WPS-16 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-21 | WPS | WPS-17 | Successor WPS IDs | WPS¦WPS-21 | WPS¦WPS-17 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-21 | WPS | WPS-18 | Successor WPS IDs | WPS¦WPS-21 | WPS¦WPS-18 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-21 | WPS | WPS-22 | Successor WPS IDs | WPS¦WPS-21 | WPS¦WPS-22 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
WPS | WPS-21 | WPS | WPS-24 | Successor WPS IDs | WPS¦WPS-21 | WPS¦WPS-24 | SEQUENCES | Cross-reference | Optional | Primary |  | Rev.1 completion of list "Successor WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-01 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-02 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-03 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-04 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-05 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-06 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-06 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-07 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-07 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-08 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-08 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-09 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-09 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-10 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-10 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-11 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-11 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-12 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-12 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-13 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-13 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-14 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-14 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-15 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-15 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-16 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-16 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-17 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-17 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-18 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-18 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-19 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-19 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-20 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-20 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-21 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-21 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-22 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-22 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-23 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-23 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | WPS | WPS-24 | Required WPS IDs | Gates¦GATE-0 | WPS¦WPS-24 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-1 | WPS | WPS-01 | Required WPS IDs | Gates¦GATE-1 | WPS¦WPS-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-1 | WPS | WPS-02 | Required WPS IDs | Gates¦GATE-1 | WPS¦WPS-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-1 | WPS | WPS-17 | Required WPS IDs | Gates¦GATE-1 | WPS¦WPS-17 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-1 | WPS | WPS-18 | Required WPS IDs | Gates¦GATE-1 | WPS¦WPS-18 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-2 | WPS | WPS-03 | Required WPS IDs | Gates¦GATE-2 | WPS¦WPS-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-2 | WPS | WPS-04 | Required WPS IDs | Gates¦GATE-2 | WPS¦WPS-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-2 | WPS | WPS-05 | Required WPS IDs | Gates¦GATE-2 | WPS¦WPS-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-3 | WPS | WPS-06 | Required WPS IDs | Gates¦GATE-3 | WPS¦WPS-06 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-3 | WPS | WPS-07 | Required WPS IDs | Gates¦GATE-3 | WPS¦WPS-07 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-3 | WPS | WPS-08 | Required WPS IDs | Gates¦GATE-3 | WPS¦WPS-08 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-3 | WPS | WPS-09 | Required WPS IDs | Gates¦GATE-3 | WPS¦WPS-09 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-3 | WPS | WPS-22 | Required WPS IDs | Gates¦GATE-3 | WPS¦WPS-22 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-4 | WPS | WPS-11 | Required WPS IDs | Gates¦GATE-4 | WPS¦WPS-11 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-4 | WPS | WPS-15 | Required WPS IDs | Gates¦GATE-4 | WPS¦WPS-15 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-4 | WPS | WPS-23 | Required WPS IDs | Gates¦GATE-4 | WPS¦WPS-23 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-4 | WPS | WPS-16 | Required WPS IDs | Gates¦GATE-4 | WPS¦WPS-16 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-6 | WPS | WPS-14 | Required WPS IDs | Gates¦GATE-6 | WPS¦WPS-14 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-6 | WPS | WPS-16 | Required WPS IDs | Gates¦GATE-6 | WPS¦WPS-16 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-12 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-12 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-13 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-13 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-14 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-14 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-19 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-19 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-20 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-20 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-21 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-21 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-7 | WPS | WPS-23 | Required WPS IDs | Gates¦GATE-7 | WPS¦WPS-23 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-8 | WPS | WPS-13 | Required WPS IDs | Gates¦GATE-8 | WPS¦WPS-13 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-8 | WPS | WPS-16 | Required WPS IDs | Gates¦GATE-8 | WPS¦WPS-16 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-8 | WPS | WPS-20 | Required WPS IDs | Gates¦GATE-8 | WPS¦WPS-20 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-8 | WPS | WPS-24 | Required WPS IDs | Gates¦GATE-8 | WPS¦WPS-24 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required WPS IDs" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-001 | Required Activities | Gates¦GATE-0 | Activities¦A-R-001 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-002 | Required Activities | Gates¦GATE-0 | Activities¦A-R-002 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-004 | Required Activities | Gates¦GATE-0 | Activities¦A-R-004 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-005 | Required Activities | Gates¦GATE-0 | Activities¦A-R-005 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-008 | Required Activities | Gates¦GATE-0 | Activities¦A-R-008 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-080 | Required Activities | Gates¦GATE-0 | Activities¦A-R-080 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-082 | Required Activities | Gates¦GATE-0 | Activities¦A-R-082 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-083 | Required Activities | Gates¦GATE-0 | Activities¦A-R-083 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-003 | Required Activities | Gates¦GATE-0 | Activities¦A-R-003 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-006 | Required Activities | Gates¦GATE-0 | Activities¦A-R-006 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-007 | Required Activities | Gates¦GATE-0 | Activities¦A-R-007 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-081 | Required Activities | Gates¦GATE-0 | Activities¦A-R-081 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-088 | Required Activities | Gates¦GATE-0 | Activities¦A-R-088 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-089 | Required Activities | Gates¦GATE-0 | Activities¦A-R-089 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-009 | Required Activities | Gates¦GATE-0 | Activities¦A-R-009 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-010 | Required Activities | Gates¦GATE-0 | Activities¦A-R-010 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-011 | Required Activities | Gates¦GATE-0 | Activities¦A-R-011 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-016 | Required Activities | Gates¦GATE-0 | Activities¦A-R-016 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-017 | Required Activities | Gates¦GATE-0 | Activities¦A-R-017 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-018 | Required Activities | Gates¦GATE-0 | Activities¦A-R-018 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-012 | Required Activities | Gates¦GATE-0 | Activities¦A-R-012 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-013 | Required Activities | Gates¦GATE-0 | Activities¦A-R-013 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-014 | Required Activities | Gates¦GATE-0 | Activities¦A-R-014 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-015 | Required Activities | Gates¦GATE-0 | Activities¦A-R-015 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-019 | Required Activities | Gates¦GATE-0 | Activities¦A-R-019 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-020 | Required Activities | Gates¦GATE-0 | Activities¦A-R-020 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-021 | Required Activities | Gates¦GATE-0 | Activities¦A-R-021 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-022 | Required Activities | Gates¦GATE-0 | Activities¦A-R-022 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-023 | Required Activities | Gates¦GATE-0 | Activities¦A-R-023 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-024 | Required Activities | Gates¦GATE-0 | Activities¦A-R-024 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-025 | Required Activities | Gates¦GATE-0 | Activities¦A-R-025 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-026 | Required Activities | Gates¦GATE-0 | Activities¦A-R-026 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-027 | Required Activities | Gates¦GATE-0 | Activities¦A-R-027 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-028 | Required Activities | Gates¦GATE-0 | Activities¦A-R-028 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-029 | Required Activities | Gates¦GATE-0 | Activities¦A-R-029 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-030 | Required Activities | Gates¦GATE-0 | Activities¦A-R-030 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-031 | Required Activities | Gates¦GATE-0 | Activities¦A-R-031 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-036 | Required Activities | Gates¦GATE-0 | Activities¦A-R-036 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-032 | Required Activities | Gates¦GATE-0 | Activities¦A-R-032 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-033 | Required Activities | Gates¦GATE-0 | Activities¦A-R-033 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-034 | Required Activities | Gates¦GATE-0 | Activities¦A-R-034 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-071 | Required Activities | Gates¦GATE-0 | Activities¦A-R-071 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-075 | Required Activities | Gates¦GATE-0 | Activities¦A-R-075 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-076 | Required Activities | Gates¦GATE-0 | Activities¦A-R-076 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-077 | Required Activities | Gates¦GATE-0 | Activities¦A-R-077 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-078 | Required Activities | Gates¦GATE-0 | Activities¦A-R-078 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-086 | Required Activities | Gates¦GATE-0 | Activities¦A-R-086 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-037 | Required Activities | Gates¦GATE-0 | Activities¦A-R-037 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-038 | Required Activities | Gates¦GATE-0 | Activities¦A-R-038 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-039 | Required Activities | Gates¦GATE-0 | Activities¦A-R-039 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-040 | Required Activities | Gates¦GATE-0 | Activities¦A-R-040 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-041 | Required Activities | Gates¦GATE-0 | Activities¦A-R-041 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-042 | Required Activities | Gates¦GATE-0 | Activities¦A-R-042 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-035 | Required Activities | Gates¦GATE-0 | Activities¦A-R-035 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-043 | Required Activities | Gates¦GATE-0 | Activities¦A-R-043 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-085 | Required Activities | Gates¦GATE-0 | Activities¦A-R-085 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-044 | Required Activities | Gates¦GATE-0 | Activities¦A-R-044 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-045 | Required Activities | Gates¦GATE-0 | Activities¦A-R-045 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-046 | Required Activities | Gates¦GATE-0 | Activities¦A-R-046 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-047 | Required Activities | Gates¦GATE-0 | Activities¦A-R-047 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-048 | Required Activities | Gates¦GATE-0 | Activities¦A-R-048 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-049 | Required Activities | Gates¦GATE-0 | Activities¦A-R-049 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-050 | Required Activities | Gates¦GATE-0 | Activities¦A-R-050 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-059 | Required Activities | Gates¦GATE-0 | Activities¦A-R-059 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-060 | Required Activities | Gates¦GATE-0 | Activities¦A-R-060 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-084 | Required Activities | Gates¦GATE-0 | Activities¦A-R-084 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-051 | Required Activities | Gates¦GATE-0 | Activities¦A-R-051 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-052 | Required Activities | Gates¦GATE-0 | Activities¦A-R-052 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-053 | Required Activities | Gates¦GATE-0 | Activities¦A-R-053 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-054 | Required Activities | Gates¦GATE-0 | Activities¦A-R-054 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-072 | Required Activities | Gates¦GATE-0 | Activities¦A-R-072 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-073 | Required Activities | Gates¦GATE-0 | Activities¦A-R-073 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-055 | Required Activities | Gates¦GATE-0 | Activities¦A-R-055 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-056 | Required Activities | Gates¦GATE-0 | Activities¦A-R-056 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-057 | Required Activities | Gates¦GATE-0 | Activities¦A-R-057 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-058 | Required Activities | Gates¦GATE-0 | Activities¦A-R-058 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-061 | Required Activities | Gates¦GATE-0 | Activities¦A-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-062 | Required Activities | Gates¦GATE-0 | Activities¦A-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-063 | Required Activities | Gates¦GATE-0 | Activities¦A-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-064 | Required Activities | Gates¦GATE-0 | Activities¦A-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-065 | Required Activities | Gates¦GATE-0 | Activities¦A-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-066 | Required Activities | Gates¦GATE-0 | Activities¦A-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-067 | Required Activities | Gates¦GATE-0 | Activities¦A-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-068 | Required Activities | Gates¦GATE-0 | Activities¦A-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-069 | Required Activities | Gates¦GATE-0 | Activities¦A-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-070 | Required Activities | Gates¦GATE-0 | Activities¦A-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-074 | Required Activities | Gates¦GATE-0 | Activities¦A-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-079 | Required Activities | Gates¦GATE-0 | Activities¦A-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-R-087 | Required Activities | Gates¦GATE-0 | Activities¦A-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-17-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-17-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-17-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-17-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-17-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-17-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-17-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-17-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-17-05 | Required Activities | Gates¦GATE-0 | Activities¦A-S-17-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-18-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-18-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-18-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-18-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-18-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-18-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-18-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-18-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-18-05 | Required Activities | Gates¦GATE-0 | Activities¦A-S-18-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-19-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-19-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-19-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-19-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-19-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-19-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-19-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-19-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-19-05 | Required Activities | Gates¦GATE-0 | Activities¦A-S-19-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-20-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-20-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-20-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-20-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-20-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-20-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-20-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-20-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-20-05 | Required Activities | Gates¦GATE-0 | Activities¦A-S-20-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-21-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-21-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-21-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-21-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-21-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-21-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-21-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-21-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-21-05 | Required Activities | Gates¦GATE-0 | Activities¦A-S-21-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-22-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-22-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-22-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-22-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-22-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-22-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-22-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-22-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-22-05 | Required Activities | Gates¦GATE-0 | Activities¦A-S-22-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-23-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-23-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-23-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-23-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-23-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-23-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-23-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-23-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-24-01 | Required Activities | Gates¦GATE-0 | Activities¦A-S-24-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-24-02 | Required Activities | Gates¦GATE-0 | Activities¦A-S-24-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-24-03 | Required Activities | Gates¦GATE-0 | Activities¦A-S-24-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Activities | A-S-24-04 | Required Activities | Gates¦GATE-0 | Activities¦A-S-24-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-001 | Required Activities | Gates¦GATE-1 | Activities¦A-R-001 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-002 | Required Activities | Gates¦GATE-1 | Activities¦A-R-002 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-004 | Required Activities | Gates¦GATE-1 | Activities¦A-R-004 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-005 | Required Activities | Gates¦GATE-1 | Activities¦A-R-005 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-008 | Required Activities | Gates¦GATE-1 | Activities¦A-R-008 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-080 | Required Activities | Gates¦GATE-1 | Activities¦A-R-080 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-082 | Required Activities | Gates¦GATE-1 | Activities¦A-R-082 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-083 | Required Activities | Gates¦GATE-1 | Activities¦A-R-083 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-003 | Required Activities | Gates¦GATE-1 | Activities¦A-R-003 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-006 | Required Activities | Gates¦GATE-1 | Activities¦A-R-006 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-007 | Required Activities | Gates¦GATE-1 | Activities¦A-R-007 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-081 | Required Activities | Gates¦GATE-1 | Activities¦A-R-081 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-088 | Required Activities | Gates¦GATE-1 | Activities¦A-R-088 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-R-089 | Required Activities | Gates¦GATE-1 | Activities¦A-R-089 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-17-01 | Required Activities | Gates¦GATE-1 | Activities¦A-S-17-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-17-02 | Required Activities | Gates¦GATE-1 | Activities¦A-S-17-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-17-03 | Required Activities | Gates¦GATE-1 | Activities¦A-S-17-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-17-04 | Required Activities | Gates¦GATE-1 | Activities¦A-S-17-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-17-05 | Required Activities | Gates¦GATE-1 | Activities¦A-S-17-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-18-01 | Required Activities | Gates¦GATE-1 | Activities¦A-S-18-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-18-02 | Required Activities | Gates¦GATE-1 | Activities¦A-S-18-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-18-03 | Required Activities | Gates¦GATE-1 | Activities¦A-S-18-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-18-04 | Required Activities | Gates¦GATE-1 | Activities¦A-S-18-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-1 | Activities | A-S-18-05 | Required Activities | Gates¦GATE-1 | Activities¦A-S-18-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-009 | Required Activities | Gates¦GATE-2 | Activities¦A-R-009 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-010 | Required Activities | Gates¦GATE-2 | Activities¦A-R-010 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-011 | Required Activities | Gates¦GATE-2 | Activities¦A-R-011 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-016 | Required Activities | Gates¦GATE-2 | Activities¦A-R-016 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-017 | Required Activities | Gates¦GATE-2 | Activities¦A-R-017 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-018 | Required Activities | Gates¦GATE-2 | Activities¦A-R-018 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-012 | Required Activities | Gates¦GATE-2 | Activities¦A-R-012 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-013 | Required Activities | Gates¦GATE-2 | Activities¦A-R-013 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-014 | Required Activities | Gates¦GATE-2 | Activities¦A-R-014 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-2 | Activities | A-R-015 | Required Activities | Gates¦GATE-2 | Activities¦A-R-015 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-019 | Required Activities | Gates¦GATE-3 | Activities¦A-R-019 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-020 | Required Activities | Gates¦GATE-3 | Activities¦A-R-020 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-021 | Required Activities | Gates¦GATE-3 | Activities¦A-R-021 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-022 | Required Activities | Gates¦GATE-3 | Activities¦A-R-022 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-023 | Required Activities | Gates¦GATE-3 | Activities¦A-R-023 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-024 | Required Activities | Gates¦GATE-3 | Activities¦A-R-024 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-025 | Required Activities | Gates¦GATE-3 | Activities¦A-R-025 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-026 | Required Activities | Gates¦GATE-3 | Activities¦A-R-026 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-027 | Required Activities | Gates¦GATE-3 | Activities¦A-R-027 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-028 | Required Activities | Gates¦GATE-3 | Activities¦A-R-028 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-029 | Required Activities | Gates¦GATE-3 | Activities¦A-R-029 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-030 | Required Activities | Gates¦GATE-3 | Activities¦A-R-030 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-031 | Required Activities | Gates¦GATE-3 | Activities¦A-R-031 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-036 | Required Activities | Gates¦GATE-3 | Activities¦A-R-036 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-032 | Required Activities | Gates¦GATE-3 | Activities¦A-R-032 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-033 | Required Activities | Gates¦GATE-3 | Activities¦A-R-033 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-034 | Required Activities | Gates¦GATE-3 | Activities¦A-R-034 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-071 | Required Activities | Gates¦GATE-3 | Activities¦A-R-071 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-075 | Required Activities | Gates¦GATE-3 | Activities¦A-R-075 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-076 | Required Activities | Gates¦GATE-3 | Activities¦A-R-076 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-077 | Required Activities | Gates¦GATE-3 | Activities¦A-R-077 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-078 | Required Activities | Gates¦GATE-3 | Activities¦A-R-078 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-R-086 | Required Activities | Gates¦GATE-3 | Activities¦A-R-086 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-S-22-01 | Required Activities | Gates¦GATE-3 | Activities¦A-S-22-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-S-22-02 | Required Activities | Gates¦GATE-3 | Activities¦A-S-22-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-S-22-03 | Required Activities | Gates¦GATE-3 | Activities¦A-S-22-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-S-22-04 | Required Activities | Gates¦GATE-3 | Activities¦A-S-22-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-3 | Activities | A-S-22-05 | Required Activities | Gates¦GATE-3 | Activities¦A-S-22-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-035 | Required Activities | Gates¦GATE-4 | Activities¦A-R-035 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-043 | Required Activities | Gates¦GATE-4 | Activities¦A-R-043 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-085 | Required Activities | Gates¦GATE-4 | Activities¦A-R-085 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-055 | Required Activities | Gates¦GATE-4 | Activities¦A-R-055 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-056 | Required Activities | Gates¦GATE-4 | Activities¦A-R-056 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-057 | Required Activities | Gates¦GATE-4 | Activities¦A-R-057 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-058 | Required Activities | Gates¦GATE-4 | Activities¦A-R-058 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-S-23-01 | Required Activities | Gates¦GATE-4 | Activities¦A-S-23-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-S-23-02 | Required Activities | Gates¦GATE-4 | Activities¦A-S-23-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-S-23-03 | Required Activities | Gates¦GATE-4 | Activities¦A-S-23-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-S-23-04 | Required Activities | Gates¦GATE-4 | Activities¦A-S-23-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-061 | Required Activities | Gates¦GATE-4 | Activities¦A-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-062 | Required Activities | Gates¦GATE-4 | Activities¦A-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-063 | Required Activities | Gates¦GATE-4 | Activities¦A-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-064 | Required Activities | Gates¦GATE-4 | Activities¦A-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-065 | Required Activities | Gates¦GATE-4 | Activities¦A-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-066 | Required Activities | Gates¦GATE-4 | Activities¦A-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-067 | Required Activities | Gates¦GATE-4 | Activities¦A-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-068 | Required Activities | Gates¦GATE-4 | Activities¦A-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-069 | Required Activities | Gates¦GATE-4 | Activities¦A-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-070 | Required Activities | Gates¦GATE-4 | Activities¦A-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-074 | Required Activities | Gates¦GATE-4 | Activities¦A-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-079 | Required Activities | Gates¦GATE-4 | Activities¦A-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-4 | Activities | A-R-087 | Required Activities | Gates¦GATE-4 | Activities¦A-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-5 | Activities | A-R-037 | Required Activities | Gates¦GATE-5 | Activities¦A-R-037 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-5 | Activities | A-R-038 | Required Activities | Gates¦GATE-5 | Activities¦A-R-038 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-5 | Activities | A-R-039 | Required Activities | Gates¦GATE-5 | Activities¦A-R-039 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-5 | Activities | A-R-040 | Required Activities | Gates¦GATE-5 | Activities¦A-R-040 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-5 | Activities | A-R-041 | Required Activities | Gates¦GATE-5 | Activities¦A-R-041 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-5 | Activities | A-R-042 | Required Activities | Gates¦GATE-5 | Activities¦A-R-042 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-051 | Required Activities | Gates¦GATE-6 | Activities¦A-R-051 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-052 | Required Activities | Gates¦GATE-6 | Activities¦A-R-052 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-053 | Required Activities | Gates¦GATE-6 | Activities¦A-R-053 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-054 | Required Activities | Gates¦GATE-6 | Activities¦A-R-054 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-072 | Required Activities | Gates¦GATE-6 | Activities¦A-R-072 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-073 | Required Activities | Gates¦GATE-6 | Activities¦A-R-073 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-061 | Required Activities | Gates¦GATE-6 | Activities¦A-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-062 | Required Activities | Gates¦GATE-6 | Activities¦A-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-063 | Required Activities | Gates¦GATE-6 | Activities¦A-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-064 | Required Activities | Gates¦GATE-6 | Activities¦A-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-065 | Required Activities | Gates¦GATE-6 | Activities¦A-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-066 | Required Activities | Gates¦GATE-6 | Activities¦A-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-067 | Required Activities | Gates¦GATE-6 | Activities¦A-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-068 | Required Activities | Gates¦GATE-6 | Activities¦A-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-069 | Required Activities | Gates¦GATE-6 | Activities¦A-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-070 | Required Activities | Gates¦GATE-6 | Activities¦A-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-074 | Required Activities | Gates¦GATE-6 | Activities¦A-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-079 | Required Activities | Gates¦GATE-6 | Activities¦A-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-6 | Activities | A-R-087 | Required Activities | Gates¦GATE-6 | Activities¦A-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-044 | Required Activities | Gates¦GATE-7 | Activities¦A-R-044 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-045 | Required Activities | Gates¦GATE-7 | Activities¦A-R-045 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-046 | Required Activities | Gates¦GATE-7 | Activities¦A-R-046 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-047 | Required Activities | Gates¦GATE-7 | Activities¦A-R-047 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-048 | Required Activities | Gates¦GATE-7 | Activities¦A-R-048 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-049 | Required Activities | Gates¦GATE-7 | Activities¦A-R-049 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-050 | Required Activities | Gates¦GATE-7 | Activities¦A-R-050 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-059 | Required Activities | Gates¦GATE-7 | Activities¦A-R-059 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-060 | Required Activities | Gates¦GATE-7 | Activities¦A-R-060 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-084 | Required Activities | Gates¦GATE-7 | Activities¦A-R-084 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-051 | Required Activities | Gates¦GATE-7 | Activities¦A-R-051 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-052 | Required Activities | Gates¦GATE-7 | Activities¦A-R-052 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-053 | Required Activities | Gates¦GATE-7 | Activities¦A-R-053 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-054 | Required Activities | Gates¦GATE-7 | Activities¦A-R-054 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-072 | Required Activities | Gates¦GATE-7 | Activities¦A-R-072 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-R-073 | Required Activities | Gates¦GATE-7 | Activities¦A-R-073 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-19-01 | Required Activities | Gates¦GATE-7 | Activities¦A-S-19-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-19-02 | Required Activities | Gates¦GATE-7 | Activities¦A-S-19-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-19-03 | Required Activities | Gates¦GATE-7 | Activities¦A-S-19-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-19-04 | Required Activities | Gates¦GATE-7 | Activities¦A-S-19-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-19-05 | Required Activities | Gates¦GATE-7 | Activities¦A-S-19-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-20-01 | Required Activities | Gates¦GATE-7 | Activities¦A-S-20-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-20-02 | Required Activities | Gates¦GATE-7 | Activities¦A-S-20-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-20-03 | Required Activities | Gates¦GATE-7 | Activities¦A-S-20-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-20-04 | Required Activities | Gates¦GATE-7 | Activities¦A-S-20-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-20-05 | Required Activities | Gates¦GATE-7 | Activities¦A-S-20-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-21-01 | Required Activities | Gates¦GATE-7 | Activities¦A-S-21-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-21-02 | Required Activities | Gates¦GATE-7 | Activities¦A-S-21-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-21-03 | Required Activities | Gates¦GATE-7 | Activities¦A-S-21-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-21-04 | Required Activities | Gates¦GATE-7 | Activities¦A-S-21-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-21-05 | Required Activities | Gates¦GATE-7 | Activities¦A-S-21-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-23-01 | Required Activities | Gates¦GATE-7 | Activities¦A-S-23-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-23-02 | Required Activities | Gates¦GATE-7 | Activities¦A-S-23-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-23-03 | Required Activities | Gates¦GATE-7 | Activities¦A-S-23-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-7 | Activities | A-S-23-04 | Required Activities | Gates¦GATE-7 | Activities¦A-S-23-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-049 | Required Activities | Gates¦GATE-8 | Activities¦A-R-049 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-050 | Required Activities | Gates¦GATE-8 | Activities¦A-R-050 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-059 | Required Activities | Gates¦GATE-8 | Activities¦A-R-059 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-060 | Required Activities | Gates¦GATE-8 | Activities¦A-R-060 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-084 | Required Activities | Gates¦GATE-8 | Activities¦A-R-084 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-061 | Required Activities | Gates¦GATE-8 | Activities¦A-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-062 | Required Activities | Gates¦GATE-8 | Activities¦A-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-063 | Required Activities | Gates¦GATE-8 | Activities¦A-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-064 | Required Activities | Gates¦GATE-8 | Activities¦A-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-065 | Required Activities | Gates¦GATE-8 | Activities¦A-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-066 | Required Activities | Gates¦GATE-8 | Activities¦A-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-067 | Required Activities | Gates¦GATE-8 | Activities¦A-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-068 | Required Activities | Gates¦GATE-8 | Activities¦A-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-069 | Required Activities | Gates¦GATE-8 | Activities¦A-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-070 | Required Activities | Gates¦GATE-8 | Activities¦A-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-074 | Required Activities | Gates¦GATE-8 | Activities¦A-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-079 | Required Activities | Gates¦GATE-8 | Activities¦A-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-R-087 | Required Activities | Gates¦GATE-8 | Activities¦A-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-20-01 | Required Activities | Gates¦GATE-8 | Activities¦A-S-20-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-20-02 | Required Activities | Gates¦GATE-8 | Activities¦A-S-20-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-20-03 | Required Activities | Gates¦GATE-8 | Activities¦A-S-20-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-20-04 | Required Activities | Gates¦GATE-8 | Activities¦A-S-20-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-20-05 | Required Activities | Gates¦GATE-8 | Activities¦A-S-20-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-24-01 | Required Activities | Gates¦GATE-8 | Activities¦A-S-24-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-24-02 | Required Activities | Gates¦GATE-8 | Activities¦A-S-24-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-24-03 | Required Activities | Gates¦GATE-8 | Activities¦A-S-24-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-8 | Activities | A-S-24-04 | Required Activities | Gates¦GATE-8 | Activities¦A-S-24-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Activities" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-001 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-001 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-002 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-002 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-003 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-003 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-004 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-004 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-005 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-005 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-006 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-006 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-007 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-007 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-008 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-008 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-009 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-009 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-010 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-010 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-011 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-011 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-012 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-012 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-013 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-013 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-014 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-014 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-015 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-015 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-016 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-016 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-017 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-017 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-018 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-018 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-019 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-019 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-020 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-020 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-021 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-021 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-022 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-022 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-023 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-023 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-024 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-024 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-025 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-025 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-026 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-026 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-027 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-027 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-028 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-028 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-029 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-029 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-030 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-030 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-031 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-031 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-032 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-032 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-033 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-033 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-034 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-034 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-035 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-035 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-036 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-036 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-037 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-037 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-038 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-038 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-039 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-039 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-040 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-040 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-041 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-041 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-042 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-042 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-043 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-043 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-044 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-044 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-045 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-045 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-046 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-046 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-047 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-047 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-048 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-048 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-049 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-049 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-050 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-050 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-051 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-051 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-052 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-052 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-053 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-053 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-054 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-054 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-055 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-055 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-056 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-056 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-057 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-057 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-058 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-058 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-059 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-059 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-060 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-060 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-061 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-062 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-063 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-064 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-065 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-066 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-067 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-068 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-069 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-070 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-071 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-071 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-072 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-072 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-073 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-073 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-074 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-075 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-075 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-076 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-076 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-077 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-077 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-078 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-078 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-079 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-080 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-080 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-081 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-081 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-082 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-082 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-083 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-083 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-084 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-084 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-085 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-085 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-086 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-086 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-087 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-088 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-088 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-R-089 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-R-089 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-17-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-17-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-17-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-17-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-17-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-17-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-17-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-17-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-17-05 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-17-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-18-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-18-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-18-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-18-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-18-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-18-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-18-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-18-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-18-05 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-18-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-19-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-19-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-19-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-19-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-19-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-19-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-19-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-19-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-19-05 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-19-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-20-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-20-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-20-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-20-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-20-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-20-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-20-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-20-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-20-05 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-20-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-21-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-21-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-21-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-21-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-21-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-21-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-21-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-21-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-21-05 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-21-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-22-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-22-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-22-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-22-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-22-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-22-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-22-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-22-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-22-05 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-22-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-23-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-23-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-23-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-23-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-23-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-23-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-23-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-23-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-24-01 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-24-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-24-02 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-24-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-24-03 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-24-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-0 | Deliverables | D-S-24-04 | Required Deliverables | Gates¦GATE-0 | Deliverables¦D-S-24-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-001 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-001 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-002 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-002 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-003 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-003 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-004 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-004 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-005 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-005 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-006 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-006 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-007 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-007 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-008 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-008 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-080 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-080 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-081 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-081 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-082 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-082 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-083 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-083 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-088 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-088 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-R-089 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-R-089 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-17-01 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-17-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-17-02 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-17-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-17-03 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-17-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-17-04 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-17-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-17-05 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-17-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-18-01 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-18-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-18-02 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-18-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-18-03 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-18-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-18-04 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-18-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-1 | Deliverables | D-S-18-05 | Required Deliverables | Gates¦GATE-1 | Deliverables¦D-S-18-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-009 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-009 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-010 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-010 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-011 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-011 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-012 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-012 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-013 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-013 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-014 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-014 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-015 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-015 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-016 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-016 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-017 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-017 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-2 | Deliverables | D-R-018 | Required Deliverables | Gates¦GATE-2 | Deliverables¦D-R-018 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-019 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-019 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-020 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-020 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-021 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-021 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-022 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-022 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-023 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-023 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-024 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-024 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-025 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-025 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-026 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-026 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-027 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-027 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-028 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-028 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-029 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-029 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-030 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-030 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-031 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-031 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-032 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-032 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-033 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-033 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-034 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-034 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-036 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-036 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-071 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-071 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-075 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-075 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-076 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-076 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-077 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-077 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-078 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-078 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-R-086 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-R-086 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-S-22-01 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-S-22-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-S-22-02 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-S-22-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-S-22-03 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-S-22-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-S-22-04 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-S-22-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-3 | Deliverables | D-S-22-05 | Required Deliverables | Gates¦GATE-3 | Deliverables¦D-S-22-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-035 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-035 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-043 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-043 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-055 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-055 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-056 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-056 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-057 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-057 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-058 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-058 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-061 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-062 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-063 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-064 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-065 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-066 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-067 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-068 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-069 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-070 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-074 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-079 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-085 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-085 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-R-087 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-S-23-01 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-S-23-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-S-23-02 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-S-23-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-S-23-03 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-S-23-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-4 | Deliverables | D-S-23-04 | Required Deliverables | Gates¦GATE-4 | Deliverables¦D-S-23-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-5 | Deliverables | D-R-037 | Required Deliverables | Gates¦GATE-5 | Deliverables¦D-R-037 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-5 | Deliverables | D-R-038 | Required Deliverables | Gates¦GATE-5 | Deliverables¦D-R-038 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-5 | Deliverables | D-R-039 | Required Deliverables | Gates¦GATE-5 | Deliverables¦D-R-039 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-5 | Deliverables | D-R-040 | Required Deliverables | Gates¦GATE-5 | Deliverables¦D-R-040 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-5 | Deliverables | D-R-041 | Required Deliverables | Gates¦GATE-5 | Deliverables¦D-R-041 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-5 | Deliverables | D-R-042 | Required Deliverables | Gates¦GATE-5 | Deliverables¦D-R-042 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-051 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-051 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-052 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-052 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-053 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-053 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-054 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-054 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-061 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-062 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-063 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-064 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-065 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-066 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-067 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-068 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-069 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-070 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-072 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-072 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-073 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-073 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-074 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-079 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-6 | Deliverables | D-R-087 | Required Deliverables | Gates¦GATE-6 | Deliverables¦D-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-044 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-044 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-045 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-045 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-046 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-046 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-047 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-047 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-048 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-048 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-049 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-049 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-050 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-050 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-051 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-051 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-052 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-052 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-053 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-053 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-054 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-054 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-059 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-059 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-060 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-060 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-072 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-072 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-073 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-073 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-R-084 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-R-084 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-19-01 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-19-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-19-02 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-19-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-19-03 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-19-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-19-04 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-19-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-19-05 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-19-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-20-01 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-20-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-20-02 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-20-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-20-03 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-20-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-20-04 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-20-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-20-05 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-20-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-21-01 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-21-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-21-02 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-21-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-21-03 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-21-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-21-04 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-21-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-21-05 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-21-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-23-01 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-23-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-23-02 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-23-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-23-03 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-23-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-7 | Deliverables | D-S-23-04 | Required Deliverables | Gates¦GATE-7 | Deliverables¦D-S-23-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-049 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-049 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-050 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-050 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-059 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-059 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-060 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-060 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-061 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-061 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-062 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-062 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-063 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-063 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-064 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-064 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-065 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-065 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-066 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-066 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-067 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-067 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-068 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-068 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-069 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-069 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-070 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-070 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-074 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-074 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-079 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-079 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-084 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-084 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-R-087 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-R-087 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-20-01 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-20-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-20-02 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-20-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-20-03 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-20-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-20-04 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-20-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-20-05 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-20-05 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-24-01 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-24-01 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-24-02 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-24-02 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-24-03 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-24-03 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)
Gates | GATE-8 | Deliverables | D-S-24-04 | Required Deliverables | Gates¦GATE-8 | Deliverables¦D-S-24-04 | GATE_COVERS | Structural | Required | Primary |  | Rev.1 completion of list "Required Deliverables" (was missing from canonical link table)

## Gap_WPS
Gap ID | WPS ID | Gap Open | Critical Open
G-009 | WPS-03
G-S-23-02 | WPS-23
G-064 | WPS-16
G-030 | WPS-08
G-053 | WPS-14
G-S-24-03 | WPS-24
G-018 | WPS-03
G-073 | WPS-14
G-001 | WPS-01
G-S-20-03 | WPS-20
G-088 | WPS-02
G-065 | WPS-16
G-027 | WPS-07
G-066 | WPS-16
G-S-17-02 | WPS-17
G-046 | WPS-12
G-045 | WPS-12
G-086 | WPS-09
G-037 | WPS-10
G-087 | WPS-16
G-S-21-02 | WPS-21
G-S-17-05 | WPS-17
G-S-20-04 | WPS-20
G-071 | WPS-09
G-019 | WPS-06
G-049 | WPS-13
G-078 | WPS-09
G-002 | WPS-01
G-044 | WPS-12
G-S-21-05 | WPS-21
G-003 | WPS-02
G-055 | WPS-15
G-S-20-02 | WPS-20
G-007 | WPS-02
G-S-21-01 | WPS-21
G-016 | WPS-03
G-S-24-02 | WPS-24
G-043 | WPS-11
G-036 | WPS-08
G-082 | WPS-01
G-028 | WPS-07
G-079 | WPS-16
G-023 | WPS-07
G-048 | WPS-12
G-068 | WPS-16
G-035 | WPS-11
G-047 | WPS-12
G-031 | WPS-08
G-081 | WPS-02
G-S-20-01 | WPS-20
G-S-17-04 | WPS-17
G-S-22-01 | WPS-22
G-062 | WPS-16
G-021 | WPS-06
G-051 | WPS-14
G-020 | WPS-06
G-S-18-03 | WPS-18
G-S-24-04 | WPS-24
G-025 | WPS-07
G-034 | WPS-09
G-008 | WPS-01
G-014 | WPS-05
G-004 | WPS-01
G-069 | WPS-16
G-S-22-04 | WPS-22
G-024 | WPS-07
G-029 | WPS-08
G-052 | WPS-14
G-060 | WPS-13
G-076 | WPS-09
G-S-19-03 | WPS-19
G-017 | WPS-03
G-061 | WPS-16
G-S-23-03 | WPS-23
G-S-20-05 | WPS-20
G-063 | WPS-16
G-077 | WPS-09
G-006 | WPS-02
G-067 | WPS-16
G-S-19-01 | WPS-19
G-S-18-01 | WPS-18
G-S-22-03 | WPS-22
G-S-23-01 | WPS-23
G-032 | WPS-09
G-S-22-05 | WPS-22
G-S-17-03 | WPS-17
G-S-18-04 | WPS-18
G-050 | WPS-13
G-S-18-02 | WPS-18
G-S-17-01 | WPS-17
G-083 | WPS-01
G-056 | WPS-15
G-089 | WPS-02
G-010 | WPS-03
G-011 | WPS-03
G-075 | WPS-09
G-S-18-05 | WPS-18
G-041 | WPS-10
G-S-21-03 | WPS-21
G-040 | WPS-10
G-042 | WPS-10
G-S-22-02 | WPS-22
G-039 | WPS-10
G-012 | WPS-04
G-026 | WPS-07
G-072 | WPS-14
G-S-24-01 | WPS-24
G-057 | WPS-15
G-S-19-04 | WPS-19
G-005 | WPS-01
G-038 | WPS-10
G-070 | WPS-16
G-059 | WPS-13
G-S-23-04 | WPS-23
G-085 | WPS-11
G-058 | WPS-15
G-022 | WPS-06
G-033 | WPS-09
G-S-21-04 | WPS-21
G-054 | WPS-14
G-080 | WPS-01
G-074 | WPS-16
G-013 | WPS-04
G-084 | WPS-13
G-015 | WPS-05
G-S-19-05 | WPS-19
G-S-19-02 | WPS-19

## LISTS
Rules: Applicability Status | Rules: Criticality | Rules: Status | WPS: Applicability Status | WPS: WPS Status | Activities: Applicability Status | Gaps: Criticality | Gaps: Status | Evidence: Status | Execution: Relationship Type | Execution: Currency | Execution: Procurement Status | Execution: Long Lead Item | Execution: Risk Level | Risks: Status
Conditional | Critical | Approved | Conditional / Information Gap | Approved | Conditional | Critical | Approved | Approved | FS | USD | Not Started | No | Critical | Approved
Confirmed in principle | Major | Closed |  | Closed | Confirmed | High | Closed | Closed | Finish-to-Start |  |  |  | Major | Closed
Confirmed methodology |  | Completed |  | Completed | Confirmed in principle | Major | Completed | Completed | [5 empty] | Completed
|  | In Progress |  | In Progress | Confirmed methodology |  | In Progress | In Progress | [5 empty] | In Progress
|  | Not Applicable |  | Not Applicable |  |  | Not Applicable | Missing | [5 empty] | Not Applicable
|  | Not Started |  | Not Started |  |  | Not Opened | Missing / To Verify | [5 empty] | Not Started
|  | On Hold |  | On Hold |  |  | Not Started | Not Applicable | [5 empty] | On Hold
|  | Open |  | Open |  |  | On Hold | Not Started | [5 empty] | Open
|  | Rejected |  | Planned |  |  | Open | On Hold | [5 empty] | Recorded
|  | Submitted |  | Rejected |  |  | Rejected | Open | [5 empty] | Rejected
|  | Verified |  | Submitted |  |  | Submitted | Rejected | [5 empty] | Submitted
|  |  |  | Verified |  |  | Verified | Submitted | [5 empty] | Verified
Verified

## Department_Summary
Department | Executions | Approved Budget | Actual Cost | Weighted Progress
All Departments
Aviation / HSE
Aviation / Marine
Aviation / Regulatory
Aviation / Technical
Class & Regulatory
Engineering
Engineering / Environmental
Engineering / Medical
Environmental / Logistics
Environmental / Marine
HR / HSE
HR / Logistics
HR / Operations
HSE
HSE / Aviation
HSE / Operations
Maintenance
Maintenance / IT
Marine / E&I
Marine / HSE
Marine / Mechanical
Marine / Survey
Marine Operations
Medical / HSE
PMO
Procurement
Technical
UNASSIGNED
Warehouse / Maintenance

## MIGRATION_ISSUES
Entity | ID | Field | Source Value | Treatment
WPS | WPS-01 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-02 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-03 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-04 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-05 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-06 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-07 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-08 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-09 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-10 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-11 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-12 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-13 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-14 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-15 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-16 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-17 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-18 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-19 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-20 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-21 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-22 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-23 | Closure Date | TBC | Text date retained here; model input blank
WPS | WPS-24 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-001 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-001 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-001 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-002 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-002 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-002 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-003 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-003 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-003 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-004 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-004 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-004 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-005 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-005 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-005 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-006 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-006 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-006 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-007 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-007 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-007 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-008 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-008 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-008 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-009 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-009 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-009 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-010 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-010 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-010 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-011 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-011 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-011 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-012 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-012 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-012 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-013 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-013 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-013 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-014 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-014 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-014 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-015 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-015 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-015 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-016 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-016 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-016 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-017 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-017 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-017 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-018 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-018 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-018 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-019 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-019 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-019 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-020 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-020 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-020 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-021 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-021 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-021 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-022 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-022 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-022 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-023 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-023 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-023 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-024 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-024 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-024 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-025 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-025 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-025 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-026 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-026 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-026 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-027 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-027 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-027 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-028 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-028 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-028 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-029 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-029 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-029 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-030 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-030 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-030 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-031 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-031 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-031 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-032 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-032 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-032 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-033 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-033 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-033 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-034 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-034 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-034 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-035 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-035 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-035 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-036 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-036 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-036 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-037 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-037 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-037 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-038 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-038 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-038 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-039 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-039 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-039 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-040 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-040 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-040 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-041 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-041 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-041 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-042 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-042 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-042 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-043 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-043 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-043 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-044 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-044 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-044 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-045 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-045 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-045 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-046 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-046 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-046 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-047 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-047 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-047 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-048 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-048 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-048 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-049 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-049 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-049 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-050 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-050 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-050 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-051 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-051 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-051 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-052 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-052 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-052 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-053 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-053 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-053 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-054 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-054 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-054 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-055 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-055 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-055 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-056 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-056 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-056 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-057 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-057 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-057 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-058 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-058 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-058 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-059 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-059 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-059 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-060 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-060 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-060 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-061 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-061 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-061 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-062 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-062 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-062 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-063 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-063 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-063 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-064 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-064 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-064 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-065 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-065 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-065 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-066 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-066 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-066 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-067 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-067 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-067 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-068 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-068 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-068 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-069 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-069 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-069 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-070 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-070 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-070 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-071 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-071 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-071 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-072 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-072 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-072 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-073 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-073 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-073 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-074 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-074 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-074 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-075 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-075 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-075 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-076 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-076 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-076 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-077 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-077 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-077 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-078 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-078 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-078 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-079 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-079 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-079 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-080 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-080 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-080 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-081 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-081 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-081 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-082 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-082 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-082 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-083 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-083 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-083 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-084 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-084 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-084 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-085 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-085 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-085 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-086 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-086 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-086 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-087 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-087 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-087 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-088 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-088 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-088 | Closure Date | TBC | Text date retained here; model input blank
Activities | A-R-089 | Planned Start | TBC | Text date retained here; model input blank
Activities | A-R-089 | Planned Finish | TBC | Text date retained here; model input blank
Activities | A-R-089 | Closure Date | TBC | Text date retained here; model input blank
Deliverables | D-R-001 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-002 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-003 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-004 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-005 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-006 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-007 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-008 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-009 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-010 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-011 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-012 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-013 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-014 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-015 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-016 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-017 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-018 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-019 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-020 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-021 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-022 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-023 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-024 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-025 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-026 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-027 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-028 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-029 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-030 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-031 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-032 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-033 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-034 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-035 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-036 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-037 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-038 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-039 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-040 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-041 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-042 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-043 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-044 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-045 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-046 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-047 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-048 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-049 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-050 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-051 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-052 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-053 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-054 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-055 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-056 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-057 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-058 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-059 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-060 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-061 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-062 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-063 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-064 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-065 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-066 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-067 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-068 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-069 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-070 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-071 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-072 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-073 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-074 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-075 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-076 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-077 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-078 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-079 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-080 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-081 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-082 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-083 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-084 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-085 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-086 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-087 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-088 | Date | TBC | Text date retained here; model input blank
Deliverables | D-R-089 | Date | TBC | Text date retained here; model input blank
Tasks | T-R-001-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-001-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-001-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-001-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-001-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-001-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-002-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-002-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-002-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-002-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-002-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-002-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-003-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-003-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-003-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-003-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-003-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-003-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-004-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-004-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-004-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-004-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-004-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-004-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-005-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-005-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-005-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-005-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-005-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-005-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-006-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-006-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-006-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-006-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-006-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-006-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-007-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-007-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-007-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-007-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-007-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-007-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-008-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-008-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-008-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-008-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-008-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-008-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-009-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-009-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-009-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-009-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-009-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-009-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-010-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-010-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-010-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-010-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-010-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-010-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-011-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-011-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-011-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-011-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-011-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-011-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-012-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-012-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-012-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-012-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-012-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-012-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-013-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-013-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-013-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-013-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-013-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-013-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-014-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-014-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-014-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-014-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-014-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-014-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-015-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-015-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-015-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-015-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-015-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-015-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-016-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-016-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-016-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-016-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-016-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-016-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-017-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-017-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-017-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-017-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-017-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-017-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-018-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-018-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-018-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-018-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-018-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-018-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-019-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-019-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-019-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-019-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-019-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-019-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-020-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-020-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-020-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-020-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-020-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-020-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-021-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-021-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-021-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-021-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-021-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-021-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-022-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-022-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-022-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-022-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-022-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-022-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-023-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-023-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-023-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-023-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-023-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-023-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-024-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-024-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-024-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-024-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-024-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-024-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-025-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-025-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-025-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-025-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-025-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-025-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-026-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-026-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-026-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-026-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-026-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-026-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-027-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-027-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-027-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-027-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-027-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-027-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-028-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-028-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-028-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-028-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-028-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-028-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-029-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-029-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-029-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-029-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-029-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-029-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-030-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-030-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-030-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-030-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-030-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-030-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-031-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-031-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-031-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-031-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-031-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-031-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-032-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-032-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-032-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-032-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-032-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-032-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-033-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-033-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-033-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-033-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-033-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-033-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-034-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-034-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-034-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-034-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-034-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-034-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-035-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-035-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-035-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-035-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-035-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-035-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-036-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-036-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-036-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-036-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-036-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-036-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-037-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-037-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-037-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-037-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-037-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-037-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-038-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-038-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-038-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-038-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-038-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-038-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-039-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-039-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-039-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-039-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-039-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-039-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-040-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-040-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-040-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-040-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-040-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-040-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-041-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-041-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-041-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-041-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-041-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-041-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-042-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-042-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-042-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-042-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-042-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-042-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-043-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-043-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-043-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-043-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-043-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-043-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-044-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-044-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-044-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-044-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-044-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-044-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-045-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-045-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-045-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-045-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-045-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-045-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-046-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-046-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-046-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-046-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-046-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-046-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-047-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-047-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-047-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-047-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-047-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-047-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-048-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-048-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-048-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-048-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-048-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-048-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-049-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-049-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-049-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-049-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-049-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-049-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-050-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-050-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-050-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-050-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-050-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-050-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-051-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-051-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-051-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-051-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-051-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-051-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-052-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-052-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-052-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-052-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-052-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-052-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-053-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-053-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-053-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-053-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-053-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-053-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-054-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-054-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-054-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-054-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-054-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-054-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-055-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-055-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-055-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-055-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-055-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-055-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-056-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-056-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-056-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-056-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-056-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-056-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-057-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-057-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-057-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-057-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-057-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-057-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-058-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-058-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-058-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-058-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-058-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-058-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-059-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-059-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-059-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-059-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-059-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-059-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-060-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-060-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-060-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-060-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-060-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-060-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-061-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-061-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-061-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-061-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-061-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-061-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-062-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-062-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-062-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-062-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-062-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-062-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-063-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-063-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-063-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-063-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-063-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-063-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-064-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-064-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-064-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-064-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-064-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-064-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-065-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-065-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-065-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-065-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-065-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-065-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-066-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-066-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-066-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-066-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-066-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-066-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-067-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-067-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-067-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-067-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-067-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-067-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-068-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-068-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-068-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-068-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-068-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-068-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-069-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-069-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-069-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-069-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-069-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-069-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-070-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-070-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-070-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-070-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-070-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-070-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-071-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-071-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-071-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-071-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-071-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-071-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-072-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-072-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-072-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-072-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-072-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-072-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-073-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-073-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-073-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-073-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-073-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-073-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-074-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-074-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-074-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-074-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-074-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-074-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-075-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-075-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-075-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-075-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-075-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-075-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-076-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-076-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-076-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-076-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-076-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-076-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-077-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-077-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-077-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-077-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-077-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-077-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-078-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-078-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-078-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-078-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-078-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-078-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-079-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-079-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-079-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-079-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-079-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-079-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-080-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-080-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-080-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-080-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-080-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-080-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-081-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-081-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-081-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-081-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-081-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-081-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-082-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-082-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-082-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-082-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-082-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-082-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-083-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-083-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-083-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-083-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-083-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-083-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-084-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-084-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-084-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-084-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-084-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-084-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-085-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-085-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-085-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-085-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-085-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-085-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-086-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-086-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-086-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-086-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-086-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-086-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-087-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-087-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-087-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-087-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-087-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-087-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-088-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-088-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-088-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-088-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-088-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-088-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-089-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-089-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-089-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-089-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-R-089-03 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-R-089-03 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-05-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-05-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-17-05-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-17-05-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-05-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-05-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-18-05-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-18-05-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-05-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-05-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-19-05-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-19-05-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-05-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-05-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-20-05-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-20-05-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-05-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-05-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-21-05-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-21-05-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-05-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-05-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-22-05-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-22-05-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-23-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-23-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-01-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-01-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-01-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-01-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-02-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-02-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-02-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-02-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-03-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-03-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-03-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-03-02 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-04-01 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-04-01 | Planned Finish | TBC | Text date retained here; model input blank
Tasks | T-S-24-04-02 | Planned Start | TBC | Text date retained here; model input blank
Tasks | T-S-24-04-02 | Planned Finish | TBC | Text date retained here; model input blank
Gaps | G-001 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-001 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-002 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-002 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-003 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-003 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-004 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-004 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-005 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-005 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-006 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-006 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-007 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-007 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-008 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-008 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-009 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-009 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-010 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-010 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-011 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-011 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-012 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-012 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-013 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-013 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-014 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-014 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-015 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-015 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-016 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-016 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-017 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-017 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-018 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-018 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-019 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-019 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-020 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-020 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-021 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-021 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-022 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-022 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-023 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-023 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-024 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-024 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-025 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-025 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-026 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-026 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-027 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-027 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-028 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-028 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-029 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-029 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-030 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-030 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-031 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-031 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-032 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-032 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-033 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-033 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-034 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-034 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-035 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-035 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-036 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-036 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-037 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-037 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-038 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-038 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-039 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-039 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-040 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-040 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-041 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-041 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-042 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-042 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-043 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-043 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-044 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-044 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-045 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-045 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-046 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-046 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-047 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-047 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-048 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-048 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-049 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-049 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-050 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-050 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-051 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-051 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-052 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-052 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-053 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-053 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-054 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-054 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-055 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-055 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-056 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-056 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-057 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-057 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-058 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-058 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-059 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-059 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-060 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-060 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-061 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-061 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-062 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-062 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-063 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-063 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-064 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-064 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-065 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-065 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-066 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-066 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-067 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-067 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-068 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-068 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-069 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-069 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-070 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-070 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-071 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-071 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-072 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-072 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-073 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-073 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-074 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-074 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-075 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-075 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-076 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-076 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-077 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-077 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-078 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-078 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-079 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-079 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-080 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-080 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-081 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-081 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-082 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-082 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-083 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-083 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-084 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-084 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-085 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-085 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-086 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-086 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-087 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-087 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-088 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-088 | Closure Date | TBC | Text date retained here; model input blank
Gaps | G-089 | Due Date | TBC | Text date retained here; model input blank
Gaps | G-089 | Closure Date | TBC | Text date retained here; model input blank
Acceptance | AC-R-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-002 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-003 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-004 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-005 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-006 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-007 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-008 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-009 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-010 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-011 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-012 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-013 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-014 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-015 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-016 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-017 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-018 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-019 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-020 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-021 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-022 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-023 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-024 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-025 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-026 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-027 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-028 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-029 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-030 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-031 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-032 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-033 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-034 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-035 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-036 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-037 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-038 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-039 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-040 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-041 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-042 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-043 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-044 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-045 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-046 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-047 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-048 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-049 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-050 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-051 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-052 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-053 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-054 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-055 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-056 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-057 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-058 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-059 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-060 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-061 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-062 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-063 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-064 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-065 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-066 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-067 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-068 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-069 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-070 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-071 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-072 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-073 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-074 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-075 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-076 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-077 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-078 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-079 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-080 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-081 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-082 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-083 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-084 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-085 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-086 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-087 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-088 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-R-089 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-01-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-02-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-03-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-04-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-05-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-06-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-07-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-08-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-09-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-10-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-11-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-12-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-13-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-14-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-15-001 | Date Verified | TBC | Text date retained here; model input blank
Acceptance | AC-WPS-16-001 | Date Verified | TBC | Text date retained here; model input blank
Evidence | E-001 | Date | TBC | Text date retained here; model input blank
Evidence | E-001 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-001 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-002 | Date | TBC | Text date retained here; model input blank
Evidence | E-002 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-002 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-003 | Date | TBC | Text date retained here; model input blank
Evidence | E-003 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-003 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-004 | Date | TBC | Text date retained here; model input blank
Evidence | E-004 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-004 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-005 | Date | TBC | Text date retained here; model input blank
Evidence | E-005 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-005 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-006 | Date | TBC | Text date retained here; model input blank
Evidence | E-006 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-006 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-007 | Date | TBC | Text date retained here; model input blank
Evidence | E-007 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-007 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-008 | Date | TBC | Text date retained here; model input blank
Evidence | E-008 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-008 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-009 | Date | TBC | Text date retained here; model input blank
Evidence | E-009 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-009 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-010 | Date | TBC | Text date retained here; model input blank
Evidence | E-010 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-010 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-011 | Date | TBC | Text date retained here; model input blank
Evidence | E-011 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-011 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-012 | Date | TBC | Text date retained here; model input blank
Evidence | E-012 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-012 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-013 | Date | TBC | Text date retained here; model input blank
Evidence | E-013 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-013 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-014 | Date | TBC | Text date retained here; model input blank
Evidence | E-014 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-014 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-015 | Date | TBC | Text date retained here; model input blank
Evidence | E-015 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-015 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-016 | Date | TBC | Text date retained here; model input blank
Evidence | E-016 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-016 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-017 | Date | TBC | Text date retained here; model input blank
Evidence | E-017 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-017 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-018 | Date | TBC | Text date retained here; model input blank
Evidence | E-018 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-018 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-019 | Date | TBC | Text date retained here; model input blank
Evidence | E-019 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-019 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-020 | Date | TBC | Text date retained here; model input blank
Evidence | E-020 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-020 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-021 | Date | TBC | Text date retained here; model input blank
Evidence | E-021 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-021 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-022 | Date | TBC | Text date retained here; model input blank
Evidence | E-022 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-022 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-023 | Date | TBC | Text date retained here; model input blank
Evidence | E-023 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-023 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-024 | Date | TBC | Text date retained here; model input blank
Evidence | E-024 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-024 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-025 | Date | TBC | Text date retained here; model input blank
Evidence | E-025 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-025 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-026 | Date | TBC | Text date retained here; model input blank
Evidence | E-026 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-026 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-027 | Date | TBC | Text date retained here; model input blank
Evidence | E-027 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-027 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-028 | Date | TBC | Text date retained here; model input blank
Evidence | E-028 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-028 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-029 | Date | TBC | Text date retained here; model input blank
Evidence | E-029 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-029 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-030 | Date | TBC | Text date retained here; model input blank
Evidence | E-030 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-030 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-031 | Date | TBC | Text date retained here; model input blank
Evidence | E-031 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-031 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-032 | Date | TBC | Text date retained here; model input blank
Evidence | E-032 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-032 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-033 | Date | TBC | Text date retained here; model input blank
Evidence | E-033 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-033 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-034 | Date | TBC | Text date retained here; model input blank
Evidence | E-034 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-034 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-035 | Date | TBC | Text date retained here; model input blank
Evidence | E-035 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-035 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-036 | Date | TBC | Text date retained here; model input blank
Evidence | E-036 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-036 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-037 | Date | TBC | Text date retained here; model input blank
Evidence | E-037 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-037 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-038 | Date | TBC | Text date retained here; model input blank
Evidence | E-038 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-038 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-039 | Date | TBC | Text date retained here; model input blank
Evidence | E-039 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-039 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-040 | Date | TBC | Text date retained here; model input blank
Evidence | E-040 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-040 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-041 | Date | TBC | Text date retained here; model input blank
Evidence | E-041 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-041 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-042 | Date | TBC | Text date retained here; model input blank
Evidence | E-042 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-042 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-043 | Date | TBC | Text date retained here; model input blank
Evidence | E-043 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-043 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-044 | Date | TBC | Text date retained here; model input blank
Evidence | E-044 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-044 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-045 | Date | TBC | Text date retained here; model input blank
Evidence | E-045 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-045 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-046 | Date | TBC | Text date retained here; model input blank
Evidence | E-046 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-046 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-047 | Date | TBC | Text date retained here; model input blank
Evidence | E-047 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-047 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-048 | Date | TBC | Text date retained here; model input blank
Evidence | E-048 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-048 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-049 | Date | TBC | Text date retained here; model input blank
Evidence | E-049 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-049 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-050 | Date | TBC | Text date retained here; model input blank
Evidence | E-050 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-050 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-051 | Date | TBC | Text date retained here; model input blank
Evidence | E-051 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-051 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-052 | Date | TBC | Text date retained here; model input blank
Evidence | E-052 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-052 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-053 | Date | TBC | Text date retained here; model input blank
Evidence | E-053 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-053 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-054 | Date | TBC | Text date retained here; model input blank
Evidence | E-054 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-054 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-055 | Date | TBC | Text date retained here; model input blank
Evidence | E-055 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-055 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-056 | Date | TBC | Text date retained here; model input blank
Evidence | E-056 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-056 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-057 | Date | TBC | Text date retained here; model input blank
Evidence | E-057 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-057 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-058 | Date | TBC | Text date retained here; model input blank
Evidence | E-058 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-058 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-059 | Date | TBC | Text date retained here; model input blank
Evidence | E-059 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-059 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-060 | Date | TBC | Text date retained here; model input blank
Evidence | E-060 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-060 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-061 | Date | TBC | Text date retained here; model input blank
Evidence | E-061 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-061 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-062 | Date | TBC | Text date retained here; model input blank
Evidence | E-062 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-062 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-063 | Date | TBC | Text date retained here; model input blank
Evidence | E-063 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-063 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-064 | Date | TBC | Text date retained here; model input blank
Evidence | E-064 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-064 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-065 | Date | TBC | Text date retained here; model input blank
Evidence | E-065 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-065 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-066 | Date | TBC | Text date retained here; model input blank
Evidence | E-066 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-066 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-067 | Date | TBC | Text date retained here; model input blank
Evidence | E-067 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-067 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-068 | Date | TBC | Text date retained here; model input blank
Evidence | E-068 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-068 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-069 | Date | TBC | Text date retained here; model input blank
Evidence | E-069 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-069 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-070 | Date | TBC | Text date retained here; model input blank
Evidence | E-070 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-070 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-071 | Date | TBC | Text date retained here; model input blank
Evidence | E-071 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-071 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-072 | Date | TBC | Text date retained here; model input blank
Evidence | E-072 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-072 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-073 | Date | TBC | Text date retained here; model input blank
Evidence | E-073 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-073 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-074 | Date | TBC | Text date retained here; model input blank
Evidence | E-074 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-074 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-075 | Date | TBC | Text date retained here; model input blank
Evidence | E-075 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-075 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-076 | Date | TBC | Text date retained here; model input blank
Evidence | E-076 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-076 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-077 | Date | TBC | Text date retained here; model input blank
Evidence | E-077 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-077 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-078 | Date | TBC | Text date retained here; model input blank
Evidence | E-078 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-078 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-079 | Date | TBC | Text date retained here; model input blank
Evidence | E-079 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-079 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-080 | Date | TBC | Text date retained here; model input blank
Evidence | E-080 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-080 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-081 | Date | TBC | Text date retained here; model input blank
Evidence | E-081 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-081 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-082 | Date | TBC | Text date retained here; model input blank
Evidence | E-082 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-082 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-083 | Date | TBC | Text date retained here; model input blank
Evidence | E-083 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-083 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-084 | Date | TBC | Text date retained here; model input blank
Evidence | E-084 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-084 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-085 | Date | TBC | Text date retained here; model input blank
Evidence | E-085 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-085 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-086 | Date | TBC | Text date retained here; model input blank
Evidence | E-086 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-086 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-087 | Date | TBC | Text date retained here; model input blank
Evidence | E-087 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-087 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-088 | Date | TBC | Text date retained here; model input blank
Evidence | E-088 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-088 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-089 | Date | TBC | Text date retained here; model input blank
Evidence | E-089 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-089 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-090 | Date | TBC | Text date retained here; model input blank
Evidence | E-090 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-090 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-091 | Date | TBC | Text date retained here; model input blank
Evidence | E-091 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-091 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-092 | Date | TBC | Text date retained here; model input blank
Evidence | E-092 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-092 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-093 | Date | TBC | Text date retained here; model input blank
Evidence | E-093 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-093 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-094 | Date | TBC | Text date retained here; model input blank
Evidence | E-094 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-094 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-095 | Date | TBC | Text date retained here; model input blank
Evidence | E-095 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-095 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-096 | Date | TBC | Text date retained here; model input blank
Evidence | E-096 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-096 | Verification Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-05 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-17-05 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-05 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-18-05 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-05 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-19-05 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-05 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-20-05 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-05 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-21-05 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-05 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-22-05 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-23-04 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-01 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-01 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-02 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-02 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-03 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-03 | Expiry Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-04 | Date | TBC | Text date retained here; model input blank
Evidence | E-S-24-04 | Expiry Date | TBC | Text date retained here; model input blank
Gates | GATE-0 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-1 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-2 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-3 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-4 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-5 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-6 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-7 | Review Date | TBC | Text date retained here; model input blank
Gates | GATE-8 | Review Date | TBC | Text date retained here; model input blank
Execution | T-R-001-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-001-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-001-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-001-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-001-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-001-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-002-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-002-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-002-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-002-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-002-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-002-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-003-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-003-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-003-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-003-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-003-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-003-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-004-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-004-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-004-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-004-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-004-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-004-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-005-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-005-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-005-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-005-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-005-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-005-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-006-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-006-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-006-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-006-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-006-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-006-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-007-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-007-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-007-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-007-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-007-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-007-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-008-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-008-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-008-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-008-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-008-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-008-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-009-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-009-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-009-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-009-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-009-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-009-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-010-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-010-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-010-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-010-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-010-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-010-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-011-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-011-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-011-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-011-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-011-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-011-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-012-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-012-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-012-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-012-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-012-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-012-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-013-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-013-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-013-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-013-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-013-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-013-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-014-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-014-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-014-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-014-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-014-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-014-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-015-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-015-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-015-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-015-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-015-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-015-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-016-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-016-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-016-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-016-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-016-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-016-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-017-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-017-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-017-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-017-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-017-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-017-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-018-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-018-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-018-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-018-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-018-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-018-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-019-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-019-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-019-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-019-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-019-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-019-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-020-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-020-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-020-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-020-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-020-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-020-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-021-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-021-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-021-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-021-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-021-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-021-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-022-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-022-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-022-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-022-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-022-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-022-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-023-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-023-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-023-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-023-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-023-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-023-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-024-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-024-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-024-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-024-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-024-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-024-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-025-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-025-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-025-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-025-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-025-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-025-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-026-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-026-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-026-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-026-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-026-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-026-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-027-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-027-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-027-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-027-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-027-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-027-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-028-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-028-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-028-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-028-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-028-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-028-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-029-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-029-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-029-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-029-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-029-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-029-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-030-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-030-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-030-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-030-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-030-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-030-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-031-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-031-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-031-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-031-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-031-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-031-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-032-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-032-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-032-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-032-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-032-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-032-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-033-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-033-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-033-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-033-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-033-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-033-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-034-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-034-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-034-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-034-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-034-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-034-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-035-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-035-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-035-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-035-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-035-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-035-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-036-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-036-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-036-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-036-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-036-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-036-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-037-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-037-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-037-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-037-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-037-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-037-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-038-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-038-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-038-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-038-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-038-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-038-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-039-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-039-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-039-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-039-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-039-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-039-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-040-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-040-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-040-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-040-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-040-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-040-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-041-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-041-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-041-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-041-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-041-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-041-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-042-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-042-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-042-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-042-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-042-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-042-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-043-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-043-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-043-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-043-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-043-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-043-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-044-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-044-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-044-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-044-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-044-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-044-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-045-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-045-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-045-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-045-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-045-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-045-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-046-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-046-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-046-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-046-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-046-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-046-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-047-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-047-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-047-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-047-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-047-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-047-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-048-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-048-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-048-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-048-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-048-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-048-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-049-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-049-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-049-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-049-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-049-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-049-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-050-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-050-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-050-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-050-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-050-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-050-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-051-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-051-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-051-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-051-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-051-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-051-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-052-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-052-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-052-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-052-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-052-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-052-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-053-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-053-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-053-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-053-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-053-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-053-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-054-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-054-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-054-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-054-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-054-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-054-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-055-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-055-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-055-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-055-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-055-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-055-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-056-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-056-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-056-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-056-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-056-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-056-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-057-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-057-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-057-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-057-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-057-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-057-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-058-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-058-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-058-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-058-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-058-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-058-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-059-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-059-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-059-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-059-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-059-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-059-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-060-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-060-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-060-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-060-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-060-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-060-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-061-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-061-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-061-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-061-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-061-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-061-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-062-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-062-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-062-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-062-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-062-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-062-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-063-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-063-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-063-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-063-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-063-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-063-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-064-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-064-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-064-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-064-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-064-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-064-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-065-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-065-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-065-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-065-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-065-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-065-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-066-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-066-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-066-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-066-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-066-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-066-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-067-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-067-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-067-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-067-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-067-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-067-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-068-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-068-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-068-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-068-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-068-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-068-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-069-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-069-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-069-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-069-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-069-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-069-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-070-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-070-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-070-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-070-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-070-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-070-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-071-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-071-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-071-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-071-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-071-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-071-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-072-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-072-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-072-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-072-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-072-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-072-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-073-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-073-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-073-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-073-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-073-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-073-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-074-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-074-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-074-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-074-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-074-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-074-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-075-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-075-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-075-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-075-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-075-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-075-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-076-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-076-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-076-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-076-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-076-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-076-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-077-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-077-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-077-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-077-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-077-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-077-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-078-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-078-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-078-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-078-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-078-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-078-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-079-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-079-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-079-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-079-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-079-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-079-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-080-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-080-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-080-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-080-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-080-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-080-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-081-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-081-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-081-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-081-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-081-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-081-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-082-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-082-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-082-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-082-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-082-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-082-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-083-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-083-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-083-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-083-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-083-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-083-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-084-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-084-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-084-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-084-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-084-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-084-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-085-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-085-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-085-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-085-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-085-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-085-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-086-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-086-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-086-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-086-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-086-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-086-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-087-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-087-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-087-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-087-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-087-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-087-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-088-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-088-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-088-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-088-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-088-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-088-03 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-089-01 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-089-01 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-089-02 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-089-02 | Planned Finish | TBC | Text date retained here; model input blank
Execution | T-R-089-03 | Planned Start | TBC | Text date retained here; model input blank
Execution | T-R-089-03 | Planned Finish | TBC | Text date retained here; model input blank

## REDTEAM_RESULTS
Run ID | Test ID | Category | Entity | Record ID | Expected | Actual | Result | Timestamp
NOT RUN

## REDTEAM_HISTORY
Run ID | Timestamp | Checks | Failures | Result
NOT RUN

## DATA_DICTIONARY
Entity | Field | Role | Source
Rules | Rule ID | Primary key | 01_RULES_BOOKLET
Rules | Rule Group ID | Input / source attribute | 01_RULES_BOOKLET
Rules | Rule Title / Requirement | Input / source attribute | 01_RULES_BOOKLET
Rules | Authority / Source | Input / source attribute | 01_RULES_BOOKLET
Rules | Source Document | Input / source attribute | 01_RULES_BOOKLET
Rules | Document Number | Input / source attribute | 01_RULES_BOOKLET
Rules | Edition / Year | Input / source attribute | 01_RULES_BOOKLET
Rules | Effective Date | Input / source attribute | 01_RULES_BOOKLET
Rules | Part | Input / source attribute | 01_RULES_BOOKLET
Rules | Chapter | Input / source attribute | 01_RULES_BOOKLET
Rules | Section | Input / source attribute | 01_RULES_BOOKLET
Rules | Paragraph | Input / source attribute | 01_RULES_BOOKLET
Rules | Requirement Text | Input / source attribute | 01_RULES_BOOKLET
Rules | Applicability Trigger | Input / source attribute | 01_RULES_BOOKLET
Rules | Applicability Status | Input / source attribute | 01_RULES_BOOKLET
Rules | Requirement Type | Input / source attribute | 01_RULES_BOOKLET
Rules | PMS-11 System | Input / source attribute | 01_RULES_BOOKLET
Rules | Required Evidence | Input / source attribute | 01_RULES_BOOKLET
Rules | Evidence Owner | Input / source attribute | 01_RULES_BOOKLET
Rules | Verification Method | Input / source attribute | 01_RULES_BOOKLET
Rules | Criticality | Input / source attribute | 01_RULES_BOOKLET
Rules | WPS ID | Input / source attribute | 01_RULES_BOOKLET
Rules | Activity ID | Input / source attribute | 01_RULES_BOOKLET
Rules | Deliverable ID | Input / source attribute | 01_RULES_BOOKLET
Rules | Gap ID | Input / source attribute | 01_RULES_BOOKLET
Rules | Acceptance Criteria ID | Input / source attribute | 01_RULES_BOOKLET
Rules | Closure Authority | Input / source attribute | 01_RULES_BOOKLET
Rules | Status | Input / source attribute | 01_RULES_BOOKLET
Rules | Source URL | Input / source attribute | 01_RULES_BOOKLET
Rules | Notes | Input / source attribute | 01_RULES_BOOKLET
Rules | Source Rule ID | Input / source attribute | 01_RULES_BOOKLET
WPS | WPS ID | Primary key | 03_WPS_REGISTER
WPS | WPS Name | Input / source attribute | 03_WPS_REGISTER
WPS | Rule Count | Calculated | 03_WPS_REGISTER
WPS | Verification Streams | Input / source attribute | 03_WPS_REGISTER
WPS | Primary Rule Domains | Input / source attribute | 03_WPS_REGISTER
WPS | Readiness Gate | Input / source attribute | 03_WPS_REGISTER
WPS | Objective | Input / source attribute | 03_WPS_REGISTER
WPS | Scope Included | Input / source attribute | 03_WPS_REGISTER
WPS | Scope Excluded | Input / source attribute | 03_WPS_REGISTER
WPS | Source Rule IDs | Input / source attribute | 03_WPS_REGISTER
WPS | Governing Sources | Input / source attribute | 03_WPS_REGISTER
WPS | Applicability Status | Input / source attribute | 03_WPS_REGISTER
WPS | Prerequisites / Inputs | Input / source attribute | 03_WPS_REGISTER
WPS | Required Activities | Input / source attribute | 03_WPS_REGISTER
WPS | Required Deliverables | Input / source attribute | 03_WPS_REGISTER
WPS | Predecessor WPS IDs | Input / source attribute | 03_WPS_REGISTER
WPS | Successor WPS IDs | Input / source attribute | 03_WPS_REGISTER
WPS | Dependency Type | Input / source attribute | 03_WPS_REGISTER
WPS | Responsible Lead | Input / source attribute | 03_WPS_REGISTER
WPS | Accountable Authority | Input / source attribute | 03_WPS_REGISTER
WPS | Consulted Parties | Input / source attribute | 03_WPS_REGISTER
WPS | Informed Parties | Input / source attribute | 03_WPS_REGISTER
WPS | Criticality | Input / source attribute | 03_WPS_REGISTER
WPS | WPS Acceptance Criteria ID | Input / source attribute | 03_WPS_REGISTER
WPS | WPS Acceptance Evidence | Input / source attribute | 03_WPS_REGISTER
WPS | WPS Status | Input / source attribute | 03_WPS_REGISTER
WPS | Open Gap Count | Calculated | 03_WPS_REGISTER
WPS | Critical Gap Count | Calculated | 03_WPS_REGISTER
WPS | Closure Authority | Input / source attribute | 03_WPS_REGISTER
WPS | Closure Date | Input / source attribute | 03_WPS_REGISTER
WPS | Notes | Input / source attribute | 03_WPS_REGISTER
WPS | Execution Count | Calculated | 03_WPS_REGISTER
WPS | Weighted Progress | Calculated | 03_WPS_REGISTER
WPS | Control Readiness | Calculated | 03_WPS_REGISTER
Activities | Activity ID | Primary key | 04_ACTIVITY_REGISTER
Activities | WPS ID | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Activity Group ID | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Activity Title | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Activity Description | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Activity Type | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Source Rule IDs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Applicability Status | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Trigger | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Required Inputs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Activity Owner | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Accountable Authority | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Consulted Parties | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Predecessor Activity IDs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Dependency Type | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Successor Activity IDs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Planned Start | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Planned Finish | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Duration | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Actual Start | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Actual Finish | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Status | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Priority | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Critical Path | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Related Deliverable IDs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Related Acceptance Criteria IDs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Related Gap IDs | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Evidence Required | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Verification Method | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Closure Authority | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Closure Date | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Source Activity ID | Input / source attribute | 04_ACTIVITY_REGISTER
Activities | Notes | Input / source attribute | 04_ACTIVITY_REGISTER
Deliverables | Deliverable ID | Primary key | 05_DELIVERABLE_REGISTER
Deliverables | WPS ID | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Activity ID | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Deliverable Name | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Deliverable Type | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Description | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Source Rule IDs | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Required Format | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Prepared By | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Reviewed By | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Approved By | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Required Before | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Acceptance Criteria ID | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Evidence Location | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Revision | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Date | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Status | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Rejected Reason | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Superseded By | Input / source attribute | 05_DELIVERABLE_REGISTER
Deliverables | Notes | Input / source attribute | 05_DELIVERABLE_REGISTER
Tasks | Task ID | Primary key | 06_TASK_REGISTER
Tasks | Activity ID | Input / source attribute | 06_TASK_REGISTER
Tasks | WPS ID | Input / source attribute | 06_TASK_REGISTER
Tasks | Task Title | Input / source attribute | 06_TASK_REGISTER
Tasks | Task Description | Input / source attribute | 06_TASK_REGISTER
Tasks | Task Sequence | Input / source attribute | 06_TASK_REGISTER
Tasks | Task Owner | Input / source attribute | 06_TASK_REGISTER
Tasks | Required Input | Input / source attribute | 06_TASK_REGISTER
Tasks | Expected Output | Input / source attribute | 06_TASK_REGISTER
Tasks | Predecessor Task IDs | Input / source attribute | 06_TASK_REGISTER
Tasks | Dependency Type | Input / source attribute | 06_TASK_REGISTER
Tasks | Successor Task IDs | Input / source attribute | 06_TASK_REGISTER
Tasks | Planned Start | Input / source attribute | 06_TASK_REGISTER
Tasks | Planned Finish | Input / source attribute | 06_TASK_REGISTER
Tasks | Duration | Input / source attribute | 06_TASK_REGISTER
Tasks | Actual Start | Input / source attribute | 06_TASK_REGISTER
Tasks | Actual Finish | Input / source attribute | 06_TASK_REGISTER
Tasks | Status | Input / source attribute | 06_TASK_REGISTER
Tasks | Related Deliverable ID | Input / source attribute | 06_TASK_REGISTER
Tasks | Related Gap ID | Input / source attribute | 06_TASK_REGISTER
Tasks | Acceptance Criteria ID | Input / source attribute | 06_TASK_REGISTER
Tasks | Completion Evidence | Input / source attribute | 06_TASK_REGISTER
Tasks | Completion Authority | Input / source attribute | 06_TASK_REGISTER
Tasks | Notes | Input / source attribute | 06_TASK_REGISTER
Gaps | Gap ID | Primary key | 08_GAP_REGISTER
Gaps | Gap Title | Input / source attribute | 08_GAP_REGISTER
Gaps | Gap Category | Input / source attribute | 08_GAP_REGISTER
Gaps | Detailed Description | Input / source attribute | 08_GAP_REGISTER
Gaps | Source Rule IDs | Input / source attribute | 08_GAP_REGISTER
Gaps | Related WPS IDs | Input / source attribute | 08_GAP_REGISTER
Gaps | Related Activity IDs | Input / source attribute | 08_GAP_REGISTER
Gaps | Related Deliverable IDs | Input / source attribute | 08_GAP_REGISTER
Gaps | Why It Matters | Input / source attribute | 08_GAP_REGISTER
Gaps | Consequence | Input / source attribute | 08_GAP_REGISTER
Gaps | Criticality | Input / source attribute | 08_GAP_REGISTER
Gaps | Risk Rating | Input / source attribute | 08_GAP_REGISTER
Gaps | Required Closure Action | Input / source attribute | 08_GAP_REGISTER
Gaps | Required Evidence | Input / source attribute | 08_GAP_REGISTER
Gaps | Gap Owner | Input / source attribute | 08_GAP_REGISTER
Gaps | Closure Authority | Input / source attribute | 08_GAP_REGISTER
Gaps | Blocked Gate | Input / source attribute | 08_GAP_REGISTER
Gaps | Due Date | Input / source attribute | 08_GAP_REGISTER
Gaps | Status | Input / source attribute | 08_GAP_REGISTER
Gaps | Residual Risk | Input / source attribute | 08_GAP_REGISTER
Gaps | Risk Acceptance Authority | Input / source attribute | 08_GAP_REGISTER
Gaps | Closure Evidence | Input / source attribute | 08_GAP_REGISTER
Gaps | Closure Date | Input / source attribute | 08_GAP_REGISTER
Gaps | Notes | Input / source attribute | 08_GAP_REGISTER
Acceptance | Acceptance Criteria ID | Primary key | 09_ACCEPTANCE_CRITERIA
Acceptance | Applies To Type | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Applies To ID | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Rule ID | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | WPS ID | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Activity ID | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Task ID | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Criteria Statement | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Verification Method | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Measurement / Threshold | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Required Evidence | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Acceptance Authority | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Rejection Condition | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Escalation Condition | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Status | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Evidence ID | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Date Verified | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Reviewer | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Acceptance | Comments | Input / source attribute | 09_ACCEPTANCE_CRITERIA
Evidence | Evidence ID | Primary key | 10_EVIDENCE_REGISTER
Evidence | Document Title / Request | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Document Type | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Document Number | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Revision | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Date | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Expiry Date | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Issuing Authority | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Vessel/System/Equipment | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Rule IDs | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | WPS IDs | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Activity IDs | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Task IDs | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Gap IDs | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Acceptance Criteria IDs | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Custodian | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | File Location | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Status | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Verified By | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Verification Date | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Approved By | Input / source attribute | 10_EVIDENCE_REGISTER
Evidence | Comments | Input / source attribute | 10_EVIDENCE_REGISTER
Gates | Gate ID | Primary key | 13_READINESS_GATES
Gates | Gate Name | Input / source attribute | 13_READINESS_GATES
Gates | Objective | Input / source attribute | 13_READINESS_GATES
Gates | Required WPS IDs | Input / source attribute | 13_READINESS_GATES
Gates | Required Activities | Input / source attribute | 13_READINESS_GATES
Gates | Required Deliverables | Input / source attribute | 13_READINESS_GATES
Gates | Critical Gaps Allowed | Input / source attribute | 13_READINESS_GATES
Gates | No-Go Conditions | Input / source attribute | 13_READINESS_GATES
Gates | Acceptance Criteria IDs | Input / source attribute | 13_READINESS_GATES
Gates | Approving Authority | Input / source attribute | 13_READINESS_GATES
Gates | Review Date | Input / source attribute | 13_READINESS_GATES
Gates | Status | Input / source attribute | 13_READINESS_GATES
Gates | Decision | Input / source attribute | 13_READINESS_GATES
Gates | Decision Evidence | Input / source attribute | 13_READINESS_GATES
Gates | Open Conditions | Input / source attribute | 13_READINESS_GATES
Gates | Notes | Input / source attribute | 13_READINESS_GATES
Execution | Execution ID | Primary key | 30_EXECUTION_CONTROL
Execution | WPS ID | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Activity / Task Title | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Source Type | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Canonical Reference | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Responsible Department | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Discipline Lead | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Accountable Manager | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Logical Predecessor IDs | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Schedule Predecessor IDs | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Relationship Type | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Lag Days | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Planned Start | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Planned Finish | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Forecast Finish | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Actual Start | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Actual Finish | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Duration Days | Calculated | 30_EXECUTION_CONTROL
Execution | Status | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Completion % | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Weight % | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Earned Progress % | Calculated | 30_EXECUTION_CONTROL
Execution | Estimated Cost | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Approved Budget | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Committed Cost | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Actual Cost | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Estimate at Completion | Calculated | 30_EXECUTION_CONTROL
Execution | Budget Variance | Calculated | 30_EXECUTION_CONTROL
Execution | Currency | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Manpower Required | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Planned Manhours | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Actual Manhours | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Materials Required | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Spare Parts Required | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Procurement Status | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Procurement Lead Time Days | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Long Lead Item | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Required On Site | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Evidence Required | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Acceptance Authority | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Risk Level | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Blocking Gate | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Classified Input Ref | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Comments | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Remaining Estimate | Input / source attribute | 30_EXECUTION_CONTROL
Execution | Overdue | Calculated | 30_EXECUTION_CONTROL
Execution | Data Quality | Calculated | 30_EXECUTION_CONTROL
Functional | Functional_Activity_ID | Primary key | 24_FUSED_ACTIVITY_MASTER
Functional | WPS_ID | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | WPS_Name | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Deliverable_Name | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Governing_Rule_Ref | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Activity_Seq_No | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Activity_Type | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Detailed_Activity_Desc | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Responsible_Owner | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | External_Authority | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Prerequisite_Activity_ID | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Evidence_Document_Type | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Evidence_Output | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Final_Acceptance_Criteria | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Risk_Level | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Jordan_Context_Note | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Canonical_Acceptance_Criteria_ID | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Gap_ID | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Canonical_Activity_ID | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Canonical_Deliverable_ID | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Functional | Readiness_Gate | Input / source attribute | 24_FUSED_ACTIVITY_MASTER
Dependencies | Link ID | Primary key | 32_WPS_LOGIC_NETWORK
Dependencies | Predecessor ID | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Successor ID | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Relationship | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Lag Days | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Dependency Class | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Rationale | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Validated By | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Validation Status | Input / source attribute | 32_WPS_LOGIC_NETWORK
Dependencies | Comments | Input / source attribute | 32_WPS_LOGIC_NETWORK
Sources | Source Record ID | Primary key | 02_SOURCE_REGISTER
Sources | Source ID | Input / source attribute | 02_SOURCE_REGISTER
Sources | Authority | Input / source attribute | 02_SOURCE_REGISTER
Sources | Source Type | Input / source attribute | 02_SOURCE_REGISTER
Sources | Document Title | Input / source attribute | 02_SOURCE_REGISTER
Sources | Document Number | Input / source attribute | 02_SOURCE_REGISTER
Sources | Edition | Input / source attribute | 02_SOURCE_REGISTER
Sources | Issue Date | Input / source attribute | 02_SOURCE_REGISTER
Sources | Effective Date | Input / source attribute | 02_SOURCE_REGISTER
Sources | URL | Input / source attribute | 02_SOURCE_REGISTER
Sources | Local Copy Available | Input / source attribute | 02_SOURCE_REGISTER
Sources | Verified Against Official Source | Input / source attribute | 02_SOURCE_REGISTER
Sources | Applicability Note | Input / source attribute | 02_SOURCE_REGISTER
Sources | Related Rule IDs | Input / source attribute | 02_SOURCE_REGISTER
Sources | Status | Input / source attribute | 02_SOURCE_REGISTER
Sources | Notes | Input / source attribute | 02_SOURCE_REGISTER
Responsibilities | Responsibility Record ID | Primary key | 11_RESPONSIBILITY_MATRIX
Responsibilities | WPS ID | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Activity ID | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Task ID | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Rule ID | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Owner | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Accountable | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | DNV | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Egyptian Flag | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Jordan Maritime Commission | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | ASEZA | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Harbor Master / VTS | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | OEM | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Client | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | MWS | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Diving Contractor | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Tow Contractor | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Responsibilities | Status | Input / source attribute | 11_RESPONSIBILITY_MATRIX
Risks | Record ID | Primary key | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Type | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Description | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Related Rule IDs | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Related WPS IDs | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Related Gap IDs | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Impact | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Probability | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Risk Rating | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Mitigation | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Owner | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Decision Authority | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Assumption Valid Until | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Status | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Decision Date | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Evidence | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Risks | Notes | Input / source attribute | 14_RISK_ASSUMPTIONS_DECISIONS
Changes | Change ID | Primary key | 15_CHANGE_CONTROL
Changes | Date Raised | Input / source attribute | 15_CHANGE_CONTROL
Changes | Raised By | Input / source attribute | 15_CHANGE_CONTROL
Changes | Change Description | Input / source attribute | 15_CHANGE_CONTROL
Changes | Affected Rule IDs | Input / source attribute | 15_CHANGE_CONTROL
Changes | Affected WPS IDs | Input / source attribute | 15_CHANGE_CONTROL
Changes | Affected Activities | Input / source attribute | 15_CHANGE_CONTROL
Changes | Affected Deliverables | Input / source attribute | 15_CHANGE_CONTROL
Changes | Reason | Input / source attribute | 15_CHANGE_CONTROL
Changes | Impact | Input / source attribute | 15_CHANGE_CONTROL
Changes | Review Authority | Input / source attribute | 15_CHANGE_CONTROL
Changes | Approval Authority | Input / source attribute | 15_CHANGE_CONTROL
Changes | Decision | Input / source attribute | 15_CHANGE_CONTROL
Changes | Revision Required | Input / source attribute | 15_CHANGE_CONTROL
Changes | Status | Input / source attribute | 15_CHANGE_CONTROL
Changes | Closure Evidence | Input / source attribute | 15_CHANGE_CONTROL

## POWERPIVOT_RELATIONS
Foreign Table | Foreign Column | Primary Table | Primary Column | Mode | Purpose
tblRules | WPS ID | tblWPS | WPS ID | ACTIVE
tblActivities | WPS ID | tblWPS | WPS ID | ACTIVE
tblDeliverables | WPS ID | tblWPS | WPS ID | ACTIVE
tblTasks | WPS ID | tblWPS | WPS ID | ACTIVE
tblAcceptance | WPS ID | tblWPS | WPS ID | ACTIVE
tblExecution | WPS ID | tblWPS | WPS ID | ACTIVE
tblResponsibilities | WPS ID | tblWPS | WPS ID | ACTIVE
tblFunctional | WPS_ID | tblWPS | WPS ID | ACTIVE
tblWPS | Readiness Gate | tblGates | Gate ID | ACTIVE
tblGapWPS | WPS ID | tblWPS | WPS ID | ACTIVE
tblGapWPS | Gap ID | tblGaps | Gap ID | ACTIVE | Bridge: use DAX to filter gap measures by WPS
tblTasks | Activity ID | tblActivities | Activity ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblDeliverables | Activity ID | tblActivities | Activity ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblAcceptance | Rule ID | tblRules | Rule ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblAcceptance | Activity ID | tblActivities | Activity ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblRules | Activity ID | tblActivities | Activity ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblAcceptance | Evidence ID | tblEvidence | Evidence ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblFunctional | Canonical_Activity_ID | tblActivities | Activity ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblFunctional | Governing_Rule_Ref | tblRules | Rule ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblResponsibilities | Task ID | tblTasks | Task ID | INACTIVE | Alternate path; activate explicitly with USERELATIONSHIP in DAX
tblRelationships | Parent Object Key | tblObjects | Object Key | ACTIVE | Generic lineage; objects query is rebuilt from master tables on refresh
tblRelationships | Child Object Key | tblObjects | Object Key | INACTIVE | Alternate lineage direction

## POWERPIVOT_STATUS
Timestamp | Step | Object | Result | Details
| Setup | Model | NOT RUN | Run SetupPowerPivot in Windows Excel

## POWERPIVOT_GUIDE
POWER PIVOT SETUP — NOT EMBEDDED
1 | Save as .xlsm and import PowerPivotSetup.bas plus RedTeam.bas.
2 | Run SetupPowerPivot; review POWERPIVOT_STATUS for all imports and links.
3 | Open Power Pivot > Manage > Diagram View. Model tables use PP_ prefixes.
4 | Run RedTeam and correct data issues. Rerun SetupPowerPivot after key corrections.
5 | RefreshPowerPivot refreshes query data but does not create new relationships.
All tables | Every worksheet Excel table is loaded, including administrative tables. Administrative tables remain disconnected unless a valid business key exists.
Relationships | WPS is the central dimension. Secondary links are inactive. Power Pivot filtering is not automatically bidirectional through bridges.
Orphans | Relationships with missing foreign keys are logged and skipped. No original data is silently repaired.
Metadata | Generic relationship edges use Entity¦ID object keys. The Objects dimension is rebuilt by Power Query.
Known limitations | Macros have not been compiled or executed in Windows Excel here. No embedded Data Model exists until setup succeeds.
Refresh semantics | Power Query snapshots require refresh after edits. Original list fields and normalized Relationships remain separately maintained.

## Master_Departments
Department ID | Department Name | Canonical | Notes
DEP-01 | Class & Regulatory | Yes
DEP-02 | Technical | Yes
DEP-03 | PMO | Yes
DEP-04 | HSE | Yes
DEP-05 | Aviation | Yes
DEP-06 | Marine Operations | Yes
DEP-07 | Engineering | Yes
DEP-08 | Maintenance | Yes
DEP-09 | Warehouse | Yes
DEP-10 | Procurement | Yes
DEP-11 | IT | Yes
DEP-12 | Survey | Yes
DEP-13 | Environmental | Yes
DEP-14 | HR | Yes
DEP-15 | Medical | Yes
DEP-16 | Logistics | Yes

## Master_Owner_Roles
Role ID | Operational Role | Type | Notes
OR-001 | Marine Superintendent | Company Role
OR-002 | Technical Superintendent | Company Role
OR-003 | Chief Engineer | Company Role
OR-004 | Class Manager | Company Role
OR-005 | HSE Manager | Company Role
OR-006 | Aviation Coordinator | Company Role
OR-007 | Environmental Manager | Company Role
OR-008 | Project Director | Company Role
OR-009 | Project Manager | Company Role
OR-010 | Project Controls Manager | Company Role
OR-011 | Maintenance Superintendent | Company Role
OR-012 | Stores Manager | Company Role
OR-013 | Procurement Manager | Company Role
OR-014 | Survey Manager | Company Role
OR-015 | HR Manager | Company Role
OR-016 | Medical Coordinator | Company Role
OR-017 | DNV | Authority
OR-018 | Egyptian Flag/EAMS | Authority
OR-019 | Jordan Maritime Commission | Authority
OR-020 | ASEZA | Authority
OR-021 | Harbor Master / VTS | Authority
OR-022 | OEM | Authority
OR-023 | Client | Authority
OR-024 | MWS | Authority
OR-025 | Diving Contractor | Company Role
OR-026 | Tow Contractor | Company Role

## Master_Application_Roles
Application Role | Description
admin | Full configuration and governance rights
reviewer | Can review/approve/reject closure items
contributor | Can create/update own department records and evidence
viewer | Read-only access

## Dept_Owner_Map
Department Name | Owner / Operational Role | Relationship Role | Evidence Source
Class & Regulatory | Class Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Class & Regulatory | DNV | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Class & Regulatory | Egyptian Flag/EAMS | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Technical | Technical Superintendent | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Technical | Chief Engineer | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
PMO | Project Director | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
PMO | Project Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
PMO | Project Controls Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
HSE | HSE Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Aviation | Aviation Coordinator | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Aviation | HSE Manager | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Marine Operations | Marine Superintendent | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Engineering | Chief Engineer | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Maintenance | Maintenance Superintendent | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Maintenance | Chief Engineer | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Warehouse | Stores Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Procurement | Procurement Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Procurement | Stores Manager | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
IT | Maintenance Superintendent | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Survey | Survey Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Survey | Marine Superintendent | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Environmental | Environmental Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
HR | HR Manager | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Medical | Medical Coordinator | Primary | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead
Logistics | HR Manager | Supporting | Execution.Discipline Lead + Activities.Activity Owner + WPS.Responsible Lead

## Dept_Application_Role_Map
Department Scope | Application Role | Basis | Status
All Departments | admin | Platform administrators only | Proposed — requires Admin confirmation
PMO | reviewer | Closure reviewers / gate authorities | Proposed — requires Admin confirmation
Class & Regulatory | reviewer | Verification authority | Proposed — requires Admin confirmation
All Departments | contributor | Department staff entering execution/evidence | Proposed — requires Admin confirmation
All Departments | viewer | Read-only stakeholders | Proposed — requires Admin confirmation

## MASTER_DATA_CHANGE_REPORT
Category | Sheet | Record ID | Field | Old Value | New Value | Basis / Evidence
A5 Multi-value expansion | WPS | WPS-13 | Readiness Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | WPS | WPS-14 | Readiness Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | WPS | WPS-15 | Readiness Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | WPS | WPS-16 | Readiness Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | WPS | WPS-20 | Readiness Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | WPS | WPS-23 | Readiness Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-049 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-050 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-051 | Blocked Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-052 | Blocked Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-053 | Blocked Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-054 | Blocked Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-055 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-056 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-057 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-058 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-059 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-060 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-061 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-062 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-063 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-064 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-065 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-066 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-067 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-068 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-069 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-070 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-072 | Blocked Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-073 | Blocked Gate | GATE-6/7 | GATE-6 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-074 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-079 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-084 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-087 | Blocked Gate | GATE-4/6/8 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-20-01 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-20-02 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-20-03 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-20-04 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-20-05 | Blocked Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-23-01 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-23-02 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-23-03 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Gaps | G-S-23-04 | Blocked Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-20-01 | Blocking Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-20-02 | Blocking Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-20-03 | Blocking Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-20-04 | Blocking Gate | GATE-7/8 | GATE-7 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-23-01 | Blocking Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-23-02 | Blocking Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-23-03 | Blocking Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
A5 Multi-value expansion | Execution | WPS-23-04 | Blocking Gate | GATE-4/7 | GATE-4 — each as independent typed relationship in Relationships sheet | All referenced Gate IDs exist canonically in Gates sheet; M:N preserved, never collapsed to one Gate
Canonical ID repair | Acceptance | AC-R-001 | Evidence ID | E-R-001 | E-001 | AC-R-001 <-> Rule R-001; E-001 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-002 | Evidence ID | E-R-002 | E-002 | AC-R-002 <-> Rule R-002; E-002 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-003 | Evidence ID | E-R-003 | E-003 | AC-R-003 <-> Rule R-003; E-003 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-004 | Evidence ID | E-R-004 | E-004 | AC-R-004 <-> Rule R-004; E-004 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-005 | Evidence ID | E-R-005 | E-005 | AC-R-005 <-> Rule R-005; E-005 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-006 | Evidence ID | E-R-006 | E-006 | AC-R-006 <-> Rule R-006; E-006 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-007 | Evidence ID | E-R-007 | E-007 | AC-R-007 <-> Rule R-007; E-007 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-008 | Evidence ID | E-R-008 | E-008 | AC-R-008 <-> Rule R-008; E-008 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-009 | Evidence ID | E-R-009 | E-009 | AC-R-009 <-> Rule R-009; E-009 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-010 | Evidence ID | E-R-010 | E-010 | AC-R-010 <-> Rule R-010; E-010 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-011 | Evidence ID | E-R-011 | E-011 | AC-R-011 <-> Rule R-011; E-011 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-012 | Evidence ID | E-R-012 | E-012 | AC-R-012 <-> Rule R-012; E-012 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-013 | Evidence ID | E-R-013 | E-013 | AC-R-013 <-> Rule R-013; E-013 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-014 | Evidence ID | E-R-014 | E-014 | AC-R-014 <-> Rule R-014; E-014 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-015 | Evidence ID | E-R-015 | E-015 | AC-R-015 <-> Rule R-015; E-015 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-016 | Evidence ID | E-R-016 | E-016 | AC-R-016 <-> Rule R-016; E-016 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-017 | Evidence ID | E-R-017 | E-017 | AC-R-017 <-> Rule R-017; E-017 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-018 | Evidence ID | E-R-018 | E-018 | AC-R-018 <-> Rule R-018; E-018 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-019 | Evidence ID | E-R-019 | E-019 | AC-R-019 <-> Rule R-019; E-019 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-020 | Evidence ID | E-R-020 | E-020 | AC-R-020 <-> Rule R-020; E-020 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-021 | Evidence ID | E-R-021 | E-021 | AC-R-021 <-> Rule R-021; E-021 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-022 | Evidence ID | E-R-022 | E-022 | AC-R-022 <-> Rule R-022; E-022 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-023 | Evidence ID | E-R-023 | E-023 | AC-R-023 <-> Rule R-023; E-023 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-024 | Evidence ID | E-R-024 | E-024 | AC-R-024 <-> Rule R-024; E-024 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-025 | Evidence ID | E-R-025 | E-025 | AC-R-025 <-> Rule R-025; E-025 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-026 | Evidence ID | E-R-026 | E-026 | AC-R-026 <-> Rule R-026; E-026 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-027 | Evidence ID | E-R-027 | E-027 | AC-R-027 <-> Rule R-027; E-027 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-028 | Evidence ID | E-R-028 | E-028 | AC-R-028 <-> Rule R-028; E-028 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-029 | Evidence ID | E-R-029 | E-029 | AC-R-029 <-> Rule R-029; E-029 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-030 | Evidence ID | E-R-030 | E-030 | AC-R-030 <-> Rule R-030; E-030 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-031 | Evidence ID | E-R-031 | E-031 | AC-R-031 <-> Rule R-031; E-031 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-032 | Evidence ID | E-R-032 | E-032 | AC-R-032 <-> Rule R-032; E-032 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-033 | Evidence ID | E-R-033 | E-033 | AC-R-033 <-> Rule R-033; E-033 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-034 | Evidence ID | E-R-034 | E-034 | AC-R-034 <-> Rule R-034; E-034 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-035 | Evidence ID | E-R-035 | E-035 | AC-R-035 <-> Rule R-035; E-035 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-036 | Evidence ID | E-R-036 | E-036 | AC-R-036 <-> Rule R-036; E-036 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-037 | Evidence ID | E-R-037 | E-037 | AC-R-037 <-> Rule R-037; E-037 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-038 | Evidence ID | E-R-038 | E-038 | AC-R-038 <-> Rule R-038; E-038 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-039 | Evidence ID | E-R-039 | E-039 | AC-R-039 <-> Rule R-039; E-039 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-040 | Evidence ID | E-R-040 | E-040 | AC-R-040 <-> Rule R-040; E-040 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-041 | Evidence ID | E-R-041 | E-041 | AC-R-041 <-> Rule R-041; E-041 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-042 | Evidence ID | E-R-042 | E-042 | AC-R-042 <-> Rule R-042; E-042 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-043 | Evidence ID | E-R-043 | E-043 | AC-R-043 <-> Rule R-043; E-043 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-044 | Evidence ID | E-R-044 | E-044 | AC-R-044 <-> Rule R-044; E-044 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-045 | Evidence ID | E-R-045 | E-045 | AC-R-045 <-> Rule R-045; E-045 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-046 | Evidence ID | E-R-046 | E-046 | AC-R-046 <-> Rule R-046; E-046 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-047 | Evidence ID | E-R-047 | E-047 | AC-R-047 <-> Rule R-047; E-047 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-048 | Evidence ID | E-R-048 | E-048 | AC-R-048 <-> Rule R-048; E-048 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-049 | Evidence ID | E-R-049 | E-049 | AC-R-049 <-> Rule R-049; E-049 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-050 | Evidence ID | E-R-050 | E-050 | AC-R-050 <-> Rule R-050; E-050 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-051 | Evidence ID | E-R-051 | E-051 | AC-R-051 <-> Rule R-051; E-051 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-052 | Evidence ID | E-R-052 | E-052 | AC-R-052 <-> Rule R-052; E-052 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-053 | Evidence ID | E-R-053 | E-053 | AC-R-053 <-> Rule R-053; E-053 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-054 | Evidence ID | E-R-054 | E-054 | AC-R-054 <-> Rule R-054; E-054 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-055 | Evidence ID | E-R-055 | E-055 | AC-R-055 <-> Rule R-055; E-055 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-056 | Evidence ID | E-R-056 | E-056 | AC-R-056 <-> Rule R-056; E-056 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-057 | Evidence ID | E-R-057 | E-057 | AC-R-057 <-> Rule R-057; E-057 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-058 | Evidence ID | E-R-058 | E-058 | AC-R-058 <-> Rule R-058; E-058 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-059 | Evidence ID | E-R-059 | E-059 | AC-R-059 <-> Rule R-059; E-059 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-060 | Evidence ID | E-R-060 | E-060 | AC-R-060 <-> Rule R-060; E-060 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-061 | Evidence ID | E-R-061 | E-061 | AC-R-061 <-> Rule R-061; E-061 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-062 | Evidence ID | E-R-062 | E-062 | AC-R-062 <-> Rule R-062; E-062 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-063 | Evidence ID | E-R-063 | E-063 | AC-R-063 <-> Rule R-063; E-063 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-064 | Evidence ID | E-R-064 | E-064 | AC-R-064 <-> Rule R-064; E-064 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-065 | Evidence ID | E-R-065 | E-065 | AC-R-065 <-> Rule R-065; E-065 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-066 | Evidence ID | E-R-066 | E-066 | AC-R-066 <-> Rule R-066; E-066 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-067 | Evidence ID | E-R-067 | E-067 | AC-R-067 <-> Rule R-067; E-067 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-068 | Evidence ID | E-R-068 | E-068 | AC-R-068 <-> Rule R-068; E-068 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-069 | Evidence ID | E-R-069 | E-069 | AC-R-069 <-> Rule R-069; E-069 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-070 | Evidence ID | E-R-070 | E-070 | AC-R-070 <-> Rule R-070; E-070 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-071 | Evidence ID | E-R-071 | E-071 | AC-R-071 <-> Rule R-071; E-071 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-072 | Evidence ID | E-R-072 | E-072 | AC-R-072 <-> Rule R-072; E-072 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-073 | Evidence ID | E-R-073 | E-073 | AC-R-073 <-> Rule R-073; E-073 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-074 | Evidence ID | E-R-074 | E-074 | AC-R-074 <-> Rule R-074; E-074 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-075 | Evidence ID | E-R-075 | E-075 | AC-R-075 <-> Rule R-075; E-075 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-076 | Evidence ID | E-R-076 | E-076 | AC-R-076 <-> Rule R-076; E-076 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-077 | Evidence ID | E-R-077 | E-077 | AC-R-077 <-> Rule R-077; E-077 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-078 | Evidence ID | E-R-078 | E-078 | AC-R-078 <-> Rule R-078; E-078 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-079 | Evidence ID | E-R-079 | E-079 | AC-R-079 <-> Rule R-079; E-079 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-080 | Evidence ID | E-R-080 | E-080 | AC-R-080 <-> Rule R-080; E-080 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-081 | Evidence ID | E-R-081 | E-081 | AC-R-081 <-> Rule R-081; E-081 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-082 | Evidence ID | E-R-082 | E-082 | AC-R-082 <-> Rule R-082; E-082 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-083 | Evidence ID | E-R-083 | E-083 | AC-R-083 <-> Rule R-083; E-083 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-084 | Evidence ID | E-R-084 | E-084 | AC-R-084 <-> Rule R-084; E-084 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-085 | Evidence ID | E-R-085 | E-085 | AC-R-085 <-> Rule R-085; E-085 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-086 | Evidence ID | E-R-086 | E-086 | AC-R-086 <-> Rule R-086; E-086 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-087 | Evidence ID | E-R-087 | E-087 | AC-R-087 <-> Rule R-087; E-087 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-088 | Evidence ID | E-R-088 | E-088 | AC-R-088 <-> Rule R-088; E-088 exists in Evidence register; legacy alias pattern E-R-nnn
Canonical ID repair | Acceptance | AC-R-089 | Evidence ID | E-R-089 | E-089 | AC-R-089 <-> Rule R-089; E-089 exists in Evidence register; legacy alias pattern E-R-nnn
Workstream verification | WPS | WPS-23 | WPS Name | Crew Mobilization, Medical & Behavioral Safety | Crew Mobilization, Medical & Behavioral Safety | Expected workstream keyword "Crew" present: YES
Workstream verification | WPS | WPS-19 | WPS Name | Helideck & Aviation Interface Readiness | Helideck & Aviation Interface Readiness | Expected workstream keyword "Helideck" present: YES
Workstream verification | WPS | WPS-15 | WPS Name | Accommodation, Welfare, Manning & Competence | Accommodation, Welfare, Manning & Competence | Expected workstream keyword "Accommodation" present: YES

## RELATIONSHIP_REPAIR_REPORT
Parent Entity | Parent ID | Child Entity | Child ID | Relationship Type | Reason | Source
WPS | WPS-13 | Gates | GATE-7 | READINESS_GATE_MULTI_EXPANDED | Multi-value "Readiness Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
WPS | WPS-14 | Gates | GATE-6 | READINESS_GATE_MULTI_EXPANDED | Multi-value "Readiness Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
WPS | WPS-15 | Gates | GATE-4 | READINESS_GATE_MULTI_EXPANDED | Multi-value "Readiness Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
WPS | WPS-16 | Gates | GATE-4 | READINESS_GATE_MULTI_EXPANDED | Multi-value "Readiness Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
WPS | WPS-20 | Gates | GATE-7 | READINESS_GATE_MULTI_EXPANDED | Multi-value "Readiness Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
WPS | WPS-23 | Gates | GATE-4 | READINESS_GATE_MULTI_EXPANDED | Multi-value "Readiness Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-049 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-050 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-051 | Gates | GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-052 | Gates | GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-053 | Gates | GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-054 | Gates | GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-055 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-056 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-057 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-058 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-059 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-060 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-061 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-062 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-063 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-064 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-065 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-066 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-067 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-068 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-069 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-070 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-072 | Gates | GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-073 | Gates | GATE-6 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-6/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-074 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-079 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-084 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-087 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/6/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-20-01 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-20-02 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-20-03 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-20-04 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-20-05 | Gates | GATE-7 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-23-01 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-23-02 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-23-03 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Gaps | G-S-23-04 | Gates | GATE-4 | BLOCKS_GATE_MULTI_EXPANDED | Multi-value "Blocked Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-20-01 | Gates | GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-20-02 | Gates | GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-20-03 | Gates | GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-20-04 | Gates | GATE-7 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-7/8 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-23-01 | Gates | GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-23-02 | Gates | GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-23-03 | Gates | GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
Execution | WPS-23-04 | Gates | GATE-4 | BLOCKING_GATE_MULTI_EXPANDED | Multi-value "Blocking Gate"=GATE-4/7 expanded into independent relationships (M:N preserved) | All Gate IDs verified against Gates register
WPS | WPS-17 | WPS | WPS-01 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-17 | WPS | WPS-02 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-01 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-02 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-19 | WPS | WPS-14 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-19 | WPS | WPS-16 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-20 | WPS | WPS-09 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-20 | WPS | WPS-13 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-20 | WPS | WPS-16 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-22 | WPS | WPS-08 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-22 | WPS | WPS-09 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-22 | WPS | WPS-13 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-22 | WPS | WPS-14 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-23 | WPS | WPS-15 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-23 | WPS | WPS-16 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-09 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-10 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-12 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-14 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-17 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-18 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-19 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-20 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-21 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-22 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-24 | WPS | WPS-23 | SEQUENCES | List member of "Predecessor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-17 | WPS | WPS-03 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-17 | WPS | WPS-10 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-17 | WPS | WPS-13 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-17 | WPS | WPS-14 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-17 | WPS | WPS-16 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-03 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-10 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-13 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-14 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-18 | WPS | WPS-16 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-21 | WPS | WPS-17 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-21 | WPS | WPS-18 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-21 | WPS | WPS-22 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
WPS | WPS-21 | WPS | WPS-24 | SEQUENCES | List member of "Successor WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-01 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-02 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-03 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-04 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-05 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-06 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-07 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-08 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-09 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-10 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-11 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-12 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-13 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-14 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-15 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-16 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-17 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-18 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-19 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-20 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-21 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-22 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-23 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | WPS | WPS-24 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | WPS | WPS-01 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | WPS | WPS-02 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | WPS | WPS-17 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | WPS | WPS-18 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | WPS | WPS-03 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | WPS | WPS-04 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | WPS | WPS-05 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | WPS | WPS-06 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | WPS | WPS-07 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | WPS | WPS-08 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | WPS | WPS-09 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | WPS | WPS-22 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | WPS | WPS-11 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | WPS | WPS-15 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | WPS | WPS-23 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | WPS | WPS-16 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | WPS | WPS-14 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | WPS | WPS-16 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-12 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-13 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-14 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-19 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-20 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-21 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | WPS | WPS-23 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | WPS | WPS-13 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | WPS | WPS-16 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | WPS | WPS-20 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | WPS | WPS-24 | GATE_COVERS | List member of "Required WPS IDs" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-001 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-002 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-004 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-005 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-008 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-080 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-082 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-083 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-003 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-006 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-007 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-081 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-088 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-089 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-009 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-010 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-011 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-016 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-017 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-018 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-012 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-013 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-014 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-015 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-019 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-020 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-021 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-022 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-023 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-024 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-025 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-026 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-027 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-028 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-029 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-030 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-031 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-036 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-032 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-033 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-034 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-071 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-075 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-076 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-077 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-078 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-086 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-037 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-038 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-039 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-040 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-041 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-042 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-035 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-043 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-085 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-044 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-045 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-046 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-047 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-048 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-049 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-050 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-059 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-060 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-084 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-051 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-052 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-053 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-054 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-072 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-073 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-055 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-056 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-057 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-058 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-061 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-062 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-063 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-064 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-065 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-066 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-067 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-068 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-069 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-070 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-074 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-079 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-R-087 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-17-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-17-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-17-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-17-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-17-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-18-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-18-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-18-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-18-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-18-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-19-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-19-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-19-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-19-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-19-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-20-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-20-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-20-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-20-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-20-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-21-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-21-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-21-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-21-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-21-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-22-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-22-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-22-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-22-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-22-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-23-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-23-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-23-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-23-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-24-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-24-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-24-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Activities | A-S-24-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-001 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-002 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-004 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-005 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-008 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-080 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-082 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-083 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-003 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-006 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-007 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-081 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-088 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-R-089 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-17-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-17-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-17-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-17-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-17-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-18-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-18-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-18-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-18-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Activities | A-S-18-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-009 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-010 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-011 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-016 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-017 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-018 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-012 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-013 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-014 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Activities | A-R-015 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-019 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-020 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-021 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-022 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-023 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-024 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-025 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-026 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-027 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-028 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-029 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-030 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-031 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-036 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-032 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-033 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-034 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-071 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-075 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-076 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-077 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-078 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-R-086 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-S-22-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-S-22-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-S-22-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-S-22-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Activities | A-S-22-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-035 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-043 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-085 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-055 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-056 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-057 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-058 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-S-23-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-S-23-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-S-23-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-S-23-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-061 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-062 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-063 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-064 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-065 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-066 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-067 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-068 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-069 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-070 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-074 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-079 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Activities | A-R-087 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Activities | A-R-037 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Activities | A-R-038 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Activities | A-R-039 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Activities | A-R-040 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Activities | A-R-041 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Activities | A-R-042 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-051 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-052 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-053 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-054 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-072 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-073 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-061 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-062 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-063 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-064 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-065 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-066 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-067 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-068 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-069 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-070 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-074 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-079 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Activities | A-R-087 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-044 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-045 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-046 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-047 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-048 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-049 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-050 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-059 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-060 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-084 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-051 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-052 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-053 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-054 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-072 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-R-073 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-19-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-19-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-19-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-19-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-19-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-20-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-20-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-20-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-20-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-20-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-21-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-21-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-21-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-21-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-21-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-23-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-23-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-23-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Activities | A-S-23-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-049 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-050 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-059 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-060 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-084 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-061 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-062 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-063 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-064 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-065 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-066 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-067 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-068 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-069 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-070 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-074 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-079 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-R-087 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-20-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-20-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-20-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-20-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-20-05 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-24-01 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-24-02 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-24-03 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Activities | A-S-24-04 | GATE_COVERS | List member of "Required Activities" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-001 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-002 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-003 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-004 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-005 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-006 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-007 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-008 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-009 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-010 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-011 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-012 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-013 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-014 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-015 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-016 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-017 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-018 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-019 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-020 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-021 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-022 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-023 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-024 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-025 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-026 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-027 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-028 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-029 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-030 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-031 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-032 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-033 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-034 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-035 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-036 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-037 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-038 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-039 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-040 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-041 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-042 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-043 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-044 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-045 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-046 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-047 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-048 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-049 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-050 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-051 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-052 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-053 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-054 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-055 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-056 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-057 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-058 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-059 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-060 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-061 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-062 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-063 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-064 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-065 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-066 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-067 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-068 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-069 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-070 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-071 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-072 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-073 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-074 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-075 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-076 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-077 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-078 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-079 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-080 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-081 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-082 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-083 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-084 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-085 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-086 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-087 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-088 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-R-089 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-17-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-17-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-17-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-17-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-17-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-18-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-18-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-18-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-18-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-18-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-19-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-19-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-19-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-19-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-19-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-20-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-20-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-20-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-20-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-20-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-21-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-21-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-21-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-21-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-21-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-22-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-22-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-22-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-22-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-22-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-23-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-23-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-23-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-23-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-24-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-24-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-24-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-0 | Deliverables | D-S-24-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-001 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-002 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-003 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-004 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-005 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-006 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-007 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-008 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-080 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-081 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-082 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-083 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-088 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-R-089 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-17-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-17-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-17-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-17-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-17-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-18-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-18-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-18-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-18-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-1 | Deliverables | D-S-18-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-009 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-010 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-011 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-012 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-013 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-014 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-015 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-016 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-017 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-2 | Deliverables | D-R-018 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-019 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-020 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-021 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-022 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-023 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-024 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-025 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-026 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-027 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-028 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-029 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-030 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-031 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-032 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-033 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-034 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-036 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-071 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-075 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-076 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-077 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-078 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-R-086 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-S-22-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-S-22-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-S-22-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-S-22-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-3 | Deliverables | D-S-22-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-035 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-043 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-055 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-056 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-057 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-058 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-061 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-062 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-063 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-064 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-065 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-066 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-067 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-068 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-069 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-070 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-074 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-079 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-085 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-R-087 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-S-23-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-S-23-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-S-23-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-4 | Deliverables | D-S-23-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Deliverables | D-R-037 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Deliverables | D-R-038 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Deliverables | D-R-039 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Deliverables | D-R-040 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Deliverables | D-R-041 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-5 | Deliverables | D-R-042 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-051 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-052 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-053 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-054 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-061 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-062 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-063 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-064 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-065 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-066 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-067 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-068 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-069 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-070 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-072 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-073 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-074 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-079 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-6 | Deliverables | D-R-087 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-044 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-045 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-046 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-047 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-048 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-049 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-050 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-051 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-052 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-053 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-054 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-059 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-060 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-072 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-073 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-R-084 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-19-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-19-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-19-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-19-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-19-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-20-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-20-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-20-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-20-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-20-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-21-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-21-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-21-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-21-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-21-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-23-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-23-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-23-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-7 | Deliverables | D-S-23-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-049 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-050 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-059 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-060 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-061 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-062 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-063 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-064 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-065 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-066 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-067 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-068 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-069 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-070 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-074 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-079 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-084 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-R-087 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-20-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-20-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-20-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-20-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-20-05 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-24-01 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-24-02 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-24-03 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Gates | GATE-8 | Deliverables | D-S-24-04 | GATE_COVERS | List member of "Required Deliverables" materialized as explicit typed relationship | Canonical ID verified in target register
Acceptance | AC-R-001 | Evidence | E-001 | PROVEN_BY | Legacy alias E-R-001 resolved to canonical Evidence ID | AC-R-001 <-> Rule R-001; E-001 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-002 | Evidence | E-002 | PROVEN_BY | Legacy alias E-R-002 resolved to canonical Evidence ID | AC-R-002 <-> Rule R-002; E-002 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-003 | Evidence | E-003 | PROVEN_BY | Legacy alias E-R-003 resolved to canonical Evidence ID | AC-R-003 <-> Rule R-003; E-003 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-004 | Evidence | E-004 | PROVEN_BY | Legacy alias E-R-004 resolved to canonical Evidence ID | AC-R-004 <-> Rule R-004; E-004 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-005 | Evidence | E-005 | PROVEN_BY | Legacy alias E-R-005 resolved to canonical Evidence ID | AC-R-005 <-> Rule R-005; E-005 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-006 | Evidence | E-006 | PROVEN_BY | Legacy alias E-R-006 resolved to canonical Evidence ID | AC-R-006 <-> Rule R-006; E-006 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-007 | Evidence | E-007 | PROVEN_BY | Legacy alias E-R-007 resolved to canonical Evidence ID | AC-R-007 <-> Rule R-007; E-007 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-008 | Evidence | E-008 | PROVEN_BY | Legacy alias E-R-008 resolved to canonical Evidence ID | AC-R-008 <-> Rule R-008; E-008 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-009 | Evidence | E-009 | PROVEN_BY | Legacy alias E-R-009 resolved to canonical Evidence ID | AC-R-009 <-> Rule R-009; E-009 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-010 | Evidence | E-010 | PROVEN_BY | Legacy alias E-R-010 resolved to canonical Evidence ID | AC-R-010 <-> Rule R-010; E-010 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-011 | Evidence | E-011 | PROVEN_BY | Legacy alias E-R-011 resolved to canonical Evidence ID | AC-R-011 <-> Rule R-011; E-011 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-012 | Evidence | E-012 | PROVEN_BY | Legacy alias E-R-012 resolved to canonical Evidence ID | AC-R-012 <-> Rule R-012; E-012 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-013 | Evidence | E-013 | PROVEN_BY | Legacy alias E-R-013 resolved to canonical Evidence ID | AC-R-013 <-> Rule R-013; E-013 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-014 | Evidence | E-014 | PROVEN_BY | Legacy alias E-R-014 resolved to canonical Evidence ID | AC-R-014 <-> Rule R-014; E-014 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-015 | Evidence | E-015 | PROVEN_BY | Legacy alias E-R-015 resolved to canonical Evidence ID | AC-R-015 <-> Rule R-015; E-015 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-016 | Evidence | E-016 | PROVEN_BY | Legacy alias E-R-016 resolved to canonical Evidence ID | AC-R-016 <-> Rule R-016; E-016 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-017 | Evidence | E-017 | PROVEN_BY | Legacy alias E-R-017 resolved to canonical Evidence ID | AC-R-017 <-> Rule R-017; E-017 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-018 | Evidence | E-018 | PROVEN_BY | Legacy alias E-R-018 resolved to canonical Evidence ID | AC-R-018 <-> Rule R-018; E-018 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-019 | Evidence | E-019 | PROVEN_BY | Legacy alias E-R-019 resolved to canonical Evidence ID | AC-R-019 <-> Rule R-019; E-019 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-020 | Evidence | E-020 | PROVEN_BY | Legacy alias E-R-020 resolved to canonical Evidence ID | AC-R-020 <-> Rule R-020; E-020 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-021 | Evidence | E-021 | PROVEN_BY | Legacy alias E-R-021 resolved to canonical Evidence ID | AC-R-021 <-> Rule R-021; E-021 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-022 | Evidence | E-022 | PROVEN_BY | Legacy alias E-R-022 resolved to canonical Evidence ID | AC-R-022 <-> Rule R-022; E-022 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-023 | Evidence | E-023 | PROVEN_BY | Legacy alias E-R-023 resolved to canonical Evidence ID | AC-R-023 <-> Rule R-023; E-023 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-024 | Evidence | E-024 | PROVEN_BY | Legacy alias E-R-024 resolved to canonical Evidence ID | AC-R-024 <-> Rule R-024; E-024 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-025 | Evidence | E-025 | PROVEN_BY | Legacy alias E-R-025 resolved to canonical Evidence ID | AC-R-025 <-> Rule R-025; E-025 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-026 | Evidence | E-026 | PROVEN_BY | Legacy alias E-R-026 resolved to canonical Evidence ID | AC-R-026 <-> Rule R-026; E-026 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-027 | Evidence | E-027 | PROVEN_BY | Legacy alias E-R-027 resolved to canonical Evidence ID | AC-R-027 <-> Rule R-027; E-027 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-028 | Evidence | E-028 | PROVEN_BY | Legacy alias E-R-028 resolved to canonical Evidence ID | AC-R-028 <-> Rule R-028; E-028 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-029 | Evidence | E-029 | PROVEN_BY | Legacy alias E-R-029 resolved to canonical Evidence ID | AC-R-029 <-> Rule R-029; E-029 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-030 | Evidence | E-030 | PROVEN_BY | Legacy alias E-R-030 resolved to canonical Evidence ID | AC-R-030 <-> Rule R-030; E-030 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-031 | Evidence | E-031 | PROVEN_BY | Legacy alias E-R-031 resolved to canonical Evidence ID | AC-R-031 <-> Rule R-031; E-031 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-032 | Evidence | E-032 | PROVEN_BY | Legacy alias E-R-032 resolved to canonical Evidence ID | AC-R-032 <-> Rule R-032; E-032 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-033 | Evidence | E-033 | PROVEN_BY | Legacy alias E-R-033 resolved to canonical Evidence ID | AC-R-033 <-> Rule R-033; E-033 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-034 | Evidence | E-034 | PROVEN_BY | Legacy alias E-R-034 resolved to canonical Evidence ID | AC-R-034 <-> Rule R-034; E-034 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-035 | Evidence | E-035 | PROVEN_BY | Legacy alias E-R-035 resolved to canonical Evidence ID | AC-R-035 <-> Rule R-035; E-035 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-036 | Evidence | E-036 | PROVEN_BY | Legacy alias E-R-036 resolved to canonical Evidence ID | AC-R-036 <-> Rule R-036; E-036 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-037 | Evidence | E-037 | PROVEN_BY | Legacy alias E-R-037 resolved to canonical Evidence ID | AC-R-037 <-> Rule R-037; E-037 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-038 | Evidence | E-038 | PROVEN_BY | Legacy alias E-R-038 resolved to canonical Evidence ID | AC-R-038 <-> Rule R-038; E-038 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-039 | Evidence | E-039 | PROVEN_BY | Legacy alias E-R-039 resolved to canonical Evidence ID | AC-R-039 <-> Rule R-039; E-039 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-040 | Evidence | E-040 | PROVEN_BY | Legacy alias E-R-040 resolved to canonical Evidence ID | AC-R-040 <-> Rule R-040; E-040 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-041 | Evidence | E-041 | PROVEN_BY | Legacy alias E-R-041 resolved to canonical Evidence ID | AC-R-041 <-> Rule R-041; E-041 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-042 | Evidence | E-042 | PROVEN_BY | Legacy alias E-R-042 resolved to canonical Evidence ID | AC-R-042 <-> Rule R-042; E-042 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-043 | Evidence | E-043 | PROVEN_BY | Legacy alias E-R-043 resolved to canonical Evidence ID | AC-R-043 <-> Rule R-043; E-043 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-044 | Evidence | E-044 | PROVEN_BY | Legacy alias E-R-044 resolved to canonical Evidence ID | AC-R-044 <-> Rule R-044; E-044 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-045 | Evidence | E-045 | PROVEN_BY | Legacy alias E-R-045 resolved to canonical Evidence ID | AC-R-045 <-> Rule R-045; E-045 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-046 | Evidence | E-046 | PROVEN_BY | Legacy alias E-R-046 resolved to canonical Evidence ID | AC-R-046 <-> Rule R-046; E-046 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-047 | Evidence | E-047 | PROVEN_BY | Legacy alias E-R-047 resolved to canonical Evidence ID | AC-R-047 <-> Rule R-047; E-047 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-048 | Evidence | E-048 | PROVEN_BY | Legacy alias E-R-048 resolved to canonical Evidence ID | AC-R-048 <-> Rule R-048; E-048 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-049 | Evidence | E-049 | PROVEN_BY | Legacy alias E-R-049 resolved to canonical Evidence ID | AC-R-049 <-> Rule R-049; E-049 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-050 | Evidence | E-050 | PROVEN_BY | Legacy alias E-R-050 resolved to canonical Evidence ID | AC-R-050 <-> Rule R-050; E-050 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-051 | Evidence | E-051 | PROVEN_BY | Legacy alias E-R-051 resolved to canonical Evidence ID | AC-R-051 <-> Rule R-051; E-051 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-052 | Evidence | E-052 | PROVEN_BY | Legacy alias E-R-052 resolved to canonical Evidence ID | AC-R-052 <-> Rule R-052; E-052 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-053 | Evidence | E-053 | PROVEN_BY | Legacy alias E-R-053 resolved to canonical Evidence ID | AC-R-053 <-> Rule R-053; E-053 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-054 | Evidence | E-054 | PROVEN_BY | Legacy alias E-R-054 resolved to canonical Evidence ID | AC-R-054 <-> Rule R-054; E-054 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-055 | Evidence | E-055 | PROVEN_BY | Legacy alias E-R-055 resolved to canonical Evidence ID | AC-R-055 <-> Rule R-055; E-055 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-056 | Evidence | E-056 | PROVEN_BY | Legacy alias E-R-056 resolved to canonical Evidence ID | AC-R-056 <-> Rule R-056; E-056 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-057 | Evidence | E-057 | PROVEN_BY | Legacy alias E-R-057 resolved to canonical Evidence ID | AC-R-057 <-> Rule R-057; E-057 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-058 | Evidence | E-058 | PROVEN_BY | Legacy alias E-R-058 resolved to canonical Evidence ID | AC-R-058 <-> Rule R-058; E-058 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-059 | Evidence | E-059 | PROVEN_BY | Legacy alias E-R-059 resolved to canonical Evidence ID | AC-R-059 <-> Rule R-059; E-059 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-060 | Evidence | E-060 | PROVEN_BY | Legacy alias E-R-060 resolved to canonical Evidence ID | AC-R-060 <-> Rule R-060; E-060 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-061 | Evidence | E-061 | PROVEN_BY | Legacy alias E-R-061 resolved to canonical Evidence ID | AC-R-061 <-> Rule R-061; E-061 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-062 | Evidence | E-062 | PROVEN_BY | Legacy alias E-R-062 resolved to canonical Evidence ID | AC-R-062 <-> Rule R-062; E-062 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-063 | Evidence | E-063 | PROVEN_BY | Legacy alias E-R-063 resolved to canonical Evidence ID | AC-R-063 <-> Rule R-063; E-063 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-064 | Evidence | E-064 | PROVEN_BY | Legacy alias E-R-064 resolved to canonical Evidence ID | AC-R-064 <-> Rule R-064; E-064 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-065 | Evidence | E-065 | PROVEN_BY | Legacy alias E-R-065 resolved to canonical Evidence ID | AC-R-065 <-> Rule R-065; E-065 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-066 | Evidence | E-066 | PROVEN_BY | Legacy alias E-R-066 resolved to canonical Evidence ID | AC-R-066 <-> Rule R-066; E-066 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-067 | Evidence | E-067 | PROVEN_BY | Legacy alias E-R-067 resolved to canonical Evidence ID | AC-R-067 <-> Rule R-067; E-067 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-068 | Evidence | E-068 | PROVEN_BY | Legacy alias E-R-068 resolved to canonical Evidence ID | AC-R-068 <-> Rule R-068; E-068 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-069 | Evidence | E-069 | PROVEN_BY | Legacy alias E-R-069 resolved to canonical Evidence ID | AC-R-069 <-> Rule R-069; E-069 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-070 | Evidence | E-070 | PROVEN_BY | Legacy alias E-R-070 resolved to canonical Evidence ID | AC-R-070 <-> Rule R-070; E-070 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-071 | Evidence | E-071 | PROVEN_BY | Legacy alias E-R-071 resolved to canonical Evidence ID | AC-R-071 <-> Rule R-071; E-071 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-072 | Evidence | E-072 | PROVEN_BY | Legacy alias E-R-072 resolved to canonical Evidence ID | AC-R-072 <-> Rule R-072; E-072 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-073 | Evidence | E-073 | PROVEN_BY | Legacy alias E-R-073 resolved to canonical Evidence ID | AC-R-073 <-> Rule R-073; E-073 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-074 | Evidence | E-074 | PROVEN_BY | Legacy alias E-R-074 resolved to canonical Evidence ID | AC-R-074 <-> Rule R-074; E-074 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-075 | Evidence | E-075 | PROVEN_BY | Legacy alias E-R-075 resolved to canonical Evidence ID | AC-R-075 <-> Rule R-075; E-075 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-076 | Evidence | E-076 | PROVEN_BY | Legacy alias E-R-076 resolved to canonical Evidence ID | AC-R-076 <-> Rule R-076; E-076 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-077 | Evidence | E-077 | PROVEN_BY | Legacy alias E-R-077 resolved to canonical Evidence ID | AC-R-077 <-> Rule R-077; E-077 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-078 | Evidence | E-078 | PROVEN_BY | Legacy alias E-R-078 resolved to canonical Evidence ID | AC-R-078 <-> Rule R-078; E-078 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-079 | Evidence | E-079 | PROVEN_BY | Legacy alias E-R-079 resolved to canonical Evidence ID | AC-R-079 <-> Rule R-079; E-079 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-080 | Evidence | E-080 | PROVEN_BY | Legacy alias E-R-080 resolved to canonical Evidence ID | AC-R-080 <-> Rule R-080; E-080 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-081 | Evidence | E-081 | PROVEN_BY | Legacy alias E-R-081 resolved to canonical Evidence ID | AC-R-081 <-> Rule R-081; E-081 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-082 | Evidence | E-082 | PROVEN_BY | Legacy alias E-R-082 resolved to canonical Evidence ID | AC-R-082 <-> Rule R-082; E-082 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-083 | Evidence | E-083 | PROVEN_BY | Legacy alias E-R-083 resolved to canonical Evidence ID | AC-R-083 <-> Rule R-083; E-083 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-084 | Evidence | E-084 | PROVEN_BY | Legacy alias E-R-084 resolved to canonical Evidence ID | AC-R-084 <-> Rule R-084; E-084 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-085 | Evidence | E-085 | PROVEN_BY | Legacy alias E-R-085 resolved to canonical Evidence ID | AC-R-085 <-> Rule R-085; E-085 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-086 | Evidence | E-086 | PROVEN_BY | Legacy alias E-R-086 resolved to canonical Evidence ID | AC-R-086 <-> Rule R-086; E-086 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-087 | Evidence | E-087 | PROVEN_BY | Legacy alias E-R-087 resolved to canonical Evidence ID | AC-R-087 <-> Rule R-087; E-087 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-088 | Evidence | E-088 | PROVEN_BY | Legacy alias E-R-088 resolved to canonical Evidence ID | AC-R-088 <-> Rule R-088; E-088 exists in Evidence register; legacy alias pattern E-R-nnn
Acceptance | AC-R-089 | Evidence | E-089 | PROVEN_BY | Legacy alias E-R-089 resolved to canonical Evidence ID | AC-R-089 <-> Rule R-089; E-089 exists in Evidence register; legacy alias pattern E-R-nnn

## UNRESOLVED_REFERENCE_REPORT
Finding ID | Entity | Record ID | Field | Current Value | Problem | Classification | Severity | Root Cause | Needs AI | Needs Admin | Confidence | Required To Resolve
RT-0001 | Relationships | Activities:A-R-001->Rules:R-001 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0002 | Relationships | Activities:A-R-002->Rules:R-002 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0003 | Relationships | Activities:A-R-003->Rules:R-003 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0004 | Relationships | Activities:A-R-004->Rules:R-004 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0005 | Relationships | Activities:A-R-005->Rules:R-005 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0006 | Relationships | Activities:A-R-006->Rules:R-006 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0007 | Relationships | Activities:A-R-007->Rules:R-007 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0008 | Relationships | Activities:A-R-008->Rules:R-008 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0009 | Relationships | Activities:A-R-009->Rules:R-009 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0010 | Relationships | Activities:A-R-010->Rules:R-010 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0011 | Relationships | Activities:A-R-011->Rules:R-011 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0012 | Relationships | Activities:A-R-012->Rules:R-012 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0013 | Relationships | Activities:A-R-013->Rules:R-013 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0014 | Relationships | Activities:A-R-014->Rules:R-014 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0015 | Relationships | Activities:A-R-015->Rules:R-015 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0016 | Relationships | Activities:A-R-016->Rules:R-016 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0017 | Relationships | Activities:A-R-017->Rules:R-017 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0018 | Relationships | Activities:A-R-018->Rules:R-018 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0019 | Relationships | Activities:A-R-019->Rules:R-019 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0020 | Relationships | Activities:A-R-020->Rules:R-020 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0021 | Relationships | Activities:A-R-021->Rules:R-021 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0022 | Relationships | Activities:A-R-022->Rules:R-022 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0023 | Relationships | Activities:A-R-023->Rules:R-023 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0024 | Relationships | Activities:A-R-024->Rules:R-024 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0025 | Relationships | Activities:A-R-025->Rules:R-025 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0026 | Relationships | Activities:A-R-026->Rules:R-026 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0027 | Relationships | Activities:A-R-027->Rules:R-027 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0028 | Relationships | Activities:A-R-028->Rules:R-028 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0029 | Relationships | Activities:A-R-029->Rules:R-029 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0030 | Relationships | Activities:A-R-030->Rules:R-030 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0031 | Relationships | Activities:A-R-031->Rules:R-031 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0032 | Relationships | Activities:A-R-032->Rules:R-032 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0033 | Relationships | Activities:A-R-033->Rules:R-033 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0034 | Relationships | Activities:A-R-034->Rules:R-034 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0035 | Relationships | Activities:A-R-035->Rules:R-035 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0036 | Relationships | Activities:A-R-036->Rules:R-036 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0037 | Relationships | Activities:A-R-037->Rules:R-037 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0038 | Relationships | Activities:A-R-038->Rules:R-038 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0039 | Relationships | Activities:A-R-039->Rules:R-039 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0040 | Relationships | Activities:A-R-040->Rules:R-040 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0041 | Relationships | Activities:A-R-041->Rules:R-041 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0042 | Relationships | Activities:A-R-042->Rules:R-042 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0043 | Relationships | Activities:A-R-043->Rules:R-043 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0044 | Relationships | Activities:A-R-044->Rules:R-044 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0045 | Relationships | Activities:A-R-045->Rules:R-045 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0046 | Relationships | Activities:A-R-046->Rules:R-046 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0047 | Relationships | Activities:A-R-047->Rules:R-047 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0048 | Relationships | Activities:A-R-048->Rules:R-048 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0049 | Relationships | Activities:A-R-049->Rules:R-049 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0050 | Relationships | Activities:A-R-050->Rules:R-050 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0051 | Relationships | Activities:A-R-051->Rules:R-051 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0052 | Relationships | Activities:A-R-052->Rules:R-052 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0053 | Relationships | Activities:A-R-053->Rules:R-053 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0054 | Relationships | Activities:A-R-054->Rules:R-054 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0055 | Relationships | Activities:A-R-055->Rules:R-055 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0056 | Relationships | Activities:A-R-056->Rules:R-056 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0057 | Relationships | Activities:A-R-057->Rules:R-057 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0058 | Relationships | Activities:A-R-058->Rules:R-058 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0059 | Relationships | Activities:A-R-059->Rules:R-059 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0060 | Relationships | Activities:A-R-060->Rules:R-060 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0061 | Relationships | Activities:A-R-061->Rules:R-061 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0062 | Relationships | Activities:A-R-062->Rules:R-062 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0063 | Relationships | Activities:A-R-063->Rules:R-063 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0064 | Relationships | Activities:A-R-064->Rules:R-064 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0065 | Relationships | Activities:A-R-065->Rules:R-065 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0066 | Relationships | Activities:A-R-066->Rules:R-066 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0067 | Relationships | Activities:A-R-067->Rules:R-067 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0068 | Relationships | Activities:A-R-068->Rules:R-068 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0069 | Relationships | Activities:A-R-069->Rules:R-069 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0070 | Relationships | Activities:A-R-070->Rules:R-070 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0071 | Relationships | Activities:A-R-071->Rules:R-071 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0072 | Relationships | Activities:A-R-072->Rules:R-072 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0073 | Relationships | Activities:A-R-073->Rules:R-073 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0074 | Relationships | Activities:A-R-074->Rules:R-074 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0075 | Relationships | Activities:A-R-075->Rules:R-075 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0076 | Relationships | Activities:A-R-076->Rules:R-076 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0077 | Relationships | Activities:A-R-077->Rules:R-077 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0078 | Relationships | Activities:A-R-078->Rules:R-078 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0079 | Relationships | Activities:A-R-079->Rules:R-079 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0080 | Relationships | Activities:A-R-080->Rules:R-080 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0081 | Relationships | Activities:A-R-081->Rules:R-081 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0082 | Relationships | Activities:A-R-082->Rules:R-082 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0083 | Relationships | Activities:A-R-083->Rules:R-083 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0084 | Relationships | Activities:A-R-084->Rules:R-084 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0085 | Relationships | Activities:A-R-085->Rules:R-085 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0086 | Relationships | Activities:A-R-086->Rules:R-086 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0087 | Relationships | Activities:A-R-087->Rules:R-087 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0088 | Relationships | Activities:A-R-088->Rules:R-088 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0089 | Relationships | Activities:A-R-089->Rules:R-089 | Parent/Child Entity | Activities->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0090 | Relationships | Deliverables:D-R-001->Activities:A-R-001 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0091 | Relationships | Deliverables:D-R-001->Rules:R-001 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0092 | Relationships | Deliverables:D-R-002->Activities:A-R-002 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0093 | Relationships | Deliverables:D-R-002->Rules:R-002 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0094 | Relationships | Deliverables:D-R-003->Activities:A-R-003 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0095 | Relationships | Deliverables:D-R-003->Rules:R-003 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0096 | Relationships | Deliverables:D-R-004->Activities:A-R-004 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0097 | Relationships | Deliverables:D-R-004->Rules:R-004 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0098 | Relationships | Deliverables:D-R-005->Activities:A-R-005 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0099 | Relationships | Deliverables:D-R-005->Rules:R-005 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0100 | Relationships | Deliverables:D-R-006->Activities:A-R-006 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0101 | Relationships | Deliverables:D-R-006->Rules:R-006 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0102 | Relationships | Deliverables:D-R-007->Activities:A-R-007 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0103 | Relationships | Deliverables:D-R-007->Rules:R-007 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0104 | Relationships | Deliverables:D-R-008->Activities:A-R-008 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0105 | Relationships | Deliverables:D-R-008->Rules:R-008 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0106 | Relationships | Deliverables:D-R-009->Activities:A-R-009 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0107 | Relationships | Deliverables:D-R-009->Rules:R-009 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0108 | Relationships | Deliverables:D-R-010->Activities:A-R-010 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0109 | Relationships | Deliverables:D-R-010->Rules:R-010 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0110 | Relationships | Deliverables:D-R-011->Activities:A-R-011 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0111 | Relationships | Deliverables:D-R-011->Rules:R-011 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0112 | Relationships | Deliverables:D-R-012->Activities:A-R-012 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0113 | Relationships | Deliverables:D-R-012->Rules:R-012 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0114 | Relationships | Deliverables:D-R-013->Activities:A-R-013 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0115 | Relationships | Deliverables:D-R-013->Rules:R-013 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0116 | Relationships | Deliverables:D-R-014->Activities:A-R-014 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0117 | Relationships | Deliverables:D-R-014->Rules:R-014 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0118 | Relationships | Deliverables:D-R-015->Activities:A-R-015 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0119 | Relationships | Deliverables:D-R-015->Rules:R-015 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0120 | Relationships | Deliverables:D-R-016->Activities:A-R-016 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0121 | Relationships | Deliverables:D-R-016->Rules:R-016 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0122 | Relationships | Deliverables:D-R-017->Activities:A-R-017 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0123 | Relationships | Deliverables:D-R-017->Rules:R-017 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0124 | Relationships | Deliverables:D-R-018->Activities:A-R-018 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0125 | Relationships | Deliverables:D-R-018->Rules:R-018 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0126 | Relationships | Deliverables:D-R-019->Activities:A-R-019 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0127 | Relationships | Deliverables:D-R-019->Rules:R-019 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0128 | Relationships | Deliverables:D-R-020->Activities:A-R-020 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0129 | Relationships | Deliverables:D-R-020->Rules:R-020 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0130 | Relationships | Deliverables:D-R-021->Activities:A-R-021 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0131 | Relationships | Deliverables:D-R-021->Rules:R-021 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0132 | Relationships | Deliverables:D-R-022->Activities:A-R-022 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0133 | Relationships | Deliverables:D-R-022->Rules:R-022 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0134 | Relationships | Deliverables:D-R-023->Activities:A-R-023 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0135 | Relationships | Deliverables:D-R-023->Rules:R-023 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0136 | Relationships | Deliverables:D-R-024->Activities:A-R-024 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0137 | Relationships | Deliverables:D-R-024->Rules:R-024 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0138 | Relationships | Deliverables:D-R-025->Activities:A-R-025 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0139 | Relationships | Deliverables:D-R-025->Rules:R-025 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0140 | Relationships | Deliverables:D-R-026->Activities:A-R-026 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0141 | Relationships | Deliverables:D-R-026->Rules:R-026 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0142 | Relationships | Deliverables:D-R-027->Activities:A-R-027 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0143 | Relationships | Deliverables:D-R-027->Rules:R-027 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0144 | Relationships | Deliverables:D-R-028->Activities:A-R-028 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0145 | Relationships | Deliverables:D-R-028->Rules:R-028 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0146 | Relationships | Deliverables:D-R-029->Activities:A-R-029 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0147 | Relationships | Deliverables:D-R-029->Rules:R-029 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0148 | Relationships | Deliverables:D-R-030->Activities:A-R-030 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0149 | Relationships | Deliverables:D-R-030->Rules:R-030 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0150 | Relationships | Deliverables:D-R-031->Activities:A-R-031 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0151 | Relationships | Deliverables:D-R-031->Rules:R-031 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0152 | Relationships | Deliverables:D-R-032->Activities:A-R-032 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0153 | Relationships | Deliverables:D-R-032->Rules:R-032 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0154 | Relationships | Deliverables:D-R-033->Activities:A-R-033 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0155 | Relationships | Deliverables:D-R-033->Rules:R-033 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0156 | Relationships | Deliverables:D-R-034->Activities:A-R-034 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0157 | Relationships | Deliverables:D-R-034->Rules:R-034 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0158 | Relationships | Deliverables:D-R-035->Activities:A-R-035 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0159 | Relationships | Deliverables:D-R-035->Rules:R-035 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0160 | Relationships | Deliverables:D-R-036->Activities:A-R-036 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0161 | Relationships | Deliverables:D-R-036->Rules:R-036 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0162 | Relationships | Deliverables:D-R-037->Activities:A-R-037 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0163 | Relationships | Deliverables:D-R-037->Rules:R-037 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0164 | Relationships | Deliverables:D-R-038->Activities:A-R-038 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0165 | Relationships | Deliverables:D-R-038->Rules:R-038 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0166 | Relationships | Deliverables:D-R-039->Activities:A-R-039 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0167 | Relationships | Deliverables:D-R-039->Rules:R-039 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0168 | Relationships | Deliverables:D-R-040->Activities:A-R-040 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0169 | Relationships | Deliverables:D-R-040->Rules:R-040 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0170 | Relationships | Deliverables:D-R-041->Activities:A-R-041 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0171 | Relationships | Deliverables:D-R-041->Rules:R-041 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0172 | Relationships | Deliverables:D-R-042->Activities:A-R-042 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0173 | Relationships | Deliverables:D-R-042->Rules:R-042 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0174 | Relationships | Deliverables:D-R-043->Activities:A-R-043 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0175 | Relationships | Deliverables:D-R-043->Rules:R-043 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0176 | Relationships | Deliverables:D-R-044->Activities:A-R-044 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0177 | Relationships | Deliverables:D-R-044->Rules:R-044 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0178 | Relationships | Deliverables:D-R-045->Activities:A-R-045 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0179 | Relationships | Deliverables:D-R-045->Rules:R-045 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0180 | Relationships | Deliverables:D-R-046->Activities:A-R-046 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0181 | Relationships | Deliverables:D-R-046->Rules:R-046 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0182 | Relationships | Deliverables:D-R-047->Activities:A-R-047 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0183 | Relationships | Deliverables:D-R-047->Rules:R-047 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0184 | Relationships | Deliverables:D-R-048->Activities:A-R-048 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0185 | Relationships | Deliverables:D-R-048->Rules:R-048 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0186 | Relationships | Deliverables:D-R-049->Activities:A-R-049 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0187 | Relationships | Deliverables:D-R-049->Rules:R-049 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0188 | Relationships | Deliverables:D-R-050->Activities:A-R-050 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0189 | Relationships | Deliverables:D-R-050->Rules:R-050 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0190 | Relationships | Deliverables:D-R-051->Activities:A-R-051 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0191 | Relationships | Deliverables:D-R-051->Rules:R-051 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0192 | Relationships | Deliverables:D-R-052->Activities:A-R-052 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0193 | Relationships | Deliverables:D-R-052->Rules:R-052 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0194 | Relationships | Deliverables:D-R-053->Activities:A-R-053 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0195 | Relationships | Deliverables:D-R-053->Rules:R-053 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0196 | Relationships | Deliverables:D-R-054->Activities:A-R-054 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0197 | Relationships | Deliverables:D-R-054->Rules:R-054 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0198 | Relationships | Deliverables:D-R-055->Activities:A-R-055 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0199 | Relationships | Deliverables:D-R-055->Rules:R-055 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0200 | Relationships | Deliverables:D-R-056->Activities:A-R-056 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0201 | Relationships | Deliverables:D-R-056->Rules:R-056 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0202 | Relationships | Deliverables:D-R-057->Activities:A-R-057 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0203 | Relationships | Deliverables:D-R-057->Rules:R-057 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0204 | Relationships | Deliverables:D-R-058->Activities:A-R-058 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0205 | Relationships | Deliverables:D-R-058->Rules:R-058 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0206 | Relationships | Deliverables:D-R-059->Activities:A-R-059 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0207 | Relationships | Deliverables:D-R-059->Rules:R-059 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0208 | Relationships | Deliverables:D-R-060->Activities:A-R-060 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0209 | Relationships | Deliverables:D-R-060->Rules:R-060 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0210 | Relationships | Deliverables:D-R-061->Activities:A-R-061 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0211 | Relationships | Deliverables:D-R-061->Rules:R-061 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0212 | Relationships | Deliverables:D-R-062->Activities:A-R-062 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0213 | Relationships | Deliverables:D-R-062->Rules:R-062 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0214 | Relationships | Deliverables:D-R-063->Activities:A-R-063 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0215 | Relationships | Deliverables:D-R-063->Rules:R-063 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0216 | Relationships | Deliverables:D-R-064->Activities:A-R-064 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0217 | Relationships | Deliverables:D-R-064->Rules:R-064 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0218 | Relationships | Deliverables:D-R-065->Activities:A-R-065 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0219 | Relationships | Deliverables:D-R-065->Rules:R-065 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0220 | Relationships | Deliverables:D-R-066->Activities:A-R-066 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0221 | Relationships | Deliverables:D-R-066->Rules:R-066 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0222 | Relationships | Deliverables:D-R-067->Activities:A-R-067 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0223 | Relationships | Deliverables:D-R-067->Rules:R-067 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0224 | Relationships | Deliverables:D-R-068->Activities:A-R-068 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0225 | Relationships | Deliverables:D-R-068->Rules:R-068 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0226 | Relationships | Deliverables:D-R-069->Activities:A-R-069 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0227 | Relationships | Deliverables:D-R-069->Rules:R-069 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0228 | Relationships | Deliverables:D-R-070->Activities:A-R-070 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0229 | Relationships | Deliverables:D-R-070->Rules:R-070 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0230 | Relationships | Deliverables:D-R-071->Activities:A-R-071 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0231 | Relationships | Deliverables:D-R-071->Rules:R-071 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0232 | Relationships | Deliverables:D-R-072->Activities:A-R-072 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0233 | Relationships | Deliverables:D-R-072->Rules:R-072 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0234 | Relationships | Deliverables:D-R-073->Activities:A-R-073 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0235 | Relationships | Deliverables:D-R-073->Rules:R-073 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0236 | Relationships | Deliverables:D-R-074->Activities:A-R-074 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0237 | Relationships | Deliverables:D-R-074->Rules:R-074 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0238 | Relationships | Deliverables:D-R-075->Activities:A-R-075 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0239 | Relationships | Deliverables:D-R-075->Rules:R-075 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0240 | Relationships | Deliverables:D-R-076->Activities:A-R-076 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0241 | Relationships | Deliverables:D-R-076->Rules:R-076 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0242 | Relationships | Deliverables:D-R-077->Activities:A-R-077 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0243 | Relationships | Deliverables:D-R-077->Rules:R-077 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0244 | Relationships | Deliverables:D-R-078->Activities:A-R-078 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0245 | Relationships | Deliverables:D-R-078->Rules:R-078 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0246 | Relationships | Deliverables:D-R-079->Activities:A-R-079 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0247 | Relationships | Deliverables:D-R-079->Rules:R-079 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0248 | Relationships | Deliverables:D-R-080->Activities:A-R-080 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0249 | Relationships | Deliverables:D-R-080->Rules:R-080 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0250 | Relationships | Deliverables:D-R-081->Activities:A-R-081 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0251 | Relationships | Deliverables:D-R-081->Rules:R-081 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0252 | Relationships | Deliverables:D-R-082->Activities:A-R-082 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0253 | Relationships | Deliverables:D-R-082->Rules:R-082 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0254 | Relationships | Deliverables:D-R-083->Activities:A-R-083 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0255 | Relationships | Deliverables:D-R-083->Rules:R-083 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0256 | Relationships | Deliverables:D-R-084->Activities:A-R-084 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0257 | Relationships | Deliverables:D-R-084->Rules:R-084 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0258 | Relationships | Deliverables:D-R-085->Activities:A-R-085 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0259 | Relationships | Deliverables:D-R-085->Rules:R-085 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0260 | Relationships | Deliverables:D-R-086->Activities:A-R-086 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0261 | Relationships | Deliverables:D-R-086->Rules:R-086 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0262 | Relationships | Deliverables:D-R-087->Activities:A-R-087 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0263 | Relationships | Deliverables:D-R-087->Rules:R-087 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0264 | Relationships | Deliverables:D-R-088->Activities:A-R-088 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0265 | Relationships | Deliverables:D-R-088->Rules:R-088 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0266 | Relationships | Deliverables:D-R-089->Activities:A-R-089 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0267 | Relationships | Deliverables:D-R-089->Rules:R-089 | Parent/Child Entity | Deliverables->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0268 | Relationships | Deliverables:D-S-17-01->Activities:A-S-17-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0269 | Relationships | Deliverables:D-S-17-02->Activities:A-S-17-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0270 | Relationships | Deliverables:D-S-17-03->Activities:A-S-17-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0271 | Relationships | Deliverables:D-S-17-04->Activities:A-S-17-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0272 | Relationships | Deliverables:D-S-17-05->Activities:A-S-17-05 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0273 | Relationships | Deliverables:D-S-18-01->Activities:A-S-18-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0274 | Relationships | Deliverables:D-S-18-02->Activities:A-S-18-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0275 | Relationships | Deliverables:D-S-18-03->Activities:A-S-18-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0276 | Relationships | Deliverables:D-S-18-04->Activities:A-S-18-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0277 | Relationships | Deliverables:D-S-18-05->Activities:A-S-18-05 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0278 | Relationships | Deliverables:D-S-19-01->Activities:A-S-19-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0279 | Relationships | Deliverables:D-S-19-02->Activities:A-S-19-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0280 | Relationships | Deliverables:D-S-19-03->Activities:A-S-19-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0281 | Relationships | Deliverables:D-S-19-04->Activities:A-S-19-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0282 | Relationships | Deliverables:D-S-19-05->Activities:A-S-19-05 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0283 | Relationships | Deliverables:D-S-20-01->Activities:A-S-20-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0284 | Relationships | Deliverables:D-S-20-02->Activities:A-S-20-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0285 | Relationships | Deliverables:D-S-20-03->Activities:A-S-20-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0286 | Relationships | Deliverables:D-S-20-04->Activities:A-S-20-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0287 | Relationships | Deliverables:D-S-20-05->Activities:A-S-20-05 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0288 | Relationships | Deliverables:D-S-21-01->Activities:A-S-21-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0289 | Relationships | Deliverables:D-S-21-02->Activities:A-S-21-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0290 | Relationships | Deliverables:D-S-21-03->Activities:A-S-21-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0291 | Relationships | Deliverables:D-S-21-04->Activities:A-S-21-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0292 | Relationships | Deliverables:D-S-21-05->Activities:A-S-21-05 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0293 | Relationships | Deliverables:D-S-22-01->Activities:A-S-22-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0294 | Relationships | Deliverables:D-S-22-02->Activities:A-S-22-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0295 | Relationships | Deliverables:D-S-22-03->Activities:A-S-22-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0296 | Relationships | Deliverables:D-S-22-04->Activities:A-S-22-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0297 | Relationships | Deliverables:D-S-22-05->Activities:A-S-22-05 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0298 | Relationships | Deliverables:D-S-23-01->Activities:A-S-23-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0299 | Relationships | Deliverables:D-S-23-02->Activities:A-S-23-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0300 | Relationships | Deliverables:D-S-23-03->Activities:A-S-23-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0301 | Relationships | Deliverables:D-S-23-04->Activities:A-S-23-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0302 | Relationships | Deliverables:D-S-24-01->Activities:A-S-24-01 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0303 | Relationships | Deliverables:D-S-24-02->Activities:A-S-24-02 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0304 | Relationships | Deliverables:D-S-24-03->Activities:A-S-24-03 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0305 | Relationships | Deliverables:D-S-24-04->Activities:A-S-24-04 | Parent/Child Entity | Deliverables->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0306 | Relationships | Evidence:E-001->Rules:R-001 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0307 | Relationships | Evidence:E-002->Rules:R-002 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0308 | Relationships | Evidence:E-003->Rules:R-003 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0309 | Relationships | Evidence:E-004->Rules:R-004 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0310 | Relationships | Evidence:E-005->Rules:R-005 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0311 | Relationships | Evidence:E-006->Rules:R-006 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0312 | Relationships | Evidence:E-007->Rules:R-007 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0313 | Relationships | Evidence:E-008->Rules:R-008 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0314 | Relationships | Evidence:E-009->Rules:R-009 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0315 | Relationships | Evidence:E-010->Rules:R-010 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0316 | Relationships | Evidence:E-011->Rules:R-011 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0317 | Relationships | Evidence:E-012->Rules:R-012 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0318 | Relationships | Evidence:E-013->Rules:R-013 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0319 | Relationships | Evidence:E-014->Rules:R-014 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0320 | Relationships | Evidence:E-015->Rules:R-015 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0321 | Relationships | Evidence:E-016->Rules:R-016 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0322 | Relationships | Evidence:E-017->Rules:R-017 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0323 | Relationships | Evidence:E-018->Rules:R-018 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0324 | Relationships | Evidence:E-019->Rules:R-019 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0325 | Relationships | Evidence:E-020->Rules:R-020 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0326 | Relationships | Evidence:E-021->Rules:R-021 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0327 | Relationships | Evidence:E-022->Rules:R-022 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0328 | Relationships | Evidence:E-023->Rules:R-023 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0329 | Relationships | Evidence:E-024->Rules:R-024 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0330 | Relationships | Evidence:E-025->Rules:R-025 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0331 | Relationships | Evidence:E-026->Rules:R-026 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0332 | Relationships | Evidence:E-027->Rules:R-027 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0333 | Relationships | Evidence:E-028->Rules:R-028 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0334 | Relationships | Evidence:E-029->Rules:R-029 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0335 | Relationships | Evidence:E-030->Rules:R-030 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0336 | Relationships | Evidence:E-031->Rules:R-031 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0337 | Relationships | Evidence:E-032->Rules:R-032 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0338 | Relationships | Evidence:E-033->Rules:R-033 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0339 | Relationships | Evidence:E-034->Rules:R-034 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0340 | Relationships | Evidence:E-035->Rules:R-035 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0341 | Relationships | Evidence:E-036->Rules:R-036 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0342 | Relationships | Evidence:E-037->Rules:R-037 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0343 | Relationships | Evidence:E-038->Rules:R-038 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0344 | Relationships | Evidence:E-039->Rules:R-039 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0345 | Relationships | Evidence:E-040->Rules:R-040 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0346 | Relationships | Evidence:E-041->Rules:R-041 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0347 | Relationships | Evidence:E-042->Rules:R-042 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0348 | Relationships | Evidence:E-043->Rules:R-043 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0349 | Relationships | Evidence:E-044->Rules:R-044 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0350 | Relationships | Evidence:E-045->Rules:R-045 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0351 | Relationships | Evidence:E-046->Rules:R-046 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0352 | Relationships | Evidence:E-047->Rules:R-047 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0353 | Relationships | Evidence:E-048->Rules:R-048 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0354 | Relationships | Evidence:E-049->Rules:R-049 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0355 | Relationships | Evidence:E-050->Rules:R-050 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0356 | Relationships | Evidence:E-051->Rules:R-051 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0357 | Relationships | Evidence:E-052->Rules:R-052 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0358 | Relationships | Evidence:E-053->Rules:R-053 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0359 | Relationships | Evidence:E-054->Rules:R-054 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0360 | Relationships | Evidence:E-055->Rules:R-055 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0361 | Relationships | Evidence:E-056->Rules:R-056 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0362 | Relationships | Evidence:E-057->Rules:R-057 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0363 | Relationships | Evidence:E-058->Rules:R-058 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0364 | Relationships | Evidence:E-059->Rules:R-059 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0365 | Relationships | Evidence:E-060->Rules:R-060 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0366 | Relationships | Evidence:E-061->Rules:R-061 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0367 | Relationships | Evidence:E-062->Rules:R-062 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0368 | Relationships | Evidence:E-063->Rules:R-063 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0369 | Relationships | Evidence:E-064->Rules:R-064 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0370 | Relationships | Evidence:E-065->Rules:R-065 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0371 | Relationships | Evidence:E-066->Rules:R-066 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0372 | Relationships | Evidence:E-067->Rules:R-067 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0373 | Relationships | Evidence:E-068->Rules:R-068 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0374 | Relationships | Evidence:E-069->Rules:R-069 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0375 | Relationships | Evidence:E-070->Rules:R-070 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0376 | Relationships | Evidence:E-071->Rules:R-071 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0377 | Relationships | Evidence:E-072->Rules:R-072 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0378 | Relationships | Evidence:E-073->Rules:R-073 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0379 | Relationships | Evidence:E-074->Rules:R-074 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0380 | Relationships | Evidence:E-075->Rules:R-075 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0381 | Relationships | Evidence:E-076->Rules:R-076 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0382 | Relationships | Evidence:E-077->Rules:R-077 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0383 | Relationships | Evidence:E-078->Rules:R-078 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0384 | Relationships | Evidence:E-079->Rules:R-079 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0385 | Relationships | Evidence:E-080->Rules:R-080 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0386 | Relationships | Evidence:E-081->Rules:R-081 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0387 | Relationships | Evidence:E-082->Rules:R-082 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0388 | Relationships | Evidence:E-083->Rules:R-083 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0389 | Relationships | Evidence:E-084->Rules:R-084 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0390 | Relationships | Evidence:E-085->Rules:R-085 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0391 | Relationships | Evidence:E-086->Rules:R-086 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0392 | Relationships | Evidence:E-087->Rules:R-087 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0393 | Relationships | Evidence:E-088->Rules:R-088 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0394 | Relationships | Evidence:E-089->Rules:R-089 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0395 | Relationships | Evidence:E-090->Rules:R-026 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0396 | Relationships | Evidence:E-090->Rules:R-050 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0397 | Relationships | Evidence:E-091->Rules:R-026 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0398 | Relationships | Evidence:E-091->Rules:R-050 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0399 | Relationships | Evidence:E-092->Rules:R-026 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0400 | Relationships | Evidence:E-092->Rules:R-050 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0401 | Relationships | Evidence:E-093->Rules:R-026 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0402 | Relationships | Evidence:E-093->Rules:R-050 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0403 | Relationships | Evidence:E-094->Rules:R-001 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0404 | Relationships | Evidence:E-095->Rules:R-001 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0405 | Relationships | Evidence:E-096->Rules:R-001 | Parent/Child Entity | Evidence->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0406 | Relationships | Execution:WPS-17-01->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0407 | Relationships | Execution:WPS-17-02->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0408 | Relationships | Execution:WPS-17-03->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0409 | Relationships | Execution:WPS-17-04->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0410 | Relationships | Execution:WPS-17-05->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0411 | Relationships | Execution:WPS-18-01->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0412 | Relationships | Execution:WPS-18-02->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0413 | Relationships | Execution:WPS-18-03->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0414 | Relationships | Execution:WPS-18-04->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0415 | Relationships | Execution:WPS-18-05->Gates:GATE-1 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0416 | Relationships | Execution:WPS-19-01->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0417 | Relationships | Execution:WPS-19-02->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0418 | Relationships | Execution:WPS-19-03->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0419 | Relationships | Execution:WPS-19-04->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0420 | Relationships | Execution:WPS-19-05->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0421 | Relationships | Execution:WPS-20-01->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0422 | Relationships | Execution:WPS-20-02->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0423 | Relationships | Execution:WPS-20-03->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0424 | Relationships | Execution:WPS-20-04->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0425 | Relationships | Execution:WPS-20-05->Gates:GATE-8 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0426 | Relationships | Execution:WPS-21-01->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0427 | Relationships | Execution:WPS-21-02->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0428 | Relationships | Execution:WPS-21-03->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0429 | Relationships | Execution:WPS-21-04->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0430 | Relationships | Execution:WPS-21-05->Gates:GATE-7 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0431 | Relationships | Execution:WPS-22-01->Gates:GATE-3 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0432 | Relationships | Execution:WPS-22-02->Gates:GATE-3 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0433 | Relationships | Execution:WPS-22-03->Gates:GATE-3 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0434 | Relationships | Execution:WPS-22-04->Gates:GATE-3 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0435 | Relationships | Execution:WPS-22-05->Gates:GATE-3 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0436 | Relationships | Execution:WPS-23-01->Gates:GATE-4 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0437 | Relationships | Execution:WPS-23-02->Gates:GATE-4 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0438 | Relationships | Execution:WPS-23-03->Gates:GATE-4 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0439 | Relationships | Execution:WPS-23-04->Gates:GATE-4 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0440 | Relationships | Execution:WPS-24-01->Gates:GATE-8 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0441 | Relationships | Execution:WPS-24-02->Gates:GATE-8 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0442 | Relationships | Execution:WPS-24-03->Gates:GATE-8 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0443 | Relationships | Execution:WPS-24-04->Gates:GATE-8 | Parent/Child Entity | Execution->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0444 | Relationships | Gaps:G-001->Activities:A-R-001 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0445 | Relationships | Gaps:G-001->Deliverables:D-R-001 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0446 | Relationships | Gaps:G-001->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0447 | Relationships | Gaps:G-001->Rules:R-001 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0448 | Relationships | Gaps:G-002->Activities:A-R-002 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0449 | Relationships | Gaps:G-002->Deliverables:D-R-002 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0450 | Relationships | Gaps:G-002->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0451 | Relationships | Gaps:G-002->Rules:R-002 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0452 | Relationships | Gaps:G-003->Activities:A-R-003 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0453 | Relationships | Gaps:G-003->Deliverables:D-R-003 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0454 | Relationships | Gaps:G-003->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0455 | Relationships | Gaps:G-003->Rules:R-003 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0456 | Relationships | Gaps:G-004->Activities:A-R-004 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0457 | Relationships | Gaps:G-004->Deliverables:D-R-004 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0458 | Relationships | Gaps:G-004->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0459 | Relationships | Gaps:G-004->Rules:R-004 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0460 | Relationships | Gaps:G-005->Activities:A-R-005 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0461 | Relationships | Gaps:G-005->Deliverables:D-R-005 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0462 | Relationships | Gaps:G-005->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0463 | Relationships | Gaps:G-005->Rules:R-005 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0464 | Relationships | Gaps:G-006->Activities:A-R-006 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0465 | Relationships | Gaps:G-006->Deliverables:D-R-006 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0466 | Relationships | Gaps:G-006->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0467 | Relationships | Gaps:G-006->Rules:R-006 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0468 | Relationships | Gaps:G-007->Activities:A-R-007 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0469 | Relationships | Gaps:G-007->Deliverables:D-R-007 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0470 | Relationships | Gaps:G-007->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0471 | Relationships | Gaps:G-007->Rules:R-007 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0472 | Relationships | Gaps:G-008->Activities:A-R-008 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0473 | Relationships | Gaps:G-008->Deliverables:D-R-008 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0474 | Relationships | Gaps:G-008->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0475 | Relationships | Gaps:G-008->Rules:R-008 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0476 | Relationships | Gaps:G-009->Activities:A-R-009 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0477 | Relationships | Gaps:G-009->Deliverables:D-R-009 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0478 | Relationships | Gaps:G-009->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0479 | Relationships | Gaps:G-009->Rules:R-009 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0480 | Relationships | Gaps:G-010->Activities:A-R-010 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0481 | Relationships | Gaps:G-010->Deliverables:D-R-010 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0482 | Relationships | Gaps:G-010->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0483 | Relationships | Gaps:G-010->Rules:R-010 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0484 | Relationships | Gaps:G-011->Activities:A-R-011 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0485 | Relationships | Gaps:G-011->Deliverables:D-R-011 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0486 | Relationships | Gaps:G-011->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0487 | Relationships | Gaps:G-011->Rules:R-011 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0488 | Relationships | Gaps:G-012->Activities:A-R-012 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0489 | Relationships | Gaps:G-012->Deliverables:D-R-012 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0490 | Relationships | Gaps:G-012->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0491 | Relationships | Gaps:G-012->Rules:R-012 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0492 | Relationships | Gaps:G-013->Activities:A-R-013 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0493 | Relationships | Gaps:G-013->Deliverables:D-R-013 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0494 | Relationships | Gaps:G-013->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0495 | Relationships | Gaps:G-013->Rules:R-013 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0496 | Relationships | Gaps:G-014->Activities:A-R-014 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0497 | Relationships | Gaps:G-014->Deliverables:D-R-014 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0498 | Relationships | Gaps:G-014->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0499 | Relationships | Gaps:G-014->Rules:R-014 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0500 | Relationships | Gaps:G-015->Activities:A-R-015 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0501 | Relationships | Gaps:G-015->Deliverables:D-R-015 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0502 | Relationships | Gaps:G-015->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0503 | Relationships | Gaps:G-015->Rules:R-015 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0504 | Relationships | Gaps:G-016->Activities:A-R-016 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0505 | Relationships | Gaps:G-016->Deliverables:D-R-016 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0506 | Relationships | Gaps:G-016->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0507 | Relationships | Gaps:G-016->Rules:R-016 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0508 | Relationships | Gaps:G-017->Activities:A-R-017 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0509 | Relationships | Gaps:G-017->Deliverables:D-R-017 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0510 | Relationships | Gaps:G-017->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0511 | Relationships | Gaps:G-017->Rules:R-017 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0512 | Relationships | Gaps:G-018->Activities:A-R-018 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0513 | Relationships | Gaps:G-018->Deliverables:D-R-018 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0514 | Relationships | Gaps:G-018->Gates:GATE-2 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0515 | Relationships | Gaps:G-018->Rules:R-018 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0516 | Relationships | Gaps:G-019->Activities:A-R-019 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0517 | Relationships | Gaps:G-019->Deliverables:D-R-019 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0518 | Relationships | Gaps:G-019->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0519 | Relationships | Gaps:G-019->Rules:R-019 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0520 | Relationships | Gaps:G-020->Activities:A-R-020 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0521 | Relationships | Gaps:G-020->Deliverables:D-R-020 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0522 | Relationships | Gaps:G-020->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0523 | Relationships | Gaps:G-020->Rules:R-020 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0524 | Relationships | Gaps:G-021->Activities:A-R-021 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0525 | Relationships | Gaps:G-021->Deliverables:D-R-021 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0526 | Relationships | Gaps:G-021->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0527 | Relationships | Gaps:G-021->Rules:R-021 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0528 | Relationships | Gaps:G-022->Activities:A-R-022 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0529 | Relationships | Gaps:G-022->Deliverables:D-R-022 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0530 | Relationships | Gaps:G-022->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0531 | Relationships | Gaps:G-022->Rules:R-022 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0532 | Relationships | Gaps:G-023->Activities:A-R-023 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0533 | Relationships | Gaps:G-023->Deliverables:D-R-023 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0534 | Relationships | Gaps:G-023->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0535 | Relationships | Gaps:G-023->Rules:R-023 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0536 | Relationships | Gaps:G-024->Activities:A-R-024 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0537 | Relationships | Gaps:G-024->Deliverables:D-R-024 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0538 | Relationships | Gaps:G-024->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0539 | Relationships | Gaps:G-024->Rules:R-024 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0540 | Relationships | Gaps:G-025->Activities:A-R-025 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0541 | Relationships | Gaps:G-025->Deliverables:D-R-025 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0542 | Relationships | Gaps:G-025->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0543 | Relationships | Gaps:G-025->Rules:R-025 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0544 | Relationships | Gaps:G-026->Activities:A-R-026 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0545 | Relationships | Gaps:G-026->Deliverables:D-R-026 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0546 | Relationships | Gaps:G-026->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0547 | Relationships | Gaps:G-026->Rules:R-026 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0548 | Relationships | Gaps:G-027->Activities:A-R-027 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0549 | Relationships | Gaps:G-027->Deliverables:D-R-027 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0550 | Relationships | Gaps:G-027->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0551 | Relationships | Gaps:G-027->Rules:R-027 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0552 | Relationships | Gaps:G-028->Activities:A-R-028 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0553 | Relationships | Gaps:G-028->Deliverables:D-R-028 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0554 | Relationships | Gaps:G-028->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0555 | Relationships | Gaps:G-028->Rules:R-028 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0556 | Relationships | Gaps:G-029->Activities:A-R-029 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0557 | Relationships | Gaps:G-029->Deliverables:D-R-029 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0558 | Relationships | Gaps:G-029->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0559 | Relationships | Gaps:G-029->Rules:R-029 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0560 | Relationships | Gaps:G-030->Activities:A-R-030 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0561 | Relationships | Gaps:G-030->Deliverables:D-R-030 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0562 | Relationships | Gaps:G-030->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0563 | Relationships | Gaps:G-030->Rules:R-030 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0564 | Relationships | Gaps:G-031->Activities:A-R-031 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0565 | Relationships | Gaps:G-031->Deliverables:D-R-031 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0566 | Relationships | Gaps:G-031->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0567 | Relationships | Gaps:G-031->Rules:R-031 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0568 | Relationships | Gaps:G-032->Activities:A-R-032 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0569 | Relationships | Gaps:G-032->Deliverables:D-R-032 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0570 | Relationships | Gaps:G-032->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0571 | Relationships | Gaps:G-032->Rules:R-032 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0572 | Relationships | Gaps:G-033->Activities:A-R-033 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0573 | Relationships | Gaps:G-033->Deliverables:D-R-033 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0574 | Relationships | Gaps:G-033->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0575 | Relationships | Gaps:G-033->Rules:R-033 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0576 | Relationships | Gaps:G-034->Activities:A-R-034 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0577 | Relationships | Gaps:G-034->Deliverables:D-R-034 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0578 | Relationships | Gaps:G-034->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0579 | Relationships | Gaps:G-034->Rules:R-034 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0580 | Relationships | Gaps:G-035->Activities:A-R-035 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0581 | Relationships | Gaps:G-035->Deliverables:D-R-035 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0582 | Relationships | Gaps:G-035->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0583 | Relationships | Gaps:G-035->Rules:R-035 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0584 | Relationships | Gaps:G-036->Activities:A-R-036 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0585 | Relationships | Gaps:G-036->Deliverables:D-R-036 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0586 | Relationships | Gaps:G-036->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0587 | Relationships | Gaps:G-036->Rules:R-036 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0588 | Relationships | Gaps:G-037->Activities:A-R-037 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0589 | Relationships | Gaps:G-037->Deliverables:D-R-037 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0590 | Relationships | Gaps:G-037->Gates:GATE-5 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0591 | Relationships | Gaps:G-037->Rules:R-037 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0592 | Relationships | Gaps:G-038->Activities:A-R-038 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0593 | Relationships | Gaps:G-038->Deliverables:D-R-038 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0594 | Relationships | Gaps:G-038->Gates:GATE-5 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0595 | Relationships | Gaps:G-038->Rules:R-038 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0596 | Relationships | Gaps:G-039->Activities:A-R-039 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0597 | Relationships | Gaps:G-039->Deliverables:D-R-039 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0598 | Relationships | Gaps:G-039->Gates:GATE-5 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0599 | Relationships | Gaps:G-039->Rules:R-039 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0600 | Relationships | Gaps:G-040->Activities:A-R-040 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0601 | Relationships | Gaps:G-040->Deliverables:D-R-040 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0602 | Relationships | Gaps:G-040->Gates:GATE-5 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0603 | Relationships | Gaps:G-040->Rules:R-040 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0604 | Relationships | Gaps:G-041->Activities:A-R-041 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0605 | Relationships | Gaps:G-041->Deliverables:D-R-041 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0606 | Relationships | Gaps:G-041->Gates:GATE-5 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0607 | Relationships | Gaps:G-041->Rules:R-041 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0608 | Relationships | Gaps:G-042->Activities:A-R-042 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0609 | Relationships | Gaps:G-042->Deliverables:D-R-042 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0610 | Relationships | Gaps:G-042->Gates:GATE-5 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0611 | Relationships | Gaps:G-042->Rules:R-042 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0612 | Relationships | Gaps:G-043->Activities:A-R-043 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0613 | Relationships | Gaps:G-043->Deliverables:D-R-043 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0614 | Relationships | Gaps:G-043->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0615 | Relationships | Gaps:G-043->Rules:R-043 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0616 | Relationships | Gaps:G-044->Activities:A-R-044 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0617 | Relationships | Gaps:G-044->Deliverables:D-R-044 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0618 | Relationships | Gaps:G-044->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0619 | Relationships | Gaps:G-044->Rules:R-044 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0620 | Relationships | Gaps:G-045->Activities:A-R-045 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0621 | Relationships | Gaps:G-045->Deliverables:D-R-045 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0622 | Relationships | Gaps:G-045->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0623 | Relationships | Gaps:G-045->Rules:R-045 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0624 | Relationships | Gaps:G-046->Activities:A-R-046 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0625 | Relationships | Gaps:G-046->Deliverables:D-R-046 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0626 | Relationships | Gaps:G-046->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0627 | Relationships | Gaps:G-046->Rules:R-046 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0628 | Relationships | Gaps:G-047->Activities:A-R-047 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0629 | Relationships | Gaps:G-047->Deliverables:D-R-047 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0630 | Relationships | Gaps:G-047->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0631 | Relationships | Gaps:G-047->Rules:R-047 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0632 | Relationships | Gaps:G-048->Activities:A-R-048 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0633 | Relationships | Gaps:G-048->Deliverables:D-R-048 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0634 | Relationships | Gaps:G-048->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0635 | Relationships | Gaps:G-048->Rules:R-048 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0636 | Relationships | Gaps:G-049->Activities:A-R-049 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0637 | Relationships | Gaps:G-049->Deliverables:D-R-049 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0638 | Relationships | Gaps:G-049->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0639 | Relationships | Gaps:G-049->Rules:R-049 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0640 | Relationships | Gaps:G-050->Activities:A-R-050 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0641 | Relationships | Gaps:G-050->Deliverables:D-R-050 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0642 | Relationships | Gaps:G-050->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0643 | Relationships | Gaps:G-050->Rules:R-050 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0644 | Relationships | Gaps:G-051->Activities:A-R-051 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0645 | Relationships | Gaps:G-051->Deliverables:D-R-051 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0646 | Relationships | Gaps:G-051->Gates:GATE-6 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0647 | Relationships | Gaps:G-051->Rules:R-051 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0648 | Relationships | Gaps:G-052->Activities:A-R-052 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0649 | Relationships | Gaps:G-052->Deliverables:D-R-052 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0650 | Relationships | Gaps:G-052->Gates:GATE-6 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0651 | Relationships | Gaps:G-052->Rules:R-052 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0652 | Relationships | Gaps:G-053->Activities:A-R-053 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0653 | Relationships | Gaps:G-053->Deliverables:D-R-053 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0654 | Relationships | Gaps:G-053->Gates:GATE-6 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0655 | Relationships | Gaps:G-053->Rules:R-053 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0656 | Relationships | Gaps:G-054->Activities:A-R-054 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0657 | Relationships | Gaps:G-054->Deliverables:D-R-054 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0658 | Relationships | Gaps:G-054->Gates:GATE-6 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0659 | Relationships | Gaps:G-054->Rules:R-054 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0660 | Relationships | Gaps:G-055->Activities:A-R-055 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0661 | Relationships | Gaps:G-055->Deliverables:D-R-055 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0662 | Relationships | Gaps:G-055->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0663 | Relationships | Gaps:G-055->Rules:R-055 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0664 | Relationships | Gaps:G-056->Activities:A-R-056 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0665 | Relationships | Gaps:G-056->Deliverables:D-R-056 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0666 | Relationships | Gaps:G-056->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0667 | Relationships | Gaps:G-056->Rules:R-056 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0668 | Relationships | Gaps:G-057->Activities:A-R-057 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0669 | Relationships | Gaps:G-057->Deliverables:D-R-057 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0670 | Relationships | Gaps:G-057->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0671 | Relationships | Gaps:G-057->Rules:R-057 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0672 | Relationships | Gaps:G-058->Activities:A-R-058 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0673 | Relationships | Gaps:G-058->Deliverables:D-R-058 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0674 | Relationships | Gaps:G-058->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0675 | Relationships | Gaps:G-058->Rules:R-058 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0676 | Relationships | Gaps:G-059->Activities:A-R-059 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0677 | Relationships | Gaps:G-059->Deliverables:D-R-059 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0678 | Relationships | Gaps:G-059->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0679 | Relationships | Gaps:G-059->Rules:R-059 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0680 | Relationships | Gaps:G-060->Activities:A-R-060 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0681 | Relationships | Gaps:G-060->Deliverables:D-R-060 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0682 | Relationships | Gaps:G-060->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0683 | Relationships | Gaps:G-060->Rules:R-060 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0684 | Relationships | Gaps:G-061->Activities:A-R-061 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0685 | Relationships | Gaps:G-061->Deliverables:D-R-061 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0686 | Relationships | Gaps:G-061->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0687 | Relationships | Gaps:G-061->Rules:R-061 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0688 | Relationships | Gaps:G-062->Activities:A-R-062 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0689 | Relationships | Gaps:G-062->Deliverables:D-R-062 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0690 | Relationships | Gaps:G-062->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0691 | Relationships | Gaps:G-062->Rules:R-062 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0692 | Relationships | Gaps:G-063->Activities:A-R-063 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0693 | Relationships | Gaps:G-063->Deliverables:D-R-063 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0694 | Relationships | Gaps:G-063->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0695 | Relationships | Gaps:G-063->Rules:R-063 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0696 | Relationships | Gaps:G-064->Activities:A-R-064 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0697 | Relationships | Gaps:G-064->Deliverables:D-R-064 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0698 | Relationships | Gaps:G-064->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0699 | Relationships | Gaps:G-064->Rules:R-064 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0700 | Relationships | Gaps:G-065->Activities:A-R-065 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0701 | Relationships | Gaps:G-065->Deliverables:D-R-065 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0702 | Relationships | Gaps:G-065->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0703 | Relationships | Gaps:G-065->Rules:R-065 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0704 | Relationships | Gaps:G-066->Activities:A-R-066 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0705 | Relationships | Gaps:G-066->Deliverables:D-R-066 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0706 | Relationships | Gaps:G-066->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0707 | Relationships | Gaps:G-066->Rules:R-066 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0708 | Relationships | Gaps:G-067->Activities:A-R-067 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0709 | Relationships | Gaps:G-067->Deliverables:D-R-067 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0710 | Relationships | Gaps:G-067->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0711 | Relationships | Gaps:G-067->Rules:R-067 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0712 | Relationships | Gaps:G-068->Activities:A-R-068 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0713 | Relationships | Gaps:G-068->Deliverables:D-R-068 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0714 | Relationships | Gaps:G-068->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0715 | Relationships | Gaps:G-068->Rules:R-068 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0716 | Relationships | Gaps:G-069->Activities:A-R-069 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0717 | Relationships | Gaps:G-069->Deliverables:D-R-069 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0718 | Relationships | Gaps:G-069->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0719 | Relationships | Gaps:G-069->Rules:R-069 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0720 | Relationships | Gaps:G-070->Activities:A-R-070 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0721 | Relationships | Gaps:G-070->Deliverables:D-R-070 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0722 | Relationships | Gaps:G-070->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0723 | Relationships | Gaps:G-070->Rules:R-070 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0724 | Relationships | Gaps:G-071->Activities:A-R-071 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0725 | Relationships | Gaps:G-071->Deliverables:D-R-071 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0726 | Relationships | Gaps:G-071->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0727 | Relationships | Gaps:G-071->Rules:R-071 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0728 | Relationships | Gaps:G-072->Activities:A-R-072 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0729 | Relationships | Gaps:G-072->Deliverables:D-R-072 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0730 | Relationships | Gaps:G-072->Gates:GATE-6 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0731 | Relationships | Gaps:G-072->Rules:R-072 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0732 | Relationships | Gaps:G-073->Activities:A-R-073 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0733 | Relationships | Gaps:G-073->Deliverables:D-R-073 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0734 | Relationships | Gaps:G-073->Gates:GATE-6 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0735 | Relationships | Gaps:G-073->Rules:R-073 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0736 | Relationships | Gaps:G-074->Activities:A-R-074 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0737 | Relationships | Gaps:G-074->Deliverables:D-R-074 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0738 | Relationships | Gaps:G-074->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0739 | Relationships | Gaps:G-074->Rules:R-074 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0740 | Relationships | Gaps:G-075->Activities:A-R-075 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0741 | Relationships | Gaps:G-075->Deliverables:D-R-075 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0742 | Relationships | Gaps:G-075->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0743 | Relationships | Gaps:G-075->Rules:R-075 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0744 | Relationships | Gaps:G-076->Activities:A-R-076 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0745 | Relationships | Gaps:G-076->Deliverables:D-R-076 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0746 | Relationships | Gaps:G-076->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0747 | Relationships | Gaps:G-076->Rules:R-076 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0748 | Relationships | Gaps:G-077->Activities:A-R-077 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0749 | Relationships | Gaps:G-077->Deliverables:D-R-077 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0750 | Relationships | Gaps:G-077->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0751 | Relationships | Gaps:G-077->Rules:R-077 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0752 | Relationships | Gaps:G-078->Activities:A-R-078 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0753 | Relationships | Gaps:G-078->Deliverables:D-R-078 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0754 | Relationships | Gaps:G-078->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0755 | Relationships | Gaps:G-078->Rules:R-078 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0756 | Relationships | Gaps:G-079->Activities:A-R-079 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0757 | Relationships | Gaps:G-079->Deliverables:D-R-079 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0758 | Relationships | Gaps:G-079->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0759 | Relationships | Gaps:G-079->Rules:R-079 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0760 | Relationships | Gaps:G-080->Activities:A-R-080 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0761 | Relationships | Gaps:G-080->Deliverables:D-R-080 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0762 | Relationships | Gaps:G-080->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0763 | Relationships | Gaps:G-080->Rules:R-080 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0764 | Relationships | Gaps:G-081->Activities:A-R-081 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0765 | Relationships | Gaps:G-081->Deliverables:D-R-081 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0766 | Relationships | Gaps:G-081->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0767 | Relationships | Gaps:G-081->Rules:R-081 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0768 | Relationships | Gaps:G-082->Activities:A-R-082 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0769 | Relationships | Gaps:G-082->Deliverables:D-R-082 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0770 | Relationships | Gaps:G-082->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0771 | Relationships | Gaps:G-082->Rules:R-082 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0772 | Relationships | Gaps:G-083->Activities:A-R-083 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0773 | Relationships | Gaps:G-083->Deliverables:D-R-083 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0774 | Relationships | Gaps:G-083->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0775 | Relationships | Gaps:G-083->Rules:R-083 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0776 | Relationships | Gaps:G-084->Activities:A-R-084 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0777 | Relationships | Gaps:G-084->Deliverables:D-R-084 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0778 | Relationships | Gaps:G-084->Gates:GATE-7 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0779 | Relationships | Gaps:G-084->Rules:R-084 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0780 | Relationships | Gaps:G-085->Activities:A-R-085 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0781 | Relationships | Gaps:G-085->Deliverables:D-R-085 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0782 | Relationships | Gaps:G-085->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0783 | Relationships | Gaps:G-085->Rules:R-085 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0784 | Relationships | Gaps:G-086->Activities:A-R-086 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0785 | Relationships | Gaps:G-086->Deliverables:D-R-086 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0786 | Relationships | Gaps:G-086->Gates:GATE-3 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0787 | Relationships | Gaps:G-086->Rules:R-086 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0788 | Relationships | Gaps:G-087->Activities:A-R-087 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0789 | Relationships | Gaps:G-087->Deliverables:D-R-087 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0790 | Relationships | Gaps:G-087->Gates:GATE-4 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0791 | Relationships | Gaps:G-087->Rules:R-087 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0792 | Relationships | Gaps:G-088->Activities:A-R-088 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0793 | Relationships | Gaps:G-088->Deliverables:D-R-088 | Parent/Child Entity | Gaps->Deliverables | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0794 | Relationships | Gaps:G-088->Gates:GATE-1 | Parent/Child Entity | Gaps->Gates | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0795 | Relationships | Gaps:G-088->Rules:R-088 | Parent/Child Entity | Gaps->Rules | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.
RT-0796 | Relationships | Gaps:G-089->Activities:A-R-089 | Parent/Child Entity | Gaps->Activities | Relationship pair has no defined type in the contract. | Model Error | Medium | Schema | No | Yes | n/a | Define Relationship Type for this entity pair in the Data Contract.